Southern Company

2013 Integrated Resource Plan

Resource Mix Study

January, 2013

(This page is intentionally blank.)

# SUMMARY

## STUDY OBJECTIVE

The primary objective of this study is to provide information regarding the development of an optimum resource addition schedule.  The resulting base case schedule was selected to minimize revenue requirements and average electricity rates within reliability guidelines and environmental compliance requirements, while also considering risk and flexibility.  This supply-side plan will serve as the basis for a variety of financial and engineering studies throughout the next year or years including the consideration of demand-side options (“DSOs”).

## ASSUMPTIONS

The key inputs to the study are the operating companies’ load forecasts, projected DSOs, cost of capital and escalation rates, a reliability criterion, cost and performance characteristics of candidate generating technologies, environmental compliance strategies, fuel forecasts and the operating data and retirement or projected unavailability dates of existing and committed generating units.  For Georgia Power Company and the other regulated retail operating companies, discrete retirement dates of owned generating units were utilized in the base case for any particular unit which had previously been requested for retirement.  Also, some units in the Southern Company system are modeled as being unavailable upon the date of required MATS compliance.  However, this projected disposition of the System fleet is only an assumption at this time because not all final decisions have been made and possible MATS compliance strategies are still being evaluated across the System.  For any units remaining available, it was assumed that the respective thermal units would continue to operate throughout the planning period. The operating companies’ load forecasts were completed in fall 2012.  Escalation and cost of capital rates are based on the Moody’s Analytics March 2012 forecast.  Long term fuel price projections were developed for Southern Company by Charles River Associates® (a.k.a. CRA International® or “CRA”).  Generation technology capital cost estimates and escalation were developed by Southern Company Generation – Engineering and Construction Services (or “SCG Engineering”).  The reserve margin constraint used to develop the least cost resource addition schedule coincides with the present planning reserve guideline which recommends a 15% system planning target reserve margin.

## EXISTING CAPACITY AND ENERGY MIX

The retail operating companies’ primary fuel is coal, accounting for approximately REDACTED% of their energy requirement with the balance provided by REDACTED% from oil and gas, REDACTED% from nuclear, and REDACTED% from hydro and other. The generating capacity of the retail operating companies consists of REDACTED% coal, REDACTED% oil and gas, REDACTED% nuclear, and REDACTED% hydro.

The retail operating companies’ base combined peak demand is forecast to increase at approximately REDACTED% per year on average over the next 20 years. As a result, additional generating capacity will be required to reliably meet the increasing demand and maintain the appropriate reserve margins.

## SELECTION OF CANDIDATE TECHNOLOGIES

Base load coal with carbon capture and sequestration (“CCS”), base load nuclear, base/intermediate load combined cycle, base/intermediate load combined cycle with carbon capture and sequestration (“CCS”) and peaking load combustion turbines were the technologies selected for the mix analysis. The technology selection was based on results from the supply side technology screening and generation economic comparative analysis.    The initial list of candidate technologies was based on various viable technologies discussed in the “Technical Assessment Guide” (“TAG”) by Electric Power Research Institute (“EPRI”) and recommendations of SCG Engineering and Research & Environmental Affairs.  The initial list covered both conventional and developing technologies.  Several factors, such as cost and performance, technology maturity, environmental issues, and other associated risks and uncertainties were considered in determining the selected technologies.

## OPTIMIZATION PROCESS

Data about the existing generation system of the retail operating companies and various projections for the future load growth, DSOs, and cost and performance characteristics of candidate technologies were used in the generation production cost model, Strategist®, and its optimization sub module, PROVIEW.  PROVIEW™ uses a dynamic programming technique to develop the least cost capacity addition schedule.  The model considers all possible combinations of capacity additions on a yearly basis that would satisfy reserve margin constraints.  The combination of alternatives with the smallest production and capital cost over the planning horizon is the least cost plan. The output of the model was used as the primary guide in developing the base case system expansion plan for the retail operating companies.

## OPTIMUM MIX

The conclusion of this study, based upon the results of the base case, sensitivities and scenario case analyses, is that additional generation capacity requirements will involve a mixture of combustion turbine generation, combined cycle generation, combined cycle generation with CCS, and nuclear generation (or purchases).  In cases without CO2 emissions cost, the REDACTED and the      REDACTED       comprised   the   majority   of   the   new   capacity    added    during the planning period.  For cases that included CO2 emissions cost, as the    CO2     prices    reach   elevated   levels,     REDACTED     and     REDACTED     are the primary technologies selected.

For any mix study case in which nuclear was selected, a nuclear strategy of adding no more than approximately REDACTED units every REDACTED years was employed.  This strategy gives consideration for anticipated increase in demand for nuclear generation and potential financing limitations.

Due to the uncertainty related to long term fuel cost and potential CO2 legislation, nine fully interrelated planning scenario cases were developed to explore the potential impacts.  This resulted in nine internally-consistent outlooks of correlated fuel prices and carbon compliance costs, electricity demand and prices, and capacity and energy mixes.

As additional capacity is required, more detailed implementation studies will be performed with the latest fuel and unit cost projections while considering advancements in generation technology.  These projections will be reviewed as input data assumptions are updated.

## DEMAND SIDE OPTIONS

Demand side options are either “dispatchable” or “non-dispatchable”.   Examples of dispatchable DSO include interruptible load and other options which can be controlled and dispatched by a utility.  Examples of non-dispatchable DSO include options such as insulation or end-use equipment efficiency which are not directly controllable by a utility.  Non-dispatchable DSO impacts varied in this study, by CO2 scenario case.  Dispatchable DSOs were included as a capacity resource in this study.  Non-dispatchable DSOs were accounted for in the load forecasts.

# INTRODUCTION

This report summarizes the results of the 2013 Resource Mix Study.  The recommendations of the study provide input to an optimum resource addition schedule for the retail operating companies.  The base case resource addition schedule is based on maintaining a minimum reserve margin and minimizing the total operating and capital costs over the planning horizon.

The Southern Electric System is comprised of five operating companies: Alabama Power Company, Georgia Power Company, Gulf Power Company, and Mississippi Power Company (collectively, the “retail operating companies” or “ROCs”) and Southern Power Company. The retail operating companies provide electric service in most of the state of Georgia, the majority of Alabama, southeast Mississippi, and northwest Florida.  Southern Power is a wholesale energy affiliate of Georgia Power and the other retail operating companies.  Southern Power Company began business in 2001 and owns and manages generating assets and serves territorial requirements loads in Georgia and other parts of the Southeast. Southern Power also provides capacity and energy to Georgia Power, Alabama Power, and Gulf Power through purchase power agreements. The five entities separately own their generation facilities; however, the composite system is operated as a tight pool and includes close coordination in planning among the four retail operating companies to achieve the maximum efficiency possible.  This practice allows cost savings in the construction and operation for the retail operating companies.  A coordinated integrated expansion planning study is performed as requested by the four retail operating companies in order to update the expected resource additions necessary to supply the projected load for individual companies.  Southern Power produces its own separate generation expansion plan which is then coordinated with the other companies’ plan.  All Southern Power loads, obligations and non-requirements load and assets were aggregated in the planning process.

In developing a resource expansion plan, it is important to consider both investment risk and plan flexibility.  The expansion plan needs to be flexible enough to adapt to the changing forecasts of load growth, inflation, construction escalation rates, fuel prices, and the cost of capital.  Also, the expansion plan should be flexible with respect to changing environmental law and/or regulation.  In addition, the investment risk associated with adding generation must be considered.  There is risk inherent with managing the construction process in connection with the addition of generation.  During construction of a plant, the state of the regional or national economy could change, resulting in slower than anticipated load growth.  This could delay the need for additional capacity.  Risk assessment also includes considering the benefits of fuel diversity and evaluating the availability of various fuels.

The main optimization tool used in the mix analysis is the PROVIEW™ module in Strategist®. The Strategist® model uses many data inputs and assumptions in the process of optimizing system generation additions for the retail operating companies; the key assumptions are load forecasts, DSOs, candidate units, reserve margin, cost of capital, fuel forecast and escalation rates.

PROVIEW™ uses a dynamic programming technique to develop the optimum resource mix (see Appendix G for a description of the algorithm).  This technique allows PROVIEW™ to evaluate, in every year, each combination of generation additions that satisfy the reserve margin constraint.  For each combination, annual operating costs are simulated and are added to the construction costs required to build that particular combination of resource additions.  A least cost resource plan is developed only after reviewing many construction options.

Candidate units for mix analysis were selected based upon the results of generation busbar analysis.  Factors including cost and performance, maturity of technology, environmental issues, and risk to the system are considered when selecting candidate units.  The candidate units for this study are:

- REDACTED MW  Base Load Pulverized Coal with CCS (“PC” or “PC w/CCS”)

- REDACTED MW  Base Load Nuclear (“Nuclear”)

- REDACTED MW  Base/Intermediate Load ‘G’ Combined Cycle (“CC”)

- REDACTED MW  Base/Intermediate Load ‘G’ Combined Cycle (“CC”) with CCS

- REDACTED MW  Peaking Load Dual Fuel Combustion Turbine (“CT”)

Note: All MW output values are net of station service.

SCG Engineering provided the candidate unit data that forms the basis of comparison among various technologies. This data includes $/kW EPC cost, construction schedule, heat rate, fuel type and emission rates.  This data was also used in busbar comparisons that are developed to review the relative economics of each candidate technology.  A busbar analysis is simply a calculation, over a range of capacity factors, of the total (fixed and variable) cost per kilowatt-hour to operate a generating unit. Busbar analysis is used to screen generating technologies and develop recommendations in the selection process of the candidate technologies carried forward into the resource mix analysis.

The reserve margin constraint used to develop the least cost resource addition schedule coincides with the present planning reserve guideline which recommends a 15% system planning target reserve margin.

# DATA ASSUMPTIONS

## STRATEGIST® SUB-PERIOD DEFINITION

For an accurate estimation of production cost, Strategist® divides the day into peak and off peak hours called sub-periods for dispatch of the available resources.  This feature provides a more realistic estimation of the operation of cycling and storage units with the load variations.  For accuracy of modeling, pump storage units were allowed to do pumping in the off peak sub-period and operate in generation mode during the peak sub-period.

Table 1 shows the typical week periods that were modeled in Strategist®.  With changing load pattern over various seasons, hours included in each of the sub-periods are changed.  Also the lower load hours over the weekend are modeled to be in the off peak sub-period.

- Strategist® Sub-Period Definition of Hours

|  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| January | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| February | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| March | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| April | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| May | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| June | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| July | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| August | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| September | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| October | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| November | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| December | Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
|  | Off-Peak | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |

## HYDRO UNIT MODELING

The system conventional hydro energy was modeled as having two components: run of river and peak shaving.  The two components were modeled as separate units.  The energy and capacity of each type were derived from the records of historical operation of the Southern hydroelectric system.  The run of river units were allowed to have a capacity factor of 100% while the peak shaving units have much lower capacity factors.  The seasonal variation in the availability of total as well as firm hydro energy was modeled by monthly variations in the energy and capacity of each type.

## DEMAND-SIDE OPTIONS MODELING

Dispatchable DSOs (interruptible load and other options that are controllable and/or dispatchable by a utility) were included as capacity resources in this study.  Each interruptible contract load was appropriately adjusted to equate it to the supply side by one or a combination of the following corresponding factors: availability factor, loss factor, and the Incremental Capacity Equivalent (“ICE”) Factor (which was based on the 2012 ICE Factor Review conducted by SCS Resource Planning).  For all operating companies, non-dispatchable DSOs (options such as insulation or end-use equipment’s energy efficiency which are not directly controllable by the utility) are accounted for in the load forecast.

## FINANCIAL ASSUMPTIONS

Table 2 details the capital structure and weighted costs used in the mix study.  Table 3 shows the escalation rates based on the Moody’s Analytics March 2012 Forecast except as noted.

- Capital Structure

| Component | Ratio | Cost | Weighted | After Tax | Pretax |
| --- | --- | --- | --- | --- | --- |
| Debt | 50% | REDACTED | REDACTED | REDACTED | REDACTED |
| Preferred | 5% | REDACTED | REDACTED | REDACTED | REDACTED |
| Equity | 45% | REDACTED | REDACTED | REDACTED | REDACTED |
| Weighted Cost |  |  | REDACTED | REDACTED | REDACTED |

- Discount and Inflation Rates

| Component | Cost |
| --- | --- |
| Discount Rate | REDACTED |
| Construction Escalation Rate | REDACTED |
| Long-Term Inflation Rate | REDACTED |
| Variable O&M | REDACTED |
| Fixed O&M | REDACTED |

## EXISTING UNITS

A discussion of the Strategist® inputs associated with the existing units can be found in Section 1.2. The data consists of the following:

Unit Ratings – This information based on data provided fall 2012 by each operating company

In-Service Dates

Retirement Dates – The approved unit retirement date was provided by each operating company

Projected Unavailability Dates – The most recent assumptions were provided by each operating company

## CANDIDATE UNITS

### Candidate Unit Installation Costs

Candidate units were selected based upon the results of busbar analysis.  As Table 4 shows, the candidate units for this study are base load coal with CCS, base load nuclear, combined cycle, combined cycle with CCS, and a peaking combustion turbine.  The overnight construction cost, design data, reliability data, and operating and maintenance costs for these technologies are contained in the attached 2013 Integrated Resource Plan Generation Technology Data Book prepared by SCG Engineering.

- Candidate Technology Assumptions

|  | Base Load Pulverized Coal PRB with CCS | Base Load Nuclear | Intermediate Combined Cycle – “G” | Intermediate Combined Cycle – “G” with CCS | Peaking Combustion Turbine |
| --- | --- | --- | --- | --- | --- |
| Installed Cost $/KW | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| Installed / In service Year | ## REDACTED | REDACTED | ## REDACTED | ## REDACTED | ## REDACTED |
| Heat Rate | REDACTED (BTU/KWh) | REDACTED (BTU/KWh) | REDACTED (BTU/KWh) | REDACTED (BTU/KWh) | REDACTED (BTU/KWh) |
| Size (MW) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |
| Life (Years) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED |

Spending Curves:

- Table 5 shows the direct spending curves used to spread the overnight construction cost over the entire construction period.

- Direct Spending Curves

| Year | CT | CC | Base Coal | Base Nuclear |
| --- | --- | --- | --- | --- |
| 1 | REDACTED | REDACTED | REDACTED | REDACTED |
| 2 | REDACTED | REDACTED | REDACTED | REDACTED |
| 3 | REDACTED | REDACTED | REDACTED | REDACTED |
| 4 | REDACTED | REDACTED | REDACTED | REDACTED |
| 5 | REDACTED | REDACTED | REDACTED | REDACTED |
| 6 | REDACTED | REDACTED | REDACTED | REDACTED |
| 7 | REDACTED | REDACTED | REDACTED | REDACTED |
| 8 | REDACTED | REDACTED | REDACTED | REDACTED |
| 9 | REDACTED | REDACTED | REDACTED | REDACTED |
| 10 | REDACTED | REDACTED | REDACTED | REDACTED |
| 11 | REDACTED | REDACTED | REDACTED | REDACTED |
| 12 | REDACTED | REDACTED | REDACTED | REDACTED |
| Total | REDACTED | REDACTED | REDACTED | REDACTED |

### Escalation and Performance Assumptions

Real escalation and performance assumptions, for all technologies, were developed by SCG Engineering. The real escalation is assumed to be REDACTED% for the entire planning period. This was modeled in PROVIEW™ by having construction costs for all technologies inflate at REDACTED percentage points for the duration of the planning period.

### Unit Sizes for Mix Study

The PROVIEW™ model selects new units based on minimizing total operating and capital costs. From Section 2 above, the generic size of each candidate technology is as follows: Coal REDACTED MW, Nuclear REDACTED MW, CC ‘G’ REDACTED MW, CC ‘G’ with CCS REDACTED MW and CT REDACTED MW.  If these sizes were used, the optimum resource schedule would be biased toward picking the units that happen to be the size which equals or slightly exceeds the minimum reserve margin constraint.  In order to avoid this bias, a unit size of 300 MW was considered for all technologies.  The model adds resources in multiples of 300 MW.  The actual unit additions are matched as closely as possible to this resource schedule of 300 MW units.  For a slight improvement in accuracy, a smaller unit size (200, 100 MW) can be used, resulting in a considerable increase in the analysis time.  However, for a system the size of Southern, a 300 MW unit size is appropriate.

### Carbon Capture and Storage for Generic Units

Carbon capture and storage is seen as a potential technology that can lower costs of electricity production under a legislative regime regulating carbon dioxide emissions.  Fossil fuel units outfitted with CCS technology can either strip carbon dioxide before combustion – as is the case with IGCC plants – or post combustion in pulverized coal and natural gas combined-cycle units.  The two technologies are described further in the Generation Technology Data Book (Technical Appendix 1A).  Estimates for IGCC technology outfitted with CCS were provided by SCG Engineering based on discussions with vendors.  Post-combustion CCS technology is still an emerging technology, and for this study the additional cost of adding CCS to pulverized coal and combined-cycle units were derived from EPRI and DOE technology assessments.  The table below shows the cost increases applied to generic pulverized coal and combined-cycle estimates in order to estimate units outfitted with CCS.  Estimates for heat rate and capital cost increases on pulverized coal units were developed by Southern Company based on early experience at the 25-MW pilot study at Plant Barry in Alabama.

- Increases applied to generic units to simulate CCS technology

|  | Pulverized Coal with CCS | Combined Cycle with CCS |
| --- | --- | --- |
| Heat Rate | REDACTED | REDACTED |
| Variable O&M | REDACTED | REDACTED |
| Fixed O&M | REDACTED | REDACTED |
| Capital Cost | REDACTED | REDACTED |

## FUEL PRICES

Near term base fuel costs are based on the Southern Company fuel budgeting process.  Long term base fuel costs are based on forecasts developed for Southern Company by CRA.  Representative fuel price projection curves for coal, nuclear, gas and oil are given in Figure 3.7.1.

Figure 3.7.1 - Fuel Cost Projections

### Candidate Unit Fuel Prices

The candidate unit coal price is based on 0.35% sulfur coal and is used as the proxy price for all coal technologies with emissions respective to the assumed fuel type.  The candidate unit nuclear price is based on an average of the potential plant location within the Southern system.  The candidate unit gas price is a load weighted average, by operating company, of several potential plant locations throughout the Southern system.  Intermediate load combined cycle additions include the cost of contracting for firm natural gas delivery.  Peaking combustion turbines are expected to utilize firm natural gas supply during summer months, interruptible natural gas contracts during the non-summer months and, where permitted, will operate on #2 fuel oil during periods of curtailment.

## LOADS

### Load Forecasts

Load forecasts were provided by each retail operating company.  More information on load forecasts can be found in the Load and Energy Forecast in Technical Appendix Volume 2.

### Load Shapes

The load shape used in Strategist® was derived from forecasted hourly load data for the retail operating companies.  The development of the load profile used in Strategist® is described below.

#### Representative Load Profiles (Seed Shapes)

Representative load profiles have been assembled and maintained for each operating company.  Each company’s seed shape contains one year (8760 hours) of load data.

#### Company Load Shape

The monthly demand and energy forecasts provided in each operating company’s load forecast were utilized by the load shaping program, along with the company seed shape, to produce the initial year of company load data.  If the future years of the company load forecast represent typical load growth, each additional year is assumed to have the same shape as the initial year.  If the load forecast includes additional influences (such as the introduction of affordable and practical electrical vehicles) each additional year must be represented with a seed shape; typically, the previous year of company load data output becomes the current seed shape unless a specific user-supplied seed shape is utilized.

#### retail operating Companies’ Load Shape

The system load shape is the sum of each retail operating company 8760-hour load shape with each month’s peak constrained to fit the user-supplied diversity constraints.  The diversity constraint is user supplied as a monthly percent diversity to forecast the system monthly target from the sum of each individual company monthly peak.  The diversity percentages are based on a historical ten-year average of monthly diversities from 2002 through 2011 and can be found in Appendix D.

#### retail operating Companies’ STRATEGIST® Load Shape

The seed load shape used in Strategist® was derived from historical 8760 hourly recorded load.  The data was converted to typical week (168 hours) holding official monthly peaks and energy forecasts.  Load forecast peaks and energies were then incorporated on a monthly basis.

# SELECTION OF CANDIDATE UNITS

The candidate generating units investigated were selected based on the results of generation busbar analysis.  The candidate generating technologies considered for future installation on the Southern Electric System are:

- REDACTED MW  Base Load Pulverized Coal with CCS (net of station service)

- REDACTED MW  Base Load Nuclear (net of station service)

- REDACTED MW  Intermediate Load ‘G’ Combined Cycle (net of station service)

- REDACTED MW  Intermediate Load ‘G’ Combined Cycle (“CC”) with CCS (net of station service)

- REDACTED MW  Peaking Load Dual Fuel Combustion Turbine (net of station service)

A screening of numerous electric generating and energy storage technologies was conducted utilizing Electric Power Research Institute TAG (Technology Assessment Guide) unit data combined with SCG Engineering and Research & Environmental Affairs data for cost comparison.  The EPRI data covers both conventional technologies and developing technologies.  Thirty-nine different electric generating technologies were included in the initial screening.  Technology cost projections were analyzed using a generation busbar screening that depicts the levelized annual revenue per kilowatt versus the technology's capacity factor.

The candidate units were then selected based on the results of the busbar assessment concerning the maturity of the technology, its cost, an evaluation of risk associated with installing the technology on the Southern Electric System, and various other factors.

In general, the operating characteristics and the projected costs associated with installing a more mature or "proven" technology can be more accurately anticipated than a less mature technology.  As a result, cost estimates for proven technologies can be developed with more confidence than estimates for an immature technology.  Even though cost is an important aspect of evaluating technologies, risk factors associated with installing a technology must be considered.  These risk factors include construction lead time, fuel diversity, environmental considerations, and operational flexibility.

Since the Southern Electric System must anticipate future generation requirements far enough in advance to allow for ample construction lead time, technologies that require longer lead times inherently have more risk.  Load growth forecasts, the inflation outlook, anticipated fuel prices, and financing costs will tend to change during the time lag between the start of a project and its completion.  As the construction lead time is increased, there is more opportunity for the general health of the economy to change.  In addition, environmental factors must be considered in evaluating technologies.  The environmental legislation regulating the operation of utility generation is subject to change.  As a result, the candidate technologies must be selected with present and potential emission compliance issues considered.

Additionally, future improvements in real cost and operating efficiency associated with anticipated technological advancement of the design and manufacturing process were projected (see Generation Technology Data Book found in Technical Appendix Volume 1).

# RECOMMENDATION

The following base case capacity addition schedule was used as an input to the integrated resource planning process for the Southern Electric System.  The table below shows the recommended capacity addition schedule based on 300 MW capacity block sizes.  Adjustments to this schedule may be required to utilize actual unit sizes when developing the IRP and to meet the minimum target reserve margin.

- The Base Case

This schedule represents the lowest cost sequence of generic generation additions to the Southern Electric System when utilizing the base case assumptions.  This schedule is the result of optimizing generation requirements based upon a minimum reserve margin, the base case load forecast, DSOs, and generation capital costs.  Currently, the planning reserve margin target is 15%.

The conclusion of this study, based upon the results of the base case, sensitivities and planning scenario case analyses, is that additional generation capacity requirements will likely be satisfied with a mixture of combustion turbine, combined cycle, combined cycle with CCS and nuclear (or purchases).

# DISCUSSION OF RESULTS

## THE REFERENCE CASE

For the 2013 IRP, the reference case is identical to the base case and is shown in the table below.  The reference case was used to evaluate sensitivities where appropriate. These results indicate that additional generation capacity requirements will likely be satisfied with a mixture of REDACTED and                                                                       REDACTED   REDACTED   REDACTED.  The    reference    case     was    allowed to optimize starting in year 2013. Capital cost projections will be reviewed as input data assumptions are updated.  As mentioned earlier, the PROVIEW™ slice or block size in this case and all scenario and sensitivity cases discussed in the following sections is 300 MW.

- The Reference Case

## LOAD FORECASTING VARIATIONS

- No Load Growth

For the no load growth case, the load forecasts were held constant at 2013 levels throughout the planning period.  As shown in the following table, no load growth reduced  the  need for    REDACTED   slices and   REDACTED   slices  during  the twenty-year planning period.

- No Load Growth

- High Load Growth

The results of the high load growth sensitivity are shown in the following table.  The load forecast for this sensitivity was developed by GPC Load Forecasting to represent an optimistic forecast of load growth for Georgia Power Company. Over the twenty-year planning period,    REDACTED    slices, and    REDACTED    slices   were   added   to   the   generation mix.    The  need  for  additional capacity was first seen in REDACTED and then REDACTED.

- High Load Growth Case

- Low Load Growth

The results of the low load growth sensitivity are shown in the following table.  The load forecast for this case was developed by GPC Load Forecasting to represent a pessimistic forecast of load growth for Georgia Power Company.  The low load growth  sensitivity  reduced  the  need  for   REDACTED.  The  decreased  need for capacity is first seen in REDACTED.

- Low Load Growth Case

## UNIT AVAILABILITY

- Unit Availability Increase

The results of increasing unit availability are shown in the following table.  For this case, unit availability was increased for all units by lowering EFOR by 5%.  This sensitivity    resulted    in    REDACTED    and    REDACTED    within   the   twenty-year planning period.

- Unit Availability Increase

- Unit Availability Decrease

The results of decreasing unit availability are shown in the following table.  For this case, unit availability was decreased for all units by increasing EFOR by 5%.  This sensitivity resulted in trade-off between REDACTED and REDACTED technologies beginning in REDACTED but resulted in REDACTED over the twenty-year planning period.

- Unit Availability Decrease

## RATE IMPACT ANALYSIS

- See rate impact analysis in the Financial Review Section found in Technical Appendix Volume 2.

## IN SERVICE DATES OF SUPPLY AND DEMAND RESOURCES

- No Non-dispatchable DSM

The results of the no non-dispatchable DSM sensitivity are shown in the following table.  The load forecast for this case was developed by GPC Load Forecasting to represent a no non-dispatchable DSM forecast for Georgia Power Company.  The no non-dispatchable DSM case resulted in   REDACTED   and   REDACTED   within the twenty-year planning period.

- No Non-dispatchable DSM

- Aggressive Non-dispatchable DSM Expansion

For Case 5, additional measures, programs and incentives were added to achieve higher market penetration in order to achieve REDACTED energy reductions by 2023 as outlined in the nine step process approved by the GPSC.  The programs begin in REDACTED and ramp up until REDACTED; ramp up continues at a slower pace through REDACTED.  As seen in the following table, the increase in DSM programs reduced the need for additional generation capacity by    REDACTED    and    REDACTED.  Additionally, the first year of generation need was delayed to REDACTED, compared to REDACTED in the Reference Case.

- Aggressive Non-dispatchable DSM Expansion

- Combustion Turbines Only for the First Five Years of Need

For this sensitivity, combustion turbines were the only technology available for the first five years of need.  As seen in the following table,   REDACTED   replaced REDACTED in REDACTED.  The following year, REDACTED replaced REDACTED.

- Combustion Turbines Only for the First Five Years of Need

## AVAILABILITY AND COST OF PURCHASE POWER

- Economy Energy Purchase

This sensitivity includes economy purchases of REDACTED MW during the peak hours of summer months and REDACTED MW during the peak hours of non-summer months.  As   shown   in   the   following   table,   this   case  resulted  in     REDACTED    and REDACTED during the twenty-year planning period.

- Economy Energy Purchase

## PENDING FEDERAL AND/OR STATE LEGISLATION OR REGULATION

See Section 6.10.

## FUEL PRICES

See Section 6.10

## INFLATION IN PLANT CONSTRUCTION COSTS AND COST OF CAPITAL

- High Cost of Capital

The effects of elevated cost of capital were evaluated by assuming a REDACTED% increase in the cost of the capital funding sources.  This case assumed cost of debt @ REDACTED%, cost of preferred @ REDACTED% and cost of common equity @ REDACTED%.  The capital structure of 50% debt, 5% preferred and 45% common equity was not changed from the base case.  The resulting discount rate increased by approximately REDACTED basis points from the base case.   As shown in the following table, the result was  REDACTED  being replaced by  REDACTED  in REDACTED. In the following year, REDACTED was replaced by REDACTED.

- High Cost of Capital

- Double the Construction Escalation Rate

The effect of doubling the construction escalation rate was evaluated by increasing the current escalation rate of REDACTED% to REDACTED% and calculating new construction cost of generic unit additions.   As shown in the following table, this case resulted in REDACTED during the twenty-year planning period.

- Double the Construction Escalation Rate

- Triple the Construction Escalation Rate

The effects of tripling the construction escalation rate was evaluated by increasing the current escalation rate of REDACTED% to REDACTED% and calculating new construction cost of generic unit additions.  As shown in the following table, this case resulted in REDACTED          being    replaced   by         REDACTED         during    the twenty-year planning period.

- Triple the Construction Escalation Rate

## Planning Scenario Cases

With its scenario modeling consultant, Charles River Associates (“CRA”), the Company developed three possible future CO2 views and three possible future natural gas market views.  The scenarios created by the combination of these CO2 views and natural gas views were developed to represent a range of plausible outcomes.  Each of the nine scenarios provides an internally-consistent view of fuel, electricity and other markets in the US economy.  Figure 6.10.1 depicts and summarizes the nine combinations of natural gas price and CO2 cost used to develop the scenario cases.  For details on the scenario planning process, please see Technical Appendix Volume 1, Mix Study Appendix I.

Figure 6.10.1 – Natural Gas and CO2 Price Matrix

|  |  | CO2 Views |  |  |
| --- | --- | --- | --- | --- |
| Fuel Views |  | Existing | Moderate | Substantial |
|  | High |  |  |  |
|  | Moderate |  |  |  |
|  | Low |  |  |  |

Retirement Assumptions for Planning Scenario Cases

As referenced in Section 1.2 above, a projected System fleet transition plan was developed by each Retail Operating Company and coordinated through the system planning process.  Using the retirement screening results for the determination of continued, unavailable or retired status for the specified units which included the consideration of other issues and risk, the coordinated planning process ultimately determined one respective list of units to be assumed unavailable across all scenarios.

- Low Gas Existing Carbon

As shown in the following table, the existing carbon with low natural gas prices and the   associated   loads,   resulted   in    REDACTED    and    REDACTED    generation being added over the planning period.

- Effects of Low Gas Existing Carbon

- Moderate Gas Existing Carbon

As shown in the following table, the existing carbon with moderate natural gas prices and the associated loads resulted in REDACTED over the planning period.

- Effects of Moderate Gas Existing Carbon

- High Gas Existing Carbon

As shown in the following table, the existing carbon with high natural gas prices and    the    associated   loads    resulted   in     REDACTED,     REDACTED     and    REDACTED    over the planning period.

- Effects of High Gas Existing Carbon

- Low Gas Moderate Carbon

As shown in the following table, the moderate carbon with low natural gas prices and      the      associated      loads,      resulted      in      REDACTED,    REDACTED,               REDACTED,               and                REDACTED            over the planning period.

- Effects of Low Gas Moderate Carbon

- Moderate Gas Moderate Carbon

As shown in the following table, the moderate carbon with moderate natural gas prices   and   the   associated   loads,   resulted   in      REDACTED,    REDACTED,             REDACTED,               and              REDACTED                over the planning period.

- Effects of Moderate Gas Moderate Carbon

- High Gas Moderate Carbon

As shown in the following table, the moderate carbon high natural gas prices and the    associated    loads,    resulted     in       REDACTED,                    REDACTED,            REDACTED,               and                   REDACTED             over the planning period.

- Effects of High Gas Moderate Carbon

- Low Gas Substantial Carbon

As shown in the following table, the substantial carbon with low natural gas prices and     the    associated    loads,    resulted    in        REDACTED,        REDACTED,           REDACTED,         and          REDACTED                              over the planning period.

- Effects of Low Gas Substantial Carbon

- Moderate Gas Substantial Carbon

As shown in the following table, the substantial carbon with moderate natural gas prices    and    the    associated    loads,    resulted     in       REDACTED, REDACTED,         REDACTED,         and        REDACTED                                 over the planning period.

- Effects of Moderate Gas Substantial Carbon

- High Gas Substantial Carbon

As shown in the following table, the substantial carbon with high natural gas prices and        the    associated    loads,    resulted    in        REDACTED,      REDACTED,             REDACTED,           and             REDACTED                     over the planning period.

- Effects of High Gas Substantial Carbon

## SENSITIVITY RESULTS SUMMARY

The results of the sensitivity analyses are summarized in Appendix H.

Construction escalation rate was developed by Southern Company Generation - Engineering and Construction Services.

Installed cost is the overnight cost plus escalation, AFUDC and ad valorem taxes during construction. Dollar basis is nominal for in-service year.