BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S THIRTEENTH SEMI-ANNUAL VOGTLE CONSTRUCTION MONITORING REPORT | DOCKET NO. 29849 |
| --- | --- |

|  | DIRECT TESTIMONY |  |
| --- | --- | --- |
|  | AND EXHIBITS |  |
|  | OF |  |
|  | PHILIP HAYET |  |

|  | ON BEHALF OF THE |  |
| --- | --- | --- |

|  | GEORGIA PUBLIC SERVICE COMMISSION |  |
| --- | --- | --- |
|  | PUBLIC INTEREST ADVOCACY STAFF |  |

|  | NOVEMBER 20, 2015 |  |
| --- | --- | --- |

TABLE OF CONTENTS

I.	INTRODUCTION	2

II.	COST TO COMPLETE ECONOMIC EVALUATIONS	5

III.	IMPACTS OF PROJECT DELAY AND OTHER ASSUMPTION CHANGES SINCE CERTIFICATION	10

IV.	OTHER ISSUES	14

# INTRODUCTION

Q.	PLEASE STATE YOUR NAME AND BUSINESS ADDRESS.

A.	Philip Hayet, 215 Huntcliff Terrace, Atlanta, Georgia, 30350.

Q.	WHAT IS YOUR OCCUPATION AND WHERE ARE YOU EMPLOYED?

A.	I am a utility and planning consultant, and President of Hayet Power Systems Consulting (“HPSC”).

Q. 	WHAT CONSULTING SERVICES DOES HPSC PROVIDE?

A. 	HPSC provides consulting services related to electric utility system planning, resource analysis, production cost modeling, and utility industry policy issues.

Q.	PLEASE SUMMARIZE YOUR EDUCATION AND QUALIFICATIONS.

A.	I earned a Bachelor of Science degree in Electrical Engineering from Purdue University in 1979, and a Master of Science degree in Electrical Engineering, with a specialization in Power Systems in 1980 from the Georgia Institute of Technology.  I have over thirty years of experience working in the electric utility industry.  More details regarding my educational background, professional qualifications, and appearances in regulatory proceedings may be found in Exhibit No. (STF-Hayet-1).

Q.	HAVE YOU PREVIOUSLY TESTIFIED AT THE GEORGIA PUBLIC SERVICE COMMISSION (“GPSC” OR THE “COMMISSION”)?

Yes, I have testified at the GPSC on numerous occasions including in Georgia Power Company’s (“Company” or “Georgia Power”) Application for Certification of Vogtle Units 3 and 4 (Docket No. 27800), and in all of Georgia Power Company’s prior Semi-Annual Vogtle Construction Monitoring (“VCM”) proceedings in this docket (Docket No. 29849).

Q.	ON WHOSE BEHALF ARE YOU TESTIFYING AND WHAT ISSUES WILL YOU BE ADDRESSING IN THIS PROCEEDING?

A.	I am testifying on behalf of the Public Interest Advocacy Staff (“Staff”).  I discuss my review of the Company’s economic evaluations that were presented in its 13th VCM Report, as well as economic evaluations that I performed.

Q.	PLEASE SUMMARIZE YOUR FINDINGS AND RECOMMENDATIONS.

A.	Staff’s findings and recommendations are as follows:

- Staff compared its cost-to-complete economic evaluation to the Company’s and found that both evaluations indicate that completing Vogtle Units 3 & 4 (“the Units” or “the Project”) would be more economic than discontinuing construction and building an equivalent amount of combined cycle gas turbine (“CCGT”) capacity. However, as compared to the Company’s evaluation, Staff’s cost-to-complete economic evaluation indicates it is less economic to continue the project.

- The Commission’s Order in the 11th VCM proceeding stated, “….that in order to provide this Commission with an accurate and complete picture, Georgia Power and PIA Staff shall, in future Monitoring proceedings, examine both the potential benefits and detriments in their analyses….”  As such, Staff presents updated results from the 12th VCM that accounts for the impact of the recently announced proposed settlement of the litigation with the Consortium.  Based on its assumptions, Staff has determined that the incremental Project benefits since Certification have been completely eliminated by the detriments.

- Staff recommends that the Company continue to perform economic analyses of delay scenarios of 24, 36 and 48 months from the current commercial operation dates (“COD”) of the Units, as was done in previous VCM filings.  Staff also recommends that for each delay scenario, the Company should provide Total Project Cost results, and the full embedded cost revenue requirements associated with the Total Project Cost results that the Company expects customers will incur both during construction and over the operating lives of the Units.

Q.	WHAT IS THE COMPANY’S CURRENT PROJECTION FOR THE TOTAL PROJECT COST (CONSTRUCTION AND CAPITAL COSTS PLUS FINANCING COSTS)?

A.	The Company’s current estimate of Total Project Cost is $7.453 billion, which includes $5.045 billion associated with construction and capital costs, and $2.408 billion for financing costs being incurred during the construction period.  This forecast currently exceeds the Certified Total Project Cost of $6.113 billion by approximately $1.340 billion, which is a 22% increase in the cost estimate since Certification.  The Company’s current Total Project Cost estimate of $7.453 billion has decreased by $65 million since the 12th VCM proceeding due to lower projected financing costs.

Q.	HOW MUCH HAS GEORGIA POWER SPENT ON CONSTRUCTION AND CAPITAL AND WHAT FINANCING COSTS HAS THE COMPANY INCURRED THROUGH THE END OF THE 13th VCM PERIOD?

A. 	According to Table 1.1, on page 6 of the 13th VCM Report, $3.113 billion has been spent for Construction and Capital Costs associated with the Project, and $0.866 billion of financing cost has been incurred for a Total Project Cost of $3.980 billion as of June 30, 2015.  Based on the Company’s updated estimate of $7.453 billion for the Total Project Cost, the remaining cost-to-complete the Project is approximately $3.473 billion.

# COST TO COMPLETE ECONOMIC EVALUATIONS

Q.	PLEASE DESCRIBE THE COST TO COMPLETE ECONOMIC EVALUATION METHODOLOGY.

A.	The Company compares the revenue requirements associated with the remaining capital/construction and financing costs, and all operating costs of the Units to the next best generation alternative, in which the discontinued Vogtle Units are replaced by building a comparable amount of CCGT capacity.  Although only the revenue requirement on future (to be incurred) capital costs of the nuclear units is captured in the Vogtle 3 and 4 case, the revenue requirement on the entire capital cost of comparable CCGT units is captured in the next best alternative generation case.

Other Project costs and offsets, including decommissioning costs, pre- and post-Commercial Operating Date (“COD”) operating and maintenance expenses (“O&M”), nuclear fuel costs, spent nuclear fuel storage costs, Production Tax Credits (“PTC”), and Department of Energy (“DOE”) loan guarantees are accounted for as well.  All CCGT operating costs are captured in the next best alternative generation case.  On a cost-to-complete basis the case with the lowest present value of revenue requirements ("PVRR") is determined to be the most economic option.

Q.	WHAT SCENARIOS DID GEORGIA POWER PRESENT IN THIS FILING?

A.	The scenarios the Company performed, with some updated assumptions, were the same as the Company performed in the 12th VCM proceeding:

- 39 month delay case – Units delayed until July 1, 2019 and July 1, 2020, respectively.

- 63 month delay case – Units delayed until July 1, 2021 and July 1, 2022, respectively.

- 75 month delay case – Units delayed until July 1, 2022 and July 1, 2023, respectively.

- 87 month delay case – Units delayed until July 1, 2023 and July 1, 2024, respectively.

Q.	WHAT IS THE REMAINING TOTAL PROJECT COST THAT THE COMPANY USED IN ITS ECONOMIC EVALUATION?

A. 	As mentioned previously, Table 1.1 in the Company’s 13th VCM Report indicates that based on a July 1, 2019/2020 In-Service Date projection for Vogtle 3 and 4, respectively, the total cost to complete the Vogtle Units is expected to be approximately $3.5 billion.  However, the Company used a lower value, approximately $2.4 billion, in its economic evaluations.

Q.	DOES STAFF AGREE THAT THE REMAINING TOTAL PROJECT COST USED IN ECONOMIC EVALUATIONS WOULD BE LOWER THAN THE ACTUAL REMAINING TOTAL PROJECT COST?

A. 	Yes.  The Company’s $2.4 billion value is lower primarily because sunk costs and future financing costs on those sunk costs are correctly excluded from the cost-to-complete economic analysis.  In addition, the actual $3.5 billion remaining amount reflects the remaining actual Project budget as of June 30, 2015, while the $2.4 billion cost-to-complete value is always calculated based on the remaining costs beginning the day after the Company files its VCM report, which in this case was August 29, 2015.  Finally, marginal financing rates are used in the Company’s economic evaluation, which are higher than the Company’s actual embedded financing rates.

Q.	WHAT ARE THE COMPANY’S REMAINING COST-TO-COMPLETE PROJECTIONS USED IN THE ECONOMIC EVALUATIONS FOR THE OTHER DELAY SCENARIOS?

A.	The remaining total Project cost-to-complete values assumed in the 63, 75, and 87 month delay cases are $3.1 billion, $3.4 billion and $3.7 billion, respectively.

Q.	WHAT MODELING ASSUMPTIONS CHANGED IN THE 13TH VCM AND WERE THE CHANGES MATERIAL?

A.	The remaining total Project cost-to-complete amounts changed and declined in the 13th VCM proceeding.  In the 2019/2020 In-Service Date case, the remaining cost-to-complete amount decreased from $2.7 billion in the 12th VCM to $2.4 billion in the current proceeding.  The Company also revised its marginal financing rates (marginal debt and preferred stock rates) in the 13th VCM.  For example, the Company reduced the weighted average cost of capital by about 25 basis points in the 13th VCM.  Consistent with prior August VCM filings, the Company did not change the fuel price forecasts, CO2 price forecasts, and load forecasts from what had been used in the last (12th) VCM proceeding.  Finally, the Company made minor changes, and in some cases no changes, to the nuclear fuel forecast, pre- and post-COD O&M costs, post-COD capital additions, PTC savings, market capacity costs, and CC capacity cost assumptions.

Q.	PLEASE DISCUSS THE COMPANY’S COST-TO-COMPLETE ECONOMIC EVALUATION RESULTS AND DISCUSS THE TREND IN THE RESULTS OVER THE LAST FEW VCM PROCEEDINGS.

A.	The following table provides the Company’s Vogtle economic evaluation results on an expected value cost-to-complete basis, comparing results from the 11th, 12th and 13th VCM proceedings.

Table 1

Georgia Power Nuclear Cost to Complete vs. CCGT (Expected NPVRR Difference) ($Billions) 11th VCM - 21 Month Delay $5.1 12th VCM - 39 Month Delay $3.1 13th VCM - 39 Month Delay $3.7

There was a large decrease in projected benefits to complete the Units between the 11th and 12th VCM proceedings due to the Company’s announced additional 18-month delay and $814 million increase in the Total Project Cost in the 12th VCM, as well as, the fact that the Company significantly lowered its fuel forecasts in the 12th VCM, which brought the Company’s fuel forecast to be closer in line with Staff’s.  In the 13th VCM, no further delays or cost increases were announced, and the Company used the same fuel forecast as it had used in the 12th VCM.  The increase in the benefit of completing the Units in the 13th VCM partially results from the remaining cost-to-complete the Project being lower now than it was in the 12th VCM.  The increase in the benefit also partially results from the 25 basis point drop in the weighted average cost of capital that the Company assumed in the 13th VCM proceeding.

Q.	DID STAFF PERFORM ANY ANALYSES IN THIS VCM PROCEEDING?

A.	Yes, as in prior VCM proceedings, Staff reviewed the Company’s economic evaluations and developed its own studies using Staff’s gas price forecast assumptions.  All other assumptions were the same as the Company supplied.

Q.	WHAT GAS PRICE FORECAST DID STAFF USE IN THIS PROCEEDING?

A.	For this proceeding, Staff relied on the same gas price forecast it developed in the 12th VCM.  In that proceeding, Staff relied on its own Low gas price forecast, which was significantly lower than the Company’s Low gas price forecast.  However, Staff adopted the Company’s Mod and High gas price forecasts because they were not materially different than Staff’s Mod and High forecasts.  Despite the fact that short-term natural gas prices have fallen since the 12th VCM, Staff believes its 12th VCM natural gas price forecast is still reasonable over the long-term.  Furthermore, Staff will perform additional investigation of long-term gas prices in the upcoming IRP, which will then be relied on in the 14th VCM proceeding.

Q.	HOW DOES THE COMPANY’S ESTIMATE OF THE BENEFIT OF COMPLETING VOGTLE COMPARE TO STAFF’S ESTIMATE?

A.	Since Staff and the Company used the same gas price forecasts in the 13th VCM proceeding as they had used in the 12th VCM, and the other modeling assumptions that changed were not substantial, the Company’s and Staff’s economic evaluation results continue to be in line with each other.  In the 13th VCM proceeding, the Company’s expected value benefit is $3.7 billion, and Staff’s is $3.5 billion, resulting in the Company’s estimate being greater by about 6%.

# IMPACTS OF PROJECT DELAY AND OTHER ASSUMPTION CHANGES SINCE CERTIFICATION

Q.	IN THE 11TH VCM, THE COMMISSION ORDERED STAFF AND THE COMPANY TO PROVIDE AN ACCURATE AND COMPLETE PICTURE BY ANALYZING BOTH POTENTIAL BENEFITS AND DETRIMENTS IN THEIR ANALYSES.  HAS STAFF UPDATED THE ANALYSIS IT PERFORMED IN THE 12TH VCM?

A.	Yes, Staff updated the two analyses it performed in the 12th VCM, which examine delay impacts on ratepayers since Certification.  The first analysis examines the delay impacts on the Total Project Cost.  This analysis includes the cost of incurring higher replacement fuel costs due to the delay, and the cost of the recently announced proposed settlement of the litigation with the Consortium.  For purposes of this analysis the replacement cost estimate that Staff derived in the 12th VCM proceeding, $606 million, and the recently announced proposed settlement amount, $350 million, were used.  Table 2 contains a simplified version of the Company’s Table 1.1 found on page 6 of the 13th VCM Report, and contains both Total Project Costs (Consortium EPC Construction & Capital cost, Owner’s cost, and financing cost), lost fuel savings cost, and the proposed litigation settlement amount.

TABLE 2

|  | Nominal - $Millions | Certification Case | 39 Mo. Delay with Announced Settlement |  |
| --- | --- | --- | --- | --- |
|  |  |  | 13th VCM Projection |  |
|  | Construction & Capital Cost | 4,418 | 5,045 |  |
|  | Financing Cost | 1,695 | 2,408 |  |
|  | Total Project Cost | 6,113 | 7,453 |  |
|  | Lost Fuel Savings (Expected) | 0 | 606 |  |
|  | Proposed Litigation Cost | 0 | 350 |  |
|  | Liquidated Damages Offset | 0 | 0 |  |
|  | Replacement and Litigation | 0 | 956 |  |
|  | Grand Total | 6,113 | 8,409 |  |

The table contains the Total Project Cost that was assumed at certification, and compares that to the Company’s latest estimate, which is based on a 39-month delay from the original In-Service dates.  It is assumed that Georgia Power will seek Commission approval to recover the Certified Amount of $6,113 million, plus an additional $2,296 million, an increase of 38%, for a total cost of $8,409 million.

Q.	PLEASE DISCUSS THE SECOND ANALYSIS STAFF PERFORMED, WHICH WAS RESPONSIVE TO THE COMMISSION’S ORDER IN THE 11TH VCM THAT REQUIRED THE COMPANY AND STAFF TO EVALUATE BOTH POTENTIAL BENEFITS AND DETRIMENTS IN THEIR ANALYSES.

A.	The second analysis examines the incremental total revenue requirements that ratepayers will be expected to pay over the construction and operating lives of the Units, compared to what had been anticipated at Certification.  This analysis captures all additional detriments and benefits to the Project that have been identified since Certification.  The delay will result in the Company incurring higher construction, additional financing, and additional replacement fuel costs during the delay period.  As a result of these higher delay related costs and the recently announced proposed settlement cost, higher revenue requirements will result both during the construction period and over the 60 year operating lives of the Units.

This analysis also accounts for the revenue requirement impact associated with all additional benefits that the Company has identified since certification, including the lower In-Service cost from the collection of financing costs during construction, the impact of Amendment 3 that locked in escalation indices, the benefit of 100% of the available PTCs instead of the 50% that was accounted for at Certification, the impact of lower interest costs from the DOE loan guarantee, and the drop in market interest rates.

Q.	HOW DID THIS ANALYSIS DIFFER FROM THE 12TH VCM PROCEEDING?

A.	Staff used the same results from the 12th VCM proceeding, and updated them to include the impact of the proposed $350 million settlement cost.  Table 3 contains the incremental revenue requirements that will likely occur after accounting for all additional detriments and benefits since Certification, including the incremental revenue requirement impact of the settlement.  Note that positive values in the table represent an increase in revenue requirement (detriment) and negative values represent a decrease in revenue requirement (benefit).

Table 3

| 13th VCM Projected Incremental Revenue Requirement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Since Certification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Pre COD |  | Post COD |  |  |  |  | Total |  |  |  |  |
|  |  |  |  | ($million) |  | ($million) |  |  |  |  | ($million) |  |  |  |  |
| Nominal |  |  |  | 1,987 |  | 2,429 |  |  |  |  | 4,416 |  |  |  |  |
| PV 2014 |  |  |  | 1,291 |  | (1,189) |  |  |  |  | 103 |  |  |  |  |

Overall, on a Nominal basis, revenue requirements will increase by $4,416 million and on a Present Value basis, revenue requirements will increase by $103 million when considering all additional benefits and detriments of the Project identified since Certification.  Based on the 12th VCM assumptions, updated to include the revenue requirement impact of the proposed $350 million settlement costs, these results indicate that on both a nominal cost and present value cost basis, the additional benefits would be fully eliminated by the additional detriments that have been identified since Certification.  Also, as I mentioned in my testimony in the 12th VCM proceeding, if the project is delayed further such that some of the PTCs are lost, the detriments would be even greater.

# OTHER ISSUES

Q.	DO YOU CONTINUE TO RECOMMEND THAT THE COMPANY PERFORM DELAY SCENARIOS?

A.	Yes.  Staff recommends that the Company continue to perform economic analyses of delay scenarios of 24, 36 and 48 months from the current COD of the Units, as was done in previous VCM filings.  Staff also recommends that for each delay scenario, the Company should provide Total Project Cost results, and the full embedded cost revenue requirements associated with the Total Project Cost results that the Company expects customers have and will continue to incur both during construction and over the operating lives of the Units.

Q.	DOES THIS CONCLUDE YOUR TESTIMONY?

A.	Yes it does.

BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S TWELFTH SEMI-ANNUAL VOGTLE CONSTRUCTION MONITORING REPORT | DOCKET NO. 29849 |
| --- | --- |

|  | EXHIBIT |  |
| --- | --- | --- |
|  | STF-Hayet-1 |  |

EDUCATION/CERTIFICATION

M.S., Electrical Engineering, Georgia Institute of Technology, 1980

B.S., Electrical Engineering, Purdue University, 1979

Cooperative Education Certificate, Purdue University, 1979

PROFESSIONAL AFFILIATIONS

National Society of Professional Engineers

Georgia Society of Professional Engineers

Institute of Electrical and Electronic Engineers

EXPERIENCE

Since completing his Master’s program, Mr. Hayet worked for fifteen years at Energy Management Associates, now Ventyx, providing consulting services and client service support to electric utility companies for the widely used planning models, PROMOD IV and STRATEGIST.  Mr. Hayet had an instrumental role in designing some of the modeling features of those tools including the competitive market modeling logic in STRATEGIST.

In 1995, Mr. Hayet began his own utility consulting firm, Hayet Power Systems Consulting (“HPSC”), and has worked for customers in the United States, and internationally in Australia, Japan, Singapore, Malaysia, the United Kingdom, and Vietnam.  Over his more than 30-year career, Mr. Hayet has provided consulting services to Public Utility Commissions, Regional Power Pools, State Energy Offices, Consumer Advocate Offices, Electric Utilities, Global Power Developers, and Industrial Companies.  Mr. Hayet’s expertise covers a number of areas including utility system planning and operations, RTO analysis, market price forecasting, Integrated Resource Planning, renewable resource evaluation, transmission planning, demand-side analysis, and economic analysis.

Though he continues to work for HPSC, in 2000 Mr. Hayet also joined the consulting firm of J. Kennedy & Associates, Inc. (“Kennedy and Associates”).  Since joining, Mr. Hayet worked on Kennedy and Associates’ projects that required utility resource planning, analysis, and software modeling expertise.  Mr. Hayet became a Vice-President and Principal of Kennedy and Associates in 2015.

Mr. Hayet has conducted numerous consulting studies in the areas of RTO Cost/Benefit Analysis, Renewable Resource Evaluation, Renewable Portfolio Standards Evaluation, Electric Market Price Forecasting, Generating Unit Cost/Benefit Analysis, Integrated Resource Planning, Demand-Side Management, Load Forecasting, Rate Case Analysis and Regulatory Support.

2000 to	J. Kennedy and Associates, Inc.

Present:	Vice President and Principal

- Initially began as Director of Consulting, became Vice President and Principal in 2015

- Managed electric related consulting projects.

- Responsible for business development.

- Clients include Staffs of Public Utility Commissions and other State Agencies, State Energy Offices, Global Power Developers, and Industrial Groups, and large energy users.

1996 to	Hayet Power Systems Consulting

Present:	President and Principal

- Managed electric utility related consulting projects

- Clients include Staffs of Public Utility Commissions and other State Agencies, State Energy Offices, Global Power Developers, and Industrial Groups, and large energy users.

1991 to	EDS Utilities Division, Atlanta, GA (Now Ventyx)

1996:		Lead Consultant, PROSCREEN (Now STRATEGIST) Department

- Managed a client services software team that supported approximately 75 users of the STRATEGIST electric utility strategic planning software.

- Participated in the development of STRATEGIST’s competitive market modeling features and the Network Economy Interchange Module

- Provided client management direction and support, and developed new consulting business opportunities.

- Performed system planning consulting studies including integrated resource planning, DSM analysis, marketing profitability studies, optimal reserve margin analyses, etc.

- Based on experience with PROMOD IV, converted numerous PROMOD IV databases to STRATEGIST, and performed benchmark analyses of the two models.

1988 to 	Energy Management Associates (EMA), Atlanta, GA

1991:		Manager, Production Analysis Department

- Served as Project Manager of a database modeling effort to create an integrated utility operations and generation planning database.  Database items were automatically fed into PROMOD IV.

- Supervised and directed a staff of five software developers working with a 4GL database programming language.

- Interfaced with clients to determine system software specifications, and provide ongoing client training and support

1980 to	Energy Management Associates (EMA), Atlanta, GA

1988:		Senior Consultant, PROMOD IV Department

- Provided client service support to EMA’s base of over 70 electric utility customers using the PROMOD IV probabilistic production cost simulation software.

- Provided consulting services in a number of areas including generation resource planning, regulatory support, and benchmarking.

##### TESTIMONY AND EXPERT WITNESS APPEARANCES

| Date | Case | Jurisdict |  | Party | Utility | Subject |
| --- | --- | --- | --- | --- | --- | --- |
| 09/98 | 97-035-01 | UT |  | Utah Committee for Consumer Services | PacifiCorp | Utah jurisdictional Net Power Costs, PacifiCorp Rate Case Proceeding |
| 07/01 | 01-035-01 | UT |  | Utah Committee for Consumer Services | PacifiCorp | Utah Jurisdictional Net Power costs in General Rate Case |
| 2001 | ER00-2854-000 | FERC |  | Louisiana Public Service Commission | Entergy | Proposed System Agreement Modifications |
| 07/02 | 02-035-002 | UT |  | Utah Committee for Consumer Services | PacifiCorp | Special contract for industrial consumer |
| 2002/2003 | U-25888 | LA |  | Louisiana Public Service Commission | Entergy | Investigation of retail issues related to the System Agreement |
| 2003 | U-27136 Subdocket A | LA |  | Louisiana Public Service Commission Staff | Entergy | Aging gas steam-fired retirement study |
| 07/03 | EL01-88-000 | FERC |  | Louisiana Public Service Commission | Entergy | Rough production cost equalization proceeding |
| 05/04 | 03-035-14 | UT |  | Utah Committee for Consumer Services | PacifiCorp | Development of a large QF avoided cost methodology |
| 06/04 | 17687-U 17688-U | GA |  | Georgia Public Service Commission Staff | Georgia Power and Savannah Electric | 2004 Integrated Resource Planning Studies |
| 08/04 | ER03-583-000 | FERC |  | Louisiana Public Service Commission | Entergy | Affiliate power purchase agreements |
| 11/04 | 03-035-19 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Industrial customer’s request for a special economic development tariff |
| 11/04 | 03-035-38 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Large QF proceeding. |
| 03/05 | 03-035-14 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Concerning PacifiCorp’s Schedule 38 avoided cost tariff and remaining unsubscribed capacity |
| 07/05 | 03-035-14 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Concerning PacifiCorp’s Schedule 38 avoided cost proceeding |
| 12/05 | 04-035-42 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Net power costs in General Rate Case |
| 04/06 | 05-035-54 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Certification request to expand Blundell Geothermal Power Station. Related to Mid-American Energy Holding’s Acquisition of PacifiCorp |
| 05/06 | 22403-U | GA | Georgia Public Service Commission Staff |  | Georgia Power and Savannah Electric | March 2006 fuel cost recovery filing |
| 2006 | 06-35-01 | UT | Utah Committee for Consumer Services |  | PacifiCorp | 2006 rate case, net power costs |
| 08/06 | U-21453 | LA | Louisiana Public Service Commission Staff |  | Entergy Gulf States | Jurisdictional separation. |
| 11/06 | U-25116 | LA | Louisiana Public Service Commission Staff |  | Entergy Louisiana | Fuel adjustment clause filings |
| 01/07 | 23540-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | November 2005 fuel cost recovery filing |
| 04/07 | 07-035-93 | UT | Utah Committee for Consumer Services |  | PacifiCorp | General Rate Case |
| 06/07 | 24505-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | 2007 Integrated Resource Planning |
| 10/07 | U-30334 | LA | Louisiana Public Service Commission Staff |  | Cleco Power | 2008 Short-Term RFP |
| 04/08 | 26794-U (FCR-20) | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fuel cost recovery filing |
| 2008 | 6630-CE-299 | WI | Wisconsin Industrial Energy Group, Inc. |  | WEPCO | Certification Proceeding for environmental upgrades at Oak Creek power plant |
| 07/08 | ER07-956 | FERC | Louisiana Public Service Commission |  | Entergy | 2006 rough production cost equalization compliance filing in the System Agreement case |
| 09/08 | 6680-CE-170 | WI | Wisconsin Industrial Energy Group, Inc. |  | Wisconsin Power and Light | Certification proceeding concerning Nelson-Dewey coal-fired generating unit |
| 11/08 | 08-1511-E-GI | WV | West Virginia Energy Users Group |  | Allegheny Power | Fuel cost recovery filing |
| 12/08 | 27800-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Vogtle 3 and 4 nuclear unit certification proceeding |
| 2008 | 08-035-35 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Chehalis Combine Cycle Power Plant based on a waiver of the RFP solicitation process certification proceeding |
| 07/09 | ER08-1056 | FERC | Louisiana Public Service Commission |  | Entergy | 2007 rough production cost equalization compliance filing in the System Agreement case |
| 07/09 | U-30975 | LA | Louisiana Public Service Commission Staff |  | SWEPCO and Cleco | Application to acquire the Oxbow Mine to supply Dolet Hills Power Station certification proceeding |
| 09/09 | E015/PA-09-526 | MN | Large Power Intervenors |  | Minnesota Power | Request for approval to purchase Square Butte’s 500 kV DC transmission line, restructure a coal based power purchase agreement |
| 09/09 | 09-035-23 Direct | UT | Utah Office of Consumer Services |  | PacifiCorp | 2009 rate case, net power costs |
| 10/09 | 09A-415E | CO | Public Utilities Commission of Colorado |  | Black Hills/Colorado | CPCN application to construct two LMS 100 natural gas combustion turbine units |
| 10/09 | 09-035-23 Surrebuttal | UT | Utah Office of Consumer Services |  | PacifiCorp | 2009 rate case, net power costs |
| 12/09 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | First Semi-Annual Vogtle Construction Monitoring Report |
| 12/09 | ER08-1224 | FERC | Louisiana Public Service Commission |  | Entergy | 2008 production costs used to develop bandwidth payments |
| 2009 | 09-2035-01 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2008 IRP |
| 01/10 | 28945-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fuel cost recovery filing |
| 2010 | EL09-61 | FERC | Louisiana Public Service Commission |  | Entergy | System Agreement, individual operating company sales |
| 06/10 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Second Semi-Annual Vogtle Construction Monitoring Report |
| 12/10 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Third Semi-Annual Vogtle Construction Monitoring Report |
| 01/11 | ER09-1350 Direct | FERC | Louisiana Public Service Commission |  | Entergy | 2008 production costs used to develop bandwidth payments |
| 02/11 | ER09-1350 Cross-Answering | FERC | Louisiana Public Service Commission |  | Entergy | 2008 production costs used to develop bandwidth payments |
| 04/11 | 33302-U (FCR-22) | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fuel cost recovery filing |
| 06/11 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fourth Semi-Annual Vogtle Construction Monitoring Report |
| 09/11 | U-31792 | LA | Louisiana Public Service Commission Staff |  | Cleco Power | Settlement agreement, CCPN to upgrade Madison 3 coal unit to accommodate biomass fuel |
| 11/11 | 26550-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Reacquisition of wholesale block capacity |
| 11/11 | 34218-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Decertification of two aging coal units, acquire PPA resources, approve IRP update |
| 12/11 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fifth Semi-Annual Vogtle Construction Monitoring Report |
| 03/12 | U-32148 | LA | Louisiana Public Service Commission Staff |  | Entergy | Change of Control Proceeding to move to Midwest ISO |
| 2012 | 20000-EA-400-11 | WY | Wyoming Industrial Energy Consumers |  | Rocky Mountain Power | Certification of environmental upgrades at Naughton 3 |
| 05/12 | 35277-U (FCR-23) | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fuel cost recovery filing |
| 05/12 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Sixth Semi-Annual Vogtle Construction Monitoring Report |
| 07/12 | 2012-00063 | KY | Kentucky Industrial Utility Customers, Inc. |  | Big Rivers | Environmental upgrades in compliance with MATS and CSAPR |
| 09/12 | U-32275 | LA | Louisiana Public Service Commission Staff |  | Dixie Electric Member Cooperative | Ten year power supply acquisition certification proceeding |
| 12/12 | EL09-61-002 Direct | FERC | Louisiana Public Service Commission |  | Entergy | Harm calculation, violation of System Agreement |
| 12/12 | U-32557 | LA | Louisiana Public Service Commission Staff |  | Entergy | Certification of 28 MW PPA for renewable energy capacity (RAIN waste heat) in accordance with LPSC’s Renewable Energy Pilot |
| 12/12 | U-29764 | LA | Louisiana Public Service Commission Staff |  | Entergy | Retail proceeding regarding termination of cross-PPAs |
| 12/12 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Seventh Semi-Annual Vogtle Construction Monitoring Report |
| 03/13 | EL09-61-002 Cross-Answering | FERC | Louisiana Public Service Commission |  | Entergy | Harm calculation, violation of System Agreement |
| 04/13 | 2012-00578 | KY | Kentucky Industrial Utility Customers, Inc. |  | Kentucky Power Company | Mitchell Certificate of Public Convenience and Necessity |
| 05/13 | 36498-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | 2013 IRP and request to decertify over 2,000 MW of coal-fired capacity |
| 07/13 | U-32785 | LA | Louisiana Public Service Commission Staff |  | Entergy | 8.5 MW PPA for renewable energy capacity (Agrilectric rice hull)in accordance with LPSC’s Renewable Energy Pilot |
| 08/13 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Eighth Semi-Annual Vogtle Construction Monitoring Report |
| 10/13 | 2013-00199 | KY | Kentucky Industrial Utility Customers, Inc. |  | Big Rivers | Base rate case |
| 05/14 | 13-035-184 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2014 General Rate Case, net power cost |
| 06/14 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Ninth/Tenth Semi-Annual Vogtle Construction Monitoring Report |
| 07/14 | 20000-446-EA-14 | WY | Wyoming Industrial Energy Consumers |  | PacifiCorp | 2014 General Rate Case, net power cost |
| 08/14 | 2000-447-EA-14 | WY | Wyoming Industrial Energy Consumers |  | PacifiCorp | 2014 Energy Cost Adjustment Mechanism application |
| 08/14 | 14-035-31 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2014 Energy Balancing Adjustment application |
| 09/14 | ER13-432 | FERC | Louisiana Public Service Commission |  | Entergy | Allocation of Union Pacific Settlement Agreement benefits |
| 10/14 | 2014-00225 | KY | Kentucky Industrial Utility Customers, Inc. |  | Kentucky Power | Kentucky Power Company’s Fuel Adjustment Clause |
| 12/14 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Eleventh Semi-Annual Vogtle Construction Monitoring Report |
| 05/15 | 14-035-140 | UT | Utah Office of Consumer Services |  | PacifiCorp | Solar and wind capacity contribution avoided cost proceeding. |
| 06/15 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Twelfth Semi-Annual Vogtle Construction Monitoring Report |
| 08/15 | 15-035-03 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2015 Energy Balancing Adjustment application |
| 09/15 | 14-035-114 | UT | Utah Office of Consumer Services |  | PacifiCorp | Cost and Benefits of PacifiCorp’s Net Metering Program |
| 11/15 | 39638-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | FCR-24 Fuel Cost Recovery Proceeding |

ADDITIONAL PROJECT INFORMATION

- 1995 – 2000 - Modeled the Singapore Power Electricity System and analyzed the benefits of dispatching a new oil-fired unit within the system, BHP Power

- 1995 – 2000 - Modeled the Australian National Energy Market to develop market based energy price forecasts on behalf of an Independent Power Producer in Australia, BHP Power

- 1995 – 2000 - Analyzed the benefit of purchasing existing gas-fired steam turbine units within the Australian market, BHP Power

- 1995 – 2000 Developed market price forecasts for South Australia as part of the evaluation of a new gas fired combined cycle unit, BHP Power

- 1995 – 2000 - Modeled the Vietnam Electricity System as part of a project to develop Least Cost Expansion plans for Vietnam, EVN State Utility

- 1995 – 2000 - Assisted in the evaluation of Phu My  in Vietnam

- August, 2002 – Expert Report, Civil Action No. 1:00-cv-1262 in the United Stated District Court for the Middle District of North Carolina, United States v. Duke Energy Corporation

- 2002 - Worked on behalf of the Utah Committee of Consumer Services to provide guidance and assist in the analysis of PacifiCorp’s 2002 Integrated Resource Plan.

- July 2003 - Worked on behalf of the Oregon Public Utility Commission to Audit PacifiCorp’s Net Power Costs per a Settlement Agreement accepted by the Public Utility Commission of Oregon in its Order No. 01-787.  Audit report in Docket No. UE-116 filed July 2003.

- 2003 - Regulatory support to the Utah Committee of Consumer Services regarding PacifiCorp’s 2003 Utah General Rate Case Docket # 03-2035-02.

- 2004 – Assistance to the Utah Committee of Consumer Services to analyze a series of power purchase agreements and special contracts between PacifiCorp and several of its industrial customers.

- April, 2011 – Initial Expert Report, Civil Action No. 2:10-cv-13101-BAF-RSW, on behalf of the Department of Justice in US District Court, Detroit Edison

- June, 2011 – Rebuttal Expert Report, Civil Action No. 2:10-cv-13101-BAF-RSW, on behalf of the Department of Justice in US District Court, Detroit Edison

- 2005 - Worked on behalf of the Utah Committee of Consumer Services to help analyze PacifiCorp’s restructuring proposals.

- Assisted in the development of Market Price Forecasts in several regions of the US.  These forecasts were used as the basis for stranded cost estimates, which were filed in testimony in a number of jurisdictions across the country.

- Helped to analyze the rate structure and develop an electricity price forecast for the Metropolitan Atlanta Rapid Transit Authority (MARTA) in Atlanta, Georgia

- Testified regarding the reasonableness of PacifiCorp’s determination of Net Power Cost as part of a rate case proceeding in Utah

- Provided rate case support opposing PacifiCorp’s rate increases in both Oregon and Washington State.  Performed alternative power cost modeling using software simulations

- Critiqued the IRP filings of 5 utilities in South Carolina on behalf of the South Carolina State Energy Office

- Conducted research regarding ISO Tariffs and Operations for the PJM Power Pool, the California ISO, and the Midwest ISO on behalf of a Japanese Research.

- Performed research on numerous electric utility issues for 3 Japanese research organizations.  This was primarily related to deregulation issues in the US in anticipation of deregulation being introduced in Japan.

- Assisted the Utah Committee of Consumer Services by evaluating PacifiCorp’s 2005 IRP and assisted in writing comments that were filed with the Commission.

- Assisted the Utah Committee of Consumer Services by participating in a collaborative process to develop an avoided cost tariff for large QFs.

- Assisted the Utah Committee of Consumer Services to evaluate PacifiCorp’s 2007 IRP.

- Conducted an investigation of the Southern Company interchange accounting and fuel accounting practices on behalf of the Georgia Public Service Commission Staff (Docket 21162-U).

- Assisted the Georgia Public Service Commission Staff to investigate the acquisition of additional coal and combustion turbine capacity currently wholesale capacity (Docket 26550).

- Assisted the Louisiana Public Service Commission Staff with the review and evaluation of Cleco Power’s 2008 Short Term RFP and its 2010 Long-Term RFP.

- Assisted the Louisiana Public Service Commission Staff with a rulemaking for the opportunity to implement a Renewable Portfolio Standard in Louisiana. (Docket No. R-28271 Sub-Docket B)

- Assisted the Louisiana Public Service Commission Staff with a rulemaking to design Integrated Resource Planning (“IRP”) rules. (Docket No. R-30021)

PUBLICATIONS AND PRESENTATIONS

Co-authored “Review of EPA’s Section 111(d) CO2 Emission Rate Goals for the State of Montana, on behalf of the Montana Large Customer Group, October 2014.

Authored “Singapore’s Developing Power Market”, which appeared in the July/August 1999 edition of Power Value Magazine

Co-authored “The New Energy Services Industry – Part 1”, which appeared in the January/February 1999 edition of Power Value Magazine.

Co-authored and Presented “Evaluation of a Large Number of Demand-Side Measures in the IRP Process: Florida Power Corporation’s Experience”, Presented at the 3rd International Energy and DSM Conference, Vancouver British Columbia, November 1994

Co-authored “Impact of DSM Program on Delmarva’s Integrated Resource Plan”, Published in the 4th International Energy and DSM Conference Proceedings, held in Berlin, Germany, 1995

Presentation – Law Seminars International, Electric Utility Rate Cases, Case Study of the Louisiana Public Service Commission’s Quick Start Energy Efficiency Program, March 2015

A “cost-to-complete” analysis ignores costs already incurred (“sunk cost’) and only considers the remaining or prospective cost of the Project when performing an economic evaluation against alternative generation options.  This is the appropriate analysis to use in evaluating whether to finish the project because under certain circumstances Georgia law allows the Company to recover all prudently incurred sunk costs from ratepayers if the Project is halted.

Commission Order in the 11th VCM Proceeding, Docket No. 29849, February 24, 2015, Page 4, 4th Ordering  Paragraph.

In the 12th VCM proceeding, Staff estimated the replacement fuel cost would be $606 million.  This is the difference between the fuel cost of replacement power and the fuel cost of the Vogtle energy, had the Vogtle units not been delayed.

Ratepayers pay sales tax on all components of their power bills, so as the amounts of the bills increase, the sales tax paid also increases.  However, sales tax is not included in these revenue requirement calculations.

With regard to the additional benefits, the Company stated in response to STF-76-15 that there were no material changes in benefits since the 12th VCM filing.

The nominal revenue requirement increase represents the additional revenues that would be collected from ratepayers over the entire lifecycle (construction and operating periods) of the Units. The present value revenue requirement increase takes into account the difference in the timing of the revenue requirements of the certification case and the 39 month delay case.