Before the Public Service Commission

STATE OF GEORGIA

:

In Re:					  	   :

Georgia Power Company’s			   :	   DOCKET NO.:    27488

2015 Request for Proposals.

:

:

PETITION OF GRP Madison, LLC

FOR CHANGE OF CONTROL AND AMENDMENT OF

BIOMASS POWER PURCHASE AGREEMENTS

WITH GEORGIA POWER COMPANY

Comes now, GRP MADISON, LLC (“GRP Madison”) and files this Petition seeking approval of a change of control and amendment to its “Contract for the Purchase of Firm Capacity and Energy from a Renewable Qualifying Facility Utilizing the Proxy Unit Methodology” (“Madison PPA”) entered with Georgia Power Company (“GPC” or “the Company”) for the purpose of transfer of control thereof to Gaelectric Renewable Energy Developments, Ltd. (“GRED”) and a corresponding amendment to the Madison PPA to extend the Required Commercial Operation Date (“RCOD”).   GRP Madison and GPC entered the Madison PPA on or about October 21, 2015, pursuant to certain orders issued by the Georgia Public Service Commission (the “Commission”) in this docket.  Pursuant thereto, GRP Madison is developing a renewable energy biomass generation project in Madison County, Georgia.  The Madison PPA authorizes GRP Madison to sell and GPC to purchase up to fifty-eight (58) MW of electricity.  This Petition seeks Commission approval to allow GRP Madison to transfer control of its Madison County biomass facility and interests in and to the Madison PPA to GRED to allow GRED to acquire majority ownership in GRP Madison.  The confidential proposal for GRED’s acquisition of majority ownership in GRP will be provided to the Commission’s Staff and the Company for review.

For the reasons set forth herein, GRP’s Petition for Approval of a Change of Control to allow GRED to acquire majority ownership in GRP Madison is necessary to the advancement and completion of GRP Madison’s biomass generation facility and, therefore, should be granted.   The Commission has consistently approved prior change of control requests in Docket No. 27488, In re: Georgia Power Company’s 2015 Requests for Proposals.  In doing so, the Commission has demonstrated its commitment to facilitate the development and completion of biomass projects.

Consistent with this Commission precedent and to facilitate the completion of GRP Madison’s biomass generation facility, GRP Madison requests Commission authority, for the following:

Approve the Transfer of majority ownership in GRP Madison to GRED:

GRP Madison asks the Commission to approve a transfer of a majority ownership to GRED.  Based in Ireland, GRED is an independent utility with significant ownership in renewable energy generation projects, particularly biomass generation facilities.  It has the capacity to design, engineer, construct, maintain and operate GRP Madison’s biomass generation facility.   It has the technical expertise to carry out all remaining development activity associated therewith.  Its financial resources will support completion of the GRP Madison facility.  Upon the financial close of GRED’s purchase of a majority share of GRP Madison, the Madison facility will continue to be developed and operated by GRP Madison.  GRP Madison believes that the Company will defer to the Commission’s direction on transfer of control, if this Petition is approved.

Approve Amendment of the Madison PPA to Extend RCOD:

Paragraph 2.7 of the GRP Madison PPA sets the RCOD at June 1, 2017.  The Madison PPA also requires GRP Madison to pay specified liquidated damages to GPC up to June 1, 2018 in order to achieve commercial operation.  To facilitate the change of control, GRP Madison requests that RCOD and the liquidated damages period be extended from June 1, 2018 to June 1, 2019.

CONCLUSION

GRP Madison’s Petition for Change of Control and Amendment of Biomass Power Purchase Agreements with Georgia Power Company should be granted.  GRP Madison requests expedited consideration of its request to allow the change of control of its Madison County, Georgia biomass generation facility to GRED in order to facilitate the completion of the plant and allow it to come on line and commence generation.

This 24th day of January, 2017.

GALLOWAY & LYNDALL, LLP

Counsel for Georgia Renewable Power, LLC

____________________________________

Newton M. Galloway

Georgia Bar No.: 283069

Terri M. Lyndall

Georgia Bar No.: 462235

Steven L. Jones

Georgia Bar No. 639038

The Lewis Mills House

406 North Hill Street

Griffin, GA 30223

(770) 233-6230 telephone

(770) 233-6231 facsimile

ngalloway@gallyn-law.com

tlyndall@gallyn-law.com

CERTIFICATE OF SERVICE

I certify that I have this day served a copy of the foregoing petition of GRP Madison, LLC for Change of Control and Amendment of Biomass Power Purchase Agreements with Georgia Power Company upon the following persons by causing electronic copies of the same to be transmitted to each interested party that has supplied a valid email address, and all other parties to be served via e-mail or first class mail with adequate postage affixed thereon and deposited in the united states mail addressed as follows:

Mr. Reece McAlister

Executive Secretary

Georgia Public Service Commission

244 Washington Street

First Floor

Atlanta, GA  30334

reecem@psc.state.ga.us

Ms. Jamie Barber

Georgia Public Service Commission

244 Washington Street

First Floor

Atlanta, GA  30334

jamieb@psc.state.ga.us

Mr. John Kaduk

Georgia Public Service Commission

244 Washington Street

First Floor

Atlanta, GA  30334

jkaduk@psc.state.ga.us

Ms. Judith H. Fuller

TROUTMAN SANDERS

600 Peachtree Street, NE

Suite 5200

Atlanta, Georgia 30308-2216

judith.fuller@troutmansanders.com

This _____ day of January, 2017.

GALLOWAY & LYNDALL, LLP

____________________________________

Counsel for Georgia Renewable Power, LLC

GRP Madison’s biomass facility in Madison County resulted from GRP Madison’s acquisition of two existing PPAs between GPC — one PPA with North Star Jefferson, LLC (“NSJ”) for twenty-one (21) MW approved by the Commission on September 9, 2011, Order Accepting Contract as Certified, In re: Georgia Power Company’s 2015 Request for Proposals, Docket 27488, Document 138161 (Sept. 9, 2011), which was later increased to twenty five (25) MW by the Commission on February 9, 2015, Order Approving Additional Proxy-Price Capacity Contract Amendments, In re: Georgia Power Company’s 2015 Request for Proposals, Docket 27488, Document 157060 (Feb. 9, 2015), and another PPA with Green Energy Partners-DeKalb, LLC (“GEP-DeKalb”) for eleven and a half (11.5) MW approved by the Commission on August 9, 2012.  Order Approving Contract, In re: Executed Qualifying Facility Proxy Contracts between Georgia Power Company and Green Energy Partners-DeKalb, Docket 27488, Document 143661 (Aug. 9, 2012).  The Commission approved GRP Madison’s acquisition of the NSJ PPA on September 11, 2014.  Order Approving Change of Control between Georgia Renewable Power, LLC and Fort Gaines Energy, LLC, Green Energy Partners, LLC and North Star Jefferson, LLC, In re: Georgia Power Company’s 2015 Request for Proposals, Docket 27488, Document 155074 (Sept. 11, 2014).  The Commission approved GRP Madison’s acquisition of the GEP-DeKalb PPA on December 18, 2014.  Order Approving Assignment of Green Energy Partners-DeKalb, LLC’s Qualifying Facility Proxy-Price Contract to Georgia Renewable Power, LLC, In re: Georgia Power Company’s 2015 Request for Proposals, Docket 27488, Document 156295 (Dec. 18, 2014).  On April 15, 2015, this Commission approved GRP’s consolidation of the GEP-DeKalb PPA into the NSJ PPA and the transfer of twenty two (22) MW of the Ft. Gaines PPA to the NSJ PPA to modify the NSJ PPA Required Commercial Operation Date (“RCOD”) to June 1, 2017, and to relocate these facilities to its biomass facility in Madison County.  Order Approving Consolidation and Amendment of Proxy-Price Power Purchase Agreements, In re: Georgia Power Company’s 2015 Request for Proposals, Docket 27488, Document 157976 (Apr. 15, 2015).  Thereafter, the Commission approved assignment of the NSJ PPA to GRP Madison on November 10, 2015.  Order Approving Assignment and Amendment to Georgia Renewable Power, LLC’s Madison Qualifying Facility Proxy Contract, In re: Georgia Power Company’s 2015 Request for Proposals, Docket No. 27488, Document 160873 (Nov. 10, 2015).

Madison PPA at section 8.1.

E.g., Order Approving Amendments to MAS Georgia LFG, LLC’s Oak Grove, Pine Ridge and Richland Creek and MAS Georgia QF, LLC’s Eagle Point Qualifying Facility Proxy Contracts, In re: Georgia Power Company’s 2015 Request for Proposals, Docket No. 27488, Document 162242 (Feb. 22, 2016); Order Approving Change of Control Transactions between First Generation Energy, LLC and Carolina Energy Partners II, LLC, In re: Georgia Power Company’s 2015 Request for Proposals, Docket No. 27488, Document 160512 (Oct. 14, 2016); Order Approving Change of Control between Georgia Renewable Power, LLC and Fort Gaines Energy, LLC, Green Energy Partners, LLC , and North Star Jefferson, LLC, In re: Georgia Power Company’s 2015 Request for Proposals, Docket No. 27488, Document 155074 (Sept. 11, 2014).