Georgia Power Company’s

Quarterly Military Solar Report

Through December 31, 2016

This report is provided in accordance with the Georgia Public Service Commission’s (“Commission”) request for quarterly update reports regarding the military solar projects approved by the Commission in Docket Nos. 24505 and 39028.

Executive Summary

Pursuant to the Commission’s orders in Docket Nos. 24505 and 39028, the Georgia Power Company (the “Company”) has commenced design, procurement and construction of the military solar projects specified in the table below.  These projects will provide an economical supply of electric power for the Company’s customers, while also contributing towards the military’s mandates regarding renewable energy and energy security and providing a significant investment in Georgia military bases.

| Project | Project Size | Projected Commercial Operation Date | Vendor |
| --- | --- | --- | --- |
| Fort Benning | 30 MW AC | 12/31/2015 (actual) | AMEC |
| Fort Gordon | 30 MW AC | 10/4/2016 (actual) | PowerSecure |
| Fort Stewart | 30 MW AC | 10/4/2016 (actual) | PowerSecure |
| Naval Submarine Base Kings Bay | 30 MW AC | 12/1/2016 (actual) | AMEC |
| Marine Corps Logistics Base (MCLB) Albany | 31 MW AC | 2/28/2017 | AMEC |

Project Activity through December 31, 2016

Expenditures on the projects through December 31, 2016 total REDACTED. The following is a summary of work performed on each project through December 31, 2016:

Fort Benning

The Fort Benning Solar Facility’s commercial operation date was December 31, 2015.  The vendor continues working through punch list items. Other Q4 activities included finalizing site Emergency Action plan, bidding out vegetation control, and development of operational/training templates. Ribbon cutting took place on June 1, 2016.  Final site stabilization is expected to be completed in Q2 2017.

Fort Gordon

The Fort Gordon Solar Facility declared commercial operation on October 4, 2016.  Ribbon cutting took place on November 16, 2016. Final site stabilization is expected to be completed in Q2 2017.

Fort Stewart

The Fort Gordon Solar Facility declared commercial operation on October 4, 2016.  Ribbon cutting took place on December 9, 2016. Final site stabilization is expected to be completed in Q2 2017.

Naval Submarine Base Kings Bay

The Kings Bay Solar Facility declared commercial operation on December 1, 2016.  Ribbon cutting took place on September 19, 2016. Final site stabilization is expected to be completed in Q2 2017.

MCLB Albany

The Marine Corps Logistics Base Albany Solar Facility is approximately 90% complete.  All pile driving is complete.  Racking and Module installation is 85% complete.  All final pre-sync data has been approved by transmission.  Back feed power and grid synchronization was scheduled for January 2017 and COD was targeted for February 2017.  Though the event occurred outside of the reporting period for this report, the Company notes that on January 22, 2017, the MCLB Solar Facility experienced a direct impact from a tornado.  The resulting damage to the facility will cause a delay in the project schedule and the Company will provide further updates to the Commission as restoration plans are developed.

Projected Spending Curve as of December 31, 2016

A projected spending curve by quarter for the Company’s military solar project portfolio is shown below, along with expenditures to date.  The variance is primarily due to a shift in timing of certain expenditures and a slight delay in contractor mobilization for the MCLB Albany project.

Total Projected Spending Curve by Month (millions)

|  |  | Cumulative | Cumulative | Cumulative |
| --- | --- | --- | --- | --- |
|  | Projected | Projected | Actual | Variance |
|  | Spend | Spend | Expenditures | To Date |
| Through Q4 – 2014 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – January 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – February 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – March 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – April 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – May 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – June 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – July 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – August 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – September 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – October 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – November 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – December 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – January 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – February 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – March 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – April 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – May 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – June 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – July 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – August 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – September 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – October 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – November 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – December 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – 2017 |  |  |  |  |
| Q2 – 2017 |  |  |  |  |

*Spending curve includes original MCLB Albany budget. Spending curve to be adjusted when amended scope is finalized.

Ft. Benning Site Photos

Figure 1 Ribbon Cutting (June 2016)

Figure 2 Solar Array (January 2016)

Ft. Gordon Site Photos

Figure 1 Storm over solar array (October 2016)

Figure 2 Newly installed inlet to pond (November 2016)

Figure 3 Ribbon cutting (November 2016)

Ft. Stewart Site Photos

Figure 1 Ribbon cutting (December 2016)

Kings Bay Site Photos

Figure  1  Aerial Photo North Array Soil Stabilization Complete (October 2016)

Figure  2  Captain James Jenks, Ribbon Cutting Ceremony

Marine Corps Logistics Base

Figure  1  West  End of Site (Nov 2016)

Figure  2  Inverter Pad (Nov 2016)