# Georgia Power Company
Renewable Energy Development Initiative

# Request for Proposals for

# Utility Scale 
Renewable Generation

# March 24, 2017

Issued by Georgia Power Company

241 Ralph McGill Boulevard

Atlanta, Georgia 30308

http://www.georgiapower.com

Table of Contents

I.  INTRODUCTION1

II.  RENEWABLE PRODUCTS SOUGHT2

A.  Renewable Generation	2

B.  Common Criteria for All Bids	3

1.  Pricing	3

2.  Location of Facility	4

3.  Greenfield Facility vs. Existing Facility	4

4.  Interconnection and Delivery Requirements	4

(i)  Interconnection and Delivery of Electricity Requirements – General	4

(ii)  Interconnection with the Southern Company Transmission System (≥40 kV)	6

(iii)  Interconnection with ITS Participant (≥40 kV)	8

(iv)  Interconnection Outside of Both the Southern Company Transmission System and Georgia ITS	10

(v)  Interconnection to the Georgia Power Distribution System (<40 kV)	11

5.  Delivery	13

6.  Partial Output Bids	13

7.  Required Commercial Operation Date 	13

8.  Facility Size Parameters	13

9.  Term	13

10.  Performance Security 	14

11.  Environmental Attributes and Electrical Products	14

12.  Energy Storage	14

13.  Station Service	14

14.  Facility and PPA Counterparty Name	15

C.  Self-Build and Turnkey Projects; Facility Purchase Option	 15

1.  Self-Build Project(s)	 15

2.  Turnkey Projects	 15

3.  Facility Purchase Option	 15

D.  Commercial and Industrial Program 16

III.  RFP PROCESS	 16

A.  Solicitation Schedule	16

B.   The Independent Evaluator	17

1.  Purpose and Role of the IE	17

2.  The IE Website	17

3.  The Winner’s Fee	17

C.  Affiliate Standards of Conduct	17

D.  Communication	18

1.  Prior to the Submission of Bids	18

2.  Following the Submission of Bids	18

3.  Listing Determination	19

4.  Following the Execution of the Final Agreement	19

E.  Development of the RFP	19

1.  Draft Documents	 19

2.  Comment Periods	 19

3.  Pre-Bid Webinar	 19

4.  Bidders Conference	 20

5.  Final Documents Filed for Commission Approval	 20

F.  Bid Proposals and Bid Submission	 20

1.  Additional Bidder Qualifications	 20

2.  Bid Proposals	 21

3.  Bid Submission	 22

4.  Bid Fees	 23

5.  Required Supporting Documents to Accompany Each Bid	 23

G.  Confidentiality	 26

H.  Bid Evaluation Process	 27

1.  Non-Competitive Proposals Released	27

2.  Competitive Tier Identified	 28

3.  Bid Bonds	 28

4.  Non-Price and Qualitative Considerations	 28

5.  Improvement Costs Imputed	 28

6.  Due Diligence Portfolio Analysis	 28

7.  Short List Identified	 28

8.  Reserve/Release Lists Identified/Notified	 29

9.  Staff and IE Oversight/Evaluation	 29

10.  PPA Awards	 29

I.  Status Notification and Award of PPAs	 29

1.  Short List, Reserve List, Release List Determination	 29

2.  PPA Execution	 29

J.  Georgia Power Discretion in Contracting	 30

K.  Certification	 30

L.  Definitions	 30

LIST OF ATTACHMENTS

Attachment A Bidder Questionnaire

Attachment B Non-Price and Qualitative Considerations

Attachment C Overview of the Evaluation for Bid Responses

Attachment D Additional Transmission and Distribution Guidance

Attachment E	 Environmental Site Assessment Guidance

Attachment F Environmental Compliance Affidavit

Attachment G  Energy Only Pro Forma Power Purchase Agreement

Appendix B: Form of Standby Letter of Credit

Appendix C: Form of Guaranty

Attachment H  Firm Delivery Pro Forma Power Purchase Agreement

Attachment I Form Site Control Affidavit

Attachment J Variable Interest Entity Certification

Attachment K Capital Lease Certification

UTILITY SCALE

REQUEST FOR PROPOSALS

Georgia Power Company’s

Renewable Energy Development Initiative

March 24, 2017

I.	INTRODUCTION

Georgia Power Company (“Georgia Power” or the “Company”) issues this Renewable Energy Development Initiative (“REDI”) Utility Scale Request for Proposals (“RFP”) to continue the expansion of renewable development for the benefit of Georgia Power’s customers. With the help of the Georgia Public Service Commission (“Commission” or “GPSC”), Georgia Power has advanced the development of renewable resources in the state of Georgia and has launched the largest voluntary renewable procurement program in the country. Beginning in 2011, the Company sought and procured 50 megawatts (“MW”) of solar resources through the Large Scale Solar program. In 2012, Georgia Power created the Advanced Solar Initiative (“ASI”), which offered solar developers the opportunity to bring large, utility-scale solar resources to market through a competitive RFP process, and offered existing Georgia Power customers the option to sell distributed solar generation back to the Company through small- and medium-scale solar purchase programs. Georgia Power procured 40 MW of utility scale resources and 90 MW of distributed generation resources through the initial ASI program, which are online and delivering energy to customers today. Consistent with the Commission’s order in the 2013 Integrated Resource Plan docket, Georgia Power sought to capitalize on the success and lessons learned from the ASI program by soliciting 525 MW of solar resources in its 2015/2016 ASI-Prime program (425 MW of utility scale resources and 100 MW of distributed generation resources). As a result of these three programs, the Company has contracted to purchase more than 770 MW from new solar resources for the benefit of Georgia Power customers.

Georgia Power is also a leader in procuring wind and biomass generation into Georgia’s energy mix. In 2013, the Company entered into power purchase agreements (“PPA”) from two wind facilities in Oklahoma to deliver wind energy and capacity benefits totaling 250 MW imported to Georgia Power’s customers. These projects offered an extraordinary advantage to customers at the time they were procured, and Georgia Power is hopeful that additional cost-effective wind resources will be procured through this RFP. In addition, Georgia Power has entered into nineteen contracts for 638 MW of generation from biomass facilities in Georgia. Fourteen of these biomass projects were able to participate in Georgia Power’s Qualifying Facility (“QF”) Proxy Methodology Program, and more than 120 MW are now online and serving customers. The remaining five biomass projects under contract with Georgia Power have a total capacity of approximately 303 MW and are serving customers through the Company’s Energy-Only QF program. Georgia Power expects more biomass or biogas bids to be offered into this RFP, thus expanding and further diversifying Georgia Power’s overall renewable portfolio.

On August 2, 2016, the Commission issued its Order Adopting Stipulation in Docket No. 40161 (“2016 IRP Final Order”) concerning Georgia Power’s 2016 Integrated Resource Plan (“IRP”), which approved a stipulation (“Stipulation”) that set forth a supply-side plan and included the approval of REDI. REDI is designed to procure 1,050 MW of utility-scale renewable resources: 525 MW through this RFP and 525 MW through a future RFP. Pursuant to the Stipulation, this RFP is being issued in 2017 and seeks projects that will have in-service dates in 2018 and 2019. In accordance with the Stipulation, no more than 300 MW of the total 1,050 MW may be wind resources. All 300 MW of wind could be procured in this first REDI RFP.  The Stipulation also provided for the development of a commercial and industrial (“C&I”) program that has the potential to provide additional renewable opportunities by extending the resources procured through REDI by as much as an additional 200 MW. More details of this aspect of the REDI procurement will be posted on the Independent Evaluator’s (“IE”) Website once approval of the C&I program is received from the Commission.

Please note that capitalized terms used throughout this RFP are defined in Section L (page 30).

II.	RENEWABLE PRODUCTS SOUGHT

A.	Renewable Generation

Georgia Power is seeking to procure 525 MW of renewable energy from several types of renewable resources. The renewable energy must be sourced from one or more of the following types of sustainable, perpetual, or renewable fuels: (i) solar photovoltaic (fixed or tracking); (ii) solar thermal; (iii) wind; (iv) geothermal (natural or enhanced); (v) biomass or biogas; (vi) hydro; or (vii) other renewable fuel or technology (as further described in the paragraph below). The Energy must be bundled with the Environmental Attributes and Electrical Products produced by or related to the Facility (“Renewable Energy”). Georgia Power will accept bids for (1) single, unique proposals; (2) proposals that combine resource options into a single unique proposal (i.e. a wind and solar combination); provided, however, that each resource must individually meet the size requirements of this RFP; (3) proposals that are contingent upon one another; (4) “as delivered” (Energy Only) and “firm block” (Firm Delivery) proposals; and (5) proposals that include on-Site energy storage for all or part of the Facility.

A bidder desiring to submit a bid proposal for a Facility fueled by “other renewable fuel or technology” as described in (vii) above, must contact the IE no later than March 27, 2017 through the IE Website at https://gpcredi.accionpower.com and clicking on the “Other Fuel/Technology” link on the menu bar. From that link, such bidder may share information with the IE regarding the suggested “other” renewable fuel or technology. The IE will research and review the bidder’s proposed fuel/technology and discuss findings with the Commission Staff and Georgia Power’s Evaluation Team. Thereafter, the IE will advise the bidder of whether the “other” renewable fuel or technology will be accepted in a bid proposal to be submitted on the bid due date.

B.	Common Criteria for All Bids

1.	Pricing. The Renewable Cost Benefit Framework (“RCB”) proposed in the 2016 IRP, as modified by the Joint Recommendation approved by the Commission on December 22, 2016, will be used to evaluate the bids received in this RFP.

a.	Pricing Expectations. The Company received a robust response to past solar solicitations, which included multiple bids priced significantly under the Company’s Projected Avoided Costs. The Company is confident that sufficient bids will be received to fulfill the REDI portfolio with very competitively-priced utility-scale projects that will not exceed the Company’s projected levelized avoided cost. As explained in Attachment C, the projected levelized avoided cost benefit for a renewable Facility is dependent on the specific characteristics of the Facility and the assumptions used by a bidder in developing its hourly energy Profile.

b.	Avoided Cost Cap. The price for the Renewable Energy, plus the costs for any required grid improvements to the Transmission System or the Georgia Power Distribution System that Georgia Power will incur or would otherwise remain obligated to incur as more fully discussed herein, must not exceed the Company’s Projected Avoided Cost on a levelized basis.

c.	Levelized or Escalating. Pricing may be levelized over the entire PPA Term or escalate each Annual Period. However, no annual price may be lower than a prior Annual Period’s price.

d.	Front Load Performance Security. If a bidder elects levelized pricing or pricing that escalates at less than a compound average of three percent (3%) per Annual Period, such bidder must provide Front Load Performance Security, in the form of cash, a Letter of Credit or Seller Guaranty, to cover the risk to the Company and its customers of not being made whole in the event of early PPA termination or a change in the Facility operational Profile. Front Load Performance Security is separate from and in addition to the Performance Security requirements in Section 5.1 of the pro forma PPAs, and is described in more detail in Section II (B)(10) below.

e.	Payment for Test Energy. Georgia Power will pay Sellers for test energy delivered prior to the Commercial Operation Date of the Facility. The test energy price is specified as the Associated Interchange Energy Rate (“AIER”), which is the rate the Southern Company Operating Companies use to exchange energy in the Southern pool. This is the same rate the Southern Companies use for all test energy and represents the marginal cost of energy to serve the firm obligations of the Southern Company Operating Companies.

2.	Location of Facility. Georgia Power will accept proposals for a Facility located anywhere in the United States, provided it can deliver the Energy to Georgia Power pursuant to the following interconnection options:

a.	Interconnect at greater than or equal to 40 kV to the Southern Company Transmission System (i.e., transmission facilities owned by Georgia Power Company or its regulated electric utility Affiliates Alabama Power Company, Gulf Power Company, or Mississippi Power Company); or

b.	Interconnect at greater than or equal to 40 kV to the Transmission System of a Georgia Integrated Transmission System (“ITS”) participant other than Georgia Power (i.e., Georgia Transmission Corporation, Municipal Electric Authority of Georgia, or Dalton Utilities) (each an “ITS Participant”); or

c.	Interconnect outside of the Southern Balancing Authority Area (“SBAA”) (which means outside the Southern Company Transmission System and outside the Georgia ITS), and procure Firm Transmission Service to the selected Southern Transmission Interface; or

d.	Interconnect at less than 40 kV to the Georgia Power Distribution System via a Georgia Power distribution substation (including interconnection to a Georgia Power primary distribution line originating from the Georgia Power substation). If a bidder proposes to connect to a Georgia Power primary distribution line, the interconnection must be to the three-phase portion of the line.

3.	Greenfield Facility vs. Existing Facility. The Company will accept proposals for both greenfield and existing facilities. The pro forma PPAs contemplate a greenfield Facility. If an existing Facility is selected, language in the pro forma PPAs, found in Attachments G and H, relating to pre-operation phases of the Facility, will be removed and reserved as appropriate.

4.	Interconnection and Delivery Requirements. Each bidder is responsible for determining all transmission- and distribution-related rules, practices and policies with which it must comply. The details on the requirements for each of the four (4)  interconnection options described in Section II(B)(2) above, are specifically explained in Sections II(B)(4)(ii)-(v) below.

(i)	Interconnection and Delivery of Electricity Requirements – General

The following interconnection requirements apply to all bidders regardless of the location of the Facility.

a.	Transmission Projected Commercial Operation Date (“COD”). Georgia Power may decline to select a proposal for the Short List or enter into a PPA with any bidder if, in the opinion of Georgia Power, the transmission facilities cannot be constructed in time to achieve Commercial Operation prior to December 31, 2019. Except for the provision in Section II(B)(4)(ii)(f)(iii) below for a Facility interconnecting to the Southern Company Transmission System via Georgia Power, a bidder assumes all interconnection and delivery lead-time risk (if applicable) to meet the PPA Required Commercial Operation Date (“RCOD”).

b.	Bid Price Assumptions. Sections II (B)(4)(ii)-(v) below and Attachment D provide guidance for clarifying which interconnection costs will be the responsibility of the bidder. Each bidder is required to provide the assumptions regarding interconnection and, if applicable, delivery costs included in its bid price. Specifically, each bidder must provide details of these costs and refer to any completed or active Interconnection Study results related to the Facility.

c.	Bid Lead-Time Assumptions. Each bidder is required to describe its current status within the applicable interconnection process and its ability to meet the PPA RCOD based upon the applicable interconnection process timeline.

d.	Facility Specifications. A winning bidder must obtain Georgia Power’s written consent prior to making any material change to Facility design (as specified in the REDI bid) or Facility output (as considered in the evaluation of the REDI bid).

e.	Interconnection Agreement Required. Each winning bidder will be required to enter into an Interconnection Agreement with the Interconnection Provider based on the geographic location and interconnection configuration of the Facility. Each bidder is required to contact the appropriate Interconnection Provider to obtain all relevant information and interconnection requirements in this regard. The submission of a bid proposal in response to this RFP does not constitute an interconnection request or an Interconnection Agreement. Bidder is solely responsible for all fees, deposits and other charges in connection with its interconnection request and the Interconnection Agreement. At any point in time, the Facility is prohibited from delivering output that exceeds the lesser of the amount contemplated by the PPA, the Interconnection Agreement or the Generating Capacity.

f.	Timing on Initiating Interconnection Process. Georgia Power encourages each bidder to begin the interconnection process as early as possible. However, the bidder is required to initiate the interconnection process with the appropriate Interconnection Provider no later than seven (7) calendar days after notification that such bidder is on the Short List (as defined below in Section III(H)(7)).

g.	Pre-Bid Webinar. As described in Section III(E)(3), general environmental and transmission interconnection information has been presented at the Pre-Bid Webinar. The Webinar focused on Georgia Power interconnection processes or requirements applicable to a bidder who will enter into a Georgia Power Interconnection Agreement. The Pre-Bid Webinar materials are available on the IE Website.

(ii) 	Interconnection with the Southern Company Transmission System (≥40 kV)

The following requirements apply to a bidder whose Facility is interconnecting with Georgia Power or one of its regulated electric utility Affiliates (i.e., Alabama Power Company, Mississippi Power Company, or Gulf Power Company).

a. 	Procedure Guidance. If the Facility will interconnect to the Southern Company Transmission System at 40 kV or higher voltage, either the small generator interconnection procedure (“SGIP”) or large generator interconnection procedure (“LGIP”) will apply. Generally, the SGIP is utilized for generators 20 MW or smaller and the LGIP for generators larger than 20 MW. The Southern Company Transmission System includes facilities owned by Georgia Power or one of its regulated electric utility Affiliates (Alabama Power Company, Gulf Power Company, or Mississippi Power Company). The prompt submission of an accurate and complete application and prompt return of agreements will reduce the overall timeframe of the interconnection process. A bidder is responsible for determining all rules, practices, and policies with which it must comply to interconnect with the Southern Company Transmission System. A bidder may obtain additional information on Southern Company’s OASIS web site found at http://www.oasis.oati.com/SOCO/index.html.

b.	Bidder Cost Responsibility. If the Facility will interconnect with the Southern Company Transmission System, the bidder is responsible for all Interconnection Study-related costs, in addition to the interconnection costs and risk up to the Point of Interconnection (“POI”). These costs generally include equipment such as the Facility generator step-up (“GSU”) transformer (for conversion up to the interconnecting voltage level), Facility-side generator interrupting device, all Station Service equipment, and any additional equipment, such as a utility-owned interrupting device and metering needed to connect to the transmission facilities, as well as any additional real property for the interconnection substation and access.  In addition, if applicable, the bidder is responsible for the costs, risk, and coordination of Impacted System Upgrades. It is a bidder’s responsibility to determine and review all information regarding interconnection costs.

c.	Interconnection Impacts. Interconnection impacts to the Transmission System will be unique to the specific design and location of each Facility and may require new or modified equipment beyond the POI. For a Facility interconnecting to the Southern Company Transmission System, any costs beyond the POI on the Southern Company Transmission System, the Georgia ITS, or both, will be imputed against the bid during the bid evaluation and should not be included in the bid. A winning bidder will be required to fund or provide security for new or modified equipment beyond the POI. However, if a winning bidder incurs interconnection-related costs for new or modified equipment beyond the POI on the Southern Company Transmission System, transmission facilities owned by an ITS Participant, or both, the costs will be refunded to the bidder or security will be released after the Facility achieves Commercial Operation. As stated above in Section II(B)(4)(ii)(b), any costs associated with Impacted System Upgrades are solely bidder’s responsibility and should be included in the bid.

d.	Delivery Impacts. From the proposals selected in the Competitive Tier (as defined below in Section III(H)(2)), the Company will develop a cost estimate for grid improvements, if any, to the Southern Company Transmission System, the Georgia ITS, or both, necessary to deliver the Energy from the POI to Georgia Power’s customers. These costs will be included in evaluating the economics of the proposal. If grid improvement costs are anticipated to be incurred by Georgia Power to deliver the full output of the Facility, the bidder will be required to provide Additional Security, before Georgia Power commences construction of such facilities or incurs costs on behalf of bidder, that Georgia Power may draw upon in the event of early termination of the PPA caused by a Seller Event of Default that occurs prior to Commercial Operation. After the Facility obtains Commercial Operation, Georgia Power will return the Additional Security to the bidder.

e.	Facility Specifications. Each bidder will be required to provide Facility data and specifications to allow Georgia Power to identify the required modifications to the Southern Company Transmission System, the Georgia ITS, or both, to interconnect and deliver the Energy from the Facility to Georgia Power’s customers.

f.	Facility Interconnecting Directly to Georgia Power. The following provisions apply only to a Facility interconnecting directly with Georgia Power.

- Land and Property Rights. A winning bidder whose Facility will interconnect with Georgia Power will be required to timely coordinate with Georgia Power’s Land Acquisition department to obtain and provide to Georgia Power, at bidder’s cost, suitable real property (fee simple or easement, as will be designated during the Interconnection Study process) in an acceptable location for the Interconnection Facilities, along with access rights to the Site acceptable to the Company, as well as any necessary encroachment agreement, consent, or similar document. All necessary property right documents must be acceptable to Georgia Power and on its standard terms and conditions. During the Interconnection Study process, interconnection facility and access siting will be discussed and agreed upon by Georgia Power and the bidder. If property is required, the bidder must coordinate with the Land Acquisition department to satisfactorily prepare (e.g., rough grading, access road) the property and turn access to the property over to Georgia Power by no later than one (1) year prior to the projected transmission in-service date. All property rights documentation also must be timely negotiated and executed.

- Environmental Matters. A winning bidder whose Facility will interconnect with Georgia Power must cooperate with the Company, at bidder’s cost, regarding the environmental and cultural resource assessments, surveys, or studies regarding the property for the Interconnection Facilities or access required to satisfy requirements of the Company’s Land Acquisition and Environmental Affairs departments. If Georgia Power identifies any impacted media during construction or during the Term, including any impacted soil, groundwater, surface water, or solid waste, the bidder will be responsible and liable for the proper characterization, transport, disposal, and management of the waste, at such bidder’s sole expense. Each bidder will be required to submit an environmental Site assessment addressing the issues outlined in Attachment E and must execute the Environmental Compliance Affidavit provided in Attachment F at the time of bid submission. Seller under the PPA is also required to execute and re-submit an Environmental Compliance Affidavit prior to the time of PPA execution. Additional information regarding environmental matters and compliance by the bidder is found in Section III(F)(5)(e).

- Notice to Proceed. A winning bidder whose Facility will interconnect with Georgia Power is required to submit a notice to proceed (“NTP”) to initiate the construction of Interconnection Facilities by the later of: (a) fourteen (14) calendar days after the Commission issues the Certificate of Public Convenience and Necessity, or (b) May 1, 2018 (this date is subject to change if the Solicitation Schedule is modified). If NTP is received after May 1, 2018, it is unlikely that the PPA RCOD will be achieved prior to December 31, 2019. Depending upon when a bidder initiates the interconnection process, a bidder may be required to enter into an Engineering and Procurement Agreement with Georgia Power to satisfy this requirement.

- Failure to Achieve Commercial Operation by the PPA RCOD. Section 2.5 of the pro forma PPAs provides relief from payment of liquidated delay damages on a day-for-day basis if Commercial Operation will not be achieved prior to PPA RCOD for reasons wholly and solely caused by the inability of Georgia Power to construct the Interconnection Facilities (and not caused by Seller (i.e., winning bidder’s) failure to comply with the provisions of Section 6.1.4 of the pro forma PPA).

(iii) 	Interconnection with ITS Participant (≥40 kV)

The following requirements apply to a bidder whose Facility is interconnecting with Georgia Transmission Corporation (“GTC”), Municipal Electric Authority of Georgia (“MEAG Power”) or Dalton Utilities (“Dalton”).

a. 	Procedure Guidance. If the Facility will interconnect to a transmission facility owned by an ITS Participant (GTC, MEAG Power or Dalton), such bidder’s interconnection application and Interconnection Agreement will be with the applicable ITS Participant. While ITS Participants utilize Interconnection Study processes comparable to Georgia Power’s, the bidder is responsible for determining all rules, practices, and policies with which it must comply.

b.	Bidder Cost Responsibility. If a bidder’s Facility will interconnect with an ITS Participant, such bidder is responsible for all Interconnection Study-related costs, in addition to the interconnection costs and risks up to the POI. These costs generally include equipment such as the GSU transformer (for conversion up to the interconnecting voltage level), Facility-side generator interrupting device, all Station Service equipment, and any additional equipment, such as a utility-owned interrupting device and metering needed to connect to the Interconnection Facilities, as well as any additional real property for the interconnection substation and access. In addition, if applicable, a winning bidder is responsible for the costs, risks, and coordination of the Impacted System Upgrades. It is a bidder’s responsibility to determine and review all information regarding interconnection costs.

c.	Interconnection Impacts. Interconnection impacts to the Transmission System will be unique to the specific design and location of each Facility and may require new or modified equipment beyond the POI. For a Facility interconnecting with an ITS Participant, any costs beyond the POI on the Southern Company Transmission System, the Georgia ITS, or both will be imputed against the bid during the bid evaluation and should not be included in the bid. A winning bidder will be required to fund or provide security for any new or modified equipment beyond the POI. However, if a winning bidder incurs interconnection-related costs for new or modified equipment beyond the POI on the Southern Company Transmission System, or Interconnection Facilities owned by an ITS Participant, or both, the costs will be refunded to the bidder after the Facility achieves Commercial Operation. As stated above in Section II(B)(4)(iii)(b), any costs associated with Impacted System Upgrades are solely bidder’s responsibility and should be included in the bid.

d.	Delivery Impacts. From the proposals selected in the Competitive Tier, the Company will develop a cost estimate for grid improvements, if any, to the Southern Company Transmission System, the Georgia ITS, or both, necessary to deliver the Energy from the POI to Georgia Power’s customers. These costs will be included in evaluating the economics of the proposal. If grid improvement costs are anticipated to be incurred by Georgia Power to deliver the full output of the Facility, the bidder will be required to provide Additional Security before Georgia Power commences construction of such facilities or incurs costs on the bidder’s behalf. Georgia Power will return the Additional Security to the bidder once the Facility obtains Commercial Operation.

e.	Facility Specifications. Each bidder will be required to provide Facility data and specifications to allow the Evaluation Team during the bid evaluation to identify the required modifications to the Southern Company Transmission System, Georgia ITS, or both, to interconnect and deliver Energy from the Facility to Georgia Power’s customers.

(iv) 	Interconnection Outside of Both the Southern Company Transmission System and Georgia ITS

The following requirements apply to a bidder whose Facility is interconnecting outside of the SBAA.

a. 	Procedure Guidance. If the Facility will interconnect outside the SBAA (which means outside of both the Southern Company Transmission System and the Georgia ITS), the bidder is responsible for determining all rules, practices and policies with which it must comply for both interconnection and delivery to the selected Southern Transmission Interface.

b.	Bidder Cost Responsibility. If the Facility will interconnect outside the SBAA such bidder is responsible for all costs and risks, including interconnection and delivery, and coordination necessary to transmit Energy from the Facility to the selected Southern Transmission Interface. For the avoidance of doubt, these costs can include, but are not limited to, transmission and distribution costs, scheduling costs, generation and energy imbalance costs, congestion charges, operating reserve charges, and the costs of rights to utilize the Transmission System or distribution system. Each such bidder must procure Firm Transmission Service for the full output of the Facility from Commercial Operation through the remainder of the Term of the PPA to effectuate delivery to the selected Southern Transmission Interface. A bidder will be required to identify the Southern Transmission Interface to which the Facility will deliver.

c.	Delivery to Southern Transmission Interface. Georgia Power encourages each bidder to begin any applicable Transmission Service Request (“TSR”) process(es) from the POI to the selected Southern Transmission Interface as early as possible. In any event, the bidder must initiate the TSR process(s) with the appropriate provider(s) no later than seven (7) calendar days after notification that the bidder is on the Short List in order to procure the required Firm Transmission Service from Commercial Operation through the remainder of the Term of the PPA. A bidder is also required to describe its ability to meet the PPA RCOD based upon the applicable Firm Transmission Service process timeline(s) to deliver to the selected Southern Transmission Interface.

d.	Interconnection Impacts. Except as provided in the following sentence, for a Facility interconnecting outside the SBAA, no interconnection costs will be imputed against the bid during the bid evaluation and all such costs and risks are the bidder’s responsibility. If Georgia Power or one of its regulated electric utility Affiliates has transmission impacts and incurs costs for a Facility interconnecting outside the SBAA, such costs will be imputed against the bid during bid evaluation.

e.	Delivery Impacts. From the proposals selected in the Competitive Tier, the Company will develop a cost estimate for grid improvements, if any, to the Southern Company Transmission System, or the Georgia ITS, or both necessary to deliver the Energy from the selected Southern Transmission Interface to Georgia Power’s customers. These costs will be included in evaluating the economics of the proposal. If grid improvement costs are anticipated to be incurred by Georgia Power to deliver the full output of the Facility, the winning bidder will be required to provide Additional Security before Georgia Power commences construction of such facilities or incurs costs on the bidder’s behalf. Georgia Power will return the Additional Security to the bidder once the Facility obtains Commercial Operation.

(v) 	Interconnection to the Georgia Power Distribution System (<40 kV)

The following requirements apply to a bidder whose Facility is interconnecting with the Georgia Power Distribution System.

a. 	Procedure Guidance. A Facility to be interconnected at a voltage less than 40 kV must interconnect to a Georgia Power Substation or a Georgia Power Feeder. The bidder is responsible for determining all rules, practices, and policies with which it must comply to interconnect with the Georgia Power Distribution System.

b. 	PURPA Compliance. If a Facility interconnects via the Georgia Power Distribution System, the Facility must certify as a Qualifying Facility under the Public Utilities Regulatory Policies Act of 1978 (“PURPA”).

c.	Standards Compliance. A bidder whose Facility will interconnect to a Georgia Power Feeder must comply with the Southern Company Distribution Interconnection Policy, which can be found on the IE Website, and at https://www.georgiapower.com/docs/energy-efficiency/SOCO_Interconnection_Standard_Rev2013_13.pdf. For a Facility interconnecting to a Georgia Power Substation, interconnection requirements can be found on Southern Company’s OASIS website at http://www.oasis.oati.com/SOCO/index.html.

d.	Bidder Cost Responsibility. A bidder whose Facility will interconnect with the Georgia Power Distribution System is responsible for all Interconnection Study-related costs in addition to the interconnection costs and risks up to the POI. These costs generally include equipment such as the GSU transformer (for conversion up to the interconnecting voltage level), Facility-side generator interrupting device, all Station Service equipment, and any additional equipment, such as a utility-owned interrupting device and metering needed to connect to the distribution facilities, necessary easements, or, if applicable, additional real property for the interconnection substation or access. In addition, if applicable, a winning bidder is responsible for the costs, risks, and coordination of Impacted System Upgrades. It is the bidder’s responsibility to determine and review all information regarding interconnection costs.

e. 	Substation Expansion. If additional property for the interconnection substation is required, the winning bidder must follow the provisions concerning land and property rights, environmental matters and the NTP described in Section II(B)(4)(ii)(f) and its subparts.

f. 	Interconnection Impacts. Interconnection impacts to the Georgia Power Distribution System will be unique to the specific design and location of each Facility and may require new or modified equipment beyond the POI. Any costs beyond the POI on the Southern Company Transmission System, the Georgia ITS, and/or the Georgia Power Distribution System will be imputed against the bid during the bid evaluation and should not be included in the bid. If applicable, a winning bidder will be required to pay for any Impacted System Upgrades or new or modified equipment beyond the POI on facilities of an ITS Participant. Additionally, if applicable, a winning bidder will be required to provide security for costs to be incurred for new or modified equipment beyond the POI on the Southern Company Transmission System or the Georgia Power Distribution System. However, if a winning bidder incurs interconnection-related costs for new or modified equipment beyond the POI on the Southern Company Transmission System, transmission facilities owned by an ITS Participant, and/or the Georgia Power Distribution System, the costs will be refunded to the bidder or security will be released after the Facility achieves Commercial Operation.

g.	Delivery Impacts. From the proposals selected in the Competitive Tier, the Company will develop a cost estimate for grid improvements, if any, to the Southern Company Transmission System, the Georgia ITS, and the Georgia Power Distribution System necessary to deliver the Energy from the POI to Georgia Power’s customers. If transmission/distribution costs are anticipated to be incurred by Georgia Power to deliver the full output of the Facility, the bidder will be required to provide Additional Security before Georgia Power commences construction of such facilities or incurs costs on such bidder’s behalf. Georgia Power will return the Additional Security to the bidder once the Facility obtains Commercial Operation.

h. 	Facility Specifications. Each bidder will be required to provide Facility data and specifications to allow Georgia Power during bid evaluation to identify the required modifications to the Southern Company Transmission System, the Georgia ITS, and/or the Georgia Power Distribution System to interconnect and deliver the Energy from the Facility to Georgia Power’s customers.

i.	Failure to Achieve Commercial Operation by the PPA RCOD. Section 2.5 of the pro forma PPAs has provisions designed to accommodate and reduce risk for a Seller with a Facility interconnecting directly with Georgia Power in the event construction of the Interconnection Facilities delays the PPA RCOD.

5.  	Delivery. Any bidder may propose to deliver Energy to Georgia Power through the provisions of the Energy Only pro forma PPA found in Attachment G. A bidder interconnecting outside the SBAA or to the Southern Company Transmission System may propose to deliver Energy through the provisions of the Firm Delivery pro forma PPA found in Attachment H. Depending on the structure of the bid, Energy delivered in accordance with the provisions of the Firm Delivery pro forma PPA may receive credit towards offsetting a portion of the avoided costs calculated pursuant to the RCB, as appropriate.

6.	Partial Output Bids. Bids that constitute partial output from a Facility will not be accepted. Bids must represent the full output of the Facility.

7.	Required Commercial Operation Date. Pursuant to the 2016 IRP Final Order, Georgia Power is seeking renewable resources designed to obtain in-service dates in 2018 and 2019.  Each bidder is required to indicate in the bid whether the Facility is designed to obtain Commercial Operation in 2018 or in 2019. There is no specified MW amount being sought for each year; rather, Georgia Power is seeking a total of 525 MW of Renewable Energy from projects with anticipated CODs of either 2018 or 2019. Nevertheless, Georgia Power may decline to enter into a PPA with any bidder if in the opinion of Georgia Power the transmission facilities cannot be constructed in time to achieve Commercial Operation prior to December 31, 2019.

8.	Facility Size Parameters. The Company will accept bids for projects sized greater than 3 MW (AC) up to 525 MW (AC). A bidder may not aggregate proposals to meet the minimum size requirement. In consultation with the Commission Staff (“Staff”) and IE, Georgia Power may request that a bidder resize the Facility in order to obtain the best portfolio for the Company’s customers. (If Georgia Power will only award the PPA to the bidder if the Facility is resized, and the bidder refuses to resize the Facility, such refusal will not be considered a withdrawn bid and the Bid Bond will be returned.) As provided in the 2016 IRP Final Order, wind resources may not comprise more than 300 MW of the total 1,050 MW of renewable resources to be procured through the two (2) utility scale REDI RFPs.

9.	Term. The Company will consider proposals for a Term of fifteen (15), twenty (20), twenty-five (25) or thirty (30) Annual Periods, at the bidder’s option. Once the bid has been submitted, a bidder will not be allowed to change the Term length. For purposes of evaluation, the Company will evaluate the proposals pursuant to the methodology outlined in Attachment C, which is consistent with how the Company has evaluated proposals with different length terms in prior RFPs.

10.  	Performance Security. In addition to the Bid Bond discussed in Section III(H)(3) below, which is due at the time of selection to the Competitive Tier, each non-Creditworthy winning bidder will be required to post and maintain Performance Security throughout the Term of the PPA. If the winning bidder is Creditworthy, the credit terms of the PPA will be adjusted to reflect such Creditworthiness. The Performance Security will be calculated by multiplying five percent (5%) with the sum of the expected revenues during the Term of the Agreement. As an example, for an Agreement with a Term of thirty (30) Annual Periods, the total expected revenues during the Term will represent the sum of thirty (30) Annual Periods of revenues. This value will be multiplied by five percent (5%) in order to calculate the appropriate amount of Performance Security.

| Applicable Dates | Performance Security (% of total revenue) During the Term |
| --- | --- |
| Effective Date to COD | 2.5% x total projected revenue during Term |
| From COD through the Term | 5% x total projected revenue during Term |

Performance Security may be in the form of cash, a Letter of Credit, or a Seller Guaranty, subject to the terms and conditions in the pro forma PPA(s). A form of Standby Letter of Credit and a Form of Seller Guaranty are included in Appendix B and Appendix C of the pro forma PPAs found in Attachments G and H. Please also see Section II(B)(1)(d) regarding the requirement to post Front Load Performance Security.

11.  	Environmental Attributes and Electrical Products. Each bid must include the Environmental Attributes and Electrical Products associated with the Energy throughout the Term of the PPA as part of the bidder’s proposal and bid price. In other words, all such benefits and entitlements in addition to electrical output that flow to the owner or operator of the Facility will be bundled with the Energy and sold to Georgia Power at no additional cost to Georgia Power.

12.	Energy Storage. Georgia Power will accept bid proposals that include on-Site energy storage options. A bidder who is proposing storage options must provide a description of such storage option and must submit two Facility output Profiles in the bid: (i) one with the storage option, and (ii) one without the storage option to demonstrate the contribution of the storage component. Any on-Site energy storage must be charged solely from the Facility. Depending on the structure of the storage option, the proposal may receive credit toward offsetting a portion of the avoided costs calculated pursuant to the RCB, as appropriate.

- 13.	Station Service. Station Service is to be purchased from Georgia Power under standard retail rates or from another provider permitted to serve customers at the Facility’s location. For a Facility in Georgia Power’s service territory, a Seller must arrange retail electric service for the Facility in accordance with the Georgia Territorial Electric Service Act (O.C.G.A. §§ 46-3-1 through 46-3-15) for energy used to serve the electrical requirements of the Facility, including GSU losses and line losses between the Facility and the POI. If Seller supplies its starting and running station service on Seller’s side of the POI, the Facility’s output is net of energy consumed and demand requirements (i.e., the energy delivered to the Point of Interconnection).

14.	Facility and PPA Counterparty Name. Due to the need to manage a multitude of renewable projects and Georgia Power’s experience with counterparties selecting very similar or confusing names for similar projects, Georgia Power reserves the right to reject a Facility name offered by a winning bidder and to propose an alternative. In order to give a bidder sufficient time to perform due diligence on the Facility name and any proposed special purpose entity name it intends to use as the counterparty to the PPA, Georgia Power will request bidder confirmation of the names to be used for the Facility and counterparty at the time a bidder is selected for the Competitive Tier.

C.	Self-Build and Turnkey Projects; Facility Purchase Option

1.	Self-Build Project(s). Georgia Power will not be submitting a self-build proposal in this RFP.

2.	Turnkey Projects. The Company is accepting turnkey proposals in response to this RFP. A bidder who is interested in submitting a turnkey proposal should mark its bid as such when submitted. For purposes of this RFP, the Company views a turnkey proposal as any proposal for the transfer of ownership of the Facility to the Company following the completion of construction and at or before the Commercial Operation Date. Additional information regarding turnkey proposals, including the form of submission and the Company contact person(s), is available on the IE’s Website.

- Facility Purchase Option. The Company will consider projects that offer Georgia Power an option to purchase the Facility after the Facility has reached Commercial Operation. A bidder who is willing to sell the Facility to Georgia Power following the Commercial Operation Date must submit two versions of the bid (under one Bid Fee): one version that does not include the Facility Purchase Option, and one that includes the Facility Purchase Option with sufficient detail concerning those instances when the option may be exercised, the period for exercise of the option and related processes (negotiation of a customary purchase agreement, timing of closing, etc.). The Facility Purchase Option does not obligate Georgia Power to purchase the Facility from Seller during the Term, but preserves the option for such purchase if it is determined to be in the best interest of Georgia Power’s customers. Georgia Power would expect the purchase price of the Facility to be its Fair Market Value at the time of closing of the purchase. In such instance, Georgia Power would seek GPSC approval of such purchase and expects that the PPA would terminate upon the closing of the purchase except for any accrued and surviving obligations thereunder.

D. 	Commercial and Industrial Program

Pursuant to the Stipulation of the 2016 IRP Final Order, the Company is considering the development of a renewable C&I Program. This program is anticipated to be an extension of the utility scale procurement through REDI. The program is under development and has the potential to increase procurement under REDI by up to 200 MW. The Stipulation states that the Company may only consider program options that will result in delivering value to all customers and will benchmark such program to the last accepted bid from this REDI RFP. More details on the C&I Program will be made available in the future through a Company filing at the Commission and will be posted on the IE Website.

III. 	RFP PROCESS

A.	Solicitation Schedule

The Solicitation Schedule below outlines the activities to be conducted for this RFP. The Company reserves the right, without qualification and at its sole discretion, and in consultation with the IE and Staff, to revise the Solicitation Schedule, as necessary. The most current Solicitation Schedule will be maintained on the IE Website throughout the solicitation.

| ACTIVITY | DATE DUE |
| --- | --- |
| Pre-Bid Webinar (Transmission, Interconnection, Environmental, Etc.) | December 14, 2016 |
| Draft RFP Documents Issued via Website First Comment Period Opens Regarding Draft RFP Documents | January 6, 2017 |
| Comments to Draft RFP Documents Due First Comment Period Closes | January 20, 2017 |
| RFP Bidders Conference and Webinar | January 27, 2017 |
| Revised Draft RFP Documents Issued via Website Second Comment Period Opens Regarding Draft RFP Documents | February 13, 2017 |
| Final Comments Regarding RFP Documents Due to Company Second Comment Period Closes | February 24, 2017 |
| Revised RFP and PPAs Shared via IE Website Final RFP and PPA Documents Filed for Commission Approval | March 10, 2017 |
| Expected Commission Decision on RFP Documents | March 21, 2017 |
| RFP Released via Website | March 24, 2017 |
| Deadline to Submit “other renewable fuel or technology” to IE | March 27, 2017 |
| Bids and Bidder’s Fee Due (Bids must be electronically submitted by 5:00 PM EPT.) | April 20, 2017 |
| Competitive Tier Selected; Non-Competitive Bids Released | May 19, 2017 |
| Finalize Evaluation of Competitive Tier Proposals | October 10, 2017 |
| Short List, Reserve List Determination and Notification | October 25, 2017 |
| Interconnection Request Submittal Deadline | November 1, 2017 |
| Finalize and Execute PPAs | By November 13, 2017 |
| Reserve List Bidders Released or Moved to C&I Program | November 14, 2017 |
| File Executed PPAs for Certification with the GPSC | November 15, 2017 |
| Tentative Certification Order by GPSC* | January 10, 2018 |
| Required Commercial Operation Date for Resource(s) for REDI 2018 | December 31, 2018 |
| Required Commercial Operation Date for Resource(s) for REDI 2019 | December 31, 2019 |

*Determined by the Commission’s procedural and scheduling order.

B.	The Independent Evaluator

1.	Purpose and Role of the IE. The Company is utilizing an IE, Accion Group, to oversee this RFP and as the point of contact for all bidders. As provided in the Commission’s rules, the IE serves to maintain transparency and fairness in the RFP process, which helps to prevent claims of Affiliate or bidder favoritism in the evaluation and selection of winning projects. The Commission’s Rules require the Company to retain an IE, who is selected by and reports to the Commission in carrying out its duties in assisting with the development and evaluation of the Company’s RFPs.

2.	The IE Website. The IE hosts a website that serves as the required vehicle for all RFP communication among Georgia Power’s Evaluation Team, all bidders and all interested parties in compliance with the RFP Rules (Commission Rule 515-3-4-.04(3)(c)(3)). The IE’s website may be accessed at https://gpcredi.accionpower.com (the “IE Website”).

3.	The Winner’s Fee. A portion of the IE cost is covered by a fee assessed upon each winning bid (the “Winner’s Fee”). The Winner’s Fee will be determined once the final amount of Renewable Energy procured and the IE costs are known after winning bids have been selected. In no event will the total of the Winner’s Fees exceed five hundred thousand ($500,000.00), which is to be allocated pro rata among all winning bids on a per MWh basis.

C.	Affiliate Standards of Conduct

Southern Power Company (“Southern Power”), an Affiliate of Georgia Power, may submit bids in response to this RFP. Commission Rule 515-3-4-.04(3)(d) incorporates measures to segregate the Company’s Evaluation Team and Southern Power’s Bid Team (“Bid Team”). The Evaluation Team members and the Bid Team members are identified on the Commission’s website and the Documents Page of the IE Website. Each bidder is strongly encouraged to review these lists and is prohibited from discussing the RFP and any related documents with the Evaluation Team. The Company implemented specific controls to ensure that Evaluation Team and Bid Team RFP-related information is confined to the appropriate Team. There are certain limited instances where the Company and Southern Power share certain services provided by other Southern Company Affiliates, which are unrelated to this RFP. Additionally, prior to receipt of bids, the Company is implementing process steps to ensure that all bids from its Affiliates and non-Affiliates are evaluated using a common methodology and applied in a manner that ensures that any Affiliate bids do not receive any advantage in the evaluation. In all instances, the Company’s Affiliate will be treated as a third-party bidder.

D.	Communication

1.	Prior to the Submission of Bids. Each bidder and each interested party registered on the IE Website may submit questions concerning this RFP, the pro forma documents, the bids, and bid evaluation on the “Q&A” page of the IE Website. The questions and the Company’s responses will be posted for viewing by all potential bidders on the IE Website. In no instance may a bidder or any interested party contact any member of the Evaluation Team or Staff to discuss any substantive issue related to the RFP, the RFP documents, the RFP process, the evaluation or the evaluation process or any related subjects. Any breach of this requirement may result in bid disqualification. All such inquiries are to be directed to the IE, through the IE Website, in compliance with Commission Rule 515-3-4-.04(3)(e)(2)(ii).

2.	Following the Submission of Bids.

a.	Bid Books. Once the bidding period commences and a bidder initiates the bidding process, each bidder will have a confidential “bid book” on the IE Website where such bidder may ask Site-specific and Facility-specific questions using the “create memo” feature in the bid book. Questions submitted in a bid book are not available to other bidders and are only viewed by the Evaluation Team, the IE and Staff. The Evaluation Team will reply to each question, after review and consultation with the IE and Staff. However, all questions determined by the IE to be generic in nature, and not unique to a specific Site or Facility may be transferred to the “Q&A” page of the IE Website so that the benefit of the question and response is shared with all bidders and registered users.

b.	Monitored Communications. Prior to the selection of the winning bid(s), any communications between any individual bidder and the Company regarding any specific bid will be confidential except to the degree that Staff and the IE monitor communications. Such communications may include face-to-face meetings with a bidder in order to discuss such bidder’s proposal(s). The Company may conduct telephonic conference calls with the bidder in order to clarify bids or resolve issues with such bids. The Staff and IE, at their discretion, may participate in all such discussions. Any meetings and communications that include representatives of the Bid Team will be monitored by the IE.

c.	Bid Deficiencies. Deficient bids will be rejected as nonresponsive to this RFP unless the Company, in its sole discretion and in consultation with the Staff and IE, determines it will permit such bidder to cure the deficiency within a specified time frame. Fees submitted with a deficient bid will not be returned. There will be no opportunity afforded to a bidder to refresh or revise its initial proposal on its own initiative.

3.	Listing Determination. Georgia Power will not publicly announce the Short List, Reserve List or Competitive Tier. The identity of the winning bid(s) and bidder(s) will become public information at the time of Georgia Power’s request for certification of the related PPA(s) before the Commission.

4.	Following the Execution of the Final Agreement. A winning bidder is prohibited from announcing its selection as a winning bid or the execution of a PPA via a press release or any other method of public communication without the express written consent of the Company. A winning bidder is responsible to ensure that its winning bid status remains confidential and is not announced by any of its contractual partners. A winning bidder is required to educate its contractual parties and any other participants in the development of the Facility (e.g., development authorities, county and state agencies) on the impact of public statements made regarding renewable facilities and how such statements jeopardize the validity of Environmental Attributes that are sold to Georgia Power under the PPA, which could result in a breach by Seller of the PPA. Upon execution of the PPA(s), the winning bidder(s) and the Company will work together to determine the timing and content of the official announcement of the winning status of the project and the execution of the PPA(s).

E.	Development of the RFP

1.	Draft Documents. Consistent with Commission Rule § 515-3-4-.04(3)(e), the Company prepared the initial draft of this RFP document and the pro forma PPAs, with the consultation and input of the Staff and IE. Draft documents are posted on the Commission website and the IE Website.

2.	Comment Periods. The Solicitation Schedule provides the dates and durations for the Comment Periods. Any potential bidder or interested party may submit written comments through the IE Website on all aspects of the RFP, including the draft RFP and pro forma PPA documents. A bidder or interested party must submit comments via the IE Website. If a bidder or interested party is commenting about a suggested substantive change to the RFP documents, the commenter will be prompted to provide a mark-up of the RFP section or the draft pro forma PPA documents found in Attachments G and H, along with the rationale for the suggested change for the Company’s consideration. The Evaluation Team, Staff and IE will review all comments received. Suggested revisions that are accepted by the Company will be incorporated in the final RFP documents. Any bidder or interested party who suggests a revision that is not incorporated will receive an explanation in an email from the IE Website.

3.	Pre-Bid Webinar. This webinar, held on December 14, 2016, provided all bidders advance information regarding environmental compliance, and interconnection and transmission issues. Specifically, the Pre-Bid Webinar was designed to assist a bidder in understanding the requirements of environmental compliance as more fully discussed in Section III(F)(5)(e), the interconnection process within the Southern Company Transmission System, including the typical lead times for requesting and executing an Interconnection Agreement, and the typical schedules for construction of interconnection facilities. For interconnection outside the Southern Company Transmission System, it will be a bidder’s responsibility to investigate the process specifics and any lead times of a Transmission Provider outside the Southern Company Transmission System. Georgia Power expects the bidder to use resources available to understand the process and schedule issues involved with completing the transmission interconnection on a timely basis. The Pre-Bid Webinar materials are available on the IE Website.

4.	Bidders Conference. Georgia Power, Staff and the IE hosted a Bidders Conference on January 27, 2017. The Bidders Conference is held to allow any potential bidder or interested party the opportunity to discuss the draft RFP Document and pro forma PPAs with the Company, Staff and IE. Potential bidders and interested parties had the opportunity to attend the Bidders Conference in person or via webinar.

5.	Final Documents Filed for Commission Approval. Final versions of this RFP Document and the pro forma PPAs will be filed for Commission approval in accordance with the Solicitation Schedule. Once approved by the Commission, the final approved version of the RFP Document and pro forma PPAs will be posted on the Commission’s website and the IE Website.

F.	Bid Proposals and Bid Submission

1.	Additional Bidder Qualifications. Each bidder is required to provide the information described below at the time of bid submission. At the time the Competitive Tier is selected, Georgia Power will screen each bidder on the criteria below to ensure basic bidder qualifications:

a.	Financial Metrics. Each bidder must provide the most recent audited annual report and any 10Q filings since the period covered in the annual report. If such report and filings are not available, the bidder should note this and provide the latest three (3) years of audited financial statements for itself and its immediate upstream parent entity. The Bidder Questionnaire in Attachment A provides additional information on the financial metrics required. If a bidder can provide any additional details related to its banking relationships or liquidity, Georgia Power will consider those items in the credit evaluation as well. All financial statements, annual reports, and other large documents may be referenced via a website address.

b.	Project Development Experience.  Each bidder must provide documentation of its previous development experience, where bidder was the primary renewable project developer and the proposed facility was similar in size and located in the United States. Such summary must include the total number of renewable MW bidder currently owns and operates in the United States. Each bidder must describe the experience of the principal members of its project team. Proposals should include information on who will be responsible for design, siting, permitting, financing, construction, and on-going operation and maintenance of the Facility, if known. Each member that will lead key aspects of the project should have experience in leading those tasks on previous projects that are similar to the proposed Facility. Please identify such similar projects. Finally, each bidder is asked to provide an executive summary of its qualifications and resume that is 5000 words or less.

c.	Contract Counterparty History. Each bidder must disclose any and all power purchase agreements that bidder or any Affiliate or parent entity was a party to in the past five (5) years that were terminated prior to the end of the contract term, and the reason for such early contract termination. Also list any instances where the bidder or any Affiliate or parent entity withdrew a project from any solicitation offered by Georgia Power or any of its Affiliates in the last five (5) years. Each bidder must identify and describe any dispute in which the bidder or any of its Affiliates has previously been involved with Georgia Power or any of its Affiliates (including all direct and indirect subsidiaries of The Southern Company). This list should identify any disputes that were resolved informally between parties, as well as disputes that have previously been, or which currently are, the subject of a mediation or arbitration proceeding, or any other litigated proceeding before a court or other governmental authority.  If a bidder or any of its Affiliates currently owe any outstanding debt to Georgia Power or one of its Affiliates, such bidder must also disclose this and provide details regarding the reason for non-payment. Prior to further consideration of such bidder’s proposal, the bidder may be required to resolve the outstanding debt to the satisfaction of all parties.

2.	Bid Proposals.

a.	RFP Issuance. After the Commission approves the final RFP documents, all registered users of the IE Website will be notified by email and a copy of the bid form and a list of required documents will be posted on the Commission’s website and the Documents Page of the IE Website.

b.	Multiple Bid Submissions. A bidder may submit multiple bids in response to this RFP. A bidder proposing multiple bids must state clearly in its proposals whether the proposals are dependent upon each other. For example, if a bidder submits multiple bids for several sites, but is only willing to develop a limited number of those facilities, the limitations must be stated clearly. If such contingencies are not identified in advance, Georgia Power will not honor requests after the Competitive Tier has been identified to reprioritize bid selection based on bidder-identified preferences. A bidder may not propose multiple bids from multiple sites to aggregate the MW to meet the minimum MW required to be submitted in this RFP. A bidder will have to pay the Bid Fee for each bid submitted for consideration in this RFP.

c.	Unique Bids. Each bid must be unique with respect to the PPA Term, Facility location, size, POI, Southern Transmission Interface (if applicable), and any characteristics that would alter the amount or timing of the delivery of Renewable Energy from the Facility (e.g., tracking capability and panel orientation for solar resources). Bids identical in all respects, but otherwise offering differing PPA Term lengths, are considered a single bid for the purpose of Bid Fees. Bids must specify whether the proposal is dependent on another bid submitted in response to this or another RFP.

d.	Pricing Alternatives. For each bid submitted, a bidder will be permitted to provide up to two pricing alternatives: (1) a fixed price for the selected Term (e.g., fifteen (15), twenty (20), twenty-five (25) or thirty (30) Annual Periods), and (2) a schedule of annual prices for each Annual Period. Georgia Power will consider a bid proposing two pricing alternatives as one bid with only one Bid Fee.

e.	Commercial Operation Date. A bidder is required to identify the day, month, and year during which the bidder proposes to begin delivery of Renewable Energy to Georgia Power (within calendar years 2018 or 2019).

f.	Bid Proposal Certification. An officer of the bidding company must electronically sign the submitted proposal(s) as part of the IE Website bid form.

g.	Pricing Requirements. Prices and dollar figures quoted will be considered to be in nominal terms for the year in which they occur. A bidder who proposes a bid with a fixed price or with an annual price that escalates at less than a compound average of three percent (3%) or offers any price schedule that Georgia Power determines has an equivalent effect, will be required to post Front-Load Performance Security pursuant to the provision of Sections 5.5 of the pro forma PPA(s).

h.	Point of Contact. Each bid must include detailed contact information for the person who will serve as the primary point of contact for the bidder. This person will serve as the contact between the Company and the bidder when questions and answers are exchanged, and will receive authority to access the bidder’s bid folder on the IE Website. This contact person must be familiar with all aspects of the bid process and bid in order to efficiently communicate with the Company as necessary, and to reduce any delay in communicating information.

i.	Bid Preparation Costs. All costs related to each bidder’s preparation of a bid proposal in response to this RFP are the sole responsibility of the bidder. The Company will not reimburse or be held responsible for costs associated with any bid proposal submitted in response to this RFP.

3. 	Bid Submission.

a.	Bid Due Date/Time. Each bid must be submitted by 5:00 PM Eastern Prevailing Time (“EPT”) on the bid due date as shown in the Solicitation Schedule. Each bidder will receive an email acknowledgment for each bid submitted. Each bidder must electronically submit a completed bid proposal to the Company via the IE Website.

b.	Effect of Bid Submission. A bidder’s submission of a proposal to the Company will constitute that bidder’s acknowledgment and acceptance of all the terms, conditions and requirements of this RFP.

c.	Bidder Questionnaire. The Bidder Questionnaire provided as Attachment A illustrates the type of information a bidder will be expected to submit on the bid form as part of its proposal.

d.	All in Price. Bid prices must include all costs that the Company will be expected to pay for the Renewable Energy sought in this RFP. Attempts by a bidder to increase its price after the bid is submitted will be grounds for rejection of the bid.

e.	Bid Release Date. Each bid submitted for consideration must remain valid until the date on which Georgia Power files the applicable executed PPA with the Commission, which is scheduled to occur in accordance with the Solicitation Schedule.

f.	Additional Information. A bidder also may supply any additional information not requested in these forms that may be needed for a thorough understanding and evaluation of the proposal. Failure to supply all of the required information (see Section III(F)(5) below) by the bid due date may disqualify the bid.

g.	Bidder Identified Errors in Bid. If a bidder discovers an error or omission in the bid after submitting the electronic filing, such bidder must note any change in the electronic filing and such change must be posted to the bidder’s bid book on the IE Website by 5:00 PM EPT on the bid due date.

4.	Bid Fees. As provided in the 2016 IRP Final Order, to help defray the cost of performing an evaluation of each bid, each bidder is required to submit with each bid a non-refundable minimum “Bid Fee” of five thousand dollars ($5,000), or three hundred dollars per MW ($300/MW), whichever is greater. The first thousand dollars ($1,000) of each Bid Fee, described in more detail below, will be used to defray a portion of the IE cost. The Bid Fees submitted by any bidder will not be refunded (unless otherwise determined at the sole discretion of the Company) in the case of any modification or withdrawal of this RFP, rejection of any bid, or failure to execute a PPA.

A bidder must pay the Bid Fees via electronic payment through the IE Website. Payment is due at the time of bid submission, and must be received no later than 5:00 PM EPT on the bid due date. Failure to submit the required fee on the due date is grounds for automatic disqualification.

5.	Required Supporting Documents to Accompany Each Bid. A bidder must complete and submit each of the following documents with its bid in order for the bid proposal to be considered complete. Any proposal that does not satisfy the requirements of this RFP may be considered nonresponsive. The Company, in its sole discretion, and in consultation with the IE and Staff, may choose to reject nonresponsive offers from further consideration.

a.	Mark-Up of Pro Forma PPA. After the Commission approves the terms and conditions of the pro forma PPAs, no substantive or material change will be allowed. Each bidder must provide a mark-up of the PPA(s) to indicate any non-material clarifications and Facility- and Site-specific changes to the pro forma PPA(s). Each bid must include (i) a “red-lined version” of the Commission-approved pro forma PPA(s) reflecting any and all necessary changes by showing the specific additions (bold and underlined) or deletions (strike-through) that bidder requires in order to enter into the PPA(s); (ii) a separate document explaining every change; and (iii) a statement confirming that the terms and conditions of the pro forma PPA(s) as proposed by a bidder are acceptable to such bidder. The Company will not consider any material or substantive exception, change or modification that would affect the value of a bidder’s proposal, or which would substantively change the risks and benefits as outlined in the pro forma PPA(s). If a bidder’s red-line suggests material changes, Georgia Power cannot consider such changes and the bid may be disqualified. The pro forma PPAs are included in Attachments G and H.

b.	Site Control Affidavit. Each bidder must submit a notarized Site Control Affidavit that affirms such bidder has obtained site control of the Site for the Term of the proposed PPA. The Form Site Control Affidavit is attached as Attachment I. If a bidder is selected for the Short List, prior to PPA execution, such bidder may be required to submit further evidence of site control, as deemed necessary by Georgia Power.

Included in the Site Control Affidavit is a representation that a bidder’s business entity is duly organized and validly existing under the laws of the state of the jurisdiction of its formation. This representation must be true with respect to the bidder at the time the bid is submitted. The Seller under the PPA must register and be in Active/Compliant standing with the Office of the Georgia Secretary of State authorizing Seller to do business in Georgia prior to the time of PPA execution.

c.	Organizational Chart. Each bidder must submit an organizational chart that includes all related parent companies, subsidiaries, Affiliates, or special purpose entities. If a bidder desires to form a new special purpose entity or subsidiary to become the PPA counterparty, Georgia Power prefers that this is disclosed to Georgia Power at the time of bidding, and in any case, it must be disclosed no later than at the time of being notified of selection for the Short List.  A bidder using or planning to use a special purpose entity or subsidiary as the PPA counterparty, as Seller under the PPA, must include a proposed organizational chart clearly showing the relationship to the special purpose entity or subsidiary.

d.	Financing Plan. Each bidder should describe its plans for acquiring the necessary funds for developing, constructing and operating the Facility. Such plans should include a discussion of the Facility’s legal ownership structure, the expected percentage of debt and equity capital that the bidder has committed to secure, and the identity and credit rating of firms that are likely to provide such financing. If available, letters of interest or letters of commitment from such firms should be provided.

e.	Environmental Compliance Affidavit.  Due to the potential impact of renewable generation when constructed in or around sensitive ecological or cultural areas, a bidder may need to conduct review, mitigation, and permitting activities. Georgia Power requires assurances from each bidder that due diligence concerning the protection of environmental attributes at the Site will be observed. Efforts should be made by the bidder to avoid environmental impacts, but where impacts are inevitable, efforts should be made by the bidder to minimize and mitigate environmental impacts accordingly. As such, Georgia Power is requiring that an environmental Site assessment be conducted by the bidder to determine what potential environmental impacts may result from construction and operation of the Facility. The required components of the environmental assessment are found in Attachment E. Accordingly, with each bid submittal, the bidder is required to submit a copy of its environmental site assessment information and a notarized Environmental Compliance Affidavit, found in Attachment F, which confirms the bidder’s (i) understanding of and compliance with the legal environmental standards and requirements respecting the Site, (ii) agreement to conduct due diligence as necessary in compliance with the outcome of the environmental Site assessment, and (iii) agreement to mitigate environmental impacts, if any, as required under applicable federal, state, and local law, for the Term of the PPA. A bidder seeking additional guidance should consider working with a consultant with environmental permitting and siting experience or coordinating directly with Department of Natural Resources (DNR) or other equivalent state agency or local US Fish and Wildlife Service, Ecological Services (FWS-ES) office, which in Georgia can be contacted at www.georgiawildlife.com, http://epd.georgia.gov, http://georgiashpo.org, and https://www.fws.gov/athens.

f.	Variable Interest Entity. Depending on the business structure of the bidder, accounting and tax rules may require that the PPA be treated as a Variable Interest, and Seller be consolidated as a Variable Interest Entity onto Georgia Power’s books. Because the Company is unwilling to be subject to accounting or tax treatment that results from VIE treatment, all bidders are required to certify, using the form attached in Attachment J, that at any time over the proposed PPA Term, Seller will not be required to deconsolidate on its books and records any assets, liabilities, cash flow, profits, or losses of Seller as a result of Georgia Power being determined to be the Primary Beneficiary. At the time of bid submission and again at PPA execution, the chief financial officer of Seller must again provide such certification. Further, any PPA that Georgia Power executes will require that (i) Seller covenant that the Company will not be subject to VIE treatment and deemed the Primary Beneficiary as contemplated by ASC Topic 810, Consolidation, as issued and modified from time to time by Financial Accounting Standards Board (FASB) at any point during the Term of the PPA, and (ii) if the PPA causes Georgia Power to be deemed the Primary Beneficiary at any point during the Term of the PPA, unless cured, such treatment will constitute a Seller Event of Default under the PPA, and the Company could terminate the PPA. If the Seller is unable to clearly demonstrate that the consolidation event was not due to the direct or indirect action of the Seller, the Seller will be liable for damages pursuant to the relevant provisions of the PPA.

g.	Capital Lease. The inclusion of a Facility Purchase Option in the pro forma PPAs, and the firm nature of Energy delivery in the Firm Delivery PPA, triggers potential Capital Lease impacts. Accordingly, if applicable, the bidder must certify as to certain factual statements for each proposal based upon such bidder’s personal consideration of the factual matters and such bidder’s understanding of accounting standards regarding Capital Leases, using the form provided in Attachment K. If the bidder responds in the affirmative on one or more of the factual statements, such bidder also must provide the amounts that the Company would be required to capitalize and the residual value of the Facility, excluding executory costs, as defined in Attachment K. In any case for which a bidder responds in the negative to all of the factual statements set forth in Attachment K, such bidder is required to certify such declaration, with supporting information sufficient to enable Georgia Power to independently verify that such Capital Lease treatment will not occur. At the time of bid submission and again at PPA execution, the chief financial officer of Seller or an officer having responsibilities for financial accounting matters associated with the PPA, must again provide such certification. For proposals declared as Capital Leases, the bid evaluation will include the cost to the Company resulting from capitalization of PPA costs on the Company’s balance sheet.

Furthermore, each bidder with a bid selected for the Short List for further evaluation also must agree to make available any and all financial and business data associated with the Seller, the Facility and the PPA(s) that the Company would need to independently make its accounting determinations. Such information may include data supporting the economic life, the fair value, investment tax credits associated with the Facility or other costs associated with the Facility including debt specific to the asset proposed. Financial data contained in a bidder’s financial statements (e.g., income statements, balance sheets, etc.) also may be required.

G.	Confidentiality

Each bidder is prohibited from disclosing to others the ongoing status of such bid, and the information exchanged and discussed between the bidder  and Georgia Power (“Bidder Information”) (such exchanges and discussions to occur pursuant to the guidelines of this REDI RFP and the GPSC Rules); provided, however, a bidder may disclose Bidder Information to its Affiliates’ officers, employees, consultants, attorneys, agents, bankers, accountants and contracting parties (“Representatives”) as reasonably necessary for such bidder to perform as a bidder in the REDI RFP; provided, further, that as a condition to any such disclosure to such Representatives (i) the bidder must direct its Representative not to disclose the Bidder Information, and (ii) such Representative must be subject to a contractual obligation to maintain the confidentiality and not disclose Bidder Information. If the Representative cannot be made subject to a contractual obligation to maintain confidentiality of the Bidder Information, the bidder must obtain the Company’s prior written consent prior to making the disclosure. Furthermore, the bidder, and its Representatives are prohibited from making any public statement or other claim regarding the Energy or Environmental Attributes to be generated by the Facility, including any statement that the Energy or Environmental Attributes are generated from any sustainable, perpetual, renewable or other particular type of fuel, including in any marketing or advertising materials, press release or public statement. Each bidder will be responsible for any statement, claim, commitment, or disclosure made by itself or its Representatives that has the effect of retiring or claiming the Environmental Attributes from the Facility or otherwise limiting or jeopardizing the Environmental Attributes from the Facility that would be conveyed to Georgia Power under the PPA.

The Company will take reasonable precautions and use reasonable efforts to protect any other proprietary or Confidential Information contained in a bid, provided a bidder clearly identifies that such information is confidential on each page on which such Confidential Information appears. Such information may, however, be made available under applicable state or federal law to governmental authorities having appropriate jurisdiction over this solicitation. The Company reserves the right to release such information, for the purpose of evaluating proposals, to the IE and Staff as needed to monitor this RFP, to regulated retail affiliates, Southern Company Services, Inc., and to affected entities who have a need to know in order to assist in the evaluation of bids, provided that such entities will observe the same care with respect to non-disclosure as the Company. Under no circumstances will the Company (including its parent, Affiliates, subsidiaries, and the officers, directors and employees of any of them) or the IE or Staff be liable for any damages resulting from any disclosure before, during or after the solicitation process.

H.	Bid Evaluation Process

- All bids submitted in response to this RFP will be evaluated in accordance with the evaluation criteria and structure described in Attachment C.

- 1.	Non-Competitive Proposals Released. Proposals that are considered to be adequately responsive to the requirements of this RFP will be ranked and screened on economic value to eliminate those that are clearly not competitive before a detailed evaluation is performed. Failure to provide all requested information may invalidate the bidder’s proposal. The Company is not required to contact any bidder to obtain any omitted information. The screening evaluation will focus primarily on price, performance considerations and value added to the Company’s renewable energy portfolio. In accordance with the Solicitation Schedule, any bidder offering a non-competitive bid will be notified of release.

- 2.	Competitive Tier Identified. The Company will select the best proposals for further evaluation. These selected proposals make up the “Competitive Tier.” Each bidder will be notified when its bid is included in the Competitive Tier.

3.	Bid Bonds. In an effort to ensure the entire 525 MW portfolio is filled in accordance with the Solicitation Schedule, any bidder who has a bid selected for the Competitive Tier will be required to post a bond within fifteen (15) Business Days in the form of (i) cash, (ii) Surety Bond issued by a Creditworthy Person or a Person rated at least A- by AM Best, if rated by AM Best, or (iii) a Letter of Credit, equal to the product of one percent (1%) multiplied by the sum of the expected revenues during the Term of the Agreement (“Bid Bond”). An acceptable form of Surety Bond will be available on the IE Website. The Bid Bond is fully refundable to the bidder (a) if such bid is placed on the Release List, or (b) on the date Seller and Georgia Power execute the PPA for such winning bid. If the Bid Bond is in the form of cash or a Letter of Credit, the bidder may opt to convert the Bid Bond to the required Performance Security at the time of PPA execution, or the bidder may replace the Bid Bond with another acceptable form of Performance Security pursuant to the provisions of the PPA. The Bid Bond is non-refundable if a bidder withdraws the bid or otherwise fails to execute the pro forma PPA after being selected for the Competitive Tier.

4.  	Non-Price and Qualitative Considerations. Qualitative and non-price factors will be considered in the detailed evaluation process. Attachment B provides additional information on these qualitative and non-price considerations. It is a bidder’s responsibility to submit additional information related to the proposal if such information will materially improve the quality of its offer and the Company’s understanding thereof.

5.	Improvement Costs Imputed. Based on the information contained in each proposal selected for the Competitive Tier, the Company will develop a cost estimate for grid improvements, if any, as described in the clauses entitled “Interconnection Impacts” and “Delivery Impacts” in the applicable interconnection scenario described under Section II(B)(4)(i) entitled “Interconnection and Delivery of Electricity Requirements - General.” Those costs will be included in evaluating the economics of the proposal. This process will ensure that the proposals selected do not exceed Projected Avoided Costs. In addition, this process will assist in identifying the potential Short List of proposals.

6.	Due Diligence Portfolio Analysis. If the potential Short List of proposals includes proposals connecting to the transmission or distribution system such that their system impact costs are not independent, evaluations of the combined effects of such proposals will be necessary to select the best combination of proposals.

7.	Short List Identified. Based on the results of the detailed evaluation, the best proposals will be chosen as the Short List. Georgia Power will contact each Short Listed bidder to finalize the PPA to conform it to the specifics of the Facility and the bidder’s business entity.

8.	Reserve/Release Lists Identified/Notified. Any bids not identified for the Short List may be placed on the Reserve List. Georgia Power will contact each bidder eligible for the Reserve List to notify such bidder that the project has been identified for continued evaluation on the Reserve List. As described in Section II(D), depending on the outcome of the C&I solicitation, Georgia Power may procure up to 200 MW of additional renewable resources from the Reserve List. Any bidder whose project is not competitive will be notified that such bidder is no longer being considered for the Short List or Reserve List. These bidders will be placed on the Release List and notified of removal from further consideration in this RFP.

9.	Staff and IE Oversight/Evaluation. In accordance with Commission Rule 515-3-4-.04(3)(e)(3), Staff and the IE actively and contemporaneously monitor all aspects of the Company’s evaluation process for transparency purposes. Staff and the IE will review all Bid submissions and conduct an independent evaluation of the resource options submitted to the Company in the RFP process pursuant to Commission Rule 515-3-4-.04(3)(e)(3). Staff and the IE are permitted access to all of the documents and information utilized by the Company in its evaluation.  Georgia Power, Staff and IE will meet to discuss and finalize the composition of the Competitive Tier identified for further evaluation, as well as the Short List identified for PPA(s) awards.

10.	PPA Awards. The Company will award and execute PPAs with the winning bidders selected from the Short List. The Company reserves the right to contact any bidder to request additional information on any aspect of the bidder’s proposal.

I.	Status Notification and Award of PPAs

1.	Short List, Reserve List, Release List Determination. In accordance with the Solicitation Schedule, and as discussed in Section III(H)(7) and (8) above, upon completion of evaluation, bidders will be notified of whether they are on the Short List, Reserve List, or Release List. Georgia Power will contact bidders selected for the Short List to finalize and execute the PPA. Bids on the Reserve List are projects that are essentially on a wait list that will continue to be under evaluation and may move on to the Short List if a Short List bidder withdraws or is unable to proceed to PPA execution. Bids on the Release List were determined to be non-competitive and will no longer be considered for selection in the RFP. Release List determinations are final and will not be reconsidered.

2.	PPA Execution. A successful bidder (“Seller”) will be asked to enter into a PPA with the Company that is consistent with the terms and conditions provided in the applicable pro forma PPA (either Attachment G or H). As stated in Sections III(E)(5), Georgia Power will not accept substantive or material changes to the pro forma PPA at the time of PPA execution. The Company will coordinate with Seller to work towards execution of the PPA in accordance with the Solicitation Schedule.

J.	Georgia Power Discretion in Contracting

The Company reserves the right, without qualification and at its sole discretion, and in consultation with the IE and Staff, to reject any, all, or portions of the proposals received for failure to meet any criteria, and further reserves the right, without qualification and at its sole discretion, and in consultation with the IE and Staff, to decline to enter into a PPA with any bidder. A bidder who submits proposals in response to this RFP thereby waives any recourse against the Company, its parent, or any of its Affiliates, or the IE for either rejection of their proposal(s) or for failure to execute a PPA for any reason.

K.	Certification

Following the completion of the RFP process, Georgia Power will seek Commission certification pursuant to O.C.G.A. § 46-3A-4 of each of the PPAs executed as a result of this RFP. The Certification process will take place under a separate Commission Docket and may take up to six (6) months to complete, unless otherwise expedited pursuant to the Procedural and Schedule Order to be issued by the Commission.

L.	Definitions

All capitalized terms used in this RFP and not otherwise defined have the respective meanings set forth below:

“2016 IRP Final Order” - means the 2016 Georgia Power Integrated Resource Plan as approved by the Commission.

“Additional Security” - means the cash, Letter of Credit or Seller Guaranty posted by Seller if Georgia Power has determined that grid improvement costs are anticipated to be incurred to deliver the full output of the Facility to Georgia Power’s customers, which Georgia Power may draw upon in the event of early termination of the PPA caused by a Seller Event of Default that occurs prior to Commercial Operation.

“Advanced Solar Initiative” or “ASI” - means the program created by Georgia Power that offered solar developers the opportunity to bring large, utility scale solar resources to market through a competitive RFP process, and offered existing Georgia Power customers the option to sell distributed solar generation back to the Company through small and medium scale solar purchase programs.

“Advanced Solar Initiative-Prime” or “ASI-Prime” - is the successor program of ASI.

“Affiliate(s)” - means for any specific Person, any other Person directly or indirectly controlling or controlled by or under common control with such specified Person.  For purposes of this definition, “control” when used with respect to any entity means the power to direct the management and policies of such entity, directly or indirectly, whether through the ownership of voting securities, by contract or otherwise.  For purposes of the pro forma PPA, it is assumed that the direct or indirect owner of fifty percent (50%) or more of the outstanding stock or other equity interest of a Person has “control” of such Person; and the terms “controlling” and “controlled” have meanings correlative to the foregoing.

“AIER” - means Associated Interchange Energy Rate, which as determined for each Hour, is based on the variable dispatch cost of the incremental resources that serve the collective obligations of the Southern Companies.

“Annual Energy Contract Amount” or “AECA” - means the sum of the Seasonal Energy Contract amounts in MWh for any identified Annual Period reflected in Appendix H of the pro forma PPAs.

“Annual Period(s)” - means any one of a succession of consecutive twelve-Month periods during the Term of pro forma PPA, the first of which will begin on the first Day of the Month following the COD; provided, however, if Commercial Operation is achieved on the first Day of a Month, the first Day of the first Annual Period is the COD.

“ASC” - means the FASB Accounting Standards Codification.

“Avoided Energy Costs” - means, for each hour of a given month, the amount, in dollars per megawatt-hour ($/MWh) that is equal to the avoided cost of generation on the Georgia Power territorial system for each hour of such month as such is calculated pursuant to the RCB approved by the Commission’s order in Docket No. 40161. Avoided Energy Cost includes the costs associated with avoided fuel costs, avoided variable O&M costs, avoided environmental compliance costs and avoided transmission/distribution energy losses.

“Bid Fee” - means the non-refundable fee a bidder is required to submit with each bid to defray costs of performing an evaluation of each bid.

“Bid Team” - means the identified members of the Southern Power team that may submit a bid in this RFP and are identified on the Commission’s and the IE’s websites.

“Bidders Conference” - means the conference held to allow potential bidders and interested parties to discuss the RFP process, the draft RFP Document and the pro forma PPAs with the Company, Staff and the IE.

“Capital Lease” - has the meaning as set forth in the Accounting Standards Codification (“ASC”) Topic 840, Leases and the meaning set forth for a “finance lease” in ASC Topic 842, Leases, as issued and modified from time to time by FASB.

“Certification” - means the certification the Company will seek from the Commission pursuant to O.C.G.A. § 46-3A-4 for each of the winning PPAs executed pursuant to this RFP.

“Commercial Operation” - has the meaning set forth in Section 2.4 of the pro forma PPAs.

“Commercial Operation Date” or “COD” - means the date on which the Facility achieves Commercial Operation.

“Commercial and Industrial (C&I) Program” - means an extension of the utility scale REDI RFP that is under development, and has the potential to increase the procurement by up to 200 MW, provided that the program options must result in delivering value to all Georgia Power customers and will be benchmarked against the last accepted bid from this REDI RFP.

“Commission” - means the Georgia Public Service Commission.

“Competitive Tier” - means the best proposals chosen for further evaluation.

“Confidential Information” - means business or technical information rightfully in the possession of either Party, which information derives actual or potential commercial value from not being generally known or readily ascertainable through independent development, or reverse engineering by persons who can obtain economic value from its disclosure and use, and includes information furnished or disclosed to the other Party in connection with discussions leading up to execution of the PPA, including the PPA. Confidential Information must be designated in writing as confidential by the bidder contemporaneously with the supply of such information to Georgia Power. Confidential Information does not include information that: (i) is or becomes publicly available other than as a result of a violation of the PPA; (ii) was, at the time of the disclosure, already in the Georgia Power’s possession; (iii) is disclosed to Georgia Power by a third party who, to Georgia Power’s knowledge, is not prohibited from disclosing the information pursuant to any agreement with the bidder; (iv) Georgia Power develops or derives without the aid, application or use of the privileged or proprietary information; or (v) Georgia Power is required to disclose pursuant to Legal Requirements.

“Creditworthy” or “Creditworthiness” - means (i) a Person with an investment grade rating from two (2) of the three (3) Rating Agencies such that its senior unsecured debt (or issuer rating if such Person has no senior unsecured debt rating) is rated at least (A) BBB- by S&P, if rated by S&P, (B) Baa3 by Moody’s, if rated by Moody’s, and (C) BBB- by Fitch, if rated by Fitch, respectively, and (ii) has satisfactory and verifiable creditworthiness determined in Georgia Power’s sole discretion.

“Documents Page” - means the page on the IE Website where relevant documents described in this RFP are electronically available.

“Effective Date” - means the date of execution of the pro forma PPA by Georgia Power and the winning bidder.

“Electrical Products” - means all electrical products produced by or related to the Facility, including spinning reserves, operating reserves, balancing energy, regulation service, ramping capability, reactive power and voltage control, frequency control and other ancillary or essential reliability service products, or any benefit Georgia Power otherwise would have realized from or related to the Facility if Georgia Power rather than Seller had constructed, owned or operated the Facility, it being the Parties’ intent that all such benefits and entitlements in addition to electrical output that flow to the owner or operator of the Facility, whether existing as of the Effective Date or at any time during the Term, will belong to Georgia Power at no additional cost to Georgia Power. For the avoidance of doubt, Electrical Products do not include any federal, state or local tax attributes arising from the ownership of the Facility, including any ITC, PTC or depreciation deductions, or any grant in lieu of investment tax credits or any similar financial payment or grant with respect to the Facility.

“Energy” - means the energy portion of the Renewable Energy delivered pursuant to the pro forma PPAs.

“Energy Contract Amount” - means the amount of energy provided for in the 8760 hourly profile submitted by the bidder.

“Engineering and Procurement Agreement” -  means an agreement that a winning bidder can execute with Georgia Power to assume cost responsibility and allow pre-construction activities, such as engineering work and procurement of long lead-time materials, to commence prior to signing an Interconnection Agreement with Georgia Power.

“Environmental Affairs” - means the environmental affairs department at Georgia Power Company.

“Environmental Attributes” - means (i) any and all fuel-related, emissions-related, air quality-related or other environmental-related aspects, claims, characteristics, benefits, credits, reductions, offsets, savings, allowances, efficiencies, certificates, tags, attributes, demand reductions or similar products or rights (including all of those relating to greenhouse gases and all green certificates, green tags, renewable certificates and RECs, CO2 credits and Emissions Rate Credits and all those that otherwise arise or result from the generation of energy from the Facility, and all those arising or resulting from the existence of the Facility) (a) howsoever titled and whether known or unknown, (b) whether existing as of the Effective Date or at any time during the Term, and (c) whether such Environmental Attributes have been certified or verified under any renewable standards, or (ii) any environmental benefit Georgia Power otherwise would have realized from or related to the Facility if Georgia Power rather than Seller had constructed, owned or operated the Facility; provided, however, that any such environmental benefit could be realized by Seller. Environmental Attributes include any such Environmental Attributes that could qualify or do qualify for application toward compliance with any local, state, federal or international renewable energy portfolio standard, green pricing program, renewable energy program, carbon reduction or greenhouse gas reduction initiative, electricity savings program, licensing requirement, verification or certification procedure, federal contract, or other environmental program, incentive mandate or objective, in each case whether voluntary or mandatory, and whether created by a Legal Requirement, or by any Governmental Authority, partnership, coalition, advisory committee, or independent certification board, group or scientific panel. Environmental Attributes include the exclusive right to report such Environmental Attributes to any Governmental Authority or other Person. Environmental Attributes do not include: (I) federal, state, or local tax attributes arising from the ownership of the Facility, including ITC, PTC and depreciation deductions; (II) grants in lieu of investment tax credits or any similar financial payment or grant with respect to the Facility or the metered electric energy output thereof; or (III) the metered electric energy produced by the Facility.

“Environmental Compliance Affidavit” - means the notarized affidavit, the form of which is found in Attachment F, that confirms that bidder understands the requirement to comply with the legal environmental standards and requirements respecting the Site, bidder’s agreement to conduct further due diligence in compliance with Attachment E if selected for the Short List, and that bidder will avoid, minimize and mitigate any environmental impacts, as required under applicable federal and state law, for the Term of the PPA.

“Evaluation Team” - means the team reviewing bids submitted in this RFP.

“Facility” - means a separately metered facility and related equipment and facilities of the renewable electric generating plant described in Appendix F of the pro forma PPAs constructed by Seller on the Site. The Facility includes the primary and auxiliary equipment and facilities installed at the Site necessary or used for the extraction or collection of fuel, or the production, control, delivery, monitoring, or storage of energy by the renewable electric generation equipment. All equipment and facilities installed on Seller’s side of the Point of Delivery will be considered a part of the Facility except for those that constitute Interconnection Facilities.

“Fair Market Value” - means, with respect to a particular time of calculation, the amount a willing buyer would pay for the Facility assets and all rights and interests associated therewith, in an arm’s-length transaction, to a willing seller under no compulsion to sell on the applicable closing date, taking into account all relevant facts and circumstances relating to the Facility, as of such closing date.

“FASB” - means the Financial Accounting Standards Board.

“Firm Transmission Service” - means transmission service that (i) has been procured and is held by a Seller under the applicable open access transmission tariffs on each applicable Transmission System for the delivery of Energy from the Facility or balancing authority area(s) to the Point of Delivery; and (ii) has a priority equal to the highest level of firm transmission service available to any Person on such Transmission System from the COD and through the remainder of the Term.

“Fitch” - means Fitch Ratings Ltd. or its successor. If Fitch ceases to exist or publish ratings, Fitch will mean a nationally recognized rating agency mutually agreed upon by the Parties.

“Front Load Performance Security” - means that cash, Letter of Credit or Seller Guaranty delivered by Seller to Georgia Power pursuant to the provisions of Section 5.5 of the pro forma PPAs, and as further discussed in Section II(B)(1)(d) in this RFP.

“Generating Capacity” - means the generating capacity of the Facility as specified in Section 2.1 of the pro forma PPAs, which excludes any on-Site energy storage capability of the Facility.

“Georgia Integrated Transmission System” or “Georgia ITS” - means the integrated transmission system in Georgia, which consists of electric transmission  facilities (>40kV) that are individually owned and maintained by participating utilities who jointly plan and operate through agreements among Georgia Transmission Corporation, Georgia Power, Municipal Electric Authority of Georgia (“MEAG Power”) and Dalton Utilities.

“Georgia Power” - means Georgia Power Company and any permitted successor or assign.

“Georgia Power Distribution System” - means collectively, the entire network of electric generating and distribution facilities, equipment and other devices owned (in whole or in part) or controlled by Georgia Power for the purposes of generating, transmitting, and receiving electric energy at a voltage less than 40 kV.

“Georgia Power Feeder” - means a Georgia Power three-phase primary distribution line originating from a Georgia Power substation.

“Georgia Power Interconnection Agreement” - means the Interconnection Agreement when Seller interconnects to the Southern Company Transmission System (that is between Seller and Georgia Power or Seller and Southern Company Services, Inc. as agent for Georgia Power) or to the Georgia Power Distribution System.

“Georgia Power Substation” - means a bus inside a Georgia Power substation.

“GPSC” - means the Georgia Public Service Commission.

“GSU” - means the generator step-up transformer, which is a device used to convert the Facility voltage level up to the interconnecting voltage level.

“Impacted System Upgrades” - means the Transmission System upgrades on systems other than the Southern Company Transmission System or Georgia ITS that are required for interconnection.

“Independent Evaluator” or “IE” - means the Accion Group, who reports to the Commission and is under contract with the Company to oversee the RFP and serves as the point of contact for all bidders.

“Interconnection Agreement” - means that certain agreement by and between Seller and the applicable Interconnection Provider containing terms and conditions governing the interconnection and parallel operation of the Facility with the Transmission System, or if applicable, the Georgia Power Distribution System.

“Interconnection Facilities” - means the specific transmission or distribution line and substation facility additions and modifications that are owned by an Interconnection Provider and that are necessary to provide the physical electrical connection at the Point of Interconnection between the Facility and the Transmission System or the Georgia Power Distribution System.

“Interconnection Provider” - means the owner or operator of the Transmission System responsible for providing transmission interconnection service to the Facility or, as applicable, to Georgia Power as Distribution Provider.

“Interconnection Study” - means a study by the Facility’s Interconnection Provider in which the provider studies the Facility’s potential impacts on the Transmission System and/or distribution system to determine the necessary Interconnection Facilities, the related estimated costs, and the schedule of construction, for purposes of entering into an Interconnection Agreement.

“ITS Participant” - means Georgia Transmission Corporation, MEAG Power, or Dalton Utilities.

“kW” - means kilowatt alternating current.

“Land Acquisition” - means the land acquisition department at Georgia Power Company.

“Letter of Credit” - means a standby letter of credit that (i) is substantially in the form set forth in Appendix B of the pro forma PPAs, (ii) is issued by a U.S. commercial bank or a U.S. branch of a foreign bank with total assets of at least ten billion dollars ($10,000,000,000) having a general long-term senior unsecured debt rating of A minus or higher as rated by S&P, or A3 or higher as rated by Moody’s, or A minus or higher as rated by Fitch, and (iii) is otherwise acceptable to Georgia Power in Georgia Power’s sole discretion.

“Moody’s” - means Moody’s Investors Service, Inc. or its successor. If Moody’s ceases to exist or publish ratings, Moody’s will mean a nationally recognized rating agency mutually agreed upon by the Parties.

“MW” - means megawatt alternating current.

“MWh” - means megawatt-hour alternating current.

“Notice to Proceed” or “NTP” - means a notice to initiate the construction of interconnection-related facilities.

“OATT” - means Southern Company’s open access transmission tariff, as further discussed in Attachment D.

“Party” or “Parties” - means either Georgia Power or bidder or both.

“Performance Security” - has the meaning set forth in Section 5.1 of the pro forma PPAs found in Attachments G and H.

“Person” - means any natural person, corporation, limited liability company, general partnership, limited partnership, proprietorship, other business organization, trust, union, association or Governmental Authority.

“Point of Delivery” - means, if a Facility is interconnecting to the Southern Company Transmission System or the Georgia ITS, the Point of Interconnection. If the Facility is interconnecting to the Georgia Power Distribution System, the Point of Delivery is the point where Seller will deliver Energy to Georgia Power as indicated on Appendix J of the pro forma PPAs. If the Facility is interconnecting outside the SBAA, the Point of Delivery is the selected Southern Transmission Interface identified in Section 8.6.2 of the pro forma PPAs.

“Point of Interconnection” or “POI” - means the point at which the Facility is interconnected to the Transmission System or the Georgia Power Distribution System, as defined in the Interconnection Agreement with the applicable Interconnection Provider as illustrated in Appendix J of the pro forma PPAs.

“PPA” - means power purchase agreement.

“Pre-Bid Webinar” - means the webinar presentation of general environmental and transmission interconnection information.

“Primary Beneficiary” - has the meaning set forth in ASC Topic 810, Consolidation, as issued and modified from time to time by FASB.

“Profile” - means, for a Facility interconnecting to the Southern Company Transmission System, the Georgia ITS, or the Georgia Power Distribution System, the Facility’s 8760 hourly generation (MWAC) at the high side of the GSU in Eastern Standard Time and unadjusted for Daylight Savings Time. For a Facility interconnecting outside the SBAA, it means the Facility’s 8760 hourly generation (MWAC) delivered to the Southern Transmission Interface in Eastern Standard Time and unadjusted for Daylight Savings Time.

“Projected Avoided Costs” - means the costs Georgia Power would incur to provide the same service as would be provided by the bidder’s proposal.

“Rating Agency” or “Rating Agencies” - means the rating entities of S&P, Moody’s or Fitch.

“REDI” - means Georgia Power’s Renewable Energy Development Initiative and the associated Request for Proposals approved by the GPSC in Docket Nos. 40161 and 40706.

“Release List” - means bids that were determined to be non-competitive and will no longer the considered for selection in the RFP.

“Renewable Cost Benefit Framework” or “RCB” - means the comprehensive framework for determining an objective assessment of the costs and benefits of renewable resources on the Southern Company electric system to be used by Georgia Power for the purposes of future program design, resource evaluations, and payment calculations that was approved by the GPSC in Georgia Power’s 2016 Integrated Resource Plan in Docket No. 40161 for Georgia Power’s evaluation of REDI bids and amended by the Joint Recommendation Regarding the Renewable Cost Benefit Framework approved by the GPSC on December 22, 2016.

“Renewable Energy” - means the Energy, including all the associated Environmental Attributes and Electrical Products, produced by the Facility and sold to and purchased by Georgia Power under the PPA. The Energy generated primarily utilizes one or more of the following type(s) of sustainable, perpetual, or renewable fuels: (i) solar photovoltaic (fixed or tracking); (ii) wind; (iii) geothermal (natural or enhanced); (iv) biomass or biogas; (v) hydro; or (vi) such other renewable fuel or technology as determined by Georgia Power in its sole and absolute discretion.

“Required Commercial Operation Date” or “RCOD” - means the date in the pro forma PPA by which the Facility is required to obtain Commercial Operation.

“Reserve List” - means the list of projects that are essentially on a wait list that will continue to be under evaluation and may move on to the Short List if a Short List bidder withdraws or is unable to proceed to PPA execution.

“RFP” - means Request for Proposals.

“S&P” - means Standard & Poor’s Financial Services LLC, or its successor. If S&P ceases to exist or publish ratings, S&P will mean a nationally recognized rating agency mutually agreed upon by the Parties

“Seasonal Energy Contract Amount” or “SECA” - has the meaning set forth in Section 7.1 and Appendix A.

“Seller” - means winning bidder who has executed a PPA with Georgia Power.

“Seller Guarantor” - means a Person that, at the time of execution and delivery of its Seller Guaranty, is an Affiliate of Seller or is otherwise an entity acceptable to Georgia Power  and (i) is Creditworthy with a consolidated Net Worth to be calculated as _________ ($____) [per MWh associated with the Annual Energy Contract Amount]; or (ii) is reasonably acceptable to Georgia Power as having verifiable creditworthiness and Net Worth sufficient to secure Seller Guarantor’s obligations under the Seller Guaranty.

“Seller Guaranty” - means a guaranty provided by Seller Guarantor that is substantially in the Form of Guaranty in Appendix C of the pro forma PPAs.

“Short List” - means the list of best proposals chosen for further evaluation, based upon the results of the detailed evaluation.

“Site” - has the meaning set forth in Appendix F of the pro forma PPAs found in Attachments G and H.

“Site Control Affidavit” - means the notarized Affidavit, the form of which is found in Attachment I, that affirms that bidder has obtained site control of the project location for the Term of the proposed PPA.

“Solicitation Schedule” - means the Schedule for this solicitation provided in Section III (A) of the RFP.

“Southern Balancing Authority Area” or “SBAA” - means the NERC and SERC recognized balancing authority area that includes the Southern Company  Transmission System and the Georgia ITS.

“Southern Companies” - means, collectively, the regulated electric operating companies of The Southern Company (currently Alabama Power Company, Georgia Power Company, Gulf Power Company, and Mississippi Power Company).

“Southern Company Transmission System” - means the transmission system consisting of transmission facilities owned by the Southern Companies, as such system may be modified or expanded from time to time, as well as any successor transmission system(s).

“Southern Power” - means Southern Power Company, an Affiliate of Georgia Power.

“Southern Transmission Interface” - means a transmission interface between the Southern Company Transmission System and another Transmission System. For a Facility located outside the SBAA, the Point of Delivery will be at the selected Southern Transmission Interface identified in Section 8.6.2.

“Staff” - means staff members of the Georgia Public Service Commission.

“Station Service” - means energy that is used to serve the electrical requirements of the Facility, and includes the step-up transformer losses and line losses between the Facility and the Point of Delivery. If Seller supplies its starting and running station service on Seller’s side of the POI, the Facility’s output is net of energy consumed and demand requirements (i.e., the energy delivered to the Point of Interconnection).

“Stipulation” - means the approved provision in Georgia Power’s 2016 IRP that set forth a supply-side plan and included approval of REDI.

“Term” - has the meaning set forth in Section 3.1 of the pro forma PPAs.

“Transmission Provider” - means any public utility (or its designated agent) that owns, controls, or operates transmission or distribution facilities used for the transmission of Energy in interstate commerce and provides transmission service under a tariff.

“Transmission Service Request” or “TSR” - means a request for Firm Transmission Service.

“Transmission System” - means, collectively, the entire network of electric generating and transmission facilities, equipment and other devices for the purposes of generating, transmitting, and receiving electric energy.

“Variable Interest” or “VI” - has the meaning set forth in ASC Topic 810, Consolidation, as issued and modified from time to time by FASB.

“Variable Interest Entity” or “VIE” - has the meaning set forth in ASC Topic 810, Consolidation, as issued and modified from time to time by FASB.

“Winner’s Fee” - means the fee assessed upon each winning bid to cover a portion of the IE cost.

ATTACHMENT A

Bidder Questionnaire

This is a summary of data needed to complete certain fields of the bid form posted on the IE Website but is not all encompassing.

Each bidder must supply the following information, as applicable and appropriate:

Acknowledgement of several items that demonstrate the proposal meets requirements of the RFP and that bidder understands key provisions of the RFP.

Bidder Information:

Legal name of contracting party, if known, and immediate upstream parent entity, if applicable.

Qualifications:

- (i)	Previous experience providing the proposed product.

- (ii) 	Letter of interest or letters of commitment from potential financing or tax                     equity partners.

Indication if the company is formed for the sole purpose of the project and a summary of the proposed Facility’s legal ownership structure.

Financial and credit information for the bidder and for the bidder’s parent company (if applicable), including:

Description of ownership and debt arrangements, including the expected percentage of debt and equity capital that the bidder has committed to secure.

Annual reports for the past three (3) years and any Form 10-K and 10-Q filings since the period covered in the last annual report.  If these documents are not available, then audited financial statements for the last three (3) years will be accepted. All financial statements, annual reports, and other large documents may be referenced via a website address. If a bidder has not been in operation for three (3) years, please provide the above information, as applicable, since the commencement of operation.

Dunn and Bradstreet identification number.

Credit rating of the bidder’s senior debt securities.

Details related to its banking relationships or liquidity.

Description of plans for acquiring the necessary funds for developing and operating the Facility, including a discussion of the Facility’s legal ownership structure, the expected percentage of debt and equity capital that the bidder has committed to secure, and the identity and credit rating of firms that are likely to provide such financing.

Any additional documentation needed to determine the bidder’s financial strength and the strength of any corporate parents.

A detailed description of any security/credit instruments proposed by the bidder to back its performance obligation. An acceptable Letter of Credit or Guaranty must include the provisions set forth in Appendix B and Appendix C of the pro forma PPAs.

Statement that the PPA will not require deconsolidation with Georgia Power as the Primary Beneficiary by the Seller with respect to Variable Interest Entity.

Statement indicating whether or not the Renewable Energy has been offered in another RFP or is otherwise obligated to another party and, if so, how it would be released to serve this proposed sale.

A map indicating the Facility location and known or proposed interconnection to the Transmission System or distribution system. All known descriptions, drawings or details are beneficial in the evaluation of bids.

A thorough description of anticipated environmental impact and compliance.

For a new Facility, a construction schedule with all major activities from award of contract to commercial operation.

Status of Interconnection Agreement:

Detailed description of the interconnection arrangements that have been or will be made to deliver the Energy to Georgia Power Company or the SBAA and how any identified costs are included in the bid.

If an Interconnection Agreement is not in place, describe the development of the negotiations for such agreement.

C.	Indicate the current status regarding property rights for the necessary interconnection facilities, including access rights for the Interconnection Provider throughout the PPA Term and any property rights and permits needed between the Facility Site and the Interconnection Provider’s facilities.

Any limitations on the use or availability of the Renewable Energy.

An ongoing operation and maintenance plan for the Facility.

Proposed changes to the Pro Forma PPA(s) to reflect the product (Facility or resource type) in the form of a red-line mark-up and a list summarizing the proposed changes with the rationale for each change.

Pricing proposal(s) – provide all that apply.

Term of proposal. (15, 20, 25, or 30 Annual Periods).

Facility information, including (but not limited to):

Name.

Location.

Site Plan.

Site Control Affidavit.

Specific technical information (i.e. number of panels, generators, turbine information, spec sheets, manufacturer, maintenance schedules, etc.).

Delivery Schedule.

Performance data:

Maximum Capability (MWAC & MWDC).

Annual Degradation after first year.

8760 Output Profile for first Annual Period (include any degradation during first Annual Period).

Describe specifications of what was used to produce 8760 Profile (Summarize model assumptions, key inputs and methodology).

Interconnection Data:

Single line diagram to Point of Interconnection.

Narrative of current path or plan for Interconnection to the System.

Impedances, Short Circuit currents, etc.

Generator Interconnection Tie Line Data.

GSU/Main Transformer Data.

kV at the Point of Interconnection.

Estimated/Assumed Interconnection Costs to Point of Interconnection.

H.	Detailed description of the interconnection arrangements, including projected timelines for Interconnection Study processes and the construction of Interconnection Facilities.

ATTACHMENT B

Non-Price and Qualitative Considerations

Although the majority of Georgia Power’s evaluation will focus on the proposals economic net benefits, other qualitative and non-price attributes will be considered. The non-price factors listed below may be used to select the winning proposals.

- Reliability associated with Facility location inside the SBAA.

- Interconnection directly to the Georgia Power Transmission System or Georgia Power Distribution System

- Bidder development experience

ATTACHMENT C

Overview of the Evaluation for Bid Responses

- General Overview:

Each proposal submitted into this RFP will be evaluated and ranked based on the net present value benefits to Georgia Power’s customers. The net benefit of a proposal is calculated by subtracting the costs customers will pay associated with the proposal from the projected costs customers would otherwise incur if the proposal was not enacted. In its evaluation, Georgia Power will consider the proposal costs, the Projected Avoided Costs pursuant to the RCB, any transmission and distribution costs, and will perform a portfolio analysis to consider the impact of such costs, together with the impact of different renewable generation types, and unequal contract Terms. These evaluation components are described in further detail below.

- Proposal Costs:

Proposal costs represent the costs Georgia Power customers will pay for implementing the bidder’s proposal.

For PPAs, the primary component of these costs would be the costs paid by Georgia Power to the Seller for the Renewable Energy. These costs are dependent upon the bid price of the Renewable Energy and the quantity of Renewable Energy delivered. Per the terms of the pro forma PPAs, this price may be adjusted depending on the performance of the Facility on an annual basis throughout the PPA Term. Georgia Power’s evaluation assumes one hundred percent (100%) of the Facility’s expected output is delivered.

For proposals offering a Facility Purchase Option, the primary component of costs would be the costs paid by Georgia Power to Seller for the legal and rightful ownership of the Facility and will include costs for operating the Facility. These costs will be in the form of annual revenue requirements.

For all proposals offering an Energy-Only product, the Annual Energy Contract Amount (“AECA”) for the first Annual Period will be equal to the Energy in the 8760 hourly Profile submitted by the bidder. The AECA in subsequent Annual Periods will decrease according to the degradation profile submitted by the bidder, which is found in Appendix G of Attachment G. The Company will perform its own analysis of the data provided to ensure reasonableness of the bid.

For all proposals offering a Firm Delivery product, the quantity of Energy delivered in each hour is specified by month in the PPA. The total quantity of Energy delivered for the first Annual Period will be equal to the sum of Hourly Energy values for each month across all hours of the year per the bidder’s proposal; however, no degradation will be applied for subsequent Annual Periods unless clearly specified by the bidder in its proposal.  Furthermore, Firm Delivery products may receive credit against those portions of the RCB cost components that are not impacted due to the firm nature of the bid.

Another component of Proposal Costs for all bidders is cost borne by Georgia Power to interconnect the Facility to the electric system and to make grid improvements, if any, necessary to accommodate the delivery of the Energy to its customers.

- Projected Avoided Costs:

Projected Avoided Costs represent the costs the Company would incur to provide the same service as would be provided by the bidder’s proposal. As provided in the RCB, components of this cost include Deferred Generation Capacity, Avoided Energy Costs, Generation Remix Costs, and Support Capacity Costs. Because Projected Avoided Costs are calculated on an hourly basis, the total evaluated projected avoided cost benefit will vary depending on the Facility’s output Profile reflected in the bidder’s proposal.

- Generation Costs – determining the Deferred Generation Capacity Costs:

The deferred generation capacity cost is a measure of the costs associated with a Facility’s availability during periods where generation capacity would most likely be needed to meet customer demand and will be calculated as follows:

1.	The equivalent kW capacity of the Facility will be determined based on the hourly output Profile for a typical year and hourly probabilities of the system needing capacity. For subsequent years, that equivalent capacity is reduced using the bidder’s provided degradation schedule. Proposals that provide more Energy at or near the Company’s peak load hours will receive a higher capacity equivalent.

During the summer months, the Company’s peak load hours tend to occur between 3:00 and 6:00 PM EPT. During winter months, the Company typically experiences two peaks, one in the early morning (6:00 – 8:00 AM EPT) and one in the late evening (5:00 – 7:00 PM EPT).  During the spring and fall months, the Company’s loads are relatively flat over the daytime hours.

2.	The projected avoided generation capacity cost for an Annual Period in dollars ($) is determined by multiplying the equivalent capacity of the Facility’s energy in kW times the annual avoided capacity rate in dollars per kilowatt-year ($/kW-yr). The avoided capacity rate is zero until Georgia Power’s IRP indicates the Company will be below the target planning reserve margin. The avoided capacity rate is then set to the economic carrying cost of a combustion turbine.

3.	The projected avoided generation capacity cost for each Annual Period is converted to $/MWh by dividing the annual costs from step 2 by the annual MWh for each Annual Period (using the bidder’s provided output for a given Annual Period and degradation as appropriate) of the proposal.

- Generation Costs – determining the Avoided Energy Cost:

Each proposal’s contribution to reducing the aggregate annual system generation fleet fuel and variable cost will be calculated by multiplying the projected hourly avoided energy rates in $/MWh by the Facility’s hourly output Profile in MWh for each Annual Period based on the bidders’ provided output for a given Annual Period and any degradation provided with each proposal. The hourly output Profile submitted by the bidder will be adjusted to account for transmission and distribution losses, as appropriate.

- Generation Remix and Support Capacity Costs:

In accordance with the RCB, and depending upon the technology associated with each proposal, there will be a $/MWh cost (or benefit) modifier attributed to the bid reflecting the impact of both the Generation Remix and Support Capacity components of the RCB. These costs (or benefits) will vary by technology and will be applied on an annual basis to the annual MWh for each Annual Period using the output Profile submitted by the bidder for a given Annual Period, and the applicable degradation, as appropriate, of the proposal.

- Avoided Cost Heat Map:

Figure 1 below is a heat map showing the relative projected avoided energy costs for a typical 24-hour Day by month. This information is provided to assist a bidder with technology selection.  Higher values indicate the hours that tend to have the highest avoided costs. The values are normalized such that the hour with the highest projected avoided cost is represented by a value of 1.0. The values in the other hours provide an indication of the projected avoided cost in any other hour relative to the maximum value.

Figure 1 Indicative Avoided Cost for Typical Days Relative to Annual Peak Avoided Cost

- Evaluation of Transmission / Distribution System Impacts of Bids:

An assessment of the transmission/distribution impact of each bid is an integral part of the total cost analysis. Each proposal is evaluated from a transmission/distribution perspective in order to assess the additional investment to the existing transmission/distribution system required to interconnect and deliver the proposed generation to Georgia Power’s customers from the COD through the Term of the PPA.

For bid evaluation purposes, the proposal is assessed the yearly amortized cost borne by Georgia Power of such improvements over the Term of the PPA.

- Due Diligence Portfolio Analysis:

Portfolio analysis will be necessary if the potential Short List of proposals includes proposals connecting to the transmission/distribution system such that the transmission/distribution cost of one proposal impacts the transmission/distribution cost of another proposal. In such case, evaluations of the combined effects of such proposals would be necessary to select the best combination of proposals.

- Portfolio Evaluation of Renewable Generation Combinations:

The benefits of combinations of various renewable energy technologies can be determined with the application of the RCB. Combinations of different renewable generation resource types submitted in response to this RFP will be investigated if obvious synergies are apparent based upon the specific details included in each respective proposal. Synergies that may exist among independently submitted proposals include, but are not limited to, resources with complimentary generation Profiles and integration benefits.

- Evaluation of Proposals with Unequal Contract Term Lengths:

The Company will consider proposals offering a Term of fifteen (15), twenty (20), twenty-five (25) or thirty (30) Annual Periods, at the bidder’s option. For the evaluation of proposals with unequal contract Term lengths, the Company will utilize its Projected Avoided Cost to enable it to evaluate the proposals on an equivalent basis given the unequal Term lengths, which is consistent with how the Company has evaluated proposals with different length terms in prior RFPs.

ATTACHMENT D

Additional Transmission and Distribution Guidance

- Facilities Interconnecting to the Southern Company Transmission System (≥40 kV), the Georgia ITS (≥40 kV), or the Georgia Power Distribution System (<40 kV)

The POI refers to the point where the Interconnection Facilities connect to the Transmission Provider’s Transmission System or Georgia Power’s Distribution System. The POI is not necessarily the same as the point of change of ownership of equipment (“Change of Ownership”).

The following example diagrams are offered to assist a bidder in making a determination of where the POI could be located in its respective bid. A bidder whose Facility will interconnect with the Southern Company Transmission System (≥40 kV), the Georgia ITS (≥40 kV), or the Georgia Power Distribution System (<40 kV) is responsible for all Interconnection Study-related costs in addition to the interconnection costs and risks up to the POI. These costs generally include equipment such as the GSU transformer (for conversion up to the interconnecting voltage level), Facility-side generator interrupting device, all Station Service equipment and any additional equipment, such as a utility-owned interrupting device and metering needed to connect to the transmission facilities, as well as any additional real property for the interconnection substation and access, operation and maintenance, and administrative charges. In addition, if applicable, the bidder also is responsible for the costs, risks, and coordination of the Impacted System Upgrades that are required for interconnection.

Information regarding interconnection to the Southern Company Transmission System may be found at Southern Company’s OASIS website at http://www.oasis.oati.com/SOCO/ index.html. Information about Generator Interconnection under Southern Company’s OATT can be found in the Generator Interconnection folder on the Southern Company OASIS home page.

Information regarding interconnection to a Georgia Power Feeder may be found in the Southern Company Distribution Interconnection Policy, which can be found on the IE Website and at https://www.georgiapower.com/docs/energy-efficiency/SOCO_Interconnection_ Standard_Rev2013_13.pdf.

Information regarding interconnection to a Georgia Power Substation, can be found on Southern Company’s OASIS website at http://www.oasis.oati.com/SOCO/index.html.

If the bidder needs further clarification, please use the question and answer process available on the IE Website.

- Facilities Interconnecting outside the Southern Company Transmission System and the Georgia ITS (≥40 kV) (i.e., outside the SBAA)

For this RFP, a Southern Transmission Interface is defined as a point where the Southern Company Transmission System connects to a neighboring Transmission Provider and can receive Firm Transmission Service deliveries from such Transmission Provider. The Southern Company Transmission System has four primary interfaces: TVA, VACAR, Florida and MISO.

For a Facility located outside the SBAA, the bidder is responsible for all costs and risks, including interconnection- and delivery-related, to effectuate delivery from the Facility to the selected Southern Transmission Interface. In addition to interconnection, this will require Firm Transmission Service from the COD through the remainder of the Term of the PPA. The bidder is responsible for determining all transmission-related rules, practices, and policies with which it must comply for both interconnection and delivery to the selected Southern Transmission Interface.

Although the bidder is responsible for all costs and risks to deliver to the selected Southern Transmission Interface, there may be additional costs to deliver from the selected Southern Transmission Interface to Georgia Power’s customers. These costs should not be included in the bid price. However, Georgia Power will assess such costs in the evaluation of the economics of the proposal. The following example diagram is offered to assist the bidder in making a determination of transmission costs to include in the bid.

Facility Outside the Southern Company Transmission System and the Georgia ITS

Key

- Include cost in bid

- Do not include in bid

All interconnection costs & delivery costs to the Southern Company Transmission System Interface

Delivery costs within the Southern Company Transmission System

ATTACHMENT E

Environmental Site Assessment Guidance

From an environmental perspective, and in Georgia Power’s view, the best property for renewable generation development is property that has been comprehensively evaluated and determined to either have no past or present environmental items of concern, or if concerns are identified, the concerns can be avoided through generation technology or site configuration. Where environmental items are unavoidable, it is necessary to address identified environmental concerns through regulatory permitting, compliance, and possibly mitigation. The concerns listed below are intended to inform the bidder about common environmental issues encountered when selecting property for renewable generation development and are consistent with Georgia Power’s environmental siting criteria for new construction projects. Since all properties have unique prior land use histories and naturally occurring natural resources, local assessment of proposed Sites by a bidder is imperative. For the avoidance of doubt, the requirements of this Attachment E do not require a NEPA Environmental Assessment. A complete environmental Site assessment for inclusion in the bid packet should consider and address the following:

- Any existing relevant and reasonably available property environmental information (prior, current/ongoing environmental studies/documents, assessments, surveys, corrective action plans, natural resource inventories, etc.) should be obtained and reviewed for relevant current condition considerations.

- Waters of the US (“WOUS”; e.g., drainage features, creeks, streams, rivers, ponds, lakes, wetlands, etc.) and their buffers should be freshly identified and flagged through field delineation. Impacts to WOUS and their buffers should be avoided where possible. Where avoidance is unachievable, additional permitting and mitigation may be required.

- 100-year floodplains should be identified and encroachments should be avoided, or hydrology studies should be completed to document no significant rise in floodplain elevation, if floodplain impacts are unavoidable.

- NPDES Construction Storm water permitting will be required for land disturbing activities of one or more acres (GA NPDES Permit Nos. GAR 100001 & 100002; similar for other states). Permitting may be required prior to any initial site preparation work (land clearing, grubbing, grading, etc.); certain specific otherwise regulated silvicultural/timber harvest activities may be exempt from NPDES permitting but, any subsequent land disturbance activities greater than 1 acre will require NPDES permitting.

- Rare, threatened and endangered species (state and federal) occurrence should be documented and any regulatory compliance requirements satisfied for the Endangered Species Act and applicable state regulations. Critical habitat for plant and animal species should be identified and avoided; other site specific mitigation or avoidance actions may be necessary during phases of construction or operation to avoid sensitive habitat for rare species. Compliance with the Migratory Bird Treaty Act and the Bald and Golden Eagle Protection Act must be achieved as applicable. Consultations with various agencies may be required to comply with these laws.

- Spill Prevention, Control and Countermeasures (SPCC) compliance and plans may be required for site development and most likely will be required for construction and operation of the Facility to address oil/petroleum storage.

- Any potentially contaminated soil or groundwater must be identified. An ASTM E1527-13 Phase I Environmental Site Assessment may be required, at a minimum.

- Any project effects to cultural resources or historic properties must be identified and any applicable compliance with Section 106 of the National Historic Preservation Act or state historic protection or cultural resource laws must be achieved. Effects to viewshed aesthetics may need to be considered and preserved where applicable.

- Air quality items may need to be considered on a Site-specific activity basis (e.g. permitting of timber/other open burning, proximity to non-attainment areas, etc.).

- Local government permitting, ordinances and restrictions may also apply. These local requirements may supersede, pre-empt or complement certain state and federal permitting/compliance requirements that are otherwise allowed (such as floodplain impacts and cultural resource area preservation).

ATTACHMENT F

Environmental Compliance Affidavit

Georgia Power Company

241 Ralph McGill Blvd NE

Bin No. 20023

Atlanta, Georgia 20208

Subject:	Georgia Power Company’s REDI RFP – Environmental Compliance

Facility Address:

Generation Facility Type:

Contact person for the Site/Facility:

Ladies and Gentlemen:

On or before [date], and in accordance with the provisions of Georgia Power’s Renewable Energy Development Initiative (“REDI”), [Insert Bidder’s full legal name], a [Insert Bidder’s form of entity and state of organization] (“Bidder”), is submitting one or more proposals for consideration to fulfill a portion of Georgia Power’s REDI solicitation on behalf of the party to execute the REDI power purchase agreement (“PPA”) with Georgia Power and to sell Renewable Energy through the REDI Program (“Seller”). Capitalized terms found herein have the meaning assigned in the RFP.

Attachment E of the RFP describes environmental features that Bidder must consider, address, and document, as applicable, as part of its completed bid packet. Failure to consider environmental permitting, compliance, or Site related impacts, or failure to provide documentation of such consideration will be deemed an incomplete bid and may preclude further consideration of the bid proposal.

Bidder hereby represents, warrants, and covenants the following:

- Bidder is familiar with all applicable federal, state and local environmental regulations respecting the Site/Facility and has considered and addressed each of the factors described in Attachment E;

- The Site/Facility will comply with all applicable federal, state and local environmental requirements, including obtaining or renewing all applicable state and federal environmental permits;

- Seller will maintain all required federal, state and local environmental permits;

- Bidder or Seller, as the case may be, will promptly notify Georgia Power in writing of any material change in the status of the Bidder or Seller’s environmental compliance; and

- Bidder and Seller will avoid environmental impacts, if possible, and will mitigate unavoidable environmental impacts as required under federal and state regulations for the term of the PPA.

Bidder does solemnly swear or affirm under penalty of perjury, that the information Bidder has provided in this Affidavit is based on Bidder’s own personal knowledge and is true, complete and correct. Bidder acknowledges that any change in compliance status constitutes a change of information, notice of which Bidder or Seller, as the case may be, must provide to Georgia Power promptly. Bidder further certifies that he/she personally examined and is familiar with all the foregoing information, including any attachments and appendices, and further certifies that information to be true, correct, and complete.

[Insert Bidder’s full legal name]

By: ______________________________

Name:____________________________

Title:_____________________________

Company: ________________________

Date:_____________________________

State of ____________________

County of __________________

On this ______ day of _____________________, ________, before me appeared [Bidder’s full legal name], the person who signed the preceding Environmental Compliance Affidavit in my presence and who swore or affirmed that he/she understood the document and freely declared it to be truthful.

____________________

Official Signature of the Notary

Official Seal of the Notary

My Commission Expires:

ATTACHMENT G

Energy Only Pro Forma Power Purchase Agreement

ATTACHMENT H

Firm Delivery Pro Forma Power Purchase Agreement

ATTACHMENT I

Form Site Control Affidavit

[Insert Bidder’s Letterhead]

[Insert Date]

Georgia Power Company

241 Ralph McGill Blvd NE

Bin No. 20023

Atlanta, Georgia 30308

Subject:  	Georgia Power Company’s REDI RFP – Site Control

Ladies and Gentlemen:

On or before [date], and in accordance with the provisions of Georgia Power’s Renewable Energy Development Initiative (“REDI”) Program, [Insert Bidder’s full legal name], a [Insert Bidder’s form of entity and state of organization] (“Bidder”), is submitting, on behalf of the party to execute the REDI power purchase agreement (“PPA”) with Georgia Power and selling Renewable Energy through the REDI Program (“Seller”), one or more proposals for consideration to fulfill a portion of Georgia Power’s REDI solicitation. In order for such Bidder to be eligible for participation, Bidder or Seller, as applicable, must, among other things, possess Site Control, as such term is defined below. Capitalized words used without definition here have the meaning shown in the RFP.

Bidder hereby represents, warrants and covenants that:

- Bidder has Site Control of the Site, located at [Insert parcel number and GPS coordinates of the Site], which is the Site where the Facility is, or will be, located if Seller and Georgia Power execute a REDI PPA;

- The Site is adequate for the Facility and lawfully zoned for the Facility, or if not already appropriately zoned, Bidder agrees to obtain appropriate zoning prior to PPA execution;

- Seller is the authorized or legal entity that will execute the PPA with Georgia Power if Bidder’s proposal is selected for the Short List;

- Seller will retain Site Control of the Site for the duration of the PPA term, subject to the Assignment provisions of the PPA;

- Bidder or Seller, as the case may be, will promptly notify Georgia Power in writing of any change in the status of Bidder or Seller’s Site Control; and

- Upon request, Bidder or Seller, as the case may be, will provide to Georgia Power a copy of the lease, deed, or other satisfactory legal evidence of Site Control.

For purposes of this Affidavit:

“Site Control” means that, with respect to the Site, as further described above, and for the duration of the PPA Term, Seller (i) owns or will own the Site pursuant to (A) a current binding written agreement between Seller and the landowner, or (B) its exercise of an option to purchase the Site pursuant to a current binding written option agreement with the landowner; or (ii) is the lessee of the Site under a binding written lease agreement with the landowner, or will lease the Site by exercise of an option pursuant to a current binding written option agreement with the landowner; and (iii) is or will be the holder of each and every right-of-way grant, easement or similar instrument(s) necessary for Seller’s intended use of the Site. The undersigned is the managing partner or other person or entity authorized to act for Seller in all matters relating to the control and operation of the Site. With respect to items (i) through (iii) immediately above, Seller’s rights to, and control of, the Site referenced therein are and will be free and clear of any lien, right, contract, or other encumbrance that could adversely affect Seller’s performance of its obligations under any PPA that Seller may enter into with Georgia Power.

Bidder does solemnly swear or affirm under penalty of perjury, that the information Bidder has provided in this Affidavit is based on Bidder’s own personal knowledge and is true, complete and correct.

[Insert Bidder’s full legal name]

By:_______________________________________

Name: ____________________________________

Title (if applicable): ___________________________

Date: _____________________________________

On this ______ day of _____________________, 2017, before me appeared [Insert Bidder’s full legal name], the person who signed the Site Control Affidavit in my presence and who swore or affirmed that he/she understood the document and freely declared it to be truthful.

_________________________________________

Official Signature of the Notary

State of ________ County of __________________

Official Seal of the Notary

ATTACHMENT J

CERTIFICATION OF WHETHER THE POWER PURCHASE AGREEMENT

WILL REQUIRE DECONSOLIDATION BY BIDDER

WITH RESPECT TO VARIABLE INTEREST ENTITY

PROPOSAL – ____________________.

The undersigned individual, being the Chief Financial Officer of Bidder and having responsibilities for financial accounting matters associated with the Power Purchase Agreement (“PPA”) that Bidder would enter with Georgia Power if Bidder is a winning bidder under the RFP, hereby certifies that the Proposal WILL (_____)/WILL NOT (_____) require Bidder, based on U.S. Generally Accepting Accounting Principles in effect as of the date of this certificate, to deconsolidate on its books and records any assets, liabilities, cash flow, profits or losses of Bidder as a result of the Georgia Power being determined to be the Primary Beneficiary. My determination of the most likely accounting treatment of this transaction results from my personal consideration after necessary discussions with relevant officers of Accounting Standards Codification (“ASC”) Topic 810, Consolidation, and the following factual matters:

- Bidder’s accounting policies, procedures, and internal controls are sufficient to provide Georgia Power with an appropriate basis for confirming the information contained herein.

________Yes

________No (please explain)

Explain:_________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

- Bidder qualifies for one of the scope exceptions listed in paragraphs 810-10-15-12 and 810-10-15-17 of ASC Topic 810.  Please explain.

________Yes

________No

Explain:_________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

- Bidder is financed with equity equal to or greater than ten percent (10%) of Bidder’s total assets per paragraphs 810-10-25-45 to 47 of ASC Topic 810.

_______ Yes

________No

- The Proposal revenues correlate with fluctuations in Bidder’s operating cash flows (operating expenses).  Please explain.

_______ Yes

________No

Explain:_________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

- The Proposal reduces variability in the fair value of Bidder’s assets, for example by absorbing fuel or electricity price risk.  Please explain.

_______ Yes

_______ No

Explain:_________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

- The Proposal term is for greater than 50% of the remaining economic life of the unit.

________ Yes

________No

- The Proposal is for substantially all of the proposed Facility’s productive output.

________Yes

________ No

- Georgia Power and/or its affiliates participated significantly in the design or redesign of the Facility.

________Yes

________ No

- The percentage that the Facility’s fair value represents, of the fair value of the proposed Bidder’s total assets, is approximately;

_______%

- The Facility is essentially the only source of payment for specified liabilities or specified other interest (there is specific debt associated with the Facility).

________Yes

________ No

Capitalized words used without definition here have the meaning shown in the RFP.

Bidder understands that Georgia Power (i) will rely upon this certification in the evaluation of this bid proposal; (ii) may require bidder to submit additional documentation supporting this certification; and (iii) reserves the right to reevaluate or disqualify bidder’s proposal if Georgia Power determines that the PPA transaction will most likely be a Variable Interest Entity.

Confirmation

The above information (and any attachment) agrees with bidder’s records as of the date hereof.

By:		______________________________

Title:		______________________________

Company:	______________________________

Date:		______________________________

ATTACHMENT K

CERTIFICATION AS TO CERTAIN FACTUAL STATEMENTS RELATED TO THE PROPOSED TRANSACTION WITH RESPECT TO CAPITAL LEASE TREATMENT

(The requirements herein are also applied to any proposal that qualifies as a finance lease under new lease accounting guidance, Accounting Standard Codification (“ASC”) Topic 842, Leases, which is effective January 1, 2019, and replaces the term “capital lease” under ASC Topic 840, Leases with the term “finance lease.”)

REDI PROPOSAL--_________________________________

The undersigned individual, being the Chief Financial Officer of ________________ and [having responsibilities/based on information I have received from individuals responsible] for financial accounting matters arising from the potential execution of a Power Purchase Agreement resulting from the acceptance of this proposal by Georgia Power, based on my personal consideration after necessary discussions with relevant officers of factual matters hereby certifies the following based on my understanding of ASC Topic 840, Leases and ASC Topic 842, Leases.

- The Proposal DOES (_____)/DOES NOT (_____) contain a purchase option that is reasonably certain to be exercised as described in paragraph 840-10-25-1(b) of ASC Topic 840 and paragraph 842-10-25-2(b) of ASC Topic 842.

- The Proposal DOES (_____)/DOES NOT (_____) anticipate potential transfer ownership of the Facility at or by the end of the proposed PPA term.

- The proposed PPA term IS (______)/IS NOT (_____) equal to the major part or 75% or more of the estimated remaining economic life of the Facility offered as described in paragraph 840-10-25-1(c) of ASC Topic 840 and paragraph 840-10-25-2(c) of ASC Topic 842.

- The present value of the minimum PPA payments at the beginning of the proposed PPA term (excluding executory costs) IS (______)/IS NOT (_____) greater than or equal to substantially all or ninety percent (90%) of the fair value of the Facility offered as described in paragraph 840-10-25-1(d) of ASC Topic 840 and paragraph 842-10-25-2(d) of ASC Topic 842.

- The Facility IS (______)/IS NOT(______) of such a specialized nature that it is expected to have no alternative use to the lessor at the end of the proposed PPA term as described in paragraph 842-10-25-2(e) of ASC Topic 842.

If I have responded in the affirmative to one or more of the above factual statements, I have attached a good faith statement of the dollar amounts that Georgia Power would be required to capitalize and the residual value of the Facility at the end of the Term.

Capitalized words used without definition here have the meaning shown in the RFP.

Bidder understands that Georgia Power (i) will rely upon this certification in the evaluation of this bid proposal; (ii) may require bidder to submit additional documentation supporting this certification; and (iii) reserves the right to reevaluate or disqualify the bidder’s proposal if Georgia Power determines that the PPA transaction will most likely be a Capital Lease.

Confirmation

The above information (and any attachment) agrees with bidder’s records as of the date hereof.

By: 		______________________________________

Title:		______________________________________

Company:	______________________________________

Date:		______________________________________

A winning bidder can execute an Engineering and Procurement Agreement (E&P) to assume cost responsibility and allow pre-construction activities, such as engineering work and procurement of long lead-time materials, to commence prior to signing an Interconnection Agreement. To enter an E&P agreement, the bidder must have completed the System Impact Study process and be in the Facility Study stage of the Interconnection Study process.

This evaluation does not include Transmission System modifications, if any, required to deliver the Energy to a Southern Transmission Interface.

Georgia Power notes that the pro forma PPA contemplates a greenfield Facility proposed by a non-Creditworthy Seller.

If the bidder’s business structure does not designate an officer with this or a similar title, the bidder must provide written documentation affirming the authority of the individual who attests to this certification.

If Bidder’s business structure does not designate an officer with this or a similar title, Bidder must provide written documentation affirming the authority of the individual who attests to this certification.

If Seller’s business structure does not designate an officer with this or a similar title, Seller must provide written documentation affirming the authority of the individual who attests to this certification.