Georgia Power Company’s

Quarterly Military Solar Report

Through March 31, 2017

This report is provided in accordance with the Georgia Public Service Commission’s (“Commission”) request for quarterly update reports regarding the military solar projects approved by the Commission in Docket Nos. 24505 and 39028.

Executive Summary

Pursuant to the Commission’s orders in Docket Nos. 24505 and 39028, Georgia Power Company (the “Company”) has commenced design, procurement and construction of the military solar projects specified in the table below.  These projects will provide an economical supply of electric power for the Company’s customers, while also contributing towards the military’s mandates regarding renewable energy and energy security and providing a significant investment in Georgia military bases.

| Project | Project Size | Projected Commercial Operation Date | Vendor |
| --- | --- | --- | --- |
| Fort Benning | 30 MW AC | 12/31/2015 (actual) | AMEC |
| Fort Gordon | 30 MW AC | 10/4/2016 (actual) | PowerSecure |
| Fort Stewart | 30 MW AC | 10/4/2016 (actual) | PowerSecure |
| Naval Submarine Base Kings Bay | 30 MW AC | 12/1/2016 (actual) | AMEC |
| Marine Corps Logistics Base (MCLB) Albany | 31 MW AC | 6/30/2017 | AMEC |

Project Activity through March 31, 2017

Expenditures on the projects through March 31, 2017 total $REDACTED. The following is a summary of work performed on each project through March 31, 2017:

Fort Benning

The Fort Benning Solar Facility’s commercial operation date was December 31, 2015.  Ribbon cutting took place on June 1, 2016.  Final site stabilization is expected to be completed in Q2 2017.

Fort Gordon

The Fort Gordon Solar Facility declared commercial operation on October 4, 2016.  Ribbon cutting took place on November 16, 2016. Final site stabilization is expected to be completed in Q2 2017.

Fort Stewart

The Fort Gordon Solar Facility declared commercial operation on October 4, 2016.  Ribbon cutting took place on December 9, 2016. Final site stabilization is expected to be completed in Q2 2017.

Naval Submarine Base Kings Bay

The Kings Bay Solar Facility declared commercial operation on December 1, 2016.  Ribbon cutting took place on September 19, 2016. Final site stabilization is expected to be completed in Q2 2017.

MCLB Albany

The Marine Corps Logistics Base Albany project is ready for grid synchronization, except the areas damaged in the January 22, 2017 tornado.  Back feed power was completed in January 2017.  COD for the entire project is targeted for June 2017, but is dependent upon completion of tornado restoration activities.

Projected Spending Curve as of March 31, 2017

A projected spending curve by quarter for the Company’s military solar project portfolio is shown below, along with expenditures to date.  The variance is primarily due to a shift in timing of certain expenditures, delay in contractor mobilization for the MCLB Albany project and timeline for expected tornado restoration.

Total Projected Spending Curve by Month (millions)

|  |  | Cumulative | Cumulative | Cumulative |
| --- | --- | --- | --- | --- |
|  | Projected | Projected | Actual | Variance |
|  | Spend | Spend | Expenditures | To Date |
| Through Q4 – 2014 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – January 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – February 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – March 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – April 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – May 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – June 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – July 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – August 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – September 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – October 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – November 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – December 2015 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – January 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – February 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – March 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – April 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – May 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q2 – June 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – July 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – August 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q3 – September 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – October 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – November 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q4 – December 2016 | $REDACTED | $REDACTED | $REDACTED | $REDACTED |
| Q1 – January 2017 |  | $REDACTED | $REDACTED | $REDACTED |
| Q1 – February 2017 |  | $REDACTED | $REDACTED | $REDACTED |
| Q1 – March 2017 |  | $REDACTED | $REDACTED | $REDACTED |

Marine Corps Logistics Base

Figure 1 Tornado Damage

Figure 2 Tornado Damage

Figure 3 Tornado Damage

Figure 4 Pond G on East Side of Johnson gate (March 2017)

Figure 5  Installation of new racking (March 2017)

Figure 6 New piles being driven (March 2017)