High Level Summary of Environmental Activities to Support the Vogtle 3&4 Project

Scenario #1: Cancelation of the Vogtle 3&4 Project (Minimal Environmental activities to secure the site)

Scenario #2: Completion of Vogtle Unit 3 & Cancellation of Vogtle Unit 4

Scenario #1 Summary

This summary is based on the assumption that the Vogtle Units 3&4 project would be cancelled and the project site secured (primarily be abandoning in place existing structures) in a manner to remove environmental hazards, stabilize/restore the disturbed areas within the construction footprint and place all applicable permits in a manner that removes/minimizes the company’s environmental risk. The applicable environmental permits that will no longer be needed will be cancelled or revised to address the cancellation of the project. This summary does not consider a delay in the project, but would represent a “worst case scenario” for planning purposes.  The majority of the permits will likely be maintained until the next renewal cycle to allow time for confirming the project future. Negotiations with the regulatory agencies will be warranted to negotiate maintaining the permits until the next renewal cycle and if successful, will minimize the company’s risk, while providing the greatest flexibility until the projects future is confirmed. The following table includes the environmental aspects of the project that would need to be addressed for project cancellation and includes an estimated cost, based on limited available information. This effort is estimated to take approximately 6-9 aggressive months to complete and is season dependent. The long lead program is site stabilization associated with the Construction Storm water - General Permit No. GAR100001 (19 Active NOIs).

Scenario #2 Summary

This summary is based on the assumption that Vogtle Unit 3 will be completed, Vogtle Unit 4 cancelled and the site environmental activities completed (abandon Unit 4 existing structures in place) in a manner to remove environmental hazards, stabilize/restore the disturbed areas and place all applicable permits in a manner that removes/minimizes the company’s environmental risk. The applicable environmental permits that will no longer be needed will be cancelled or revised to address the subject scenario. This summary does not consider a delay in completion of Unit 3, but in many cases, represents a “worst case scenario” for planning purposes.  The majority of the permits will likely be maintained as is until the next renewal cycle. Negotiations with the regulatory agencies will be warranted to negotiate maintaining the permits until the next renewal cycle and if successful, will minimize the company’s risk, while providing the greatest flexibility through completion of Unit 3. The following table includes the environmental aspects of the project that would need to be addressed and includes an estimated cost, based on limited available information. This effort is estimated to take approximately 25 aggressive months to complete and is season dependent. The long lead program is completing Unit 3 construction and site stabilization associated with the Construction Storm water - General Permit No. GAR100001 (19 Active NOIs).

| Summary of General Env Responsibilities/Permit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Scenario 1: Cancel the project (minimum environmental activities to secure the site & is based on abandon permanent structures in place) |  |  |  |  |  | Scenario 2: Complete Unit 3 and Cancel Unit 4 (abandon Unit 4 permanent structures in place) |  |  |  |  |  |  |  |
|  | CANCEL | REVISE | Estimated Cost | COMMENTS |  |  | CANCEL | REVISE | Estimated Cost | COMMENTS |  |  |  |  |
|  | Oversight, Support, Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organizational Staffing |  |  |  |  |  |  |  |  | $2,250,000 | Implementation Environmental program management |  |  |  |  |
| Subcontractor Support |  |  |  |  |  |  |  |  | $3,000,000 | SPCC, Hazardous Waste, Construction Storm water, Spill response through unit 3 construction. |  |  |  |  |
|  | Air Program Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WECTEC Construction Air Permit (SIP) 1629-033-0039-S-02-0 | X |  |  | Remove VEGP 3&4 permitted construction air equipment. |  |  | X |  | $6,000 | Cancel at end of Unit 3 construction. |  |  |  |  |
| SNC Title V Permit - 4911-033-0030V-03-0 (and 03-1) |  | X |  | Remove VEGP 3&4 permitted air equipment. |  |  |  | X |  | Remove Unit 4 equipment |  |  |  |  |
|  | Water Program Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Batch Plant NPDES Process Wastewater Discharge Permit - GA0039276 | X |  | $10,000 | - Clean solids out, process wash water, prevent water accumulation and remove features to prevent discharge opportunities. - Remove Anhydrous Ammonia from the system. |  |  | X |  | $10,000 | - At the end of Unit 3 Construction clean solids out, process wash water, prevent water accumulation and remove features to prevent discharge opportunities. - Remove Anhydrous Ammonia from the system. |  |  |  |  |
| Surface Water Withdrawal Permit - 017-0191-11 |  |  |  | - Evaluate canceling permit at the next renewal cycle. - Negotiate permit obligations associated with 316(b) and temperature validation study. |  |  |  | X |  | Revise permit to only include Unit 3. |  |  |  |  |
| Groundwater Withdrawal Permit - 017-0003 (MU3 & MU4) |  |  |  | - Convert to backup water supply for Vogtle 1&2 and maintain compliance obligations. - If the wells are not used, they would require abandoning with an estimated cost of $250,000-$500,000. |  |  |  |  |  | Keep as is. |  |  |  |  |
| Construction Dewatering Withdrawal Permit - 017-0006 | X |  | $150,000 | Abandon Wells in accordance with Well Abandonment regulation. |  |  | X |  | O&M: $ Abandon wells: $150,000 | - Maintain dewatering system through River Water Intake system construction, O&M cost by others. - Abandon Wells in accordance with Well Abandonment regulation. |  |  |  |  |
| Potable Water Permit - PG0330056 - V 3&4 | X |  |  | - Abandon & make system inoperable - Remove all chemical products. |  |  |  |  |  | Keep as is. |  |  |  |  |
| NPDES Waste Water Discharge Permit GA0039420 (V 3&4) | X |  |  |  |  |  |  | X |  | Revise permit for Unit 3 only. |  |  |  |  |
| Construction Storm water - (General Permit No. GAR100001 (19 Active NOIs)) | X |  | $1,500,000 | Complete permit obligation and submit NOT when site is stabilized. |  |  | X |  | $2,250,000 | Complete permit obligation and submit NOT when site is stabilized. |  |  |  |  |
| Sanitary Sewer Treatment Plant Support |  |  |  | Transfer operation to VEGP 1&2 |  |  |  |  |  | Keep as is. |  |  |  |  |
|  | Pollution Prevention Programs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Noise Control | X |  |  | Ensure records are maintained & Stop |  |  |  |  |  |  |  |  |  |  |
| SPCC/SWPPP | X |  | De minimis | Remove SPCC related materials (oil containing) |  |  |  |  | De minimis | - Manage SPCC/SWPPP plan through Unit 3 construction - Develop & submit Industrial Stormwater NOI. |  |  |  |  |
| Hazardous Waste Management- US EPA ID Number GAR000075085 | X |  | $100,000 | Stop activity and dispose of waste |  |  |  |  | $125,000 | Manage Hazardous Waste Disposal through Unit 3 construction |  |  |  |  |
| Universal Waste Management |  |  | De minimis | Stop activity and dispose of waste |  |  |  |  | $50,000 | Manage Universal Waste through Unit 3 construction |  |  |  |  |
| Petroleum Management |  |  | De minimis | Stop activity and dispose of waste |  |  |  |  | De minimis | Manage Petroleum products through Unit 3 construction |  |  |  |  |
| Solid Waste Management |  |  | $200,000 | Stop activity and dispose of waste |  |  |  |  | $1,550,000 | Manage solid Waste through Unit 3 construction |  |  |  |  |
|  | Critical Environmental Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wetlands Section 404 Permit - SAS-2007-01837-Modification) 9/30/2015 | X |  |  |  |  |  |  |  |  | Keep as is. |  |  |  |  |
| Migratory Birds Treaty Act - Federal Fish and Wildlife Permit #MB745135-1 |  |  |  | Keep, as this permit cover a broader scope and includes GPC. |  |  |  |  |  | Keep, as this permit cover a broader scope and includes GPC. |  |  |  |  |
| Cultural Resources MOU |  |  |  | No Action, ensure site demobilization doesn’t impact Cultural Resource sites or MOU agreement area. |  |  |  |  |  | Ensure MOU obligations are satisfied through Unit 3 construction. |  |  |  |  |
| Federal Aviation Administration (FAA) Notice to Airmen (Obstruction) | X |  |  | For permanent structure currently at height and under an FAA lighting Scheme, we will need to keep the lights on. |  |  |  |  |  |  |  |  |  |  |
| Environmental Protection Plan (EPP) | X |  |  |  |  |  |  | X |  | Revise COL License to only include Unit 3 EPP, manage by Reg Affairs |  |  |  |  |
| Demobilization Due Diligence |  |  |  |  |  |  |  |  | $450,000 | Environmental evaluation, cleanup & remediation. |  |  |  |  |
| Site Restoration |  |  | $200,000 | Restore site as agreed with in the FSEIS (Licensing Commitment) regarding temporary impacts, including Safe Harbor Agreement commitments. |  |  |  |  | $1,200,000 | - Restore the site to support operation of Unit 3. - Restore site as agreed with in the FSEIS regarding temporary impacts, including Safe Harbor Agreement commitments. |  |  |  |  |
| Waste Concrete Area Remediation |  |  | $2,500,000 | Options: - Crush concrete and beneficially reuse aggregate for erosion control - Dispose of in a permitted offsite landfill |  |  |  |  | $2,500,000 | Options: - Crush concrete and beneficially reuse aggregate for erosion control - Dispose of in a permitted offsite landfill |  |  |  |  |