## Liens
Liens | [11 empty] | 1-Invoice Match | 6818753.47
The Liens (and associated Preliminary Notices of Lien Rights) listed below have been filed on the Project (highlighted cells, if any, indicate filings or edits that are new as of this update): | [11 empty] | 2-Vendor Not in AP | 29125381.85
|  |  | 156696749.53 |  |  |  | 6818753.47 | 29125381.85 | 100100116.46 | 26883081.19 | 20652497.75 | 3-No Match | 100100116.46
Doc. No. | Claimant | Date Filed | Amount Claimed | PGH Notes | PGH Code | Vendor AP Total | 1: Invoice Match | 2: Vendor Not in A/P | 3A: No Match (Lien Total) | 3B: No Match (A/P) Total | 4: FEI Liens | 4-Fluor | 20652497.75
1 | Wachs Technical Services, Ltd. | 2017-03-22 | 1878942.49 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 100028 |  |  | 1878942.49 | 100028
2 | Thompson Industrial Svcs., Inc. | 2017-03-22 | 147893.88 | Matches specific invoice in Pre-AP Report | 1 |  | 147893.88
3 | Fluor Enterprises Inc. (Fluor Lien No. 1) | 2017-03-23 | 0 | GPC has reached a payment agreement with FEI | 4 | [5 empty] | 0
6 | Intertech Security, LLC | 2017-03-28 | 183567.9 | Not a vendor in Pre-AP Report | 2 |  |  | 183567.9
7 | Fluor Enterprises Inc. (Fluor Lien No. 2) | 2017-03-28 | 20652497.75 | Not clearly identified from Pre-AP Report | 4 | [5 empty] | 20652497.75
8 | American Equipment Co. (AMECO) | 2017-03-28 | 0 | Not clearly identified from Pre-AP Report (PAID) | 3
10 | C.A. Murren & Sons, Co. Mid-Atlantic, LLC (Lien No. 1) | 2017-03-30 | 3588299 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 208014.07 |  |  | 3588299 | 208014.07
13 | C.A. Murren & Sons, Co. Mid-Atlantic, LLC (Lien No. 2) | 2017-03-30 | 152369.52 | Not clearly identified from Pre-AP Report | 3 | See Doc 10 |  |  | 152369.52
14 | C.A. Murren & Sons, Co. Mid-Atlantic, LLC (Lien No. 3) | 2017-03-30 | 257716.51 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | See Doc 10 |  |  | 257716.51
15 | Morgan Corp. (Lien No. 1) | 2017-03-30 | 3588053.9 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 1811918.03 |  |  | 3588053.9 | 1811918.03
16 | Morgan Corp. (Lien No. 2) | 2017-03-30 | 150000 | Not clearly identified from Pre-AP Report | 3 | See Doc 15 |  |  | 150000
17 | Williams Plant Services, LLC | 2017-03-30 | 1021933.82 | Not clearly identified from Pre-AP Report | 3 | 1147188.91 |  |  | 1021933.82 | 1147188.91
18 | Williams Specialty Services, LLC | 2017-03-30 | 5354155.09 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 1353796.62 |  |  | 5354155.09 | 1353796.62
19 | Specialty Maintenance & Construction, Inc. | 2017-03-31 | 2392898.7 | Vendor not in Pre-AP Report | 2 |  |  | 2392898.7
20 | Commercial Siding & Maintenance | 2017-04-03 | 513265.94 | Equals sum of invoices in Pre-AP Report | 1 |  | 513265.94
21 | A&W Oil & Tire Co. Inc. | 2017-04-04 | 200362.91 | Equals sum of invoices in Pre-AP Report | 1 |  | 200362.91
22 | HSG Constructors LLC (Lien No. 1) | 2017-04-04 | 19594.82 | Equals invoice amount in Pre-AP Report | 1 |  | 19594.82
23 | HSG Constructors LLC (Lien No. 2) | 2017-04-04 | 33093.83 | Not clearly identified from Pre-AP Report | 3 | 146915.22 |  |  | 33093.83 | 146915.22
24 | HSG Constructors LLC (Lien No. 3) | 2017-04-04 | 26164.6 | Equals invoice amount in Pre-AP Report | 1 |  | 26164.6
25 | HSG Constructors LLC (Lien No. 4) | 2017-04-04 | 23345.2 | Equals invoice amount in Pre-AP Report | 1 |  | 23345.2
26 | HSG Constructors LLC (Lien No. 5) | 2017-04-04 | 4339.92 | Equals invoice amount in Pre-AP Report | 1 |  | 4339.92
27 | HSG Constructors LLC (Lien No. 6) | 2017-04-04 | 2979082.1 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | See Doc 23 |  |  | 2979082.1
32 | The Calvert Company, Inc. | 2017-04-07 | 5905283.93 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 30000 |  |  | 5905283.93 | 30000
33 | Cives Steel Co. | 2017-04-07 | 0 |  | 2
34 | Metl-Span | 2017-04-07 | 191232.15 | Not a vendor in Pre-AP Report | 2 |  |  | 191232.15
37 | SteelFab, Inc. | 2017-04-12 | 2581857.18 | Matches specific invoice in Pre-AP Report | 1 |  | 2581857.18
39 | Tindall Corporation | 2017-04-13 | 255460 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 255190 |  |  | 255460 | 255190
40 | Greenberry Industrial, LLC (Greenberry Lien No. 1) | 2017-04-17 | 1638579.7 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 833668.11 |  |  | 1638579.7 | 833668.11
41 | Greenberry Industrial, LLC (Greenberry Lien No. 2) | 2017-04-17 | 1687891.33 | Not a vendor in Post-AP Report | 2 |  |  | 1687891.33
42 | Garney Companies, Inc. | 2017-04-17 | 4065447.91 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 1296642.31 |  |  | 4065447.91 | 1296642.31
43 | RSCC Wire & Cable LLC | 2017-04-17 | 4792628.61 | Not a vendor in Post-AP Report | 2 |  |  | 4792628.61
44 | Thompson Construction Group, Inc. | 2017-04-17 | 8095901 | Not clearly identified from Post-AP Report (lien exceeds invoice total) | 3 | 105724.93 |  |  | 8095901 | 105724.93
46 | Consolidated Pipe & Supply Company, Inc. (Consolidated Pipe Lien No. 1) | 2017-04-19 | 306944 | Equals sum of 2 oldest invoices in Pre-AP Report | 1 |  | 306944
47 | Consolidated Pipe & Supply Company, Inc. (Consolidated Pipe Lien No. 2) | 2017-04-19 | 710.22 | Equals sum of 2 invoices in Pre-AP Report | 1 |  | 710.22
48 | Consolidated Pipe & Supply Company, Inc. (Consolidated Pipe Lien No. 3) | 2017-04-19 | 9108.96 | Not clearly identified from Pre-AP Report | 3 | 542630.57 |  |  | 9108.96 | 542630.57
49 | Consolidated Pipe & Supply Company, Inc. (Consolidated Pipe Lien No. 4) | 2017-04-19 | 134609.4 | Not clearly identified from Pre-AP Report | 3 | See Doc 49 |  |  | 134609.4
50 | Consolidated Pipe & Supply Company, Inc. (Consolidated Pipe Lien No. 5) | 2017-04-19 | 113670 | Equals sum of 2 invoices in Pre-AP Report | 1 |  | 113670
51 | HD Supply Construction Supply Co. Ltd. d/b/a HD Supply Construction & Industrial – White Cap | 2017-04-20 | 90811.03 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 87474.55 |  |  | 90811.03 | 87474.55
52 | Amec Foster Wheeler Environment & Infrastructure, Inc. | 2017-04-21 | 2607176.13 | Equals sum of invoices in Pre-AP Report | 1 |  | 2607176.13
53 | Five Star Products, Inc. | 2017-04-24 | 119375.75 | Not a vendor in Pre-AP Report | 2 |  |  | 119375.75
54 | Carolina Fabricators, Inc. | 2017-04-26 | 82556.5 | Equals sum of invoices in Pre-AP Report | 1 |  | 82556.5
55 | Owen Industries, Inc. d/b/a Paxton & Vierling Steel Co. | 2017-04-26 | 3437737.6 | Not clearly identified from Post-AP Report (lien exceeds invoice total) | 3 | 685533.29 |  |  | 3437737.6 | 685533.29
56 | Delta Termite & Pest Control, Inc. | 2017-04-27 | 54216.4 | Not clearly identified from Pre-AP Report (close to sum of 3/4 invoices) | 3 | 78960.96 |  |  | 54216.4 | 78960.96
57 | Southeastern Engineered Wood Products, Inc. | 2017-04-27 | 62186.73 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 19952.37 |  |  | 62186.73 | 19952.37
58 | Rowell Electric Co., Inc. | 2017-05-02 | 225456.25 | Not a vendor in Post-AP Report | 2 |  |  | 225456.25
59 | Maner Builders Supply Co., LLC (Maner Lien No. 1) | 2017-05-02 | 211244.7 | Not a vendor in Post-AP Report | 2 |  |  | 211244.7
60 | PPG Architectural Finishes, Inc. | 2017-05-02 | 39172.17 | Equals sum of invoices in Pre-AP Report | 1 |  | 39172.17
62 | NNI (Lien No. 1) | 2017-05-04 | 5143942.21 | Not clearly identified from Pre-AP Report | 3 | 6155543.35 |  |  | 5143942.21 | 6155543.35
63 | NNI (Lien No. 2) | 2017-05-04 | 2129128.48 | Not clearly identified from Pre-AP Report | 3 | See Doc 62 |  |  | 2129128.48
64 | Putzmeister America, Inc. | 2017-05-05 | 1132113.74 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 1118472 |  |  | 1132113.74 | 1118472
65 | General Supply & Services, Inc. d/b/a Gexpro | 2017-05-05 | 3286577.04 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 1828261.5 |  |  | 3286577.04 | 1828261.5
66 | Vigor Works LLC f/k/a Oregon Iron Works | 2017-05-08 | 8909031.64 | Not clearly identified from Post-AP Report (lien exceeds invoice total) | 3 | 34964.22 |  |  | 8909031.64 | 34964.22
68 | ABB, Inc. | 2017-05-18 | 2665498.41 | Not a vendor in Pre-AP Report | 2 |  |  | 2665498.41
69 | Ashmore Concrete Pumping LLC | 2017-05-19 | 221460.3 | Not a vendor in Pre-AP Report | 2 |  |  | 221460.3
70 | S&ME, Inc. | 2017-05-19 | 467071.39 | Not a vendor in Post-AP Report | 2 |  |  | 467071.39
71 | CBI Services LLC (f/k/a CBI Services, Inc.) (CBI Lien No. 1) | 2017-05-23 | 13606416 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 5410129.36 |  |  | 13606416 | 5410129.36
72 | CBI Services LLC (f/k/a CBI Services, Inc.) (CBI Lien No. 2) | 2017-05-23 | 3239780 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | See Doc 71 |  |  | 3239780
73 | CBI Services LLC (f/k/a CBI Services, Inc.) (CBI Lien No. 3) | 2017-05-23 | 415683.92 | Not clearly identified from Pre-AP Report | 3 | See Doc 71 |  |  | 415683.92
74 | CBI Services LLC (f/k/a CBI Services, Inc.) (CBI Lien No. 4) | 2017-05-23 | 9653934.2 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | See Doc 71 |  |  | 9653934.2
75 | CBI Services LLC (f/k/a CBI Services, Inc.) (CBI Lien No. 5) | 2017-05-23 | 369706.02 | Not clearly identified from Pre-AP Report | 3 | See Doc 71 |  |  | 369706.02
76 | DuBose National Energy Services | 2017-05-23 | 1392938.68 | Not clearly identified from Pre-AP Report (close to sum of all invoices) | 3 | 1356234.56 |  |  | 1392938.68 | 1356234.56
77 | H-MAC Systems, Inc. | 2017-05-24 | 39923 | Not a vendor in Pre-AP Report | 2 |  |  | 39923
78 | Maner Builders Supply Co., LLC (Maner Lien No. 2) | 2017-05-24 | 1108.58 | Not clearly identified from Pre-AP Report | 3 | 246859.19 |  |  | 1108.58 | 246859.19
79 | Borders States Industries, Inc. d/b/a Shealy Electrical Wholesalers, Inc. | 2017-05-25 | 51950 | Not a vendor in Post-AP Report | 2 |  |  | 51950
80 | Ascendum Machinery, Inc. | 2017-05-25 | 10700 | Matches specific invoice in Pre-AP Report | 1 |  | 10700
81 | Multimetal Products Corporation | 2017-05-26 | 81643.83 | Not a vendor in Pre-AP Report | 2 |  |  | 81643.83
85 | Augusta Industrial Services, Inc. | 2017-05-30 | 1952342.37 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 751097.03 |  |  | 1952342.37 | 751097.03
86 | Eagle Eye Power Solutions LLC | 2017-05-30 | 141000 | Equals sum of invoices in Pre-AP Report | 1 |  | 141000
87 | United Rentals (North America), Inc. | 2017-05-30 | 438594.69 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 347168.44 |  |  | 438594.69 | 347168.44
88 | CB&I Laurens, Inc. (CB&I Laurens Lien No. 1) | 2017-06-01 | 91930.11 | Not clearly identified from Pre-AP Report | 3 | 489462.48 |  |  | 91930.11 | 489462.48
89 | CB&I Laurens, Inc. (CB&I Laurens Lien No. 2) | 2017-06-01 | 974632.67 | Not clearly identified from Pre-AP Report | 3 | See Doc 88 |  |  | 974632.67
90 | CB&I Laurens, Inc. (CB&I Laurens Lien No. 3) | 2017-06-01 | 280603.42 | Not clearly identified from Pre-AP Report | 3 | See Doc 88 |  |  | 280603.42
91 | CB&I Laurens, Inc. (CB&I Laurens Lien No. 4) | 2017-06-01 | 1814095.67 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | See Doc 88 |  |  | 1814095.67
92 | CB&I Laurens, Inc. (CB&I Laurens Lien No. 5) | 2017-06-01 | 173756.71 | Not clearly identified from Pre-AP Report | 3 | See Doc 88 |  |  | 173756.71
93 | CB&I Laurens, Inc. (CB&I Laurens Lien No. 6) | 2017-06-01 | 164764.16 | Not clearly identified from Pre-AP Report | 3 | See Doc 88 |  |  | 164764.16
94 | Barnhart Crane and Rigging, Inc. | 2017-06-02 | 119705 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 7189.23 |  |  | 119705 | 7189.23
95 | Maxim Crane Works LP | 2017-06-06 | 609554.01 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 69128 |  |  | 609554.01 | 69128
96 | Boss Light Tower Rentals LLC and Boss LTG | 2017-06-06 | 500761 | Not clearly identified from Pre-AP Report (lien exceeds invoice total) | 3 | 226422.44 |  |  | 500761 | 226422.44
100 | Cives Steel Co. (Cives Lien No. 2) | 2017-06-08 | 670165.5 | Not a vendor in Post-AP Report | 2 |  |  | 670165.5
102 | Research Cottrell Cooling, Inc. | 2017-06-13 | 13384541.03 | Not a vendor in Post-AP Report | 2 |  |  | 13384541.03
103 | Acuren Inspection, Inc. | 2017-06-13 | 705225.59 | Not clearly identified from Post-AP Report (lien exceeds invoice total) | 3 | 4398.96 |  |  | 705225.59 | 4398.96
104 | Eaton Corporation (Eaton Lien No. 1) | 2017-06-13 | 27846.99 | Not clearly identified from Pre-AP Report | 3 | 134112.49 |  |  | 27846.99 | 134112.49
105 | Eaton Corporation (Eaton Lien No. 2) | 2017-06-13 | 111631.7 | Not clearly identified from Pre-AP Report | 3 | See Doc 104 |  |  | 111631.7
106 | Eaton Corporation (Eaton Lien No. 3) | 2017-06-13 | 27846.99 | Not clearly identified from Pre-AP Report | 3 | See Doc 104 |  |  | 27846.99
107 | Eaton Corporation (Eaton Lien No. 4) | 2017-06-13 | 25940 | Not clearly identified from Pre-AP Report | 3 | See Doc 104 |  |  | 25940
108 | Eaton Corporation (Eaton Lien No. 5) | 2017-06-13 | 47535.95 | Not clearly identified from Pre-AP Report | 3 | See Doc 104 |  |  | 47535.95
110 | Sargent & Lundy, L.L.C. | 2017-06-15 | 1738833 | Not a vendor in Pre-AP Report | 2 |  |  | 1738833