STF-PIA-14-15

Question:

Around 2009, Alabama Power was awarded $6 million in DOE funding for an upgrade of four units at three hydro plants on the Coosa River that was projected to increase generation by 36,087 MWh annually.

- Have these upgrades been fully completed?

- Was the increased generation achieved?

- Has the Company reviewed lessons learned from these projects to apply to its proposed projects? If not, why not.

Response:

- Yes, the upgrades were completed in 2015.

- Yes, Alabama Power Company (“APC”) received and used $6 Million towards the cost of the upgrades. APC achieved improvements in capacity, unit efficiency, and energy resulting in an average per-unit energy increase of 10.9% (much greater than the 7.3 % projected in the grant application).

- The Company has reviewed lessons learned, which are listed below.

Lessons Learned:

- Early engagement with FERC will reduce the possibility of issues coming up late in the upgrade process.

- The design phase and bid evaluation process are crucial to the project’s success.

- Increased oversight and scrutiny of the contractor’s on-site work will help ensure the installation process runs smoothly and according to project plan.