STF-PIA-14-20

Question:

As of October 31, 2020, how much of the engineering/design is completed for Terrora 1 – 2, Tugalo 1 – 4, Bartletts Ferry 1 – 4, Nacoochee 1 -2 and Oliver 1 – 4?

Response:

Please see the table below for the completed engineering/design for each project.

| Project | Month Ending | Percent Earned |
| --- | --- | --- |
| Terrora Phase I (Engineering) | Oct-20 | 82.7% |
| Terrora Phase II (Engineering) | Oct-20 | 47.5% |
| Tugalo (Engineering) | Oct-20 | 7.3% |
| Bartletts (Engineering) | Oct-20 | 7.0% |
| Oliver (Engineering) | Oct-20 | 0.0% |
| Nacoochee (Engineering) | Oct-20 | 0.0% |