STF-PIA-14-21

Question:

Please refer to Bi-Annual Hydro Modernization Report for the period ending June 30, 2020 Plant Tugalo page 2. A scoping kickoff meeting has been completed and detailed design has commenced. The procurement package for new turbines has been issued and an award is expected by year end. Please explain why the procurement package for new turbines has been issued prior to substantial completion of detailed design. Doesn’t this make the Company more exposed to change orders from the turbine manufacturer?

Response:

The final specifications of the turbine will vary based on the successful bidder's turbine design. The Company believes the lowest risk approach is obtaining final turbine specifications before beginning detailed design of the remaining equipment. Final turbine specifications are used to determine the sizing of the generator, generator step up transformer, generator breakers and most of the Balance of Plant equipment. By finalizing the turbine design first, this allows more certainty in the design of all ‘downstream’ components, unit performance and layouts of the other equipment.  Performing the design in this manner lowers the risk of change orders for the whole project.