STF-PIA-14-7

Question:

Please confirm that FERC license amendments are the only permits required for these projects and that the amendments will be requested once preliminary engineering is complete and the unit power output is determined for each unit. For each unit, indicate when the license amendment is expected to be submitted and an estimate of when the request is expected to be approved.

Response:

Yes, the FERC license amendment is the only permit required for these projects. The FERC license amendment incorporates all applicable state and federal permitting requirements. The license amendments will be requested once preliminary engineering is completed for each plant.

Based on the Company’s experience, license amendments are typically approved between six and twelve months after filing with the FERC. For each of the plants approved for modernization, the Company plans to file the license amendments based on the following schedule:

- Terrora - Filed in June of 2020

- Tugalo - Plan to file in 2021

- Bartlett’s - Plan to file in 2021

- Nacoochee - Plan to file in 2021

- Oliver - Plan to file in 2022