STF-PIA-14-8

Question:

For each unit and Balance of Plant work, please provide a description of the modernization project schedules that are currently available.

Response:

One integrated schedule, broken down by unit and major scopes of work for each Plant, is available and is provided in STF-PIA-14-8 Attachment. A Level 3 schedule has only been completed for Terrora at this time, as reflected in the aforementioned Attachment.

We currently have an initial Level 0 schedule for:

- Bartlett’s Units 1-4

- Nacoochee Units 1-2

- Oliver Units 1-4

- Tugalo Units 1-4

*A Level 0 schedule is defined as an initial schedule that includes key milestone dates but lacks a true critical path. Level 0 schedules are refined as vendor schedules are received and incorporated into the integrated schedule.

**A Level 3 schedule includes a greater level of detail and has a defined critical path of the project.