## Arkwright
PUBLIC DISCLOSURE
Arkwright
Table 10. Arkwright Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Arkwright AP-1,2,3,Landfill | Closure by removal and consolidation to permitted landfill | 24.505 | REDACTED
Total |  | 24.505
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 11. Arkwright Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 24504995.04
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of water management (transportation & disposal), groundwater monitoring, front-end planning design and engineering, and third-party permitting support. Activities expected during 2021 include continued water management, groundwater monitoring, and front-end planning.

## Bowen
PUBLIC DISCLOSURE
Bowen
Table 12. Bowen Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Advanced closure in place with liner | 96.6568 | REDACTED
Bowen CCR Landfill | Active landfill / closure in place | 0.00069492
Total |  | 96.6575
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 13. Bowen Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 96657526.8
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of front-end planning and detailed engineering design services, ash pond closure site preparation, dewatering water treatment work, electrical & instrumentation procurements, bid package development, and groundwater monitoring. Activities expected during 2021 include dewatering, groundwater monitoring, permitting, completion of contracted site prep work, and mobilization of the prime ash pond closure contractor.

## Branch
PUBLIC DISCLOSURE
Branch
Table 14. Branch Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-A | Closure by removal to permitted landfill | 1.2711 | REDACTED
AP-B | Closure by removal to permitted landfill | 8.684
AP-C | Closure by removal to permitted landfill | 6.1541
AP-D | Closure by removal to permitted landfill | 4.6745
AP-E | Closure by removal to permitted landfill | 40.1794
Landfill | Closure in place | 0
Total |  | 60.9631
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 15. Branch Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 60963054.57
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of dewatering water treatment, groundwater monitoring, ash pond water management, detailed engineering design & technical services permitting support, plant costs, and construction management. Activities expected during 2021 include construction of the long-term dewatering water treatment system, stormwater diversion system, groundwater monitoring, plant costs, and construction management.

## Hammond
PUBLIC DISCLOSURE
Hammond
Table 16. Hammond Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 6.8016 | REDACTED
AP-2 | Closure by removal to permitted landfill | 13.2025
AP-3 | Advanced closure in place | 24.8759
AP-4 | Closure by removal to permitted landfill | 20.9732
Huffaker Road CCB Facility | Closure in place | 0.26081
Total |  | 66.114
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 17. Hammond Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 66114013.77
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of the excavation of ash from AP-2 to an offsite permitted landfill, permitting, detailed design work, groundwater monitoring, and IPCC costs for AP-3. Activities expected during 2021 include commencing dewatering, groundwater monitoring, mobilization of the prime ash pond closure contractor, and development of bid proposals and associated information in preparation for contracting final closure of AP-1 and AP-2.

## Kraft
PUBLIC DISCLOSURE
Kraft
Table 18. Kraft Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 8.4459 | REDACTED
Grumman Road Landfill | Closure in place | 12.8613
Total |  | 21.3071
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 19. Kraft Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 21307143.54
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of ongoing IPCC monitoring and maintenance costs. Activities expected during 2021 include the continuation of IPCC monitoring and maintenance, additional restoration activities, permitting, and additional groundwater studies.

## McDonough
PUBLIC DISCLOSURE
McDonough
Table 20. McDonough Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Advanced closure in place | 15.729 | REDACTED
AP-2 | Closure by removal | 11.4893
AP-3 | Advanced closure in place | 28.066
AP-4 | Advanced closure in place | 33.1828
Total |  | 88.4672
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 21. McDonough Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 88467223.58
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of prime contractor work for pond closure, dewatering, water treatment, and groundwater monitoring. Activities expected during 2021 include continued prime contractor work, dewatering water treatment, groundwater monitoring, permitting, and detailed engineering design.

## McIntosh
PUBLIC DISCLOSURE
McIntosh
Table 22. McIntosh Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 9.0492 | REDACTED
Landfill 3 | Closure in place | 1.6172
Landfill 4 | Closure in place | 5.3284
Total |  | 15.9948
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 23. McIntosh Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 15994783.73
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of prime contractor work for pond closure, dewatering, water treatment, groundwater monitoring, permitting, and IPCC monitoring and maintenance costs for LF4. These activities are expected to continue through into 2021.

## McManus
PUBLIC DISCLOSURE
McManus
Table 24. McManus Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 99.0562 | REDACTED
Total |  | 99.0562
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 25. McManus Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 99056169.47
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of prime contractor work for physical completion of the pond closure and restoration, ongoing ash pond dewatering and water treatment, and groundwater monitoring and compliance reporting. The prime contractor work was completed and the contractor demobilized July 2020. Activities expected during 2021 include continuation of IPCC which principally includes groundwater compliance monitoring and reporting activities and ongoing water treatment until regulatory approval is received to cease the dewatering/water treatment activities.

## Mitchell
PUBLIC DISCLOSURE
Mitchell
Table 26. Mitchell Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-A | Closure by removal to permitted landfill and beneficial reuse | 1.1926 | REDACTED
AP-1 | Closure by removal to permitted landfill and beneficial reuse | 18.246
AP-2 | Closure by removal to permitted landfill and beneficial reuse | 21.8838
Total |  | 41.3224
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 27. Mitchell Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 41322359.9
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of detailed engineering, site preparation and maintenance, groundwater monitoring, construction of dewatering plant and water management infrastructure, and continued prime contractor work, including excavation and transportation of ash for beneficial use. These activities are expected to continue during 2021.

## Scherer
PUBLIC DISCLOSURE
Scherer
Table 28. Scherer Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Advanced closure in place | 3.7603 | REDACTED
Landfill | Active landfill / closure in place | 0.0013374
Total |  | 3.7617
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 29. Scherer Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED | [5 empty] | 3755921.5955
Program Management | [7 empty] | 1113199.6143
Front End Planning | [7 empty] | 4410.5733
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 3755921.5911
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of front end planning, groundwater monitoring, and permitting. Activities expected during 2021 include permitting, groundwater monitoring, front end planning, and general bid package development.

## Wansley
PUBLIC DISCLOSURE
Wansley
Table 30. Wansley Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Advanced closure in place | 10.5022 | REDACTED
Landfill | Active landfill / closure in place | 0.0015091
Total |  | 10.5037
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 31. Wansley Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 10502641.4966
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of groundwater monitoring and front end planning advancing detail design. Activities expected during 2021 include the continuation of front end planning and ground water monitoring, as well as permitting, bid package development, and early site prep contractor mobilization.

## Yates
PUBLIC DISCLOSURE
Yates
Table 32. Yates Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
AP-1 | Closure by removal | 16.0049 | REDACTED
AP-2 | Closure by removal | 66.1111
AP-3 | Advanced closure in place | 62.4998
AP-A | Closure by removal | 17.0861
AP-B | Closure by removal | 13.5649
AP-B' | Advanced closure in place | 6.2082
Gypsum Landfill | Inactive landfill / closure by removal to permitted landfill and beneficial reuse | 4.1
R6 Landfill | Inactive landfill / closure in place | 26.5
Total |  | 212.0984
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Table 33. Yates Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2020 | 2021 Forecast | 2022 Forecast | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast | Total
Previous Closure Cost |  | REDACTED
Program Management
Front End Planning
Detailed Engineering Costs
Construction
Post Closure Costs
Total | 212098363.17
Retail Cost Estimates
Note: Details may not add to totals due to rounding
Notes:
2020 year-to-date actuals through December of $REDACT consist primarily of closure construction material purchase, dewatering water treatment, construction management, site work/maintenance, and organics waste management. Activities expected during 2021 include the continuation of construction and dewatering activities, IPCC monitoring and maintenance for AP-1 and the gypsum landfill.

## Sheet1 (hidden)
Plant | Exec Code Name | Sum of 2020 Aug-Dec
Yates | 0. Previous Closure or Construction Cost | 0
| 1. Program Management | 1319541.19
| 10. IPCC | 336827.76
| 11. PCC | 0
| 2. Front End Planning | 28966.19
| 3. Detailed Engineering Costs​ | 230451.03
| 4. Procurement (Engineering Procured) | 264423
| 5. Construction Directs​ | 11487227.16
| 6. Construction Indirect Costs | 3996331.31
| 7. Contractor Indirect Costs | 10627764.58
| 8. Project Indirect Costs | -0.6
| 9. Contingency | 7090270.52
Yates Total |  | 35381802.14
Grand Total |  | 35381802.14

## Sheet4 (hidden)
| 2020 | 2021 | 2022 | 2023-2025 Forecast | 2026-2028 Forecast | 2029-2084 Forecast
2019 Rate Case | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Rate Case |  |  |  | 3Q20 |  |  |  | Change |  |  |  | January - July 2020 Actuals
| 2020 | 2021 | 2022 |  | 2020 | 2021 | 2022 |  | 2020 | 2021 | 2022 | Arkwright | 2.0235 | #REF!
Arkwright | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Arkwright | #REF! | #REF! | #REF! | Bowen | 11.9594 | #REF!
Bowen | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Bowen | #REF! | #REF! | #REF! | Branch | 11.2848 | #REF!
Branch | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Branch | #REF! | #REF! | #REF! | Hammond | 8.1142 | #REF!
Hammond | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Hammond | #REF! | #REF! | #REF! | Kraft | 0.24499 | #REF!
Kraft | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Kraft | #REF! | #REF! | #REF! | McDonough | 5.4482 | #REF!
McDonough | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | McDonough | #REF! | #REF! | #REF! | McIntosh | 3.5674 | #REF!
McIntosh | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | McIntosh | #REF! | #REF! | #REF! | McManus | 10.6841 | #REF!
McManus | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | McManus | #REF! | #REF! | #REF! | Mitchell | 11.7672 | #REF!
Mitchell | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Mitchell | #REF! | #REF! | #REF! | Scherer | 1.298 | #REF!
Scherer | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Scherer | #REF! | #REF! | #REF! | Wansley | 1.3256 | #REF!
Wansley | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Wansley | #REF! | #REF! | #REF! | Yates | 25.1633 | #REF!
Yates | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | Yates | #REF! | #REF! | #REF! | Total | 92.8808 | #REF!
| #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
Arkwright
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF! |  | #REF!
3Q20 Forecast | #REF! | #REF! | #REF! |  | #REF!
Bowen
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
Branch
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
Hammond
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
Kraft
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
McDonough
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
McIntosh
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
McManus
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
Mitchell
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
Scherer
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
Wansley
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!
Yates
| 2020 | 2021 | 2022
2019 Rate Case | #REF! | #REF! | #REF!
3Q20 Forecast | #REF! | #REF! | #REF!