## Summary
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2020
Total Project
Actuals ($1,000s)
Year | Period Ending | Terrora | Tugalo | Bartletts Ferry | Nacoochee | Oliver | Total Actuals | Project Forecast*
2019 | 2020-06-30 | 1041.8489 | 0 | 0 | 0 | 0 | 1041.8489 | 260.4158
2019 | 2020-12-31 | 3429.6731 | 0 | 0 | 0 | 0 | 3429.6731 | 1848.093
2020 | 2020-06-30 | 9855.3484 | 628.8861 | 683.1847 | 35.9142 | 434.24 | 11637.5734 | 10687.3078
2020 | 2020-12-31 | 15497.7998 | 5507.5219 | 1733.9284 | 6.4437 | 3.14 | 22748.8339 | 18624.3918
2021 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 8180.7575
2021 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 7693.7221
2022 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 750
2022 | 2020-12-31 |  | 0 | 0 | 0 | 0 | 0 | 0
2023 | 2020-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0
2023 | 2020-12-31 |  | 0 | 0 | 0 | 0 | 0 | 0
2024 | 2020-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0
2024 | 2020-12-31 |  | 0 | 0 | 0 | 0 | 0 | 0
2025 | 2020-06-30 |  | 0 | 0 |  | 0 | 0 | 0
2025 | 2020-12-31 |  | 0 | 0 |  | 0 | 0 | 0
2026 | 2020-06-30 |  |  | 0 |  | 0 | 0 | 0
2026 | 2020-12-31 |  |  | 0 |  | 0 | 0 | 0
2027 | 2020-06-30 |  |  |  |  | 0 | 0 | 0
2027 | 2020-12-31 |  |  |  |  | 0 | 0 | 0
TOTAL |  | 29824.6703 | 6136.408 | 2417.113 | 42.358 | 437.38 | 38857.9293 | 48044.688
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
*Added once Project Forecast estimates are updated and approved. The only project currently that has a forecast is Terrora.
Measured against 2019 IRP Budget - $446,618

## Terrora
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report - December 31, 2020
Plant Terrora
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast)
|  | Turbine | Generator | BOP | Turbine | Generator | BOP
2019 | 2019-06-30 | 0 | 0 | 0 | 594.2607 | 30.8366 | 416.7516 | 1041.8489 | 260.4158 | 300.1%
2019 | 2019-12-31 | 0 | 0 | 0 | 1677.5296 | 302.9649 | 1449.1786 | 3429.6731 | 1848.093 | 85.58%
2020 | 2020-06-30 | 1777.5108 | 0 | 12.4613 | 3948.8911 | 1582.1272 | 2534.358 | 9855.3484 | 10687.3078 | -7.785%
2020 | 2020-12-31 | 972.1517 | 1551.0082 | 802.1557 | 4512.0184 | 2647.9997 | 5012.466 | 15497.7998 | 18624.3918 | -16.79%
2021 | 2020-06-30 | [6 empty] | 0 | 8180.7575
2021 | 2020-12-31 | [6 empty] | 0 | 7693.7221
2022 | 2020-06-30 | [6 empty] | 0 | 750
TOTAL |  | 2749.6626 | 1551.0082 | 814.617 | 10732.6997 | 4563.9284 | 9412.7544 | 29824.6703 | 48044.688 | -37.92%
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved.
Measured against 2019 IRP Budget - $58,160

## Tugalo
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report - December 31, 2020
Plant Tugalo
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Unit 4 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast)
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 623.5072 |  | 5.3789 | [9 empty] | 628.8861 | 0
2020 | 2020-12-31 | 1870.5049 | 54.2629 | 91.121 | 1165.174 |  |  | 1164.9735 |  |  | 1161.4857 |  |  | 5507.5219 | 0
2021 | 2020-06-30 | [12 empty] | 0 | 0
2021 | 2020-12-31 | [12 empty] | 0 | 0
2022 | 2020-06-30 | [12 empty] | 0 | 0
2022 | 2020-12-31 | [12 empty] | 0 | 0
2023 | 2020-06-30 | [12 empty] | 0 | 0
2023 | 2020-12-31 | [12 empty] | 0 | 0
2024 | 2020-06-30 | [12 empty] | 0 | 0
2024 | 2020-12-31 | [12 empty] | 0 | 0
2025 | 2020-06-30 | [12 empty] | 0 | 0
2025 | 2020-12-31 | [12 empty] | 0 | 0
2026 | 2020-06-30
2026 | 2020-12-31
2027 | 2020-06-30
2027 | 2020-12-31
TOTAL |  | 2494.0121 | 54.2629 | 96.4999 | 1165.174 | 0 | 0 | 1164.9735 | 0 | 0 | 1161.4857 | 0 | 0 | 6136.408 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved
Measured against 2019 IRP Budget - $109,736

## Bartletts
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report - December 31, 2020
Bartletts Ferry
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Unit 4 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast)
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 683.1847 | [11 empty] | 683.1847 | 0
2020 | 2020-12-31 | 1733.8484 |  |  | 0.03197 |  |  | 0.02401 |  |  | 0.02401 |  |  | 1733.9284 | 0
2021 | 2020-06-30 | [12 empty] | 0 | 0
2021 | 2020-12-31 | [12 empty] | 0 | 0
2022 | 2020-06-30 | [12 empty] | 0 | 0
2022 | 2020-12-31 | [12 empty] | 0 | 0
2023 | 2020-06-30 | [12 empty] | 0 | 0
2023 | 2020-12-31 | [12 empty] | 0 | 0
2024 | 2020-06-30 | [12 empty] | 0 | 0
2024 | 2020-12-31 | [12 empty] | 0 | 0
2025 | 2020-06-30 | [12 empty] | 0 | 0
2025 | 2020-12-31 | [12 empty] | 0 | 0
2026 | 2020-06-30 | [12 empty] | 0 | 0
2026 | 2020-12-31 | [12 empty] | 0 | 0
2027 | 2020-06-30
2027 | 2020-12-31
TOTAL |  | 2417.033 | 0 | 0 | 0.03197 | 0 | 0 | 0.02401 | 0 | 0 | 0.02401 | 0 | 0 | 2417.113 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved
Measured against 2019 IRP Budget - $114,763

## Nacoochee
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report - December 31, 2020
Plant Nacoochee
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast)
|  | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 |  |  |  | 33.8242 |  | 2.09 | 35.9142 | 0
2020 | 2020-12-31 |  |  |  | 6.4437 |  |  | 6.4437 | 0
2021 | 2020-06-30 | [6 empty] | 0 | 0
2021 | 2020-12-31 | [6 empty] | 0 | 0
2022 | 2020-06-30 | [6 empty] | 0 | 0
2022 | 2020-12-31 | [6 empty] | 0 | 0
2023 | 2020-06-30 | [6 empty] | 0 | 0
2023 | 2020-12-31 | [6 empty] | 0 | 0
2024 | 2020-06-30 | [6 empty] | 0 | 0
2024 | 2020-12-31 | [6 empty] | 0 | 0
2025 | 2020-06-30 | [6 empty] | 0 | 0
2025 | 2020-12-31 | [6 empty] | 0 | 0
2026 | 2020-06-30
2026 | 2020-12-31
2027 | 2020-06-30
2027 | 2020-12-31
TOTAL |  | 0 | 0 | 0 | 40.268 | 0 | 2.09 | 42.358 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved
2019 IRP Budget - $44,117

## Oliver
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report - December 31, 2020
Plant Oliver
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Unit 4 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast)
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 434.24 | [11 empty] | 434.24 | 0
2020 | 2020-12-31 | 3.14 | [11 empty] | 3.14 | 0
2021 | 2020-06-30 | [12 empty] | 0 | 0
2021 | 2020-12-31 | [12 empty] | 0 | 0
2022 | 2020-06-30 | [12 empty] | 0 | 0
2022 | 2020-12-31 | [12 empty] | 0 | 0
2023 | 2020-06-30 | [12 empty] | 0 | 0
2023 | 2020-12-31 | [12 empty] | 0 | 0
2024 | 2020-06-30 | [12 empty] | 0 | 0
2024 | 2020-12-31 | [12 empty] | 0 | 0
2025 | 2020-06-30 | [12 empty] | 0 | 0
2025 | 2020-12-31 | [12 empty] | 0 | 0
2026 | 2020-06-30 | [12 empty] | 0 | 0
2026 | 2020-12-31 | [12 empty] | 0 | 0
2027 | 2020-06-30 | [12 empty] | 0 | 0
2027 | 2020-12-31 | [12 empty] | 0 | 0
TOTAL |  | 437.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437.38 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved
Measured against 2019 IRP Budget - $119,842

## Major Contracts
PUBLIC DISCLOSURE
Major Contracts
Project Monitoring Report - December 31, 2020
Major Contracts | Type | PO 1 | Estimated Amount (1000$)2 | Initial Contract Amount (1000$) | Current Contract Amount (1000$)3 | % Variance4 | Notes
Terrora
Turbine | Supply, remove and install | GPC10980282 | REDACTED | REDACTED | REDACTED | REDACTED | A, B
Generator | Supply, remove and install | GPC65084-0001 | REDACTED | REDACTED | REDACTED | REDACTED | A, C
General Contractor | Install | GPC65147-0001 | REDACTED | REDACTED | REDACTED | REDACTED | A, D
Trash Racks | Supply, remove and install | GPC67622-0001 | REDACTED | REDACTED | REDACTED | REDACTED | A
Governor HPU Skids | Supply | GPC10982009 | REDACTED | REDACTED | REDACTED | REDACTED | A
Station Service Transformers | Supply | GPC10977336 | REDACTED | REDACTED | REDACTED | REDACTED | A
Switchgear | Supply | GPC11053203 | REDACTED | REDACTED | REDACTED | REDACTED | A
Lube Oil Skids | Supply | GPC10982036 | REDACTED | REDACTED | REDACTED | REDACTED | A, E
Batteries | Supply | GPC11020730 | REDACTED | REDACTED | REDACTED | REDACTED | A
Generator Step Up Transformer | N/A | N/A | N/A | N/A | N/A | N/A
DCS | Supply | GPC10990070 | REDACTED | REDACTED | REDACTED | REDACTED | A, F
Totals |  |  | 16246.3524 | 17025.7851 | 20428.3321 | 25.74%
Tugalo
Turbine | Supply, remove and install
Generator | Supply, remove and install
General Contractor | Install
Trash Racks | Supply, remove and install
Governor HPU Skids | Supply
Station Service Transformers | Supply
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer | N/A
DCS | Supply
Spillway Gates
Sums and percentages may not add due to rounding.
Bartletts Ferry 1-4
Turbine | Supply and install
Generator | Supply and install
General Contractor | Install
Trash Racks | Supply and install
Governor HPU Skids | Supply
Station Service Transformers | Supply
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer | N/A
DCS | Supply
Spillway Gate Hoists | Supply and install
Headgates | Supply
Sums and percentages may not add due to rounding.
Nacoochee
Turbine | Supply and install
Generator | Supply and install
General Contractor | Install
Trash Racks | Supply and install
Governor HPU Skids | Supply
Station Service Transformers | Supply
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer | N/A
DCS | Supply
Sums and percentages may not add due to rounding.
Oliver
Turbine | Supply and install
Generator | Supply and install
General Contractor | Install
Trash Racks | Supply and install
Governor HPU Skids | Supply
Station Service Transformers | Supply
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer | N/A
DCS | Supply
Spillway Gate Hoists | Supply
Depressing Air Compressor | Supply
Headgates | Supply
Sums and percentages may not add due to rounding.
1 PO's included when contract value exceeds $100k following award of contract and issuance of PO.
2 Estimated amount from Project Estimate
3 This reflects change orders to the contract/purchase order
4 From Initial Amount to Current Amount
Notes on Variances
A | Variances between the Estimated Amount and the Initial Contract Amount are the result of the differences between the screening level Estimated Amount compared to the actual contract that was procured and is reflected as the Initial Contract Amount.
B | Additional work related to rehabilitation and replacement of components not included in base scope.
C | Additional rotor stability frame due to safety concerns. Additional cleaning and handling of the generator rotor.
D | Documents issued for bid vs documents issued for construction.
E | Additional valve, differential pressure transmitters, and lifting frame modification.
F | Power and water cybersecurity suite equipment, operation station, and additional start up support.

## Change Orders
PUBLIC DISCLOSURE
Project Change Orders
Project Monitoring Report - December 31, 2020
Material Change Orders (>$100k)
Terrora
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
2020-01-30 | Controls | REDACTED | 2020-05-13
2020-01-30 | Penstock manholes/platforms, turb/gen platform, air reciever tank, control room access | REDACTED | 2020-05-13
2020-05-14 | Unit 1/2 Turbine Increases. | REDACTED | 2020-05-14
2020-05-14 | Night Shift Coordinator | REDACTED | 2020-05-18
2020-06-23 | Terrora Isolation Valves | REDACTED | 2020-07-23
2020-10-19 | Terrora Overhead Crane uprate | REDACTED | 2020-10-19
2020-11-10 | Equipment and Startup support | REDACTED | 2020-11-24
2020-11-24 | Operations Procedures | REDACTED | 2020-11-24
| 15 Other Change Orders (<$100k) | 497 | Multiple
| Total | 5246.8879
Tugalo
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested | Date Approved
Nacoochee
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested | Date Approved
Bartletts Ferry
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested | Date Approved
Oliver
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested | Date Approved

## Procurement
PUBLIC DISCLOSURE
Procurement Status of Significant Components -- All Received
Project Monitoring Report - December 31, 2020
Total Project Estimate | Unit | Purchase Order Date | Required Delivery Date | Scheduled Delivery Date
Terrora
Turbine | 1&2 | 2019-08-20 | 2020-09-28 | Actual 9/28/2020
Generator | 1&2 | 2019-11-25 | 2020-07-20 | Actual 7/20/2020
General Contractor | 2 | 2020-02-28 | Actual 3/19/2019 | Actual 3/19/2020
General Contractor | 1
Trash Racks | 1&2 | 2020-07-24 | 2020-10-30 | Actual 9/1/2020
Governor HPU Skids | 1&2 | 2019-08-27 | 2020-04-15 | Actual 8/12/2020
Station Service Transformers | 1&2 | 2019-08-09 | 2020-01-15 | Actual 4/10/2020
Switchgear | 1&2 | 2020-05-20 | 2020-11-02 | Actual 3/30/2020
Lube Oil Skids | 1&2 | 2019-08-27 | 2020-02-28 | Actual 7/21/2020
Batteries | 1&2 | 2020-01-16 | 2020-06-01 | Actual 7/6/2020
Generator Step Up Transformer
DCS | 1&2 | 2019-09-25 | 2020-03-31 | Actual 7/21/2020
Required Delivery Date reflects contractual requirement for vendor, but not delivery date required to meet commercial operation.