## Table 1.1a (Trend)
Table 1.1a (Trend)
Vogtle 3&4 Project
Georgia Power Company Cost Forecast - Subject to Commission Verification and Approval
Through Period Ending December 31, 2016
|  |  | Certified | Jun 2009 | Dec 2009 | Jun 2010 | Dec 2010 | Jun 2011 | Dec 2011 | Jun 2012 | Dec 2012 | Dec 2013 | Jun 2014 | Dec 2014 | Jun 2015 | Dec 2015 | Jun 2016 | Dec 2016
|  |  | Cost | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
|  |  | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions)
Construction & Capital Cost
EPC Base
| Fixed Semi Annual Escalation |  | 1978 | 1978 | 1976 | 1976 | 1976 | 1976.446 | 1976 | 1976 | 1976 | 1976 | 1976 | 1976 | 1976 | 1976 | 1418 | 1418
| Indexed Escalation |  | 468 | 468 | 470 | 470 | 470 | 470.188 | 470 | 470 | 470 | 470 | 470 | 470 | 470 | 470 | 470 | 470
| Other Fixed Escalation |  | 670 | 670 | 674 | 674 | 674 | 673.921 | 674 | 674 | 674 | 674 | 674 | 674 | 674 | 674 | 668 | 668
| Fully Escalated | [15 empty] | 746 | 746
Total EPC Base |  |  | 3116 | 3116 | 3121 | 3121 | 3121 | 3120.555 | 3121 | 3121 | 3121 | 3121 | 3121 | 3121 | 3121 | 3121 | 3302 | 3302
EPC Escalation
| Fixed Semi Annual Escalation |  | 431 | 431 | 336 | 336 | 337 | 343.848 | 343 | 353 | 355 | 355 | 355 | 355 | 355 | 355 | 176 | 176
| Indexed Escalation |  | 142 | 142 | 142 | 142 | 142 | 119.193 | 118 | 120 | 117 | 117 | 117 | 117 | 117 | 117 | 116 | 116
| Other Fixed Escalation |  | 108 | 108 | 109 | 109 | 109 | 110.018 | 110 | 111 | 110 | 110 | 110 | 110 | 110 | 110 | 109 | 110
Total EPC Escalation |  |  | 681 | 681 | 586 | 587 | 589 | 573.06 | 572 | 585 | 582 | 582 | 582 | 582 | 582 | 582 | 400 | 401
Quality Assurance, Compliance and Operations & EPC Scope Change |  |  | 507 | 507 | 576 | 589 | 582 | 675.225 | 675 | 727 | 930 | 930 | 930 | 1094 | 1094 | 1489 | 1493 | 1507
Ad Valorem & Other Fees |  |  | 111 | 111 | 111 | 111 | 111 | 110.51 | 111 | 125 | 159 | 159 | 159 | 241 | 241 | 241 | 236 | 221
Test Fuel Offsets |  |  | -34 | -34 | -34 | -34 | -34 | -59.616 | -60 | -60 | -49 | -49 | -49 | -49 | -49 | -49 | -49 | -49
Transmission Interconnection |  |  | 37 | 37 | 37 | 40 | 40 | 40.306 | 40 | 41 | 56 | 56 | 56 | 56 | 56 | 56 | 58 | 58
|  |  |  | 621 | 689 | 706 | 699 | 766 | 766 | 833 | 1096 | 1096 | 1096 | 1342 | 1342 | 1737 | 1738 | 1737
| Subtotal |  | 621 | 4418 | 4395 | 4414 | 4408 | 4460.039 | 4459 | 4539 | 4799 | 4799 | 4799 | 5045 | 5045 | 5440 | 5440 | 5440
Contingency |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Construction & Capital Cost |  | 4418 | 4418 | 4395 | 4414 | 4408 | 4460.039 | 4459 | 4539 | 4799 | 4799 | 4799 | 5045 | 5045 | 5440 | 5440 | 5440
Other Capital Cost
Certification & Independent Evaluator Fees |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Construction Monitor |  |  | 0 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6
| Total Other Capital Cost |  | 0 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8
Vogtle 3&4 Facility
Georgia Power Company Financing Cost Forecast - Recovered Pursuant to O.C.G.A. 46-2-25 (c.1)
Project To Date
Through Period Ending December 31, 2016
|  |  | Estimated at | Jun 2009 | Dec 2009 | Jun 2010 | Dec 2010 | Jun 2011 | Dec 2011 | Jun 2012 | Dec 2012 | Dec 2013 | Jun 2014 | Dec 2014 | Jun 2015 | Dec 2015 | Jun 2016 | Dec 2016
|  |  | Certification | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
|  |  | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions) | ($ millions)
Project Schedule Financing
Return on CWIP in Rate Base |  |  | 1545 | 1507 | 1505 | 1546 | 1553 | 1524.2514 | 1516.1059 | 1551.9631 | 1941.7215 | 1826 | 1774 | 2296.9925 | 2243.3869 | 2226.8613 | 2212.1256 | 2111
AFUDC - Accrued on CWIP Above Original Certified Cost |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 22 | 67 | 55 | 102 | 100.0436 | 85
AFUDC - Accrued through Dec 2010 |  |  | 111 | 97 | 99 | 99 | 91 | 91 | 91 | 91.2706 | 91.2706 | 91.2706 | 91 | 91.2706 | 91.2706 | 91.2706 | 91.2706 | 91
Return on Unamortized AFUDC Balance |  |  | 39 | 32 | 33 | 33 | 31.2 | 19.3977 | 19.2178 | 18.3884 | 18.2139 | 18.1881 | 18 | 18.1538 | 18.1538 | 18.1635 | 18.1635 | 18
| Total Project Schedule Financing |  | 1695 | 1636 | 1637 | 1678 | 1675.2 | 1634.649 | 1626.3237 | 1661.6221 | 2051.206 | 1960 | 1905 | 2473.4169 | 2407.8113 | 2438.2953 | 2421.6033 | 2305
| Total Remaining Financing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263 | 1717.574 | 1541.8155 | 1541.8155
| Total Capital Cost and Financing |  | 6113 | 6054 | 6032 | 6092 | 6083.2 | 6094.688 | 6085.3237 | 6200.6221 | 6850.206 | 6759 | 6704 | 7518.4169 | 7452.8113 | 7878.2953 | 7861.6033 | 7745
| Notes: | No reforecast was filed in June 2013.
Details may not add to totals due to rounding.
* The Total Current Forecast for Return on CWIP in Rate Base includes $102 million of AFUDC accrued on CWIP above the original certified cost.

## Table 1.1a (Trend)2
Table 1.1 (Trend)
Vogtle 3&4 Project
Georgia Power Company Cost - Subject to Commission Verification and Approval
Total Project Costs
Through Period Ending December 31, 2020
[5 empty] | Certified | Jun 2017 | Dec 2017 | June 2018 |  | June 2019 |  | December 2019 | June 2020 | Decmeber 2020
[5 empty] | Cost | Forecast | Forecast | Forecast |  | Forecast |  | Forecast | Forecast | Forecast
[5 empty] | ($ millions) | ($ millions) | ($ millions) | ($ millions) |  | ($ millions) |  | ($ millions) | ($ millions) | ($ millions)
Construction & Capital Cost
[11 empty] | C | D | B=C-D |  |  | A-B
|  | EPC Base | [8 empty] | Table 1.1- VCM 16 | Spend to Date | Remaining | Total 1.1- VCM 17 | Total Change from VCM 16 | Total Increase
|  |  | Fixed Semi Annual Escalation |  | 1978 | 1418 |  |  | #REF! |  | #REF! | #REF! | #REF! | 7077.245 | #REF! | #REF! | Had 428M remaining to spend and added 3,374… now you have net $2,946 left to spend
|  |  | Indexed Escalation |  | 468 | 470 |  |  | #REF! |  | 996.459 | #REF! | #REF! | 1384.459 | 388 | #REF! | Had 481M remaining to spend and took out 123M of the total… now you have a total 604 left to allocate elsewhere
|  |  | Other Fixed Escalation |  | 670 | 668 |  |  | #REF! |  | 273.13 | #REF! | #REF! | 273.13 | 0 | #REF! | Had 136M remaining to spend and added 52M… now you have $84M to allocate elsewhere
|  |  | Fully Escalated |  | 0 | 746 |  |  | #REF! |  | 61 | #REF! | #REF! | -33.38 | -94.38 | #REF! | Had a 49M credit that we didn't use… now we are taking out 16 making it a $33M credit
|  | Total EPC Base |  |  | 3116 | 3302 |  |  | #REF! |  | -33 | #REF! | #REF! | 61.06 | 94.06 | #REF! | Had nothing left to spend. The total increased $3m, so we have $3M left to spend
[11 empty] | #REF! | #REF! | #REF! | 8762.514 | #REF! | #REF!
|  | EPC Escalation | [8 empty] | 240 | 0 | 240 | 0 | -240 | -1682
|  |  | Fixed Semi Annual Escalation |  | 431 | 176 |  |  | #REF! |  | #REF! | #REF! | #REF! | 8762.514 | #REF!
|  |  | Indexed Escalation |  | 142 | 116 |  |  | #REF! |  | 0 | 0 | 0 | -1682 | -1682 | 0
|  |  | Other Fixed Escalation |  | 108 | 110 |  |  | #REF! |  | #REF! | #REF! | #REF! | 7080.514 | #REF! | -3198.3971
|  | Total EPC Escalation |  |  | 681 | 401 |  |  | #REF! | [6 empty] | -413.2472
|  | Original EPC |  |  |  | 3257 | 3198 | 3198 |  | 3198.3971 |  | 3198.3971 | 3198.3971 | 3198.3971
|  | Interim Payments & Liens |  |  |  | 493 | 440 | 440 |  | 439.8787 |  | 439.844 | 413.2472 | 410.7029
Site Construction Management
|  |  | Engineering Contractor |  |  | 545 | 427 | 270 |  | 248.9637 |  | 317 | 445.0683 | 467.2233
|  |  | Procurement |  |  | 938 | 960 | 1244 |  | 1204.3428 |  | 1242 | 1309.0232 | 1320.7851
|  |  | Contract Construction |  |  | 1374 | 1571 | 2142 |  | 2186.4429 |  | 2282 | 2427.5874 | 2538.1654
|  |  | Construction Support & Project Management |  |  | 866 | 877 | 719 |  | 764.7891 |  | 715 | 661.7656 | 621.6632
[6 empty] | 3723 | 3835 | 4375 |  | 4404.5385 |  | 4555.6872 | 4843.4446 | 4947.8371
|  | Owners Cost |  |  | 477 | 996.459 | 1012 | 1173 |  | 1141.4724 |  | 1131 | 1102.655 | 1117.1121
|  | Ad Valorem Tax |  |  | 141 | 273.13 | 273 | 273 |  | 273.13 |  | 273 | 273.13 | 273.13
|  | Transmission Interconnection |  |  | -34 | 61 | 61 | 61 |  | 61.961 |  | 61.8954 | 61.7612 | 61.7314
|  | Test Fuel Offsets |  |  | 37 | -33 | -33 | -33 |  | -33.385 |  | -33.385 | -6.7671 | -4.2225
[5 empty] | 0 | 1297.589 | 1313 | 1474 |  | 1443.1785 |  | 1432.5547 | 1430.7791 | 1447.751
|  |  | Total Construction & Capital Cost |  | 4418 | 8770.589 | 8786 | 9488 |  | 9485.9928 |  | 9626.483 | 9885.868 | 10004.688
|  | Toshiba Parent Guarantee |  |  |  | -1682 | -1493 | -1493 |  | -1491.686 |  | -1491.686 | -1491.686 | -1491.686
|  | Total to be Absorbed by GPC |  |  |  | 0 | 0 | -694 |  | -694.3068 |  | -694.3068 | -694.3068 | -694.3068
|  | Allocated Contingency Included Above | [9 empty] | -140.4902 | -399.8752 | -518.6952
|  |  | Total Construction & Capital Cost Net of Parent Guarantee and amounts absorbed by GPC1 |  |  | 7088.589 | 7293 | 7300 |  | 7300 |  | 7300 | 7300 | 7300
|  | Construction Monitor | [7 empty] | 22 |  | 22 | 22 | 22
Vogtle 3&4 Project
Georgia Power Company Financing Cost - Recovered Pursuant to O.C.G.A. 46-2-25 (c.1)
and the January 3, 2017 Order Adopting Stipulation
Total Project Financing
Estimated
[5 empty] | at | Jun 2017 | Dec 2017 | June 2018 |  | June 2019 |  | December 2019 | June 2020 | Decmeber 2020
[5 empty] | Certification | Forecast | Forecast | Forecast |  | Forecast |  | Forecast | Forecast | Forecast
[5 empty] | ($ millions) | ($ millions) | ($ millions) | ($ millions) |  | ($ millions) |  | ($ millions) | ($ millions) | ($ millions)
Project Schedule Financing
|  | Return on CWIP in Rate Base |  |  | 1545 | 2862 | 2700 | 2734 |  | 2707.9614 |  | 2707 | 2677.0576 | 2669
|  | AFUDC - Accrued on CWIP Above Original Certified Cost |  |  | 0 | 428 | 253 | 349 |  | 308.8789 |  | 304 | 256.7843 | 246
|  | AFUDC - Accrued through December 2010 and Related Return |  |  | 111 | 109 | 109 | 109 |  | 109.4286 |  | 109 | 109.4286 | 109.4286
|  | Total Project Schedule Financing |  |  | 1656 | 3399 | 3062 | 3192 |  | 3126.2689 |  | 3120 | 3043.2705 | 3024.4286
| Total Capital Cost and Financing1 |  |  |  | 6074 | 12169.589 | 10355 | 10492 |  | 10426.2689 |  | 10420 | 10343 | 10324.4286
Notes:
Details may not add to totals due to rounding.
1. These totals for June 2019 Forecast forward exclude construction monitor fees pursuant to the VCM 19 Order.