## STF-198-9-a
Spending Category | Steps to Create Projection | Supporting Workpaper(s)
Total EPC | Total EPC is comprised of Original EPC Milestones and EPC. Original EPC Milestones is comprised of Original EPC Milestones costs (actuals only). EPC is comprised of cash actuals and remaining forecasted spend for Interim Payments & Liens and Site Construction Management costs (Engineering Contractor, Procurement, Contract Construction, and Construction Support & Project Management). See the GPC% EPC Support File tab of Attachment STF-198-3-b for details of the projections at the work order level by cost category on an accrual basis and is presented at GPC ownership % cost for all items. Costs are unitized through unitization codes applied to each work order. Costs on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" are presented at GPC ownership % on the cash basis by month and unit. This category includes construction contingency of $171M that was excluded from Table 1.1. | STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve) Attachment STF-198-3-b - VCM 24 Reprojected Budget File - GPC% EPC Support File tab
Shareable Owners Costs | The cash spending projection for Shareable Owners Costs is comprised of actuals and remaining forecasted spend for EPC Scope Change (actuals only), Owners Costs, and Transmission Interconnection. Trade Secret Attachment STF-198-9-b details the projections at the work order level by cost category and is presented at 100% ownership cost for all shareable items. Additionally, a unitization code is applied to each work order to assist with unitizing the costs presented on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24". Costs on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" are presented at GPC ownership % on the cash basis by month and unit. | STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve) Trade Secret Attachment STF-198-9-b - EPC Scope Change and Owners Cost by Work Order
Non-Shareable Owners Costs | The cash spending projection for Non-Shareable Owners Costs is comprised of Georgia Power costs that are not shareable with the Vogtle 3&4 Project Co-Owners. Trade Secret Attachment STF-198-9-b details the projections at the work order level by cost category and is presented at GPC% ownership cost for the non-sharable work orders. Additionally, a unitization code is applied to each work order to assist with unitizing the costs presented on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24". Costs on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" are presented at GPC ownership % on the cash basis by month and unit. | STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve) Trade Secret Attachment STF-198-9-b - EPC Scope Change and Owners Cost by Work Order
Ad Valorem Taxes | The cash spending projection for Ad Valorem Taxes is comprised of Georgia Power’s estimated Ad Valorem Taxes for the remainder of the Vogtle 3&4 Project. Trade Secret Attachment STF-198-9-b details the projections at the work order level by cost category and is presented at GPC% ownership cost for the non-sharable work orders. Additionally, a unitization code is applied to each work order to assist with unitizing the costs presented on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24". Costs on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" are presented at GPC ownership % on the cash basis by month and unit. | STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve) Trade Secret Attachment STF-198-9-b - EPC Scope Change and Owners Cost by Work Order
Parent Guarantee | Total Parent Guarantee cash spending projection is comprised of actuals to date for the Toshiba Parent Guarantee payment and Parent Guarantee Customer Refund. The Toshiba Parent Guarantee payment is a shareable credit presented at GPC ownership %. The Parent Guarantee Customer Refund is a non-shareable cost presented at GPC ownership %. Costs are unitized through unitization codes applied to each work order. Costs on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" are presented at GPC ownership % on the cash basis by month and unit. | STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve)
Test Fuel Offsets | The Test Fuel Offset calculation was based on Budget 2021 BOS lambdas and VCM 24 fuel replacement costs and is provided in Trade Secret Attachment STF-198-20-a. | STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve) Trade Secret Attachment STF-198-20-a - Test Fuel Calculation
Construction Monitor | The cash spending projection for Construction Monitor is comprised of Georgia Power costs that are not shareable with the Vogtle 3&4 Project Co-Owners. Trade Secret Attachment STF-198-9-b details the projections at the work order level by cost category and is presented at GPC% ownership cost for the non-sharable work orders. Costs on STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" are presented at GPC ownership % on the cash basis by month and unit. | STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve)
Total Project Spend Curve | The Total Project Spend Curve (Total Capital with Construction Monitor) is the combined cash spend projection for construction and capital costs for Total EPC, Shareable & Non-Shareable Owners Costs, Transmission Interconnection, Test Fuel Offsets, Ad Valorem Tax, and Parent Guarantee (including Parent Guarantee Customer Refunds), and Construction Monitor. The Total Project Spend Curve included in STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve) represents all project construction and capital costs presented at GPC ownership % on the cash basis by month and unit. | STF-198-1 Trade Secret Attachment "TS - Cash Spend Curve VCM 24" - Economic and Financing Costs (Spending Curve)