## Floyd County Project
DN 41560: STF-4-1: Floyd County Project 1st Q 2021 Project Report Status
1 | Project # | 175210
2 | Date Approved | 2019-01-28
3 | Customer Name | International Paper
4 | Estimated Project Cost | 10739395
5 | Location | Floyd County, Rome, GA
6 | Type & Size of Pipe | 12" Steel
7 | MAOP | 300 PSIG
8 | Total Length of Pipe in Feet Required | 41226
9 | Estimated Length of Pipe in Feet Installed | 15766
10 | Estimated Length of Pipe Remaining | 15766
11 | Total Budgeted for Project | 10739395
12 | Total Project Capital Expenditures Since Approval | 9200000
13 | Total Project Capital Expenditures for 1st Q 2021 | 2758419.9538
14 | Performance Percent completed | 100
15 | Estimated Completion Date | 2021-03-31
16 | Completed & In-Service Date | 2021-09-30