# REButtal TESTIMONY OF

# AARON P. ABRAMOVITZ AND SARAH P. ADAMS

# IN SUPPORT OF GEORGIA POWER COMPANY’S PLANT VOGTLE

# UNIT 3 AND COMMON RATE ADJUSTMENT APPLICATION

# DOCKET NO. 43838

INTRODUCTION

Q.	PLEASE STATE YOUR NAMES, TITLES, AND BUSINESS ADDRESSES.

A.	Aaron P. Abramovitz. I am the Executive Vice President, Chief Financial Officer, and Treasurer for Georgia Power Company (“Georgia Power” or the “Company”). My business address is 241 Ralph McGill Boulevard, Atlanta, Georgia 30308.

A. 	Sarah P. Adams. I am the Vice President and Comptroller for Georgia Power. My business address is 241 Ralph McGill Boulevard, Atlanta, Georgia 30308.

Q.	MR. ABRAMOVITZ AND MS. ADAMS, DID YOU PRESENT DIRECT TESTIMONY ON BEHALF OF GEORGIA POWER IN THIS PROCEEDING?

A.	Yes.

# Q.	ARE THERE ANY UPDATES TO THE COMPANY’S APPLICATION FILED ON JUNE 15, 2021?

# A.	Yes, the Company is currently targeting Vogtle Unit 3 to achieve Commercial Operation in June 2022. Therefore, an updated set of minimum filing requirement (“MFR”) schedules, comparable to those submitted with the Company’s Application filed on June 15, 2021 and as subsequently modified on July 21, 2021, is being submitted concurrent with this testimony that contemplates this revision to Unit 3 Commercial Operation. If subsequent changes to the construction schedule further extend the expected Unit 3 Commercial Operation date, the Company will update the MFRs, as needed.

# Q.	HOW HAS THE DELAYED IN-SERVICE DATE FOR VOGTLE UNIT 3 IMPACTED THE COMPANY’S PROJECTED REVENUE REQUIREMENT AND REQUESTED RATE INCREASE IN THIS CASE?

# A.	As shown in Table 1, the change in the projected annual revenue requirement requested by the Company between the assumed January 2022 and June 2022 in-service dates would be an increase of 0.2% or $662,000. Table 1 presents the Company’s requested annual revenue requirement assuming Unit 3 in-service dates of January, March, and June 2022.

# TABLE 1

| # ($ Millions) | # Revenue Requirement | # Increase |
| --- | --- | --- |
| # Application January 2022 In-Service Date | # $369.058 |  |
| # Direct Testimony March 2022 In-Service Date | # $369.707 | # $0.649 |
| # Rebuttal Testimony June 2022 In-Service Date | # $369.720 | # $0.013 |

# Q.	WHAT IS THE PURPOSE OF YOUR REBUTTAL TESTIMONY?

A.	The purpose of our testimony is to respond to the positions taken and recommendations made by the Georgia Public Service Commission’s (“Commission”) Public Interest Advocacy (“PIA”) Staff, Georgia Association of Manufacturing (“GAM”), and the Metropolitan Atlanta Rapid Transit Authority (“MARTA”). It is important to note, however, that to the extent a particular PIA Staff or Intervenor recommendation is not specifically addressed in this rebuttal testimony, that should not be construed as support for such position.

Q.	PLEASE SUMMARIZE YOUR TESTIMONY.

A.	In this proceeding, the ultimate issue before the Commission is how Georgia Power’s rates should be adjusted following Unit 3 reaching Commercial Operation to recover the Unit 3 and Common portion of the costs previously deemed prudent in the Commission’s January 3, 2017 Supplemental Information Review (“SIR”) Order Adopting Stipulation in Docket No. 29849 (“SIR Order”). Consistent with the Commission’s January 11, 2018 Order on the Seventeenth Semi-Annual Vogtle Construction Monitoring (“VCM”) Report in Docket No. 29849 (“VCM 17 Order”), the Company requests that $2.4 billion of capital costs be transferred into base rates following Unit 3 Commercial Operation. This, along with the inclusion of costs to operate the plant, results in a $370 million annual adjustment to base rates. The Company and PIA Staff disagree on the interpretation of the VCM 17 Order and disagree on how to address several ancillary issues on which the VCM 17 Order was silent.

There are three primary issues that make up the difference between the Company and PIA Staff’s calculations of the adjustment to base rates once Unit 3 achieves Commercial Operation. First, the Company and PIA Staff differ on treatment of the Toshiba Parent Guaranty (“TPG”) payment as directed by the Commission in the VCM 17 Order. PIA Staff claims that the capital cost deemed prudent in the SIR Order attributable to Unit 3 and Common facilities should be reduced by a portion of the TPG. However, the Commission previously applied the TPG to reduce the approved cost forecast of Vogtle Units 3 and 4 (“Project”) to $7.3 billion. Consistent with the VCM 17 Order instructions, the Company reduced the Construction Work in Progress (“CWIP”) balance by the TPG amounts, and customers were given refunds with part of the TPG proceeds. As such, the TPG has already been fully applied as directed by the Commission and should have no further impact on the Unit 3 rate adjustment.

Second, the Company and PIA Staff disagree on the Company’s proposed recovery of net operating costs related to Unit 3 and Common facilities, which includes: (1) depreciation expense; (2) Operation and Maintenance (“O&M”) expenses; (3) property taxes; and (4) nuclear decommissioning costs; and are partially offset by the full benefits of federal production tax credits (“PTCs”) (collectively, “Operating Costs”) for Georgia Power’s ownership of Unit 3 prior to Unit 4 being placed in base rates. Considering that the ultimate issue in this proceeding is the amount and method of cost recovery for a fully operating unit, PIA Staff’s primary recommendation inappropriately denies recovery of depreciation and operating expenses for the amount of Unit 3 and Common facilities in plant-in-service reflected in base rates, while retaining the full benefit of the PTCs for customers when Unit 3 achieves Commercial Operation. While it is true that the SIR Order and VCM 17 Order did not explicitly provide for the current recovery of depreciation or operating expenses, they also did not explicitly deny or disallow recovery. When Unit 3 achieves Commercial Operation, Unit 3 and Common facilities will be serving customers. Therefore, it is both reasonable and consistent with prudent utility ratemaking for the Company to currently recover the related Unit 3 and Common Operating Costs (e.g., depreciation and operating expenses) incurred to serve customers.

Finally, the Company disagrees with PIA Staff’s recommendation to retain in the NCCR tariff the Accumulated Deferred Income Taxes (“ADIT”) and the deficient non-protected ADIT regulatory asset attributed to the amount of the capital costs that are transferred from NCCR into base rates. The ADIT assets in the NCCR tariff are the direct result of the capital cost that is being recovered through the NCCR tariff and, without those capital costs incurred during construction, there would be no associated ADITs. Accordingly, the Commission should approve the transfer of ADITs from NCCR to base rates along with the capital cost from which those ADITs were derived.

I.	Costs Related to Unit 3 and Common Deemed Prudent in the SIR Stipulation

Q.	WHY IS PIA STAFF’S PROPOSED $1.493 BILLION REDUCTION OF THE AMOUNT DEEMED PRUDENT IN THE SIR ORDER FOR THE TPG UNNECESSARY AND INAPPROPRIATE?

A.	As explained in our Direct Testimony, and as explicitly directed by the Commission’s VCM 17 Order, the Company (1) credited each customer with three $25 monthly bill credits, and (2) applied the remaining TPG proceeds to the CWIP balance. Immediately applying those funds had the effect of not only reducing the capital cost that was reflected in the Company’s NCCR rate base at the time, but also permanently reducing the entire cost of the Project, thus benefitting customers because those costs will never be placed in service and customers will never be responsible for or pay those costs. Thus, the immediate application of the TPG proceeds to CWIP reduced the ultimate cost borne by customers both through reduced NCCR collections, reduced allowance for funds used during construction (“AFUDC”) deferrals, and reduced capital costs overall. Accordingly, customers have already received the benefit of the TPG as ordered by the Commission, and a further reduction of the amount transferred from CWIP to base rates would be punitive and inappropriate.

The permanent impact of applying the TPG to reduce the CWIP balance is further illustrated in paragraph 3 of the VCM 17 Order, where the Commission approved the revised capital cost forecast net of the TPG:

The Commission approves and finds reasonable the Company’s revised schedule and cost forecast. The approved cost forecast, however, shall be reduced by the actual amounts of the Toshiba Parent Guaranty applied to the project’s construction work in progress (“CWIP”) balance. This places the approved revised capital cost forecast at $7.3 Billion.

Thus, the Commission already accounted for the reduction of the TPG in setting and approving the revised capital cost forecast at $7.3 billion in the VCM 17 proceeding.

Q.	HOW MUCH DID CUSTOMERS BENEFIT FROM APPLYING THE TPG PROCEEDS TO THE CWIP BALANCE AS DIRECTED BY THE COMMISSION IN THE VCM 17 ORDER?

A.	As a result of applying the TPG proceeds to the CWIP balance, as directed in the VCM 17 Order, customers have paid approximately $80 million less through the NCCR tariff. Additionally, the Company projects that customers will pay approximately $260 million less in AFUDC costs over the operating lives of Units 3 and 4.

Q.	DID THE COMMISSION SPECIFY IN THE VCM 17 ORDER THAT THE TPG BE APPLIED TO THE CWIP BALANCE AS OF DECEMBER 31, 2015?

A.	No. The discussion of the TPG in the body of the VCM 17 Order and in the subsequent ordering paragraphs does not reference the December 31, 2015 date. Consistent with the VCM 17 Order, the Company reduced the CWIP balance as the TPG payments were made and issued the three $25 customer refunds as directed by the Commission. No language in the VCM 17 Order suggested that any portion of the TPG should later reduce the amount of the Unit 3 and Common costs deemed prudent in the SIR Stipulation that could be recovered in base rates when Unit 3 achieved Commercial Operation. Moreover, through its subsequent approvals of four separate NCCR tariff revisions, the Commission clearly has already approved the Company’s application of the TPG proceeds to reduce CWIP.

Q.	IS THE COMPANY’S REQUEST TO TRANSFER THE UNIT 3 AND COMMON PORTION OF THE DEEMED PRUDENT AMOUNT WITHOUT REDUCTION FOR THE TPG PROCEEDS IN CONFLICT WITH THE VCM 17 ORDER AS CLAIMED BY PIA STAFF?

A.	No. The VCM 17 Order explicitly addressed how the Company was to apply the TPG to provide for the immediate benefit of customers, and the Company has already reduced the CWIP balance as directed by the Commission. PIA Staff’s proposal to reduce the Unit 3 and Common portion of the deemed prudent amount to be recovered in base rates by the TPG is not supported by the language in the VCM 17 Order. The Commission could have directed that the amounts to be moved into rate base for Unit 3 and Common would be reduced by the TPG. But it did not. The TPG does not, and should not, reduce the amount that the Commission has already deemed prudent. The costs that were deemed prudent in the SIR Stipulation were incurred as of December 31, 2015, and the TPG was accounted for two years later in the VCM 17 Order and utilized for its intended purpose of reducing future costs of the Project in the absence of a fixed and firm priced construction contract. PIA Staff’s attempt to apply the TPG again, to further reduce the capital costs eligible for recovery upon Unit 3 Commercial Operation, is contrary to a plain reading of the VCM 17 Order.

Q.	WHAT OTHER ADJUSTMENTS ARE INCLUDED IN PIA STAFF’S RECOMMENDATION OF THE DEEMED PRUDENT AMOUNT OF CAPITAL COST?

A.	PIA Staff recommends that 64 percent of the total deemed prudent amount be allocated to Unit 3 and Common facilities. In addition, PIA Staff has excluded from the deemed prudent amount the construction monitoring costs and reduced the amount of the Westinghouse settlement payments incurred after December 31, 2015 from $54 million to $36 million.

Q.	IS IT REASONABLE FOR THE COMPANY TO ASSUME THAT TWO-THIRDS OF THE AMOUNT DEEMED PRUDENT IN THE SIR STIPULATION IS ATTRIBUTED TO UNIT 3 AND COMMON FACILITIES?

A.	Yes. The simplified two-thirds ratio to identify the portion of the capital costs deemed prudent in the SIR Stipulation related to Unit 3 and Common is a reasonable assumption and has been consistently applied by the Company since the VCM 17 Order. This ratio has been used in every rate impact and revenue requirement analysis submitted in the VCM filings to illustrate the impacts of the VCM 17 Order.

Q.	WHY SHOULD THE CONSTRUCTION MONITORING COSTS BE INCLUDED IN THE DEEMED PRUDENT AMOUNT TO BE TRANSFERRED TO BASE RATES?

A.	The construction monitoring costs were approved by the Commission as reasonable and prudent in the VCM 19 Order. Therefore, the Company has appropriately included the construction monitoring costs incurred through December 31, 2015 in the capital cost to be transferred to base rates.

Q.	IS IT APPROPRIATE TO REDUCE THE AMOUNT OF WESTINGHOUSE SETTLEMENT COSTS INCURRED AFTER DECEMBER 31, 2015 BY $18 MILLION?

A.	No. PIA Staff has not provided an appropriate reason for the adjustment. The SIR Order provided that all Westinghouse settlement costs were reasonable and prudent. The $54 million included in the Company’s filing represents the full Westinghouse settlement costs incurred after December 31, 2015 and, as such, has been deemed reasonable and prudent by the Commission.

II.	Recovery of Operating Expenses When Unit 3 Achieves Commercial Operation

Q.	WHY IS PIA STAFF’S PRIMARY RECOMMENDATION UNREASONABLE?

A.	As described above, PIA Staff’s primary recommendation—to increase base rates by $75 million—incorrectly subtracts the TPG proceeds, along with other inappropriate adjustments, from the Unit 3 and Common portion of the deemed prudent costs eligible for recovery in this case. In addition, PIA Staff’s primary recommendation prohibits the Company from recovering operating expenses for Unit 3 and Common once the unit has achieved Commercial Operation and is placed in service. To deny recovery of operating expenses for an operating unit is unreasonable and contrary to prudent utility ratemaking, and PIA Staff has provided no reasonable basis for disallowing these costs.

Q.	WHY IS IT APPROPRIATE FOR THE COMPANY TO RECOVER OPERATING COSTS WHEN UNIT 3 ACHIEVES COMMERCIAL OPERATION?

A.	As previously discussed in our Direct Testimony, when Unit 3 achieves Commercial Operation, the unit will be a fully dispatchable baseload unit available to serve customers. Therefore, once Unit 3 achieves Commercial Operation, customers will receive the benefits of 100% of the generation output of the Company’s ownership in Unit 3. Under typical regulatory accounting treatment, Operating Costs are either included in rates once a unit is placed in service or deferred until the regulatory review process is completed for the capital cost of the unit, to be recovered in the future. This regulatory proceeding completes the regulatory review process for a portion of the capital cost of the unit. It would be inappropriate for the Commission to disallow recovery of Operating Costs for a certified generation facility that is in service.

Q.	DOES THE VCM 17 ORDER ADDRESS THE RECOVERY OF OPERATING COSTS?

A.	No, nor should it have addressed the recovery of Operating Costs. The VCM proceeding is a construction monitoring proceeding, not a ratemaking proceeding. The Commission reviews, verifies, and approves the construction capital costs incurred in each reporting period during each VCM proceeding. While the Commission has periodically identified and resolved issues regarding the timing, process, and structure for future prudence and ratemaking proceedings, it has, appropriately, not made a rate adjustment or traditional ratemaking decision during a VCM proceeding. The VCM 17 Order was appropriately silent on Operating Costs, which is a ratemaking issue. In contrast, the current Unit 3 Rate Adjustment proceeding is a proceeding to adjust rates where it is appropriate for the Commission to determine this issue. As such, the Company has included in this proceeding a request to recover Operating Costs as part of the decision in this case.

Q.	IF PIA STAFF’S ALTERNATIVE RECOMMENDATION PERMITS THE RECOVERY OF OPERATING COSTS WHEN UNIT 3 ACHIEVES COMMERCIAL OPERATION, WHY IS THE ALTERNATIVE RECOMMENDATION ALSO UNREASONABLE?

A.	PIA Staff’s alternative recommendation—to increase base rates by $193 million including Operating Costs—is marred by the introduction of inappropriate and unacceptable performance guarantees and operating conditions post-Commercial Operation. There is no Commission precedent for imposing performance guarantees on the cost recovery of Operating Costs for a generating unit when setting rates. The Commission regularly reviews the Company’s cost of generation, performance, unit output, maintenance expenses, outages, and related costs in fuel cases, annual surveillance reviews (“ASR”), and/or base rate case proceedings. If Unit 3 experiences operational issues that prevent the Unit from operating as intended and/or requires replacement energy, the appropriate Commission review of the unit’s operation and the cost impacts related to the same is through one of these forums, not an automatic, predetermined disallowance for failure to meet performance criteria, as proposed by PIA Staff. The imposition of performance requirements is outside what was previously agreed to in the SIR Stipulation to determine when the units reach Commercial Operation and, therefore, outside the VCM 17 Order.

Q.	IS PIA STAFF CHALLENGING THE PROJECTED AMOUNT OF OPERATING COSTS THE COMPANY HAS REQUESTED TO BE RECOVERED IN BASE RATES ONCE VOGTLE UNIT 3 ACHIEVES COMMERCIAL OPERATION?

A.	No, PIA Staff’s position is centered more on whether it is appropriate for the Company to recover the Operating Costs necessary to operate Vogtle Unit 3 once it achieves Commercial Operation. Their primary position being disallowance of 100 percent of operating expenses and the depreciation expense related to the capital investment not reflected in base rates, while their alternative position would only allow recovery of operating expenses contingent upon a set of predefined unit performance criteria.

Q.	IS DEFERRAL OF OPERATING COSTS RELATED TO AN APPROVED AND NEWLY PLACED IN-SERVICE ASSET CONSISTENT WITH PAST COMMISSION PRACTICES?

A.	No. The Commission has historically allowed for current recovery of all Operating Costs, including depreciation, related to a new asset when it is placed in service, included in rate base, and operating for the benefit of customers.

III.	Depreciation

Q.	WHY IS THE AMOUNT OF DEPRECIATION AND THE TIMING FOR RECOVERY AS PROPOSED BY PIA STAFF INAPPROPRIATE?

A.	Similar to the Company’s proposed current recovery of its operating expenses, current recovery should also be provided for 100% of the depreciation expense for all of the Unit 3 and Common placed into service. Again, when Unit 3 achieves Commercial Operation, the unit will be a fully dispatchable baseload unit available to serve customers. Therefore, customers will receive the benefits of 100% of the generation output of the Company’s ownership in Unit 3. Once these facilities are placed in service, a portion of their total utility for their useful lives is being consumed or “used up” to provide generation output for the benefit of customers. The consumed utility of these capital assets is recognized over their assumed remaining useful lives and the associated costs are recovered through depreciation expense. Likewise, it would be inappropriate for the Commission to disallow recovery of the depreciation expense attributed to electric utility plant-in-service operating for the benefit of customers.

Q.	DOES THE COMPANY’S REQUEST INCLUDE LAND IN ITS DEPRECIATION EXPENSE CALCULATION?

A.	No. The capital cost for Vogtle Units 3 and 4 does not include any land. Furthermore, land is not subject to depreciation. Therefore, no land is included in the Company’s depreciation expense calculation associated with Unit 3 and Common facilities.

Q.	DOES THE COMPANY AGREE WITH PIA STAFF’S RECOMMENDATION TO APPLY A 1.677% DEPRECIATION RATE FOR VOGTLE 3 AND COMMON?

A.	No. Simply calculating a depreciation rate based only on service life ignores the cost of removal component of the depreciation rate. Current depreciation rates approved by the Commission in the 2019 base rate case, including the 1.768% depreciation rate approved for the Project, appropriately include this component.

IV.	Accumulated Deferred Income Taxes (ADITs)

Q.	DOES THE COMPANY AGREE WITH PIA STAFF’S RECOMMENDATION TO LEAVE THE ADITS AND DEFICIENT ADIT REGULATORY ASSET IN NCCR?

A.	No. The Company disagrees with PIA Staff’s recommendation to retain in the NCCR tariff the ADIT and the deficient non-protected ADIT regulatory asset attributed to the amount of the capital costs that are transferred from NCCR into base rates. The ADIT assets in the NCCR tariff are the direct result of the capital cost that is being recovered through the NCCR tariff. Without those capital costs incurred during construction, there would be no associated ADITs. It is appropriate and consistent with the Commission’s traditional regulatory precedent for the Commission to approve the transfer of ADITs from NCCR to base rates along with the capital cost from which those ADITs were derived.

Q.	HAS THE COMPANY PAID FEDERAL INCOME TAXES RELATED TO INTERNAL REVENUE CODE (“IRC”) SECTION 263A INTEREST DURING THE CONSTRUCTION PERIOD OF THE VOGTLE 3 AND COMMON PLANT COSTS BEING PLACED INTO SERVICE?

A.	Yes. The Company paid federal income taxes related to IRC Section 263A interest at a rate of 35% from the inception of the construction of Unit 3 and Common through 2017 and at a rate of 21% since 2018. When the Tax Cuts and Jobs Act of 2017 reduced the federal tax rate from 35% to 21%, the federal portion of the ADIT decreased with a corresponding increase to a regulatory asset along with the related gross-up for income taxes.

Q.	IS IT APPROPRIATE FOR THE COMPANY TO SEEK APPROVAL FOR ALL INCOME TAX COSTS RELATED TO UNIT 3 AND COMMON COSTS BEING PLACED INTO RATES, INCLUDING FEDERAL TAXES PAID AT 35% AND 21%?

A.	Yes. The Company has not yet recovered any taxes it paid through the construction period up to the time of the filing, including federal taxes paid at 35% and 21%, and the Commission has consistently approved income taxes as recoverable costs. Income taxes, as is the case with other Operating Costs, are costs incurred by the Company in order to provide service to its customers.

V.	Deferred Financing Costs

Q.	WHAT ARE THE FALLACIES IN PIA STAFF’S RECOMMENDATIONS REGARDING DEFERRED CARRYING COSTS?

A.	PIA Staff’s assumption that, “the capital costs not included in base rates or NCCR rates were financed solely by long-term debt” is without merit. All of the Company’s infrastructure and operations are financed in total using a capital structure comprised of both investment capital (equity) and borrowed funds (debt). Current Unit 3 and Common facilities capital costs excluded from the NCCR tariff are earning an AFUDC rate, which includes both equity and debt components. Beginning in 2018, for regulatory recovery purposes, the Commission set the AFUDC cost of the equity component equal to the Company’s average cost of long-term debt as provided in paragraph 7 of the VCM 17 Order; however, that order does not change either how the Project has been financed or the actual costs of that financing.

Q.	IS THERE ANY REASON THE FINANCING COSTS ON THE UNIT 3 AND COMMON FACILITIES CAPITAL COSTS NOT INCLUDED IN BASE RATES OR NCCR THAT THE COMPANY IS SEEKING TO DEFER SHOULD BE CALCULATED OR PRICED ANY DIFFERENTLY AFTER UNIT 3 ACHIEVES COMMERCIAL OPERATION THAN THEY ARE TODAY?

A.	No. Those capital costs will continue to be financed with both equity and debt components.

Q.	IS PIA STAFF CORRECT THAT THE COMPANY CANNOT DEFER AN EQUITY RETURN FOR FINANCIAL REPORTING PURPOSES UNDER THE CURRENT ACCOUNTING RULES?

A.	Yes. However, the Company can defer an equity return approved by the Commission through a regulatory mechanism and reflected for regulatory reporting purposes. As discussed on page 18 of our Direct Testimony, with Commission approval the Company can defer debt financing to a regulatory asset for financial reporting purposes, and the equity financing costs will be separately tracked and reflected as a regulatory adjustment in a future rate proceeding.

Q.	IS THE COMPANY FINANCIALLY BETTER OFF DEFERRING THE CARRYING COSTS ASSUMING 100 PERCENT DEBT FINANCING AS PROPOSED BY PIA STAFF?

A.	No. The Company’s real incurrence of its cost of equity financing cannot be “assumed” away by applying 100 percent debt financing as proposed by PIA Staff. This cost will continue to be incurred by the Company including the related income tax expenses. Under the Company’s proposal, which applies Georgia Power’s current Commission-approved capital structure setting the cost of equity at the Company’s average cost of long-term debt, the regulatory adjustment to provide future recovery of the deferred equity financing costs would include the related income tax expense, making the Company whole.

VI.	Commercial Operation and Performance Conditions

Q.	DID THE SIR STIPULATION DEFINE COMMERCIAL OPERATION?

A.	Yes. The SIR Stipulation expressly defined Commercial Operation as “fully dispatchable at the stated Net Electrical Output of 1,102 MWe.”

Q.	DOES GEORGIA POWER AGREE WITH THIS DEFINITION?

A.	Yes, the Company agrees with the definition of Commercial Operation that was agreed to by the parties in the SIR Stipulation and approved by the Commission.

Q.	PLEASE CLARIFY THE COMPANY’S POSITION ON THE PROCESS FOR DETERMINING THAT UNIT 3 HAS MET THE DEFINITION OF COMMERCIAL OPERATION AGREED TO IN THE SIR STIPULATION.

A.	In terms of procedure, Georgia Power proposes that Southern Nuclear Operating Company will determine, at the outset, whether Unit 3 is fully dispatchable at the stated net electrical output of 1,102 MWe (as required by the SIR Stipulation) along with Georgia Power, as agent and co-owner of the Unit. Then, Georgia Power will provide notice to the Commission so that the Commission is aware of the pending change in rates, which will be made as directed by the final order in this proceeding.

Q.	WHAT IS THE COMPANY’S CRITERIA FOR DETERMINING THAT UNIT 3 IS FULLY DISPATCHABLE ON DEMAND AT THE STATED NET ELECTRICAL OUTPUT OF 1,102 MWE?

A.	The Company will deem Unit 3 to be fully dispatchable on demand when it has completed start-up testing and is fully operational. Unit 3 is scheduled to operate for approximately 560 hours at or above 1,102 MWe during start-up prior to commercial operation.

Q.	DOES THE COMMISSION NEED TO DETERMINE ADDITIONAL PERFORMANCE CRITERIA FOR MEASURING UNIT 3 PERFORMANCE POST-COMMERCIAL OPERATION?

A. 	No. As stated previously, if there are post-commercial operation issues regarding unit performance and related cost impacts, other proceedings like the fuel case, ASR, or rate case are where the Commission and its Staff should appropriately review and evaluate any operational concerns. PIA Staff’s proposed additional criteria would impose an automatic disallowance should the strict performance criteria not be met, which is contrary to how other operational cost recovery determinations are made.

Q.	ARE PIA STAFF’S ADDITIONAL PERFORMANCE CRITERIA SUPPORTED BY THE SIR STIPULATION?

A.	No. As stated by the Jacobs, Roetger, and Grace panel, each party ceded benefits and accepted detriments as part of the negotiation process in reaching agreement on the SIR Stipulation. Both parties agreed to the definition of Commercial Operation and neither party agreed to other operational limitations or conditions on cost recovery, beyond those already provided for in the SIR Stipulation. By seeking to impose such operational restrictions on the Company at this point, PIA Staff is seeking to alter the agreed upon terms of the SIR Stipulation.

VII.	Response to Intervenor Requests

Q.	WHAT IS GEORGIA POWER’S RESPONSE TO GAM’S PROPOSAL TO DEFER BOTH THE UNIT 3 RATE INCREASE AND THE NCCR RATE REDUCTION TO JANUARY 1, 2023?

A.	Georgia Power respectfully disagrees with GAM’s alternative recommendation to defer the Unit 3 rate adjustment and corresponding NCCR rate reduction until January 1, 2023. First, the proposed deferral is contrary to one of the intended goals of the Commission’s VCM 17 Order, which incentivized the Company to complete Unit 3 as soon as possible by allowing the Company to recover in base rates the Unit 3 and Common costs previously deemed prudent in the SIR Stipulation in the month following Unit 3 Commercial Operation. Second, although the in-service date for Unit 3 has been delayed, Georgia Power’s customers have known about the plan and timing of this rate adjustment since January 2018. Third, by delaying placing the Unit 3 and Common portion of the previously deemed prudent amounts in base rates and keeping capital costs in NCCR longer, the Company will be unnecessarily penalized with a lower return on these capital costs while Unit 3 will be in service and operating for the benefit of all customers.

Q.	WHAT IS GEORGIA POWER’S RESPONSE TO MARTA’S REQUEST NOT TO INCREASE ITS RATES?

A.	Georgia Power fully appreciates the important role that MARTA plays in the economic development of the state of Georgia and acknowledges that MARTA’s ridership has been substantially impacted by the onset of the COVID-19 pandemic. However, many, if not all, of Georgia Power’s customers, large and small, have been impacted by the pandemic. The Company does not believe it is appropriate to exempt or carve out special treatment for one customer or customer class from the Unit 3 rate adjustment. All of Georgia Power’s customers will benefit from the long-term, carbon-free, baseload generation from Vogtle Unit 3 (and Unit 4). Upon completion, the units will be economic assets not only to Georgia Power, but also to customers, the state of Georgia, and the nation for 60 years. Therefore, it is appropriate for all of Georgia Power’s customers to share in this rate adjustment, and the Company has proposed to design rates to recover the Unit 3 rate adjustment equally across all base tariffs. That said, cost allocation is a policy decision for this Commission, and the Commission is free to determine that a different allocation is appropriate.

Q.	DOES THIS CONCLUDE YOUR TESTIMONY?

A.	Yes.