## CCR ARO
Coal Combustion Residuals Asset Retirement Obligations (CCR ARO)
This table reflects Georgia Power’s estimated costs to close ash ponds and landfills, as well as the estimated costs during post closure care, in compliance with federal and state CCR regulations.
(millions of dollars)
| Project to Date Actuals Through December 2021* | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 & Beyond | Total
Ash Pond | 856.8662 | 298.3159 | 284.0833 | 349.1112 | 413.3515 | 474.3115 | 470.5803 | 435.448 | 416.632 | 422.5855 | 454.4183 | 2239.6315 | 7115.3352
Landfill | 87.3014 | 30.8265 | 36.3117 | 59.0489 | 96.8507 | 82.5828 | 73.9619 | 106.587 | 68.5086 | 69.918 | 42.9426 | 1020.6383 | 1775.4784
Total | 944.1676 | 329.1424 | 320.395 | 408.1601 | 510.2022 | 556.8942 | 544.5421 | 542.0351 | 485.1406 | 492.5036 | 497.3609 | 3260.2698 | 8890.8136
2022 & Beyond
| Closure | 2022: Post Closure; 2023: Total
Ash Pond | REDACTED | 2022: REDACTED; 2023: 6258.469
Landfill | REDACTED | 2022: REDACTED; 2023: 1688.177
Total | REDACTED | 2022: REDACTED; 2023: 7946.646
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Note: These cost tables reflect a closure by removal strategy for the Wansley ash pond. If the Commission approves retirement of the coal units at Wansley, Georgia Power recommends modifying its ash pond closure plans at the site from closure in place to closure by removal. The Company's recommendation is being reviewed by the Commission as part of the 2022 IRP and the change of the ARO is pending the Commission's approval of this plan.

## ARO Table
Table 1. Current Cost Estimates for CCR ARO Ash Pond Closure Projects
Ash Ponds | ($ in Millions)
Facility | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Bowen | 134.3075 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Branch | 87.991 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Hammond | 83.3314 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Kraft | 8.4459 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
McDonough | 111.6653 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
McIntosh | 15.9422 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
McManus | 103.2952 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Mitchell | 64.9397 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Scherer | 8.5163 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Wansley | 18.7729 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Yates | 219.6589 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Ash Pond Subtotal | 856.8662 | 298.3159 | 284.0833 | 349.1112 | 413.3515 | 1380.3397 | 3533.2673 | 7115.3352
Escalation included in Forecast above** | N/A | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 1517.6864
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
**Forecasted escalation is applied based on ARO accounting standards under ASC 410
Note: Details may not add to totals due to rounding
Note: These cost tables reflect a closure by removal strategy for the Wansley ash pond. If the Commission approves retirement of the coal units at Wansley, Georgia Power recommends modifying its ash pond closure plans at the site from closure in place to closure by removal. The Company's recommendation is being reviewed by the Commission as part of the 2022 IRP and the change of the ARO is pending the Commission's approval of this plan.
Table 2. Current Cost Estimates for CCR ARO Landfill Projects
Landfills | ($ in Millions)
Facility | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Arkwright | 29.5026 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Bowen | 0 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Branch | 0 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Hammond | 1.4783 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Kraft | 14.2394 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
McIntosh | 9.0347 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Scherer | 8.6452e-05 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Wansley | 0.00062665 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Yates | 33.0459 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill Subtotal | 87.3014 | 30.8265 | 36.3117 | 59.0489 | 96.8507 | 263.1317 | 1202.0075 | 1775.4784
Escalation included in Forecast above** | N/A | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 748.9393
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
**Forecasted escalation is applied based on ARO accounting standards under ASC 410
Note: Details may not add to totals due to rounding
Note: These cost tables reflect a closure by removal strategy for the Wansley ash pond. If the Commission approves retirement of the coal units at Wansley, Georgia Power recommends modifying its ash pond closure plans at the site from closure in place to closure by removal. The Company's recommendation is being reviewed by the Commission as part of the 2022 IRP and the change of the ARO is pending the Commission's approval of this plan.
Table 3. Current Cost Estimates for CCR ARO Ash Pond Closure and Landfill Projects
($ in Millions)
Cateogry | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Ash Pond Subtotal | 856.8662 | 298.3159 | 284.0833 | 349.1112 | 413.3515 | 1380.3397 | 3533.2673 | 7115.3352
Landfill Subtotal | 87.3014 | 30.8265 | 36.3117 | 59.0489 | 96.8507 | 263.1317 | 1202.0075 | 1775.4784
Total | 944.1676 | 329.1424 | 320.395 | 408.1601 | 510.2022 | 1643.4714 | 4735.2748 | 8890.8136
Escalation included in Forecast above** | N/A | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 2266.6257
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
**Forecasted escalation is applied based on ARO accounting standards under ASC 410
Note: Details may not add to totals due to rounding
Note: These cost tables reflect a closure by removal strategy for the Wansley ash pond. If the Commission approves retirement of the coal units at Wansley, Georgia Power recommends modifying its ash pond closure plans at the site from closure in place to closure by removal. The Company's recommendation is being reviewed by the Commission as part of the 2022 IRP and the change of the ARO is pending the Commission's approval of this plan.

## Arkwright
Arkwright
Table 4. Arkwright Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Arkwright AP-1,2,3,Landfill | Closure by removal and consolidation to permitted landfill | 29.5026 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 29.5026 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 5. Arkwright Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 29502553.01 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding

## Bowen
Bowen
Table 6. Bowen Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Advanced closure in place with liner | 134.3075 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Bowen CCR Landfill | Active landfill / closure in place | 0 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 134.3075 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 7. Bowen Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 134307528.35 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Note: These cost tables reflect a closure by removal strategy for the Wansley ash pond. If the Commission approves retirement of the coal units at Wansley, Georgia Power recommends modifying its ash pond closure plans at the site from closure in place to closure by removal. The Company's recommendation is being reviewed by the Commission as part of the 2022 IRP and the change of the ARO is pending the Commission's approval of this plan.

## Branch
Branch
Table 8. Branch Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-A | Closure by removal to permitted landfill | 1.2725 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-B | Closure by removal to permitted landfill | 11.9874 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-C | Closure by removal to permitted landfill | 9.3516 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-D | Closure by removal to permitted landfill | 6.448 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-E | Closure by removal to permitted landfill | 58.9315 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill | Closure in place | 0 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 87.991 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding | Project to Date Actuals Through Dec 2021
Table 9. Branch Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 87990973.81 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding

## Hammond
Hammond
Table 10. Hammond Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 11.2666 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-2 | Closure by removal to permitted landfill | 22.6643 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-3 | Advanced closure in place | 25.7641 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-4 | Closure by removal to permitted landfill | 23.6364 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Huffaker Road CCB Facility | Closure in place | 1.4783 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 84.8096 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 11. Hammond Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 84809632.1 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Note: These cost tables reflect a closure by removal strategy for the Wansley ash pond. If the Commission approves retirement of the coal units at Wansley, Georgia Power recommends modifying its ash pond closure plans at the site from closure in place to closure by removal. The Company's recommendation is being reviewed by the Commission as part of the 2022 IRP and the change of the ARO is pending the Commission's approval of this plan.

## Kraft
Kraft
Table 12. Kraft Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 8.4459 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Grumman Road Landfill | Closure in place | 14.2394 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 22.6852 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 13. Kraft Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 22685237.25 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding

## McDonough
McDonough
Table 14. McDonough Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Advanced closure in place | 21.8544 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-2 | Closure by removal | 16.0857 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-3 | Advanced closure in place | 33.8786 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-4 | Advanced closure in place | 39.8466 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 111.6653 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 15. McDonough Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 111665340.82 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding

## McIntosh
McIntosh
Table 16. McIntosh Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 15.9422 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill 3 | Closure in place | 1.9673 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill 4 | Closure in place | 7.0673 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 24.9768 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 17. McIntosh Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 24976825.3 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding

## McManus
McManus
Table 18. McManus Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 103.2952 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 103.2952 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 19. McManus Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 103295176.48 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding

## Mitchell
Mitchell
Table 20. Mitchell Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-A | Closure by removal to permitted landfill and beneficial reuse | 1.411 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-1 | Closure by removal to permitted landfill and beneficial reuse | 27.0924 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-2 | Closure by removal to permitted landfill and beneficial reuse | 36.4364 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 64.9397 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 21. Mitchell Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 64939854.05 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding

## Scherer
Scherer
Table 22. Scherer Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Advanced closure in place | 8.5163 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill | Active landfill / closure in place | 8.6452e-05 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 8.5163 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 23. Scherer Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 8518692.7919 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding

## Wansley
Wansley
Table 24. Wansley Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 18.7729 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill | Closure in place | 0.00062665 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 18.7735 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 25. Wansley Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 18775102.6591 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Note: These cost tables reflect a closure by removal strategy for the Wansley ash pond. If the Commission approves retirement of the coal units at Wansley, Georgia Power recommends modifying its ash pond closure plans at the site from closure in place to closure by removal. The Company's recommendation is being reviewed by the Commission as part of the 2022 IRP and the change of the ARO is pending the Commission's approval of this plan.

## Yates
Yates
Table 26. Yates Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
AP-1 | Closure by removal | 17.0531 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-2 | Closure by removal | 91.8605 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-3 | Advanced closure in place | 69.9778 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-A | Closure by removal | 17.181 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-B | Closure by removal | 14.4121 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-B' | Advanced closure in place | 9.1744 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Gypsum Landfill | Inactive landfill / closure by removal to permitted landfill and beneficial reuse | 4.2769 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
R6 Landfill | Inactive landfill / closure in place | 28.769 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
|  | 252.7047 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Table 34. Yates Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through December 2021* | 2022 Forecast | 2023 Forecast | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2075 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 252704689.29 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2021
Note: Details may not add to totals due to rounding
Note: These cost tables reflect a closure by removal strategy for the Wansley ash pond. If the Commission approves retirement of the coal units at Wansley, Georgia Power recommends modifying its ash pond closure plans at the site from closure in place to closure by removal. The Company's recommendation is being reviewed by the Commission as part of the 2022 IRP and the change of the ARO is pending the Commission's approval of this plan.