BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S TWENTY-SIXTH SEMI-ANNUAL VOGTLE CONSTRUCTION MONITORING (“VCM”) REPORT | DOCKET NO. 29849 |
| --- | --- |

|  | DIRECT TESTIMONY |  |
| --- | --- | --- |
|  | AND EXHIBITS |  |
|  | OF |  |
|  | TOM NEWSOME, PE, CFA PHILIP HAYET LANE KOLLEN, CPA, CMA, CGMA |  |

|  | ON BEHALF OF THE |  |
| --- | --- | --- |

|  | GEORGIA PUBLIC SERVICE COMMISSION |  |
| --- | --- | --- |
|  | PUBLIC INTEREST ADVOCACY STAFF |  |

|  | June 17, 2022 |  |
| --- | --- | --- |

TABLE OF CONTENTS

I.	INTRODUCTION	1

II.	REVIEW OF GEORGIA POWER COMPANY’S VCM 26 REPORT	2

III.	STAFF ECONOMIC ANALYSES	5

Vogtle 3 And 4 Lifecycle Costs vs. Alternative Combined Cycle	6

Rate Impact	12

Replacement Power Costs	14

IV.	RATEMAKING ISSUES	14

# INTRODUCTION

Q.	PLEASE STATE YOUR NAMES, TITLES, AND BUSINESS ADDRESSES.

A.	My name is Tom J. Newsome. I am the Director of Utility Finance with the Georgia Public Service Commission (“Commission”). My business address is 244 Washington St., Atlanta, Georgia, 30334.

My name is Philip Hayet.  I am a Vice President and Principal of J. Kennedy and Associates, Inc. (“Kennedy and Associates”).  My business address is 570 Colonial Park Drive, Suite 305, Roswell, Georgia, 30075.

My name is Lane Kollen.  I am a Vice President and Principal of Kennedy and Associates.  My business address is 570 Colonial Park Drive, Suite 305, Roswell, Georgia, 30075.

Q. 	MR. NEWSOME, WHAT ARE YOUR PRIMARY RESPONSIBILITIES WITH THE COMMISSION STAFF?

A. 	I am responsible for economic, financial, and cost of equity analyses and evaluations at the Commission.

Q.	MR. HAYET AND MR. KOLLEN, WHAT ARE YOUR PRIMARY RESPONSIBILITIES WITH KENNEDY AND ASSOCIATES?

A.	Mr. Hayet provides consulting services to government agencies and utility customers related to electric utility system planning, resource analyses, production cost modeling, and other utility industry policy issues.

Mr. Kollen provides consulting services to government agencies and utility customers related to electric utility, natural gas utility, water utility, and sewer utility ratemaking, accounting, finance, taxes, planning, and other policy issues.

Q.	PLEASE SUMMARIZE YOUR EDUCATION AND EXPERIENCE.

A.	We summarize our education, experience, professional certifications, and testimony appearances on Exhibit STF-NHK-1, Exhibit STF-NHK-2, and Exhibit STF-NHK-3 for Mr. Newsome, Mr. Hayet, and Mr. Kollen, respectively.

Q.	WHAT IS THE PURPOSE OF YOUR TESTIMONY?

A.	The purpose of our testimony is to address economic analyses and other analyses related to the Georgia Power Company’s (“Company’s”) VCM 26 filing and to provide Staff’s analysis of the rate impacts of Vogtle 3 & 4 (“the Project” or “the Units”).

# REVIEW OF GEORGIA POWER COMPANY’S VCM 26 REPORT

Q.	PROVIDE A BRIEF OVERVIEW OF THE PROJECT SCHEDULE AND COST.

A.	In the VCM 26 Report, the Company reported that the commercial operation dates (“COD”) for Vogtle Units 3 and 4 would be fourth quarter of 2022 and third quarter of 2023, respectively.  Since the VCM 26 Report was filed, the Company revised the COD dates for Units 3 and 4, as reported in the Company’s first quarter 2022 10-Q filing with the Securities and Exchange Commission (“SEC”), to March 2023 and December 2023, respectively.  These revised commercial operation dates represent 84-month and 81-month delays for Unit 3 and Unit 4, respectively.

In Table 1.1 of the VCM 26 Report, the Total Project Cost was revised upward to $12.5 billion.  The new Total Project Cost of $12.5 billion compared to $6.1 billion at certification represents an increase of 104 percent.  The components of Total Project Cost are shown in the Table 1 below.

Table 1

|  | Capital / |  | Total |
| --- | --- | --- | --- |
|  | Construction | Financing | Project |
|  | Cost | Cost | Cost |
|  | ($ million) | ($ million) | ($ million) |
| VCM 26 Forecast | 9,094 | 3,384 | 12,478 |
| Certification | 4,418 | 1,695 | 6,113 |
| Cost Overrun | 4,676 | 1,689 | 6,365 |
| Percent Overrun | 106% | 100% | 104% |

The values in Table 1 represent costs that have been or may be recovered from ratepayers, including costs in excess of the approved capital cost of $7.3 billion, except for $694 million of capital cost the Company has agreed to absorb.  The values also reflect the reductions in the return on equity (“ROE”) ordered by the Commission and the Toshiba Parental Guarantee (“TPG”) payments.

Staff has assumed the Company will seek recovery of the entire amount of the $9,094 million of capital/construction cost and deferred financing cost. The Company states in the VCM 26 Report at page 4 that it may seek recovery of these amounts in the prudence review contemplated by the VCM 17 Order as follows:

The Company is not requesting Commission approval of these cost increases in this filing but may request that the Commission evaluate expenditures allocated from contingency for future rate recovery (excluding the $694 million which the Company has agreed it will not seek recovery) no earlier than the prudence review contemplated by the VCM 17 Order.

Q.	BRIEFLY DESCRIBE THE CHANGES IN THE COMPANY’S ASSUMPTIONS REGARDING THE SOUTHERN COMPANY SYSTEM REFLECTED IN THE COMPANY’S VCM 26 FILING COMPARED TO THE VCM 25 FILING.

A.	The Company described these changes in data response STF-230-5. The Company updated inputs reflecting B2022 assumptions, and it noted that it made changes to fuel, load forecast, and generation technology cost assumptions. The Company also made changes to the capital additions costs, pre and post-in-service operation and maintenance (“O&M”) expense, decommissioning expense, Production Tax Credits (“PTC”), Department of Energy (“DOE”) loan savings, financing rates, nuclear fuel expense, and most notably the unit commercial operation dates and project capital cost spend curves.

Q.	HOW MUCH HAS ALREADY BEEN SPENT ON THE PROJECT THROUGH THE END OF THE VCM 26 PERIOD?

A.	Through December 31, 2021, the Company incurred $8.4 billion of construction cost, net of the Toshiba Parental Guarantee proceeds, plus $2.9 billion of financing cost, for a total cost of $11.3 billion (rounded).

Q.	HOW MUCH REMAINS TO BE SPENT BY THE COMPANY ON THE PROJECT THROUGH THE END OF CONSTRUCTION THAT THE COMPANY MAY REQUEST RECOVERY FROM RATEPAYERS?

A.	Over the remainder of the construction period, the Company estimates it will incur an additional $1,363 million of construction and capital costs and an additional $471 million of financing cost, for a total additional cost of $1,834 million.

# STAFF ECONOMIC ANALYSES

Q.	PLEASE SUMMARIZE THE FINANCIAL IMPACT OF THE DELAYS AND COST OVERRUNS ON RATEPAYERS DURING THE CONSTRUCTION PERIOD.

A. 	During the construction period, the Company is currently expected to recover approximately $4.1 billion under the Nuclear Construction Cost Recovery (“NCCR”) tariff from customers. This is nearly double the $2.1 billion the Company would have collected if the Units had been completed in April 2016 and 2017 in accordance with the certification schedule. For the entire delay period through 4th quarter 2023 ratepayers will pay an additional $2 billion in NCCR revenue requirement during the construction period due to the delays and cost overruns.  For a typical residential customer Staff has estimated an average of $900 will be collected through the NCCR tariff over the construction period. This $900 represents an additional $452 during the construction period compared to $448 had the Units been completed on original certification schedule of April 2016 / 2017.

Q.	PLEASE SUMMARIZE THE FINANCIAL IMPACT OF THE DELAYS AND COST OVERRUNS ON RATEPAYERS ONCE THE UNITS ARE PLACED IN COMMERCIAL OPERATION.

Once Units 3 and 4 are in commercial service, the Company may seek to include $9.5 billion in the rate base used to calculate the base revenue requirement.

If the entire $9.5 billion is included in rate base, it will represent an increase of $5.1 billion, or 116%, compared to the $4.4 billion expected at certification, and will increase ratepayer revenue requirements by approximately $16.9 billion over the 60-year life of the Units.  This will result in an increase in annual revenue requirements of approximately $530 million and $495 million during the first five and ten years in operation, respectively.

The impact on residential customers will be approximately $16.80 per month and $15.70 per month during the first five and ten years in operation, respectively. These values are significantly larger than the $9.60 per month that the Company claimed at certification.

In conclusion, ratepayers will pay substantially more both prior to and after the Units begin providing service due to the delays and cost overruns.

## Vogtle 3 And 4 Lifecycle Costs vs. Alternative Combined Cycle

Q.	HOW HAVE THESE CAPITAL AND FINANCING COSTS INCREASES IMPACTED THE ECONOMIC BENEFIT OF THE UNITS FOR RATEPAYERS?

A.	The cost increases have significantly reduced the economic benefit of the Units on a cost to complete basis and have completely eliminated any benefit on a life-cycle cost basis. The figures below are based on current assumptions and provide a comparison of the cumulative revenue requirements of Vogtle 3 and 4 versus natural gas combined cycle units under different assumptions about natural gas prices and carbon dioxide (“CO2”) emission costs. Nominal revenue requirements are used in this analysis to indicate the impact on ratepayer bills.

Staff used the same approach it has relied on in prior VCM proceedings to derive what Staff refers to as consensus natural gas price forecasts.  In deriving consensus forecasts, Staff included a recent NYMEX Henry Hub futures projection from April 13, 2022, which captures the impact of the significant increase in short-term natural gas prices that has occurred since the beginning of 2022. From this analysis, Staff determined that the Company’s forecasts were reasonable for use in this VCM, but reserves the right to challenge them in the future.

Figure 1 provides a comparison of the Vogtle 3 and 4 revenue requirements to natural gas combined cycle units for the zero CO2 price forecast.  The Vogtle Units 3 and 4 cumulative nominal revenue requirement exceeds the combined cycle cumulative nominal revenue requirement under all three natural gas price forecasts.

Figure 1

Figure 2 provides a comparison for Staff’s $10/ton CO2 price forecast.  The Vogtle Units 3 and 4 cumulative nominal revenue requirement exceeds the combined cycle cumulative nominal revenue requirement under all three natural gas price forecasts.

Figure 2

Figure 3 provides a comparison for Staff’s $20/ton CO2 price forecast.  The Vogtle Units 3 and 4 cumulative nominal revenue requirement exceeds the combined cycle nominal revenue requirement under all three natural gas price forecasts.

Figure 3

Q.	PLEASE SUMMARIZE THE RESULTS OF THE THREE GRAPHS.

A.	The revenue requirements of Vogtle 3 & 4 in nominal dollars significantly exceed that of natural gas combined cycle units over the entire 60-year operating life under all nine natural gas price and carbon dioxide emission price scenarios.

Q.	WHAT DO THE RESULTS OF A TRADITIONAL ECONOMIC ANALYSIS USING PRESENT VALUE DOLLAR RESULTS INDICATE?

A.	The revenue requirements for Vogtle 3 and 4 in cumulative present value dollars are greater than the revenue requirements for the combined cycle unit alternative in every year in all nine of the natural gas price and CO2 emission price cases.

Q.	WHAT IS THE REVENUE REQUIREMENT IN DOLLARS PER MEGAWATT HOUR OF VOGTLE 3 AND 4 VERSUS A COMBINED CYCLE UNIT?

A.	Staff estimates the total average dollars per megawatt hour revenue requirement of Vogtle 3&4 to be approximately $165/MWh compared to $85/MWh for the combined cycle unit based on the Mod gas $0/Ton CO2 forecast.

Q.	WHAT IS THE ECONOMIC BENEFIT OF VOGTLE UNITS 3 AND 4 OVER THE ENTIRE PROJECT LIFE CYCLE?

A.	The bar graph below illustrates the cumulative economic benefit of Vogtle Units 3 and 4 over project life cycle based on the Mod gas $0/Ton CO2 forecast. During the construction period the cumulative negative economic benefit increases as financing costs are recovered from ratepayers under the Nuclear Construction Cost Recovery (“NCCR”) tariff. The cumulative negative economic benefit continues to increase during operating life as the revenue requirement of Vogtle Units 3 and 4 significantly exceeds alternative combined cycle unit.

Figure 4

In summary, the Vogtle 3 & 4 revenue requirement exceeds the alternative combined cycle resource in every year and ratepayers will pay an additional $40 billion over the Units’ lifecycle (construction period and 60-year operating life) versus alternative combined cycle generation under mod gas and zero carbon dioxide emission price scenario.

Q.	IF A CARBON DIOXIDE EMISSION CHARGE IS ASSUMED, DO THE VOGTLE UNITS BECOME LOWER COST THAN ALTERNATIVE COMBINED CYCLE GENERATION OVER THE UNITS’ LIFECYCLE?

A.	No. Even assuming a price on carbon dioxide emissions, the cumulative revenue requirement of Vogtle Units 3 and 4 significantly exceeds the alternative combined cycle unit on a lifecycle basis.

Figure 5

Ratepayers will pay an additional $34 billion over the Units’ lifecycle (construction and 60-year operating life) versus alternative combined cycle generation under the mod gas and $10/Ton carbon dioxide emission price scenario. The annual Vogtle 3 & 4 revenue requirement exceeds alternative combined cycle generation in nearly every year except for the last couple years of 60 year operating life. In summary, carbon dioxide emission charges do not make the Units economic and the Units are still significantly uneconomic versus alternative combine cycle generation.

## Rate Impact

Q.	DID STAFF REVIEW THE COMPANY’S RATE IMPACT ANALYSIS PROVIDED ON PAGE 7 OF ITS VCM 26 REPORT?

A.	Yes.  Staff reviewed the Company’s analysis which shows a cumulative impact of approximately 10.1% in 2024 considering a $7.3 billion project cost.  Staff has performed its own analysis and believes that the cumulative rate impact would be closer to 12.8% if considering the full $9.5 billion of project cost that the Company can request to be included in base rates.

Figure 6: Staff vs. GPC Cumulative Rate Impact

Vogtle 3 and 4 would increase rates over the next 18 months by 8 percent according to Georgia Power and 11 percent under Staff’s assumptions.  This constitutes a significant amount of rate pressure for customers.

## Replacement Power Costs

Q.	DID STAFF REVIEW THE COMPANY’S REPLACEMENT POWER ANALYSIS PROVIDED IN TABLE 1.2 OF ITS VCM 26 REPORT?

A.	Yes. As described in Staff’s prior testimony, the premise underlying the table is fundamentally flawed as the Company ignores the additional financing cost recovered from ratepayers during the delay period that would not have been collected had the Units been completed on time. Furthermore, Table 1.2 is also flawed because the analysis improperly depicts the timing when operating expenses and PTC benefits will be incurred, which leads to the inaccurate conclusion that customers have only be harmed by $178.7 million to date. When the proper analysis is performed, during the full delay period of 2016 through 2023, Staff estimates the Company will collect $3.2 billion more from ratepayers due to the increase in NCCR tariff collections ($2.0 billion) and higher fuel charges ($1.2 billion) than what would have been collected had the Units been completed on time.

# RATEMAKING ISSUES

Q.	DID THE COMPANY’S MATERIALLY INACCURATE COST ESTIMATES IMPACT ITS AND STAFF’S ECONOMIC ANALYSES AT CERTIFICATION AND EACH VCM PROCEEDING?

A.	Yes. The Company grossly under-estimated the costs of Vogtle 3 and 4 in its filings and testimony to the Commission during at least the first thirteen years of the Project. This started at certification when the Company went so far as to testify that no contingency was needed despite the scope and magnitude of the Project. The Company provided eleven cost estimates (certification and ten revisions) prior to and during construction of the Project and at least the first ten were materially inaccurate. Due to the fact that the Company provided inaccurate cost information, both the Company’s and the Staff’s economic analyses, conclusions and recommendations were inaccurate. The Commission relied on the Company’s cost estimates and economic analyses to approve construction expenditures and to allow the Company to continue construction based on the materially inaccurate estimates of the incremental cost to complete and CODs.

The Company’s management is fundamentally responsible for the prudent planning and execution of this Project, including the cost and CODs, not only for planning purposes, but, as important, for implementation.

The Company’s management failed to properly plan and execute this Project, which has resulted in escalating cost overruns and repeated COD delays.  The Company’s management is responsible for the execution of the Project, including the engineering, fabrication and procurement of components, construction, commissioning and start-up.  These responsibilities belong exclusively to the Company’s management, not to the Commission and not to the Company’s customers.

A fundamental responsibility of the Company management is to develop and provide accurate cost estimates in accordance with the requisite knowledge and skills necessary to construct this Project at a reasonable cost and in a timely manner.  The Company’s management failed to do so from the beginning in the Certification proceeding and throughout the construction period. The repeated materially inaccurate cost estimates are an example of management’s continuous poor judgement over the life of the Project that should be taken into account when the Commission conducts its prudence review.

Q.	PLEASE PROVIDE EXAMPLES OF MANAGEMENT’S POOR JUDGMENT.

A.	Management was aware of the Company’s poor performance on Vogtle Units 1 and 2. Plant McDonough Units 4 – 6 was a much more straightforward generation construction project yet the Company incurred 24 percent cost overrun. This experience should have resulted in a more diligent management oversight of Units 3 and 4. The Company made numerous claims about the protections of the EPC Agreement at certification that turned out to be exaggerated. The Company made claims that they were actively managing the Consortium only to later say that they couldn’t be held accountable for the problems before Southern Nuclear was managing the project.  Project management experienced delays and cost overruns from the very beginning of the Project with promises to rectify the situation with mitigation plans that were ineffective. For years management continuously made representations to the Commission of improvements to cost estimates and schedule that never happened. It is management’s responsibility to execute and fulfill the representations made to the Commission, and management’s failure to do so has resulted in billions of dollars of overruns.

Q.	PLEASE PROVIDE ANOTHER EXAMPLE OF MANAGEMENT’S FAILURES.

A.	Effective management would understand its own capabilities and those of its contractors or agents. Management’s performance indicates this was never the case. Management consistently overestimated the ability and performance of its agents and contractors and its ability to provide effective oversight. This occurred when the EPC Agreement with the Consortium was in effect and continued when Southern Nuclear took over the Project in 2017.

Q.	PLEASE PROVIDE ANOTHER EXAMPLE OF MANAGEMENT’S FAILURES.

A.	Management never had a complete and comprehensive schedule with realistic assumptions about duration of activities. A complete and comprehensive schedule is the cornerstone of an accurate estimate. Management made cost representations to the Commission for years without a complete and comprehensive schedule. This management failure should be taken into account when the Company requests cost recovery.

Q.	YOU NOTED PREVIOUSLY THAT THE COMPANY STATES IT MAY SEEK RECOVERY OF THE CONSTRUCTION/CAPITAL COSTS IN EXCESS OF THE APPROVED $7.3 BILLION CAPITAL COST AS EARLY AS THE PRUDENCE REVIEW CONTEMPLATED BY THE VCM 17 ORDER.  DO YOU HAVE ANY COMMENTS?

A.	Yes.  First, Staff plans to conduct an extensive prudence review that includes reviewing the Company’s planning and its execution of the Project. The test of prudence is whether the Company’s actions were reasonable based on what it knew or a reasonable person with requisite industry skills and knowledge should have known in its planning and its execution of the Project.  The Commission will be the arbiter of prudence and also will determine the prudent and reasonable cost that will be recovered from the Company’s customers.

Second, Staff notes that the prudence review is not limited to the costs above $7.3 billion. The Commission has made no determination of prudence on any costs over $3.5 billion.  The costs between $3.5 billion and $5.68 billion are only presumed prudent; however, these costs remain subject to challenge for imprudence by parties other than the Company, who have the burden to prove imprudence.  The costs above $5.68 billion are not presumed prudent and the Company has the burden to prove that the costs are prudent. Costs above $7.3 billion are not presumed prudent or reasonable and the Company has the burden to prove that they are both prudent and reasonable. Further, the Commission can review financing and AFUDC costs in the prudence review, even financing costs that have already been recovered from ratepayers through the NCCR tariff. The only financing costs that are presumed prudent are those incurred through the NCCR prior to December 31, 2019 for Unit 3 and December 31, 2020 for Unit 4.

Third, Staff has assiduously documented the Company’s executive and site management failures that have resulted in the multi-year schedule delays and multibillion-dollar cost overruns. These failures have contributed not only to the construction/capital cost increases in excess of the approved costs, but also to the cost increases in excess of the deemed prudent costs.  The construction/capital cost increases and schedule delays also have contributed to the increase in financing costs recovered through the NCCR tariff and deferred financing cost accrued to AFUDC, which has compounded the harm to ratepayers from the Company’s delays and cost increases.

Fourth, the Staff panel of Steve Roetger, Bill Jacobs, and Don Grace provides an overview of the Company’s project management failures that Staff likely will address in greater detail in the prudence review.

Q.	DOES THIS CONCLUDE YOUR TESTIMONY?

A.	Yes.

BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S TWENTY-SIXTH SEMI-ANNUAL VOGTLE CONSTRUCTION MONITORING REPORT | DOCKET NO. 29849 |
| --- | --- |

|  | EXHIBIT |  |
| --- | --- | --- |
|  | STF-NHK-1 |  |

Summary of Educational and Professional Experience of Tom J. Newsome

Mr. Newsome received a Bachelor of Chemical Engineering with certificates in Pulp & Paper and Polymers from the Georgia Institute of Technology in June 1986.  In 1994, Mr. Newsome passed both required examinations and received a professional engineering license (PE) from the State of North Carolina. Mr. Newsome received a Master of Science in Business Economics and a Master of Science in Finance from Georgia State University in August 1996 and June 1997, respectively. Mr. Newsome is the recipient of the George J. Malanos Graduate Award for Academic Excellence for completing the finance program with a 4.0 grade-point average. In 2003, Mr. Newsome received Chartered Financial Analyst (CFA) designation from the CFA Institute after successfully completing three six-hour examinations on security analysis and portfolio management.

After graduation from Georgia Tech, Mr. Newsome worked as plant/process engineer for Shaw Industries, a carpet manufacturer. In April 1988, Mr. Newsome joined Weatherly, Inc., engineering and construction firm specializing in fertilizer plants, as a process engineer. Mr. Newsome’s primary responsibilities were process design and plant start-ups, including start-ups in Korea and India. Mr. Newsome joined Midrex Direction Reduction Corp., an applied research, engineering and construction firm with proprietary iron ore processing plant technology in March 1993 as a process engineer. Mr. Newsome duties were similar to those at Weatherly, including assisting in the start-up of the world’s largest Direct Reduction Iron plant in India.

Following graduation from graduate school at Georgia State, Mr. Newsome joined Georgia Gulf Corporation in 1997 as a corporate development analyst. While at Georgia Gulf, Mr. Newsome performed financial analysis and modeling for natural gas purchasing/hedging program, developed a “make-or-buy” model for methanol business, performed financial modeling for an acquisition, and calculated and summarized the financial performance of prior capital investments. In 1999, Mr. Newsome joined FMV Opinions, Inc. as a business valuation analyst and valued private companies for gift and estate tax, transactional and management planning purposes.

Mr. Newsome joined the Georgia Public Service Commission (“Commission”) in January 2005 as a Financial Analyst/Economist. Mr. Newsome was promoted to Director of Utility Finance in 2008.

Mr. Newsome has testified in twenty Georgia Power Company (“Company” or “Georgia Power”) proceedings before the Commission.  Mr. Newsome’s most recent testimony was in Docket 44160 Integrated Resources Planning on supply side resources. Prior to that Mr. Newsome testified in Docket 29849 23rd Vogtle Construction Monitoring (“VCM”), 24th VCM and 25th VCM on Vogtle economics. Prior to that was testimony in 22nd VCM and in Docket 43011 Fuel Cost Recovery (FCR-25) on the Company’s hedging program and certain other issues. Prior to that Mr. Newsome’s testified in Docket 29849 20th / 21st Vogtle Construction Monitoring (“VCM”) on Vogtle economics. Prior to that Mr. Newsome’s testified in Docket 42310 Georgia Power Company’s 2019 Integrated Resource Plan on supply side and certain other issues. Prior to that testimony Mr. Newsome testified in Docket 29849 19th Vogtle Construction Monitoring (“VCM”), 18th VCM and 17th VCM on the economics of continuing Vogtle 3 and 4 construction and provided the Commission policy recommendations to protect ratepayers. Prior to testifying in the 17th VCM Mr. Newsome testified in the 2016 Integrated Resource Plan on the Company’s requested to capitalize cost for investigation of new nuclear units. Mr. Newsome’s testified in Docket No. 39638 Fuel Cost Recovery (FCR-24) on the Company’s natural gas hedging program. In Docket No. 22403, Mr. Newsome addressed Georgia Power Company’s natural gas hedging program and in Docket No. 24506 Mr. Newsome testified on the application of AFUDC accounting for calculating financing cost of capital projects. In Docket No. 27800, Certification of Plant Vogtle Expansion, Mr. Newsome addressed the sources, impact and mitigation of financial risk from the construction and operation of new nuclear units at Plant Vogtle.  Mr. Newsome testified in Docket No. 29849 concerning Georgia Power’s First Semi-annual Construction Monitoring Report on Plant Vogtle expansion.  Mr. Newsome evaluated the economic analysis performed by Georgia Power and developed Staff’s own independent economic and risk analysis of the Project. In the Second Vogtle Semi-annual hearing, Mr. Newsome testified on the Company’s proposal to change how escalation on certain project cost was calculated (Amendment 3).  In the Third Vogtle Semiannual hearing and in separate proceeding, Adoption of a Risk Sharing Mechanism, Mr. Newsome testified on Staff’s revised risk sharing mechanism for Vogtle 3 & 4.  In Docket No. 28945 Fuel Cost Recovery FCR–21, Mr. Newsome testified on seasonal rates.  Mr. Newsome also presented cost of equity testimony in Atmos Energy Corporation’s Rate Case in Docket No. 30442 and Generic Proceeding to Implement House Bill 168 (small telephone companies) in Docket No. 32235 in 2011 and 2018. Mr. Newsome provided testimony before the Commission in Georgia Power’s 2013 Base Rate Case in Docket No. 36989 on the Company’s projected cost of debt for 2014 – 2016. Mr. Newsome’s primarily responsibility, prior to presenting testimony in these dockets, has been performing analyses of the parties’ cost of equity capital positions in Docket Nos. 18638 (Atlanta Gas Light Company 2004/2005 Rate Case), 19758 (Savannah Electric and Power Company 2004 Rate Case), 20298 (Atmos Energy Corporation - Georgia Division 2005 Rate Case), 25060 (Georgia Power Co. 2007 Rate Case) and 27163 (Atmos Energy Corporation - Georgia Division 2008 Rate Case) and developing the Advisory PIA Staff’s cost of equity recommendation to the Commission.

BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S TWENTY-SIXTH SEMI-ANNUAL VOGTLE CONSTRUCTION MONITORING (“VCM”) REPORT | DOCKET NO. 29849 |
| --- | --- |

|  | EXHIBIT |  |
| --- | --- | --- |
|  | STF-NHK-2 |  |

EDUCATION/CERTIFICATION

M.S., Electrical Engineering, Georgia Institute of Technology, 1980

B.S., Electrical Engineering, Purdue University, 1979

Cooperative Education Certificate, Purdue University, 1979

PROFESSIONAL AFFILIATIONS

National Society of Professional Engineers

Georgia Society of Professional Engineers

Institute of Electrical and Electronic Engineers

EXPERIENCE

Since completing his Master’s program, Mr. Hayet worked for fifteen years at Energy Management Associates, now Ventyx, providing consulting services and client service support to electric utility companies for the widely used planning models, PROMOD IV and STRATEGIST.  Mr. Hayet had an instrumental role in designing some of the modeling features of those tools including the competitive market modeling logic in STRATEGIST.

In 1995, Mr. Hayet formed the utility consulting firm, Hayet Power Systems Consulting (“HPSC”), and worked for customers in the United States, and internationally in Australia, Japan, Singapore, Malaysia, the United Kingdom, and Vietnam.  Mr. Hayet provided consulting services to Public Utility Commissions, Regional Power Pools, State Energy Offices, Consumer Advocate Offices, Electric Utilities, Global Power Developers, and Industrial Companies.  Mr. Hayet’s expertise covers a number of areas including utility system planning and operations, RTO analysis, market price forecasting, Integrated Resource Planning, renewable resource evaluation, transmission planning, demand-side analysis, and economic analysis.

In 2000, Mr. Hayet also joined the consulting firm of J. Kennedy & Associates, Inc. (“Kennedy and Associates”) and assisted on projects that required utility resource planning, analysis, and software modeling expertise.  Mr. Hayet merged his firm and became a Vice-President and Principal of Kennedy and Associates in 2015.

Mr. Hayet has conducted numerous consulting studies in the areas of RTO Cost/Benefit Analysis, Renewable Resource Evaluation, Renewable Portfolio Standards Evaluation, Electric Market Price Forecasting, Generating Unit Cost/Benefit Analysis, Integrated Resource Planning, Demand-Side Management, Load Forecasting, Rate Case Analysis and Regulatory Support.

2000 to	J. Kennedy and Associates, Inc.

Present:	Vice President and Principal

- Initially began as Director of Consulting, became Vice President and Principal in 2015

- Managed electric related consulting projects.

- Responsible for business development.

- Clients include Staffs of Public Utility Commissions and other State Agencies, State Energy Offices, Global Power Developers, and Industrial Groups, and large energy users.

1996 to	Hayet Power Systems Consulting

Present:	President and Principal

- Managed electric utility related consulting projects

- Clients include Staffs of Public Utility Commissions and other State Agencies, State Energy Offices, Global Power Developers, and Industrial Groups, and large energy users.

1991 to	EDS Utilities Division, Atlanta, GA (Now Ventyx)

1996:		Lead Consultant, PROSCREEN (Now STRATEGIST) Department

- Managed a client services software team that supported approximately 75 users of the STRATEGIST electric utility strategic planning software.

- Participated in the development of STRATEGIST’s competitive market modeling features and the Network Economy Interchange Module

- Provided client management direction and support, and developed new consulting business opportunities.

- Performed system planning consulting studies including integrated resource planning, DSM analysis, marketing profitability studies, optimal reserve margin analyses, etc.

- Based on experience with PROMOD IV, converted numerous PROMOD IV databases to STRATEGIST, and performed benchmark analyses of the two models.

1988 to 	Energy Management Associates (EMA), Atlanta, GA

1991:		Manager, Production Analysis Department

- Served as Project Manager of a database modeling effort to create an integrated utility operations and generation planning database.  Database items were automatically fed into PROMOD IV.

- Supervised and directed a staff of five software developers working with a 4GL database programming language.

- Interfaced with clients to determine system software specifications, and provide ongoing client training and support

1980 to	Energy Management Associates (EMA), Atlanta, GA

1988:		Senior Consultant, PROMOD IV Department

- Provided client service support to EMA’s base of over 70 electric utility customers using the PROMOD IV probabilistic production cost simulation software.

- Provided consulting services in a number of areas including generation resource planning, regulatory support, and benchmarking.

TESTIMONY AND EXPERT WITNESS APPEARANCES

| Date | Case | Jurisdict |  | Party | Utility | Subject |
| --- | --- | --- | --- | --- | --- | --- |
| 09/98 | 97-035-01 | UT |  | Utah Committee for Consumer Services | PacifiCorp | Utah jurisdictional Net Power Costs, PacifiCorp Rate Case Proceeding |
| 07/01 | 01-035-01 | UT |  | Utah Committee for Consumer Services | PacifiCorp | Utah Jurisdictional Net Power costs in General Rate Case |
| 2001 | ER00-2854-000 | FERC |  | Louisiana Public Service Commission | Entergy | Proposed System Agreement Modifications |
| 07/02 | 02-035-002 | UT |  | Utah Committee for Consumer Services | PacifiCorp | Special contract for industrial consumer |
| 2002/2003 | U-25888 | LA |  | Louisiana Public Service Commission | Entergy | Investigation of retail issues related to the System Agreement |
| 2003 | U-27136 Subdocket A | LA |  | Louisiana Public Service Commission Staff | Entergy | Aging gas steam-fired retirement study |
| 07/03 | EL01-88-000 | FERC |  | Louisiana Public Service Commission | Entergy | Rough production cost equalization proceeding |
| 05/04 | 03-035-14 | UT |  | Utah Committee for Consumer Services | PacifiCorp | Development of a large QF avoided cost methodology |
| 06/04 | 18687-U 18688-U | GA |  | Georgia Public Service Commission Staff | Georgia Power and Savannah Electric | 2004 Integrated Resource Planning Studies |
| 08/04 | ER03-583-000 | FERC |  | Louisiana Public Service Commission | Entergy | Affiliate power purchase agreements |
| 11/04 | 03-035-19 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Industrial customer’s request for a special economic development tariff |
| 11/04 | 03-035-38 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Large QF proceeding. |
| 03/05 | 03-035-14 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Concerning PacifiCorp’s Schedule 38 avoided cost tariff and remaining unsubscribed capacity |
| 07/05 | 03-035-14 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Concerning PacifiCorp’s Schedule 38 avoided cost proceeding |
| 12/05 | 04-035-42 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Net power costs in General Rate Case |
| 04/06 | 05-035-54 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Certification request to expand Blundell Geothermal Power Station. Related to Mid-American Energy Holding’s Acquisition of PacifiCorp |
| 05/06 | 22403-U | GA | Georgia Public Service Commission Staff |  | Georgia Power and Savannah Electric | March 2006 fuel cost recovery filing |
| 2006 | 06-35-01 | UT | Utah Committee for Consumer Services |  | PacifiCorp | 2006 rate case, net power costs |
| 08/06 | U-21453 | LA | Louisiana Public Service Commission Staff |  | Entergy Gulf States | Jurisdictional separation. |
| 11/06 | U-25116 | LA | Louisiana Public Service Commission Staff |  | Entergy Louisiana | Fuel adjustment clause filings |
| 01/07 | 23540-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | November 2005 fuel cost recovery filing |
| 04/07 | 07-035-93 | UT | Utah Committee for Consumer Services |  | PacifiCorp | General Rate Case |
| 06/07 | 24505-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | 2007 Integrated Resource Planning |
| 10/07 | U-30334 | LA | Louisiana Public Service Commission Staff |  | Cleco Power | 2008 Short-Term RFP |
| 04/08 | 26794-U (FCR-20) | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fuel cost recovery filing |
| 2008 | 6630-CE-299 | WI | Wisconsin Industrial Energy Group, Inc. |  | WEPCO | Certification Proceeding for environmental upgrades at Oak Creek power plant |
| 07/08 | ER07-956 | FERC | Louisiana Public Service Commission |  | Entergy | 2006 rough production cost equalization compliance filing in the System Agreement case |
| 09/08 | 6680-CE-180 | WI | Wisconsin Industrial Energy Group, Inc. |  | Wisconsin Power and Light | Certification proceeding concerning Nelson-Dewey coal-fired generating unit |
| 11/08 | 08-1511-E-GI | WV | West Virginia Energy Users Group |  | Allegheny Power | Fuel cost recovery filing |
| 12/08 | 27800-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Vogtle 3 and 4 nuclear unit certification proceeding |
| 2008 | 08-035-35 | UT | Utah Committee for Consumer Services |  | PacifiCorp | Chehalis Combine Cycle Power Plant based on a waiver of the RFP solicitation process certification proceeding |
| 07/09 | ER08-1056 | FERC | Louisiana Public Service Commission |  | Entergy | 2007 rough production cost equalization compliance filing in the System Agreement case |
| 07/09 | U-30975 | LA | Louisiana Public Service Commission Staff |  | SWEPCO and Cleco | Application to acquire the Oxbow Mine to supply Dolet Hills Power Station certification proceeding |
| 09/09 | E015/PA-09-526 | MN | Large Power Intervenors |  | Minnesota Power | Request for approval to purchase Square Butte’s 500 kV DC transmission line, restructure a coal based power purchase agreement |
| 09/09 | 09-035-23 Direct | UT | Utah Office of Consumer Services |  | PacifiCorp | 2009 rate case, net power costs |
| 10/09 | 09A-415E | CO | Public Utilities Commission of Colorado |  | Black Hills/Colorado | CPCN application to construct two LMS 100 natural gas combustion turbine units |
| 10/09 | 09-035-23 Surrebuttal | UT | Utah Office of Consumer Services |  | PacifiCorp | 2009 rate case, net power costs |
| 12/09 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | First Semi-Annual Vogtle Construction Monitoring Report |
| 12/09 | ER08-1224 | FERC | Louisiana Public Service Commission |  | Entergy | 2008 production costs used to develop bandwidth payments |
| 2009 | 09-2035-01 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2008 IRP |
| 01/10 | 28945-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fuel cost recovery filing |
| 2010 | EL09-61 | FERC | Louisiana Public Service Commission |  | Entergy | System Agreement, individual operating company sales |
| 06/10 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Second Semi-Annual Vogtle Construction Monitoring Report |
| 12/10 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Third Semi-Annual Vogtle Construction Monitoring Report |
| 01/11 | ER09-1350 Direct | FERC | Louisiana Public Service Commission |  | Entergy | 2008 production costs used to develop bandwidth payments |
| 02/11 | ER09-1350 Cross-Answering | FERC | Louisiana Public Service Commission |  | Entergy | 2008 production costs used to develop bandwidth payments |
| 04/11 | 33302-U (FCR-22) | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fuel cost recovery filing |
| 06/11 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fourth Semi-Annual Vogtle Construction Monitoring Report |
| 09/11 | U-31892 | LA | Louisiana Public Service Commission Staff |  | Cleco Power | Settlement agreement, CPCN to upgrade Madison 3 coal unit to accommodate biomass fuel |
| 11/11 | 26550-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Reacquisition of wholesale block capacity |
| 11/11 | 34218-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Decertification of two aging coal units, acquire PPA resources, approve IRP update |
| 12/11 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fifth Semi-Annual Vogtle Construction Monitoring Report |
| 03/12 | U-32148 | LA | Louisiana Public Service Commission Staff |  | Entergy | Change of Control Proceeding to move to Midwest ISO |
| 2012 | 20000-EA-400-11 | WY | Wyoming Industrial Energy Consumers |  | Rocky Mountain Power | Certification of environmental upgrades at Naughton 3 |
| 05/12 | 35277-U (FCR-23) | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fuel cost recovery filing |
| 05/12 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Sixth Semi-Annual Vogtle Construction Monitoring Report |
| 07/12 | 2012-00063 | KY | Kentucky Industrial Utility Customers, Inc. |  | Big Rivers | Environmental upgrades in compliance with MATS and CSAPR |
| 09/12 | U-32275 | LA | Louisiana Public Service Commission Staff |  | Dixie Electric Member Cooperative | Ten year power supply acquisition certification proceeding |
| 12/12 | EL09-61-002 Direct | FERC | Louisiana Public Service Commission |  | Entergy | Harm calculation, violation of System Agreement |
| 12/12 | U-32557 | LA | Louisiana Public Service Commission Staff |  | Entergy | Certification of 28 MW PPA for renewable energy capacity (RAIN waste heat) in accordance with LPSC’s Renewable Energy Pilot |
| 12/12 | U-29764 | LA | Louisiana Public Service Commission Staff |  | Entergy | Retail proceeding regarding termination of cross-PPAs |
| 12/12 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Seventh Semi-Annual Vogtle Construction Monitoring Report |
| 03/13 | EL09-61-002 Cross-Answering | FERC | Louisiana Public Service Commission |  | Entergy | Harm calculation, violation of System Agreement |
| 04/13 | 2012-00578 | KY | Kentucky Industrial Utility Customers, Inc. |  | Kentucky Power Company | Mitchell Certificate of Public Convenience and Necessity |
| 05/13 | 36498-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | 2013 IRP and request to decertify over 2,000 MW of coal-fired capacity |
| 07/13 | U-32785 | LA | Louisiana Public Service Commission Staff |  | Entergy | 8.5 MW PPA for renewable energy capacity (Agrilectric rice hull) in accordance with LPSC’s Renewable Energy Pilot |
| 08/13 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Eighth Semi-Annual Vogtle Construction Monitoring Report |
| 10/13 | 2013-00199 | KY | Kentucky Industrial Utility Customers, Inc. |  | Big Rivers | Base rate case |
| 05/14 | 13-035-184 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2014 General Rate Case, net power cost |
| 06/14 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Ninth/Tenth Semi-Annual Vogtle Construction Monitoring Report |
| 07/14 | 20000-446-EA-14 | WY | Wyoming Industrial Energy Consumers |  | PacifiCorp | 2014 General Rate Case, net power cost |
| 08/14 | 2000-447-EA-14 | WY | Wyoming Industrial Energy Consumers |  | PacifiCorp | 2014 Energy Cost Adjustment Mechanism application |
| 08/14 | 14-035-31 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2014 Energy Balancing Adjustment application |
| 09/14 | ER13-432 | FERC | Louisiana Public Service Commission |  | Entergy | Allocation of Union Pacific Settlement Agreement benefits |
| 10/14 | 2014-00225 | KY | Kentucky Industrial Utility Customers, Inc. |  | Kentucky Power | Kentucky Power Company’s Fuel Adjustment Clause |
| 12/14 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Eleventh Semi-Annual Vogtle Construction Monitoring Report |
| 05/15 | 14-035-140 | UT | Utah Office of Consumer Services |  | PacifiCorp | Solar and wind capacity contribution avoided cost proceeding. |
| 06/15 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Twelfth Semi-Annual Vogtle Construction Monitoring Report |
| 08/15 | 15-035-03 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2015 Energy Balancing Adjustment application |
| 09/15 | 14-035-114 | UT | Utah Office of Consumer Services |  | PacifiCorp | Cost and Benefits of PacifiCorp’s Net Metering Program |
| 11/15 | 39638-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | FCR-24 Fuel Cost Recovery Proceeding |
| 11/15 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Thirteenth Semi-Annual Vogtle Construction Monitoring Report |
| 5/16 | 40161 | GA | Georgia Public Service Commission Staff |  | Georgia Power | Georgia Power Company’s 2016 IRP and Application for Decertification of Plant Mitchell Units 3, 4A, and 4B, Kraft Unit 1 CT, and Intercession City CT |
| 6/16 | 29849 | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fourteenth Semi-Annual Vogtle Construction Monitoring Report |
| 8/16 | 16-035-27 | UT | Utah Office of Consumer Services |  | PacifiCorp | Renewable Energy Services Contract between Rocky Mountain Power and Facebook, Inc |
| 8/16 | 16-035-01 | UT | Utah Office of Consumer Services |  | PacifiCorp | 2016 Energy Balancing Adjustment application |
| 9/16 | 09-035-15 | UT | Utah Office of Consumer Services |  | PacifiCorp | EBA Pilot Evaluation Direct Testimony |
| 11/16 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Fifteenth Semi-Annual Vogtle Construction Monitoring Report |
| 11/16 | 09-035-15 | UT | Utah Office of Consumer Services |  | PacifiCorp | EBA Pilot Evaluation Rebuttal Testimony |
| 11/16 | EL09-61-04 | FERC | Louisiana Public Service Commission |  | Entergy | Violation of System Agreement, Phase III, Harm Calculation, Direct |
| 3/17 | EL09-61-04 | FERC | Louisiana Public Service Commission |  | Entergy | Violation of System Agreement, Phase III, Harm Calculation, Rebuttal |
| 6/17 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Sixteenth Semi-Annual Vogtle Construction Monitoring Report |
| 9/17 | 17-035-39 | UT | Utah Office of Consumer Services |  | PacifiCorp | Approval of Resource Decision to Repower Wind Facilities, Direct |
| 11/17 | 17-035-39 | UT | Utah Office of Consumer Services |  | PacifiCorp | Approval of Resource Decision to Repower Wind Facilities, Surrebuttal |
| 4/18 | 17-035-39 | UT | Utah Office of Consumer Services |  | PacifiCorp | Approval of Resource Decision to Repower Wind Facilities, Response |
| 4/18 | 17-035-39 | UT | Utah Office of Consumer Services |  | PacifiCorp | Approval of Resource Decision to Repower Wind Facilities, Rebuttal to Response |
| 12/17 | 17-035-40 | UT | Utah Office of Consumer Services |  | PacifiCorp | Approval of Resource Decision for New Wind and New Transmission, Direct |
| 1/18 | 17-035-40 | UT | Utah Office of Consumer Services |  | PacifiCorp | Approval of Resource Decision for New Wind and New Transmission, Rebuttal |
| 4/18 | 17-035-40 | UT | Utah Office of Consumer Services |  | PacifiCorp | Approval of Resource Decision for New Wind and New Transmission, Second Rebuttal |
| 6/18 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Eighteenth Semi-Annual Vogtle Construction Monitoring Report |
| 8/18 | Cause 45052 | IN | Indiana Coal Council |  | Vectren Energy Delivery of Indiana | Request for Approval of an 850 MW CCGT Plant |
| 9/18 | U-34836 | LA | Louisiana Public Service Commission Staff |  | Entergy Louisiana, LLC | Authorization to Participate in a 50 MW Solar PPA |
| 11/18 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Nineteenth Semi-Annual Vogtle Construction Monitoring Report |
| 1/19 | U-35019 | LA | Louisiana Public Service Commission Staff |  | Entergy Louisiana | Authorization to Make Available Experimental Renewable Option and Rate Schedule RTO |
| 4/19 | 42310-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Georgia Power’s 2019 IRP Proceeding |
| 11/19 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Twenty/Twenty-First Semi-Annual Vogtle Construction Monitoring Report |
| 5/20 | 43011-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Georgia Power Fuel Cost Recovery Application (FCR-25) |
| 6/20 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Twenty-Second Semi-Annual Vogtle Construction Monitoring Report |
| 7/20 | 17-035-61 | UT | Utah Office of Consumer Services |  | Rocky Mountain Power | Approval of an Export Credit Rate for Customer Generators (Primarily Rooftop Solar) |
| 9/20 | 20-035-04 | UT | Utah Office of Consumer Services |  | Rocky Mountain Power | Utah Rate Case |
| 10/20 | 2019-226-E | SC | South Carolina Office of Regulatory Services |  | Dominion Energy South Carolina | Review of DESC’s 2020 IRP |
| 10/20 | 2019-227-E | SC | South Carolina Office of Regulatory Services |  | Lockhart Power Company | Review of Lockhart Power Company’s 2020 IRP |
| 11/20 | 29849-U | GA | Georgia Public Service Commission Staff |  | Georgia Power | Twenty-Third Semi-Annual Vogtle Construction Monitoring Report |
| 12/20 | 20-035-01 | UT | Utah Office of Consumer Services |  | Rocky Mountain Power | Application for Approval of the 2020 Energy Balancing Account |
| 2/21 | 2019-224 and 225-E | SC | South Carolina Office of Regulatory Services |  | Duke Energy Carolinas and Duke Energy Progress | Review of Duke Energy’s 2020 IRP |

ADDITIONAL JUDICIAL PROCEEDINGS AND OTHER PROJECT INFORMATION

- 1995 – 2000 - Modeled the Singapore Power Electricity System and analyzed the benefits of dispatching a new oil-fired unit within the system, BHP Power

- 1995 – 2000 - Modeled the Australian National Energy Market to develop market based energy price forecasts on behalf of an Independent Power Producer in Australia, BHP Power

- 1995 – 2000 - Analyzed the benefit of purchasing existing gas-fired steam turbine units within the Australian market, BHP Power

- 1995 – 2000 Developed market price forecasts for South Australia as part of the evaluation of a new gas fired combined cycle unit, BHP Power

- 1995 – 2000 - Modeled the Vietnam Electricity System as part of a project to develop Least Cost Expansion plans for Vietnam, EVN State Utility

- 1995 – 2000 - Assisted in the evaluation of Phu My CCGT power  plant  in Vietnam, BHP Power

- 1995 – 2000 - Assisted in the development of Market Price Forecasts in several regions of the US.  These forecasts were used as the basis for stranded cost estimates, which were filed in testimony in a number of jurisdictions across the country.

- 1995 – 2000 - Conducted research regarding ISO Tariffs and Operations for the PJM Power Pool, the California ISO, and the Midwest ISO on behalf of a Japanese Research.

- 1995 – 2000 - Performed research on numerous electric utility issues for 3 Japanese research organizations.  This was primarily related to deregulation issues in the US in anticipation of deregulation being introduced in Japan.

- 1995 – 2000 - Critiqued the IRP filings of 5 utilities in South Carolina on behalf of the South Carolina State Energy Office

- 1999 - Helped to analyze the rate structure and develop an electricity price forecast for the Metropolitan Atlanta Rapid Transit Authority (MARTA) in Atlanta, Georgia

- August 2002 – Expert Report, Civil Action No. 1:00-cv-1262 in the United Stated District Court for the Middle District of North Carolina, United States v. Duke Energy Corporation, Department of Justice

- 2002 - Worked on behalf of the Utah Committee of Consumer Services to provide guidance and assist in the analysis of PacifiCorp’s 2002 Integrated Resource Plan.

- July 2003 - Worked on behalf of the Oregon Public Utility Commission to Audit PacifiCorp’s Net Power Costs per a Settlement Agreement accepted by the Public Utility Commission of Oregon in its Order No. 01-787.  Audit report in Docket No. UE-116 filed July 2003.

- 2003 - Regulatory support to the Utah Committee of Consumer Services regarding PacifiCorp’s 2003 Utah General Rate Case Docket # 03-2035-02.

- 2004 – Assistance to the Utah Committee of Consumer Services to analyze a series of power purchase agreements and special contracts between PacifiCorp and several of its industrial customers.

- 2005 - Worked on behalf of the Utah Committee of Consumer Services to help analyze PacifiCorp’s restructuring proposals.

- 2005 - Assisted the Utah Committee of Consumer Services by evaluating PacifiCorp’s 2005 IRP and assisted in writing comments that were filed with the Commission.

- 2007 - Assisted the Utah Committee of Consumer Services to evaluate PacifiCorp’s 2007 IRP.

- 2007 - Conducted an investigation of the Southern Company interchange accounting and fuel accounting practices on behalf of the Georgia Public Service Commission Staff (Docket 21162-U).

- 2008 - Assisted the Louisiana Public Service Commission Staff with the review and evaluation of Cleco Power’s 2008 Short Term RFP and its 2010 Long-Term RFP.

- 2008 - Assisted the Utah Committee of Consumer Services by participating in a collaborative process to develop an avoided cost tariff for large QFs.

- 2008 - Assisted the Louisiana Public Service Commission Staff with a rulemaking for the opportunity to implement a Renewable Portfolio Standard in Louisiana. (Docket No. R-28271 Sub-Docket B)

- April 2011 – Initial Expert Report, Civil Action No. 2:10-cv-13101-BAF-RSW, on behalf of the Department of Justice in US District Court, United States v.Detroit Edison

- June 2011 – Rebuttal Expert Report, Civil Action No. 2:10-cv-13101-BAF-RSW, on behalf of the Department of Justice in US District Court, United States Detroit Edison

- 2011 - Assisted the Georgia Public Service Commission Staff to investigate the acquisition of additional coal and combustion turbine capacity currently wholesale capacity (Docket 26550).

- 2012 - Assisted the Louisiana Public Service Commission Staff with a rulemaking to design Integrated Resource Planning (“IRP”) rules. (Docket No. R-30021)

- December 2013 – Expert Report, Civil action no. 4:11-cv-00077-RWS, on behalf of the Department of Justice in US District Court, United States v. Ameren Missouri.

PUBLICATIONS AND PRESENTATIONS

Co-authored “Review of EPA’s Section 111(d) CO2 Emission Rate Goals for the State of Montana, on behalf of the Montana Large Customer Group, October 2014.

Authored “Singapore’s Developing Power Market”, which appeared in the July/August 1999 edition of Power Value Magazine

Co-authored “The New Energy Services Industry – Part 1”, which appeared in the January/February 1999 edition of Power Value Magazine.

Co-authored and Presented “Evaluation of a Large Number of Demand-Side Measures in the IRP Process: Florida Power Corporation’s Experience”, Presented at the 3rd International Energy and DSM Conference, Vancouver British Columbia, November 1994

Co-authored “Impact of DSM Program on Delmarva’s Integrated Resource Plan”, Published in the 4th International Energy and DSM Conference Proceedings, held in Berlin, Germany, 1995

Presentation – Law Seminars International, Electric Utility Rate Cases, Case Study of the Louisiana Public Service Commission’s Quick Start Energy Efficiency Program, March 2015.

BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S TWENTY-SIXTH SEMI-ANNUAL VOGTLE CONSTRUCTION MONITORING REPORT | DOCKET NO. 29849 |
| --- | --- |

|  | EXHIBIT |  |
| --- | --- | --- |
|  | STF-NHK-3 |  |

EDUCATION

University of Toledo, BBA

Accounting

University of Toledo, MBA

Luther Rice University, MA

PROFESSIONAL CERTIFICATIONS

Certified Public Accountant (CPA)

Certified Management Accountant (CMA)

PROFESSIONAL AFFILIATIONS

American Institute of Certified Public Accountants

Georgia Society of Certified Public Accountants

Institute of Management Accountants

Society of Depreciation Professionals

Mr. Kollen has more than thirty years of utility industry experience in the financial, rate, tax, and planning areas.  He specializes in revenue requirements analyses, taxes, evaluation of rate and financial impacts of traditional and nontraditional ratemaking, utility mergers/acquisition and diversification.  Mr. Kollen has expertise in proprietary and nonproprietary software systems used by utilities for budgeting, rate case support and strategic and financial planning.

EXPERIENCE

1986 to

Present:	J. Kennedy and Associates, Inc.:  Vice President and Principal.  Responsible for utility stranded cost analysis, revenue requirements analysis, cash flow projections and solvency, financial and cash effects of traditional and nontraditional ratemaking, and research, speaking and writing on the effects of tax law changes.  Testimony before Connecticut, Florida, Georgia, Indiana, Louisiana, Kentucky, Maine, Maryland, Minnesota, New York, North Carolina, Ohio, Pennsylvania, Tennessee, Texas, West Virginia and Wisconsin state regulatory commissions and the Federal Energy Regulatory Commission.

1983 to

1986:		Energy Management Associates:  Lead Consultant.

Consulting in the areas of strategic and financial planning, traditional and nontraditional ratemaking, rate case support and testimony, diversification and generation expansion planning.  Directed consulting and software development projects utilizing PROSCREEN II and ACUMEN proprietary software products.  Utilized ACUMEN detailed corporate simulation system, PROSCREEN II strategic planning system and other custom developed software to support utility rate case filings including test year revenue requirements, rate base, operating income and pro-forma adjustments.  Also utilized these software products for revenue simulation, budget preparation and cost-of-service analyses.

1976 to

1983:		The Toledo Edison Company:  Planning Supervisor.

Responsible for financial planning activities including generation expansion planning, capital and expense budgeting, evaluation of tax law changes, rate case strategy and support and computerized financial modeling using proprietary and nonproprietary software products.  Directed the modeling and evaluation of planning alternatives including:

Rate phase-ins.

Construction project cancellations and write-offs.

Construction project delays.

Capacity swaps.

Financing alternatives.

Competitive pricing for off-system sales.

Sale/leasebacks.

CLIENTS SERVED

Industrial Companies and Groups

Air Products and Chemicals, Inc.

Airco Industrial Gases

Alcan Aluminum

Armco Advanced Materials Co.

Armco Steel

Bethlehem Steel

CF&I Steel, L.P.

Climax Molybdenum Company

Connecticut Industrial Energy Consumers

ELCON

Enron Gas Pipeline Company

Florida Industrial Power Users Group

Gallatin Steel

General Electric Company

GPU Industrial Intervenors

Indiana Industrial Group

Industrial Consumers for

Fair Utility Rates - Indiana

Industrial Energy Consumers - Ohio

Kentucky Industrial Utility Customers, Inc.

Kimberly-Clark Company

Lehigh Valley Power Committee

Maryland Industrial Group

Multiple Intervenors (New York)

National Southwire

North Carolina Industrial

Energy Consumers

Occidental Chemical Corporation

Ohio Energy Group

Ohio Industrial Energy Consumers

Ohio Manufacturers Association

Philadelphia Area Industrial Energy

Users Group

PSI Industrial Group

Smith Cogeneration

Taconite Intervenors (Minnesota)

West Penn Power Industrial Intervenors

West Virginia Energy Users Group

Westvaco Corporation

Regulatory Commissions and
Government Agencies

Cities in Texas-New Mexico Power Company’s Service Territory

Cities in AEP Texas Central Company’s Service Territory

Cities in AEP Texas North Company’s Service Territory

Cities Served by AEP Texas

Florida Office Of Public Counsel

Georgia Public Service Commission Staff

Gulf Coast Coalition of Cities

Indiana Office of Utility Consumer Counsel

Kentucky Office of the Attorney General

Louisiana Public Service Commission

Louisiana Public Service Commission Staff

Maine Office of Public Advocate

New York State Energy Office

Office of Public Utility Counsel (Texas)

South Carolina Office of Regulatory Services

Steering Committee of Cities Served by Oncor Electric Delivery Company

Utilities

Allegheny Power System

Atlantic City Electric Company

Carolina Power & Light Company

Delmarva Power & Light Company

Duquesne Light Company

General Public Utilities

Georgia Power Company

Middle South Services

Nevada Power Company

Niagara Mohawk Power Corporation

Otter Tail Power Company

Pacific Gas & Electric Company

Public Service Electric & Gas

Public Service of Oklahoma

Rochester Gas and Electric

Savannah Electric & Power Company

Seminole Electric Cooperative

Southern California Edison

Talquin Electric Cooperative

Tampa Electric

Texas Utilities

The Cleveland Electric Illuminating Company

The Toledo Edison Company

TESTIMONY AND EXPERT WITNESS APPEARANCES

| Date | Case | Jurisdict. | Party | Utility | Subject |
| --- | --- | --- | --- | --- | --- |
| 10/86 | U-17282 Interim | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Cash revenue requirements financial solvency. |
| 11/86 | U-17282 Interim Rebuttal | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Cash revenue requirements financial solvency. |
| 12/86 | 9613 | KY | Attorney General Div. of Consumer Protection | Big Rivers Electric Corp. | Revenue requirements accounting adjustments financial workout plan. |
| 1/87 | U-17282 Interim | LA 19th Judicial District Ct. | Louisiana Public Service Commission Staff | Gulf States Utilities | Cash revenue requirements, financial solvency. |
| 3/87 | General Order 236 | WV | West Virginia Energy Users' Group | Monongahela Power Co. | Tax Reform Act of 1986. |
| 4/87 | U-17282 Prudence | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Prudence of River Bend 1, economic analyses, cancellation studies. |
| 4/87 | M-100 Sub 113 | NC | North Carolina Industrial Energy Consumers | Duke Power Co. | Tax Reform Act of 1986. |
| 5/87 | 86-524-E-SC | WV | West Virginia Energy Users' Group | Monongahela Power Co. | Revenue requirements, Tax Reform Act of 1986. |
| 5/87 | U-17282 Case In Chief | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, River Bend 1 phase-in plan, financial solvency. |
| 7/87 | U-17282 Case In Chief Surrebuttal | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, River Bend 1 phase-in plan, financial solvency. |
| 7/87 | U-17282 Prudence Surrebuttal | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Prudence of River Bend 1, economic analyses, cancellation studies. |
| 7/87 | 86-524 E-SC Rebuttal | WV | West Virginia Energy Users' Group | Monongahela Power Co. | Revenue requirements, Tax Reform Act of 1986. |
| 8/87 | 9885 | KY | Attorney General Div. of Consumer Protection | Big Rivers Electric Corp. | Financial workout plan. |
| 8/87 | E-015/GR-87-223 | MN | Taconite Intervenors | Minnesota Power & Light Co. | Revenue requirements, O&M expense, Tax Reform Act of 1986. |
| 10/87 | 870220-EI | FL | Occidental Chemical Corp. | Florida Power Corp. | Revenue requirements, O&M expense, Tax Reform Act of 1986. |
| 11/87 | 87-07-01 | CT | Connecticut Industrial Energy Consumers | Connecticut Light & Power Co. | Tax Reform Act of 1986. |
| 1/88 | U-17282 | LA 19th Judicial District Ct. | Louisiana Public Service Commission | Gulf States Utilities | Revenue requirements, River Bend 1 phase-in plan, rate of return. |
| 2/88 | 9934 | KY | Kentucky Industrial Utility Customers | Louisville Gas & Electric Co. | Economics of Trimble County, completion. |
| 2/88 | 10064 | KY | Kentucky Industrial Utility Customers | Louisville Gas & Electric Co. | Revenue requirements, O&M expense, capital structure, excess deferred income taxes. |
| 5/88 | 10217 | KY | Alcan Aluminum National Southwire | Big Rivers Electric Corp. | Financial workout plan. |
| 5/88 | M-87017-1C001 | PA | GPU Industrial Intervenors | Metropolitan Edison Co. | Nonutility generator deferred cost recovery. |
| 5/88 | M-87017-2C005 | PA | GPU Industrial Intervenors | Pennsylvania Electric Co. | Nonutility generator deferred cost recovery. |
| 6/88 | U-17282 | LA 19th Judicial District Ct. | Louisiana Public Service Commission | Gulf States Utilities | Prudence of River Bend 1 economic analyses, cancellation studies, financial modeling. |
| 7/88 | M-87017-1C001 Rebuttal | PA | GPU Industrial Intervenors | Metropolitan Edison Co. | Nonutility generator deferred cost recovery, SFAS No. 92. |
| 7/88 | M-87017-2C005 Rebuttal | PA | GPU Industrial Intervenors | Pennsylvania Electric Co. | Nonutility generator deferred cost recovery, SFAS No. 92. |
| 9/88 | 88-05-25 | CT | Connecticut Industrial Energy Consumers | Connecticut Light & Power Co. | Excess deferred taxes, O&M expenses. |
| 9/88 | 10064 Rehearing | KY | Kentucky Industrial Utility Customers | Louisville Gas & Electric Co. | Premature retirements, interest expense. |
| 10/88 | 88-170-EL-AIR | OH | Ohio Industrial Energy Consumers | Cleveland Electric Illuminating Co. | Revenue requirements, phase-in, excess deferred taxes, O&M expenses, financial considerations, working capital. |
| 10/88 | 88-171-EL-AIR | OH | Ohio Industrial Energy Consumers | Toledo Edison Co. | Revenue requirements, phase-in, excess deferred taxes, O&M expenses, financial considerations, working capital. |
| 10/88 | 8800-355-EI | FL | Florida Industrial Power Users' Group | Florida Power & Light Co. | Tax Reform Act of 1986, tax expenses, O&M expenses, pension expense (SFAS No. 87). |
| 10/88 | 3780-U | GA | Georgia Public Service Commission Staff | Atlanta Gas Light Co. | Pension expense (SFAS No. 87). |
| 11/88 | U-17282 Remand | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Rate base exclusion plan (SFAS No. 71). |
| 12/88 | U-17970 | LA | Louisiana Public Service Commission Staff | AT&T Communications of South Central States | Pension expense (SFAS No. 87). |
| 12/88 | U-17949 Rebuttal | LA | Louisiana Public Service Commission Staff | South Central Bell | Compensated absences (SFAS No. 43), pension expense (SFAS No. 87), Part 32, income tax normalization. |
| 2/89 | U-17282 Phase II | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, phase-in of River Bend 1, recovery of canceled plant. |
| 6/89 | 881602-EU 890326-EU | FL | Talquin Electric Cooperative | Talquin/City of Tallahassee | Economic analyses, incremental cost-of-service, average customer rates. |
| 7/89 | U-17970 | LA | Louisiana Public Service Commission Staff | AT&T Communications of South Central States | Pension expense (SFAS No. 87), compensated absences (SFAS No. 43), Part 32. |
| 8/89 | 8555 | TX | Occidental Chemical Corp. | Houston Lighting & Power Co. | Cancellation cost recovery, tax expense, revenue requirements. |
| 8/89 | 3840-U | GA | Georgia Public Service Commission Staff | Georgia Power Co. | Promotional practices, advertising, economic development. |
| 9/89 | U-17282 Phase II Detailed | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, detailed investigation. |
| 10/89 | 8880 | TX | Enron Gas Pipeline | Texas-New Mexico Power Co. | Deferred accounting treatment, sale/leaseback. |
| 10/89 | 8928 | TX | Enron Gas Pipeline | Texas-New Mexico Power Co. | Revenue requirements, imputed capital structure, cash working capital. |
| 10/89 | R-891364 | PA | Philadelphia Area Industrial Energy Users Group | Philadelphia Electric Co. | Revenue requirements. |
| 11/89 12/89 | R-891364 Surrebuttal (2 Filings) | PA | Philadelphia Area Industrial Energy Users Group | Philadelphia Electric Co. | Revenue requirements, sale/leaseback. |
| 1/90 | U-17282 Phase II Detailed Rebuttal | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, detailed investigation. |
| 1/90 | U-17282 Phase III | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Phase-in of River Bend 1, deregulated asset plan. |
| 3/90 | 890319-EI | FL | Florida Industrial Power Users Group | Florida Power & Light Co. | O&M expenses, Tax Reform Act of 1986. |
| 4/90 | 890319-EI Rebuttal | FL | Florida Industrial Power Users Group | Florida Power & Light Co. | O&M expenses, Tax Reform Act of 1986. |
| 4/90 | U-17282 | LA 19th Judicial District Ct. | Louisiana Public Service Commission | Gulf States Utilities | Fuel clause, gain on sale of utility assets. |
| 9/90 | 90-158 | KY | Kentucky Industrial Utility Customers | Louisville Gas & Electric Co. | Revenue requirements, post-test year additions, forecasted test year. |
| 12/90 | U-17282 Phase IV | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements. |
| 3/91 | 29327, et. al. | NY | Multiple Intervenors | Niagara Mohawk Power Corp. | Incentive regulation. |
| 5/91 | 9945 | TX | Office of Public Utility Counsel of Texas | El Paso Electric Co. | Financial modeling, economic analyses, prudence of Palo Verde 3. |
| 9/91 | P-910511 P-910512 | PA | Allegheny Ludlum Corp., Armco Advanced Materials Co., The West Penn Power Industrial Users' Group | West Penn Power Co. | Recovery of CAAA costs, least cost financing. |
| 9/91 | 91-231-E-NC | WV | West Virginia Energy Users Group | Monongahela Power Co. | Recovery of CAAA costs, least cost financing. |
| 11/91 | U-17282 | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Asset impairment, deregulated asset plan, revenue requirements. |
| 12/91 | 91-410-EL-AIR | OH | Air Products and Chemicals, Inc., Armco Steel Co., General Electric Co., Industrial Energy Consumers | Cincinnati Gas & Electric Co. | Revenue requirements, phase-in plan. |
| 12/91 | PUC Docket 10200 | TX | Office of Public Utility Counsel of Texas | Texas-New Mexico Power Co. | Financial integrity, strategic planning, declined business affiliations. |
| 5/92 | 910890-EI | FL | Occidental Chemical Corp. | Florida Power Corp. | Revenue requirements, O&M expense, pension expense, OPEB expense, fossil dismantling, nuclear decommissioning. |
| 8/92 | R-00922314 | PA | GPU Industrial Intervenors | Metropolitan Edison Co. | Incentive regulation, performance rewards, purchased power risk, OPEB expense. |
| 9/92 | 92-043 | KY | Kentucky Industrial Utility Consumers | Generic Proceeding | OPEB expense. |
| 9/92 | 920324-EI | FL | Florida Industrial Power Users' Group | Tampa Electric Co. | OPEB expense. |
| 9/92 | 39348 | IN | Indiana Industrial Group | Generic Proceeding | OPEB expense. |
| 9/92 | 910840-PU | FL | Florida Industrial Power Users' Group | Generic Proceeding | OPEB expense. |
| 9/92 | 39314 | IN | Industrial Consumers for Fair Utility Rates | Indiana Michigan Power Co. | OPEB expense. |
| 11/92 | U-19904 | LA | Louisiana Public Service Commission Staff | Gulf States Utilities /Entergy Corp. | Merger. |
| 11/92 | 8469 | MD | Westvaco Corp., Eastalco Aluminum Co. | Potomac Edison Co. | OPEB expense. |
| 11/92 | 92-1715-AU-COI | OH | Ohio Manufacturers Association | Generic Proceeding | OPEB expense. |
| 12/92 | R-00922378 | PA | Armco Advanced Materials Co., The WPP Industrial Intervenors | West Penn Power Co. | Incentive regulation, performance rewards, purchased power risk, OPEB expense. |
| 12/92 | U-19949 | LA | Louisiana Public Service Commission Staff | South Central Bell | Affiliate transactions, cost allocations, merger. |
| 12/92 | R-00922479 | PA | Philadelphia Area Industrial Energy Users' Group | Philadelphia Electric Co. | OPEB expense. |
| 1/93 | 8487 | MD | Maryland Industrial Group | Baltimore Gas & Electric Co., Bethlehem Steel Corp. | OPEB expense, deferred fuel, CWIP in rate base. |
| 1/93 | 39498 | IN | PSI Industrial Group | PSI Energy, Inc. | Refunds due to over-collection of taxes on Marble Hill cancellation. |
| 3/93 | 92-11-11 | CT | Connecticut Industrial Energy Consumers | Connecticut Light & Power Co | OPEB expense. |
| 3/93 | U-19904 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities /Entergy Corp. | Merger. |
| 3/93 | 93-01-EL-EFC | OH | Ohio Industrial Energy Consumers | Ohio Power Co. | Affiliate transactions, fuel. |
| 3/93 | EC92-21000 ER92-806-000 | FERC | Louisiana Public Service Commission Staff | Gulf States Utilities /Entergy Corp. | Merger. |
| 4/93 | 92-1464-EL-AIR | OH | Air Products Armco Steel Industrial Energy Consumers | Cincinnati Gas & Electric Co. | Revenue requirements, phase-in plan. |
| 4/93 | EC92-21000 ER92-806-000 (Rebuttal) | FERC | Louisiana Public Service Commission | Gulf States Utilities /Entergy Corp. | Merger. |
| 9/93 | 93-113 | KY | Kentucky Industrial Utility Customers | Kentucky Utilities | Fuel clause and coal contract refund. |
| 9/93 | 92-490, 92-490A, 90-360-C | KY | Kentucky Industrial Utility Customers and Kentucky Attorney General | Big Rivers Electric Corp. | Disallowances and restitution for excessive fuel costs, illegal and improper payments, recovery of mine closure costs. |
| 10/93 | U-17735 | LA | Louisiana Public Service Commission Staff | Cajun Electric Power Cooperative | Revenue requirements, debt restructuring agreement, River Bend cost recovery. |
| 1/94 | U-20647 | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Audit and investigation into fuel clause costs. |
| 4/94 | U-20647 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Nuclear and fossil unit performance, fuel costs, fuel clause principles and guidelines. |
| 4/94 | U-20647 (Supplemental Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Audit and investigation into fuel clause costs. |
| 5/94 | U-20178 | LA | Louisiana Public Service Commission Staff | Louisiana Power & Light Co. | Planning and quantification issues of least cost integrated resource plan. |
| 9/94 | U-19904 Initial Post-Merger Earnings Review | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | River Bend phase-in plan, deregulated asset plan, capital structure, other revenue requirement issues. |
| 9/94 | U-17735 | LA | Louisiana Public Service Commission Staff | Cajun Electric Power Cooperative | G&T cooperative ratemaking policies, exclusion of River Bend, other revenue requirement issues. |
| 10/94 | 3905-U | GA | Georgia Public Service Commission Staff | Southern Bell Telephone Co. | Incentive rate plan, earnings review. |
| 10/94 | 5258-U | GA | Georgia Public Service Commission Staff | Southern Bell Telephone Co. | Alternative regulation, cost allocation. |
| 11/94 | U-19904 Initial Post-Merger Earnings Review (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | River Bend phase-in plan, deregulated asset plan, capital structure, other revenue requirement issues. |
| 11/94 | U-17735 (Rebuttal) | LA | Louisiana Public Service Commission Staff | Cajun Electric Power Cooperative | G&T cooperative ratemaking policy, exclusion of River Bend, other revenue requirement issues. |
| 4/95 | R-00943271 | PA | PP&L Industrial Customer Alliance | Pennsylvania Power & Light Co. | Revenue requirements. Fossil dismantling, nuclear decommissioning. |
| 6/95 | 3905-U Rebuttal | GA | Georgia Public Service Commission | Southern Bell Telephone Co. | Incentive regulation, affiliate transactions, revenue requirements, rate refund. |
| 6/95 | U-19904 (Direct) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Gas, coal, nuclear fuel costs, contract prudence, base/fuel realignment. |
| 10/95 | 95-02614 | TN | Tennessee Office of the Attorney General Consumer Advocate | BellSouth Telecommunications, Inc. | Affiliate transactions. |
| 10/95 | U-21485 (Direct) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Nuclear O&M, River Bend phase-in plan, base/fuel realignment, NOL and AltMin asset deferred taxes, other revenue requirement issues. |
| 11/95 | U-19904 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. Division | Gas, coal, nuclear fuel costs, contract prudence, base/fuel realignment. |
| 11/95 12/95 | U-21485 (Supplemental Direct) U-21485 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Nuclear O&M, River Bend phase-in plan, base/fuel realignment, NOL and AltMin asset deferred taxes, other revenue requirement issues. |
| 1/96 | 95-299-EL-AIR 95-300-EL-AIR | OH | Industrial Energy Consumers | The Toledo Edison Co., The Cleveland Electric Illuminating Co. | Competition, asset write-offs and revaluation, O&M expense, other revenue requirement issues. |
| 2/96 | PUC Docket 14965 | TX | Office of Public Utility Counsel | Central Power & Light | Nuclear decommissioning. |
| 5/96 | 95-485-LCS | NM | City of Las Cruces | El Paso Electric Co. | Stranded cost recovery, municipalization. |
| 7/96 | 8725 | MD | The Maryland Industrial Group and Redland Genstar, Inc. | Baltimore Gas & Electric Co., Potomac Electric Power Co., and Constellation Energy Corp. | Merger savings, tracking mechanism, earnings sharing plan, revenue requirement issues. |
| 9/96 11/96 | U-22092 U-22092 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | River Bend phase-in plan, base/fuel realignment, NOL and AltMin asset deferred taxes, other revenue requirement issues, allocation of regulated/nonregulated costs. |
| 10/96 | 96-327 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Environmental surcharge recoverable costs. |
| 2/97 | R-00973877 | PA | Philadelphia Area Industrial Energy Users Group | PECO Energy Co. | Stranded cost recovery, regulatory assets and liabilities, intangible transition charge, revenue requirements. |
| 3/97 | 96-489 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Co. | Environmental surcharge recoverable costs, system agreements, allowance inventory, jurisdictional allocation. |
| 6/97 | TO-97-397 | MO | MCI Telecommunications Corp., Inc., MCImetro Access Transmission Services, Inc. | Southwestern Bell Telephone Co. | Price cap regulation, revenue requirements, rate of return. |
| 6/97 | R-00973953 | PA | Philadelphia Area Industrial Energy Users Group | PECO Energy Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning. |
| 7/97 | R-00973954 | PA | PP&L Industrial Customer Alliance | Pennsylvania Power & Light Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning. |
| 7/97 | U-22092 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Depreciation rates and methodologies, River Bend phase-in plan. |
| 8/97 | 97-300 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas & Electric Co., Kentucky Utilities Co. | Merger policy, cost savings, surcredit sharing mechanism, revenue requirements, rate of return. |
| 8/97 | R-00973954 (Surrebuttal) | PA | PP&L Industrial Customer Alliance | Pennsylvania Power & Light Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning. |
| 10/97 | 97-204 | KY | Alcan Aluminum Corp. Southwire Co. | Big Rivers Electric Corp. | Restructuring, revenue requirements, reasonableness. |
| 10/97 | R-974008 | PA | Metropolitan Edison Industrial Users Group | Metropolitan Edison Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning, revenue requirements. |
| 10/97 | R-974009 | PA | Penelec Industrial Customer Alliance | Pennsylvania Electric Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning, revenue requirements. |
| 11/97 | 97-204 (Rebuttal) | KY | Alcan Aluminum Corp. Southwire Co. | Big Rivers Electric Corp. | Restructuring, revenue requirements, reasonableness of rates, cost allocation. |
| 11/97 | U-22491 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, other revenue requirement issues. |
| 11/97 | R-00973953 (Surrebuttal) | PA | Philadelphia Area Industrial Energy Users Group | PECO Energy Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning. |
| 11/97 | R-973981 | PA | West Penn Power Industrial Intervenors | West Penn Power Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, fossil decommissioning, revenue requirements, securitization. |
| 11/97 | R-974104 | PA | Duquesne Industrial Intervenors | Duquesne Light Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning, revenue requirements, securitization. |
| 12/97 | R-973981 (Surrebuttal) | PA | West Penn Power Industrial Intervenors | West Penn Power Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, fossil decommissioning, revenue requirements. |
| 12/97 | R-974104 (Surrebuttal) | PA | Duquesne Industrial Intervenors | Duquesne Light Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning, revenue requirements, securitization. |
| 1/98 | U-22491 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, other revenue requirement issues. |
| 2/98 | 8774 | MD | Westvaco | Potomac Edison Co. | Merger of Duquesne, AE, customer safeguards, savings sharing. |
| 3/98 | U-22092 (Allocated Stranded Cost Issues) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Restructuring, stranded costs, regulatory assets, securitization, regulatory mitigation. |
| 3/98 | 8390-U | GA | Georgia Natural Gas Group, Georgia Textile Manufacturers Assoc. | Atlanta Gas Light Co. | Restructuring, unbundling, stranded costs, incentive regulation, revenue requirements. |
| 3/98 | U-22092 (Allocated Stranded Cost Issues) (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Restructuring, stranded costs, regulatory assets, securitization, regulatory mitigation. |
| 3/98 | U-22491 (Supplemental Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, other revenue requirement issues. |
| 10/98 | 97-596 | ME | Maine Office of the Public Advocate | Bangor Hydro- Electric Co. | Restructuring, unbundling, stranded costs, T&D revenue requirements. |
| 10/98 | 9355-U | GA | Georgia Public Service Commission Adversary Staff | Georgia Power Co. | Affiliate transactions. |
| 10/98 | U-17735 Rebuttal | LA | Louisiana Public Service Commission Staff | Cajun Electric Power Cooperative | G&T cooperative ratemaking policy, other revenue requirement issues. |
| 11/98 | U-23327 | LA | Louisiana Public Service Commission Staff | SWEPCO, CSW and AEP | Merger policy, savings sharing mechanism, affiliate transaction conditions. |
| 12/98 | U-23358 (Direct) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, tax issues, and other revenue requirement issues. |
| 12/98 | 98-577 | ME | Maine Office of Public Advocate | Maine Public Service Co. | Restructuring, unbundling, stranded cost, T&D revenue requirements. |
| 1/99 | 98-10-07 | CT | Connecticut Industrial Energy Consumers | United Illuminating Co. | Stranded costs, investment tax credits, accumulated deferred income taxes, excess deferred income taxes. |
| 3/99 | U-23358 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, tax issues, and other revenue requirement issues. |
| 3/99 | 98-474 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co. | Revenue requirements, alternative forms of regulation. |
| 3/99 | 98-426 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements, alternative forms of regulation. |
| 3/99 | 99-082 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co. | Revenue requirements. |
| 3/99 | 99-083 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements. |
| 4/99 | U-23358 (Supplemental Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, tax issues, and other revenue requirement issues. |
| 4/99 | 99-03-04 | CT | Connecticut Industrial Energy Consumers | United Illuminating Co. | Regulatory assets and liabilities, stranded costs, recovery mechanisms. |
| 4/99 | 99-02-05 | CT | Connecticut Industrial Utility Customers | Connecticut Light and Power Co. | Regulatory assets and liabilities, stranded costs, recovery mechanisms. |
| 5/99 | 98-426 99-082 (Additional Direct) | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co. | Revenue requirements. |
| 5/99 | 98-474 99-083 (Additional Direct) | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements. |
| 5/99 | 98-426 98-474 (Response to Amended Applications) | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co., Kentucky Utilities Co. | Alternative regulation. |
| 6/99 | 97-596 | ME | Maine Office of Public Advocate | Bangor Hydro- Electric Co. | Request for accounting order regarding electric industry restructuring costs. |
| 7/99 | U-23358 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Affiliate transactions, cost allocations. |
| 7/99 | 99-03-35 | CT | Connecticut Industrial Energy Consumers | United Illuminating Co. | Stranded costs, regulatory assets, tax effects of asset divestiture. |
| 7/99 | U-23327 | LA | Louisiana Public Service Commission Staff | Southwestern Electric Power Co., Central and South West Corp, American Electric Power Co. | Merger Settlement and Stipulation. |
| 7/99 | 97-596 Surrebuttal | ME | Maine Office of Public Advocate | Bangor Hydro- Electric Co. | Restructuring, unbundling, stranded cost, T&D revenue requirements. |
| 7/99 | 98-0452-E-GI | WV | West Virginia Energy Users Group | Monongahela Power, Potomac Edison, Appalachian Power, Wheeling Power | Regulatory assets and liabilities. |
| 8/99 | 98-577 Surrebuttal | ME | Maine Office of Public Advocate | Maine Public Service Co. | Restructuring, unbundling, stranded costs, T&D revenue requirements. |
| 8/99 | 98-426 99-082 Rebuttal | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co. | Revenue requirements. |
| 8/99 | 98-474 98-083 Rebuttal | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements. |
| 8/99 | 98-0452-E-GI Rebuttal | WV | West Virginia Energy Users Group | Monongahela Power, Potomac Edison, Appalachian Power, Wheeling Power | Regulatory assets and liabilities. |
| 10/99 | U-24182 Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, affiliate transactions, tax issues, and other revenue requirement issues. |
| 11/99 | PUC Docket 21527 | TX | The Dallas-Fort Worth Hospital Council and Coalition of Independent Colleges and Universities | TXU Electric | Restructuring, stranded costs, taxes, securitization. |
| 11/99 | U-23358 Surrebuttal Affiliate Transactions Review | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Service company affiliate transaction costs. |
| 01/00 | U-24182 Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, affiliate transactions, tax issues, and other revenue requirement issues. |
| 04/00 | 99-1212-EL-ETP 99-1213-EL-ATA 99-1214-EL-AAM | OH | Greater Cleveland Growth Association | First Energy (Cleveland Electric Illuminating, Toledo Edison) | Historical review, stranded costs, regulatory assets, liabilities. |
| 05/00 | 2000-107 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Co. | ECR surcharge roll-in to base rates. |
| 05/00 | U-24182 Supplemental Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Affiliate expense proforma adjustments. |
| 05/00 | A-110550F0147 | PA | Philadelphia Area Industrial Energy Users Group | PECO Energy | Merger between PECO and Unicom. |
| 05/00 | 99-1658-EL-ETP | OH | AK Steel Corp. | Cincinnati Gas & Electric Co. | Regulatory transition costs, including regulatory assets and liabilities, SFAS 109, ADIT, EDIT, ITC. |
| 07/00 | PUC Docket 22344 | TX | The Dallas-Fort Worth Hospital Council and The Coalition of Independent Colleges and Universities | Statewide Generic Proceeding | Escalation of O&M expenses for unbundled T&D revenue requirements in projected test year. |
| 07/00 | U-21453 | LA | Louisiana Public Service Commission | SWEPCO | Stranded costs, regulatory assets and liabilities. |
| 08/00 | U-24064 | LA | Louisiana Public Service Commission Staff | CLECO | Affiliate transaction pricing ratemaking principles, subsidization of nonregulated affiliates, ratemaking adjustments. |
| 10/00 | SOAH Docket 473-00-1015 PUC Docket 22350 | TX | The Dallas-Fort Worth Hospital Council and The Coalition of Independent Colleges and Universities | TXU Electric Co. | Restructuring, T&D revenue requirements, mitigation, regulatory assets and liabilities. |
| 10/00 | R-00974104 Affidavit | PA | Duquesne Industrial Intervenors | Duquesne Light Co. | Final accounting for stranded costs, including treatment of auction proceeds, taxes, capital costs, switchback costs, and excess pension funding. |
| 11/00 | P-00001837 R-00974008 P-00001838 R-00974009 | PA | Metropolitan Edison Industrial Users Group Penelec Industrial Customer Alliance | Metropolitan Edison Co., Pennsylvania Electric Co. | Final accounting for stranded costs, including treatment of auction proceeds, taxes, regulatory assets and liabilities, transaction costs. |
| 12/00 | U-21453, U-20925, U-22092 (Subdocket C) Surrebuttal | LA | Louisiana Public Service Commission Staff | SWEPCO | Stranded costs, regulatory assets. |
| 01/01 | U-24993 Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, tax issues, and other revenue requirement issues. |
| 01/01 | U-21453, U-20925, U-22092 (Subdocket B) Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Industry restructuring, business separation plan, organization structure, hold harmless conditions, financing. |
| 01/01 | Case No. 2000-386 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas & Electric Co. | Recovery of environmental costs, surcharge mechanism. |
| 01/01 | Case No. 2000-439 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Recovery of environmental costs, surcharge mechanism. |
| 02/01 | A-110300F0095 A-110400F0040 | PA | Met-Ed Industrial Users Group, Penelec Industrial Customer Alliance | GPU, Inc. FirstEnergy Corp. | Merger, savings, reliability. |
| 03/01 | P-00001860 P-00001861 | PA | Met-Ed Industrial Users Group, Penelec Industrial Customer Alliance | Metropolitan Edison Co., Pennsylvania Electric Co. | Recovery of costs due to provider of last resort obligation. |
| 04/01 | U-21453, U-20925, U-22092 (Subdocket B) Settlement Term Sheet | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Business separation plan: settlement agreement on overall plan structure. |
| 04/01 | U-21453, U-20925, U-22092 (Subdocket B) Contested Issues | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Business separation plan: agreements, hold harmless conditions, separations methodology. |
| 05/01 | U-21453, U-20925, U-22092 (Subdocket B) Contested Issues Transmission and Distribution Rebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Business separation plan: agreements, hold harmless conditions, separations methodology. |
| 07/01 | U-21453, U-20925, U-22092 (Subdocket B) Transmission and Distribution Term Sheet | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Business separation plan: settlement agreement on T&D issues, agreements necessary to implement T&D separations, hold harmless conditions, separations methodology. |
| 10/01 | 14000-U | GA | Georgia Public Service Commission Adversary Staff | Georgia Power Company | Revenue requirements, Rate Plan, fuel clause recovery. |
| 11/01 | 14311-U Direct Panel with Bolin Killings | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co | Revenue requirements, revenue forecast, O&M expense, depreciation, plant additions, cash working capital. |
| 11/01 | U-25687 Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, capital structure, allocation of regulated and nonregulated costs, River Bend uprate. |
| 02/02 | PUC Docket 25230 | TX | The Dallas-Fort Worth Hospital Council and the Coalition of Independent Colleges and Universities | TXU Electric | Stipulation. Regulatory assets, securitization financing. |
| 02/02 | U-25687 Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, River Bend uprate. |
| 03/02 | 14311-U Rebuttal Panel with Bolin Killings | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Revenue requirements, earnings sharing plan, service quality standards. |
| 03/02 | 14311-U Rebuttal Panel with Michelle L. Thebert | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Revenue requirements, revenue forecast, O&M expense, depreciation, plant additions, cash working capital. |
| 03/02 | 001148-EI | FL | South Florida Hospital and Healthcare Assoc. | Florida Power & Light Co. | Revenue requirements. Nuclear life extension, storm damage accruals and reserve, capital structure, O&M expense. |
| 04/02 | U-25687 (Suppl. Surrebuttal) | LA | Louisiana Public Service Commission | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, River Bend uprate. |
| 04/02 | U-21453, U-20925 U-22092 (Subdocket C) | LA | Louisiana Public Service Commission | SWEPCO | Business separation plan, T&D Term Sheet, separations methodologies, hold harmless conditions. |
| 08/02 | EL01-88-000 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | System Agreement, production cost equalization, tariffs. |
| 08/02 | U-25888 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. and Entergy Louisiana, Inc. | System Agreement, production cost disparities, prudence. |
| 09/02 | 2002-00224 2002-00225 | KY | Kentucky Industrial Utilities Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Line losses and fuel clause recovery associated with off-system sales. |
| 11/02 | 2002-00146 2002-00147 | KY | Kentucky Industrial Utilities Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Environmental compliance costs and surcharge recovery. |
| 01/03 | 2002-00169 | KY | Kentucky Industrial Utilities Customers, Inc. | Kentucky Power Co. | Environmental compliance costs and surcharge recovery. |
| 04/03 | 2002-00429 2002-00430 | KY | Kentucky Industrial Utilities Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Extension of merger surcredit, flaws in Companies’ studies. |
| 04/03 | U-26527 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, capital structure, post-test year adjustments. |
| 06/03 | EL01-88-000 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | System Agreement, production cost equalization, tariffs. |
| 06/03 | 2003-00068 | KY | Kentucky Industrial Utility Customers | Kentucky Utilities Co. | Environmental cost recovery, correction of base rate error. |
| 11/03 | ER03-753-000 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Unit power purchases and sale cost-based tariff pursuant to System Agreement. |
| 11/03 | ER03-583-000, ER03-583-001, ER03-583-002 ER03-681-000, ER03-681-001 ER03-682-000, ER03-682-001, ER03-682-002 ER03-744-000, ER03-744-001 (Consolidated) | FERC | Louisiana Public Service Commission | Entergy Services, Inc., the Entergy Operating Companies, EWO Marketing, L.P, and Entergy Power, Inc. | Unit power purchases and sale agreements, contractual provisions, projected costs, levelized rates, and formula rates. |
| 12/03 | U-26527 Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, capital structure, post-test year adjustments. |
| 12/03 | 2003-0334 2003-0335 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Earnings Sharing Mechanism. |
| 12/03 | U-27136 | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, Inc. | Purchased power contracts between affiliates, terms and conditions. |
| 03/04 | U-26527 Supplemental Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, capital structure, post-test year adjustments. |
| 03/04 | 2003-00433 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas & Electric Co. | Revenue requirements, depreciation rates, O&M expense, deferrals and amortization, earnings sharing mechanism, merger surcredit, VDT surcredit. |
| 03/04 | 2003-00434 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements, depreciation rates, O&M expense, deferrals and amortization, earnings sharing mechanism, merger surcredit, VDT surcredit. |
| 03/04 | SOAH Docket 473-04-2459 PUC Docket 29206 | TX | Cities Served by Texas- New Mexico Power Co. | Texas-New Mexico Power Co. | Stranded costs true-up, including valuation issues, ITC, ADIT, excess earnings. |
| 05/04 | 04-169-EL-UNC | OH | Ohio Energy Group, Inc. | Columbus Southern Power Co. & Ohio Power Co. | Rate stabilization plan, deferrals, T&D rate increases, earnings. |
| 06/04 | SOAH Docket 473-04-4555 PUC Docket 29526 | TX | Houston Council for Health and Education | CenterPoint Energy Houston Electric | Stranded costs true-up, including valuation issues, ITC, EDIT, excess mitigation credits, capacity auction true-up revenues, interest. |
| 08/04 | SOAH Docket 473-04-4555 PUC Docket 29526 (Suppl Direct) | TX | Houston Council for Health and Education | CenterPoint Energy Houston Electric | Interest on stranded cost pursuant to Texas Supreme Court remand. |
| 09/04 | U-23327 Subdocket B | LA | Louisiana Public Service Commission Staff | SWEPCO | Fuel and purchased power expenses recoverable through fuel adjustment clause, trading activities, compliance with terms of various LPSC Orders. |
| 10/04 | U-23327 Subdocket A | LA | Louisiana Public Service Commission Staff | SWEPCO | Revenue requirements. |
| 12/04 | Case Nos. 2004-00321, 2004-00372 | KY | Gallatin Steel Co. | East Kentucky Power Cooperative, Inc., Big Sandy Recc, et al. | Environmental cost recovery, qualified costs, TIER requirements, cost allocation. |
| 01/05 | 30485 | TX | Houston Council for Health and Education | CenterPoint Energy Houston Electric, LLC | Stranded cost true-up including regulatory Central Co. assets and liabilities, ITC, EDIT, capacity auction, proceeds, excess mitigation credits, retrospective and prospective ADIT. |
| 02/05 | 18638-U | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Revenue requirements. |
| 02/05 | 18638-U Panel with Tony Wackerly | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Comprehensive rate plan, pipeline replacement program surcharge, performance based rate plan. |
| 02/05 | 18638-U Panel with Michelle Thebert | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Energy conservation, economic development, and tariff issues. |
| 03/05 | Case Nos. 2004-00426, 2004-00421 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric | Environmental cost recovery, Jobs Creation Act of 2004 and §199 deduction, excess common equity ratio, deferral and amortization of nonrecurring O&M expense. |
| 06/05 | 2005-00068 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Co. | Environmental cost recovery, Jobs Creation Act of 2004 and §199 deduction, margins on allowances used for AEP system sales. |
| 06/05 | 050045-EI | FL | South Florida Hospital and Heallthcare Assoc. | Florida Power & Light Co. | Storm damage expense and reserve, RTO costs, O&M expense projections, return on equity performance incentive, capital structure, selective second phase post-test year rate increase. |
| 08/05 | 31056 | TX | Alliance for Valley Healthcare | AEP Texas Central Co. | Stranded cost true-up including regulatory assets and liabilities, ITC, EDIT, capacity auction, proceeds, excess mitigation credits, retrospective and prospective ADIT. |
| 09/05 | 20298-U | GA | Georgia Public Service Commission Adversary Staff | Atmos Energy Corp. | Revenue requirements, roll-in of surcharges, cost recovery through surcharge, reporting requirements. |
| 09/05 | 20298-U Panel with Victoria Taylor | GA | Georgia Public Service Commission Adversary Staff | Atmos Energy Corp. | Affiliate transactions, cost allocations, capitalization, cost of debt. |
| 10/05 | 04-42 | DE | Delaware Public Service Commission Staff | Artesian Water Co. | Allocation of tax net operating losses between regulated and unregulated. |
| 11/05 | 2005-00351 2005-00352 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric | Workforce Separation Program cost recovery and shared savings through VDT surcredit. |
| 01/06 | 2005-00341 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Co. | System Sales Clause Rider, Environmental Cost Recovery Rider. Net Congestion Rider, Storm damage, vegetation management program, depreciation, off-system sales, maintenance normalization, pension and OPEB. |
| 03/06 | PUC Docket 31994 | TX | Cities | Texas-New Mexico Power Co. | Stranded cost recovery through competition transition or change. |
| 05/06 | 31994 Supplemental | TX | Cities | Texas-New Mexico Power Co. | Retrospective ADFIT, prospective ADFIT. |
| 03/06 | U-21453, U-20925, U-22092 (Subdocket B) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Jurisdictional separation plan. |
| 03/06 | NOPR Reg 104385-OR | IRS | Alliance for Valley Health Care and Houston Council for Health Education | AEP Texas Central Company and CenterPoint Energy Houston Electric | Proposed Regulations affecting flow- through to ratepayers of excess deferred income taxes and investment tax credits on generation plant that is sold or deregulated. |
| 04/06 | U-25116 | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, Inc. | 2002-2004 Audit of Fuel Adjustment Clause Filings. Affiliate transactions. |
| 07/06 | R-00061366, Et. al. | PA | Met-Ed Ind. Users Group Pennsylvania Ind. Customer Alliance | Metropolitan Edison Co., Pennsylvania Electric Co. | Recovery of NUG-related stranded costs, government mandated program costs, storm damage costs. |
| 07/06 | U-23327 | LA | Louisiana Public Service Commission Staff | Southwestern Electric Power Co. | Revenue requirements, formula rate plan, banking proposal. |
| 08/06 | U-21453, U-20925, U-22092 (Subdocket J) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Jurisdictional separation plan. |
| 11/06 | 05CVH03-3375 Franklin County Court Affidavit | OH | Various Taxing Authorities (Non-Utility Proceeding) | State of Ohio Department of Revenue | Accounting for nuclear fuel assemblies as manufactured equipment and capitalized plant. |
| 12/06 | U-23327 Subdocket A Reply Testimony | LA | Louisiana Public Service Commission Staff | Southwestern Electric Power Co. | Revenue requirements, formula rate plan, banking proposal. |
| 03/07 | U-29764 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc., Entergy Louisiana, LLC | Jurisdictional allocation of Entergy System Agreement equalization remedy receipts. |
| 03/07 | PUC Docket 33309 | TX | Cities | AEP Texas Central Co. | Revenue requirements, including functionalization of transmission and distribution costs. |
| 03/07 | PUC Docket 33310 | TX | Cities | AEP Texas North Co. | Revenue requirements, including functionalization of transmission and distribution costs. |
| 03/07 | 2006-00472 | KY | Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative | Interim rate increase, RUS loan covenants, credit facility requirements, financial condition. |
| 03/07 | U-29157 | LA | Louisiana Public Service Commission Staff | Cleco Power, LLC | Permanent (Phase II) storm damage cost recovery. |
| 04/07 | U-29764 Supplemental and Rebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc., Entergy Louisiana, LLC | Jurisdictional allocation of Entergy System Agreement equalization remedy receipts. |
| 04/07 | ER07-682-000 Affidavit | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Allocation of intangible and general plant and A&G expenses to production and state income tax effects on equalization remedy receipts. |
| 04/07 | ER07-684-000 Affidavit | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Fuel hedging costs and compliance with FERC USOA. |
| 05/07 | ER07-682-000 Supplemental Affidavit | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Allocation of intangible and general plant and A&G expenses to production and account 924 effects on MSS-3 equalization remedy payments and receipts. |
| 06/07 | U-29764 | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, LLC, Entergy Gulf States, Inc. | Show cause for violating LPSC Order on fuel hedging costs. |
| 07/07 | 2006-00472 | KY | Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative | Revenue requirements, post-test year adjustments, TIER, surcharge revenues and costs, financial need. |
| 07/07 | ER07-956-000 Affidavit | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Storm damage costs related to Hurricanes Katrina and Rita and effects of MSS-3 equalization payments and receipts. |
| 10/07 | 05-UR-103 Direct | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company, Wisconsin Gas, LLC | Revenue requirements, carrying charges on CWIP, amortization and return on regulatory assets, working capital, incentive compensation, use of rate base in lieu of capitalization, quantification and use of Point Beach sale proceeds. |
| 10/07 | 05-UR-103 Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company, Wisconsin Gas, LLC | Revenue requirements, carrying charges on CWIP, amortization and return on regulatory assets, working capital, incentive compensation, use of rate base in lieu of capitalization, quantification and use of Point Beach sale proceeds. |
| 10/07 | 25060-U Direct | GA | Georgia Public Service Commission Public Interest Adversary Staff | Georgia Power Company | Affiliate costs, incentive compensation, consolidated income taxes, §199 deduction. |
| 11/07 | 06-0033-E-CN Direct | WV | West Virginia Energy Users Group | Appalachian Power Company | IGCC surcharge during construction period and post-in-service date. |
| 11/07 | ER07-682-000 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Functionalization and allocation of intangible and general plant and A&G expenses. |
| 01/08 | ER07-682-000 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Functionalization and allocation of intangible and general plant and A&G expenses. |
| 01/08 | 07-551-EL-AIR Direct | OH | Ohio Energy Group, Inc. | Ohio Edison Company, Cleveland Electric Illuminating Company, Toledo Edison Company | Revenue requirements. |
| 02/08 | ER07-956-000 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Functionalization of expenses, storm damage expense and reserves, tax NOL carrybacks in accounts, ADIT, nuclear service lives and effects on depreciation and decommissioning. |
| 03/08 | ER07-956-000 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Functionalization of expenses, storm damage expense and reserves, tax NOL carrybacks in accounts, ADIT, nuclear service lives and effects on depreciation and decommissioning. |
| 04/08 | 2007-00562, 2007-00563 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas and Electric Co. | Merger surcredit. |
| 04/08 | 26837 Direct Bond, Johnson, Thebert, Kollen Panel | GA | Georgia Public Service Commission Staff | SCANA Energy Marketing, Inc. | Rule Nisi complaint. |
| 05/08 | 26837 Rebuttal Bond, Johnson, Thebert, Kollen Panel | GA | Georgia Public Service Commission Staff | SCANA Energy Marketing, Inc. | Rule Nisi complaint. |
| 05/08 | 26837 Suppl Rebuttal Bond, Johnson, Thebert, Kollen Panel | GA | Georgia Public Service Commission Staff | SCANA Energy Marketing, Inc. | Rule Nisi complaint. |
| 06/08 | 2008-00115 | KY | Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative, Inc. | Environmental surcharge recoveries, including costs recovered in existing rates, TIER. |
| 07/08 | 27163 Direct | GA | Georgia Public Service Commission Public Interest Advocacy Staff | Atmos Energy Corp. | Revenue requirements, including projected test year rate base and expenses. |
| 07/08 | 27163 Taylor, Kollen Panel | GA | Georgia Public Service Commission Public Interest Advocacy Staff | Atmos Energy Corp. | Affiliate transactions and division cost allocations, capital structure, cost of debt. |
| 08/08 | 6680-CE-170 Direct | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Power and Light Company | Nelson Dewey 3 or Colombia 3 fixed financial parameters. |
| 08/08 | 6680-UR-116 Direct | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Power and Light Company | CWIP in rate base, labor expenses, pension expense, financing, capital structure, decoupling. |
| 08/08 | 6680-UR-116 Rebuttal | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Power and Light Company | Capital structure. |
| 08/08 | 6690-UR-119 Direct | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Public Service Corp. | Prudence of Weston 3 outage, incentive compensation, Crane Creek Wind Farm incremental revenue requirement, capital structure. |
| 09/08 | 6690-UR-119 Surrebuttal | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Public Service Corp. | Prudence of Weston 3 outage, Section 199 deduction. |
| 09/08 | 08-935-EL-SSO, 08-918-EL-SSO | OH | Ohio Energy Group, Inc. | First Energy | Standard service offer rates pursuant to electric security plan, significantly excessive earnings test. |
| 10/08 | 08-917-EL-SSO | OH | Ohio Energy Group, Inc. | AEP | Standard service offer rates pursuant to electric security plan, significantly excessive earnings test. |
| 10/08 | 2007-00564, 2007-00565, 2008-00251 2008-00252 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co., Kentucky Utilities Company | Revenue forecast, affiliate costs, ELG v ASL depreciation procedures, depreciation expenses, federal and state income tax expense, capitalization, cost of debt. |
| 11/08 | EL08-51 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Spindletop gas storage facilities, regulatory asset and bandwidth remedy. |
| 11/08 | 35717 | TX | Cities Served by Oncor Delivery Company | Oncor Delivery Company | Recovery of old meter costs, asset ADFIT, cash working capital, recovery of prior year restructuring costs, levelized recovery of storm damage costs, prospective storm damage accrual, consolidated tax savings adjustment. |
| 12/08 | 27800 | GA | Georgia Public Service Commission | Georgia Power Company | AFUDC versus CWIP in rate base, mirror CWIP, certification cost, use of short term debt and trust preferred financing, CWIP recovery, regulatory incentive. |
| 01/09 | ER08-1056 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Entergy System Agreement bandwidth remedy calculations, including depreciation expense, ADIT, capital structure. |
| 01/09 | ER08-1056 Supplemental Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Blytheville leased turbines; accumulated depreciation. |
| 02/09 | EL08-51 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Spindletop gas storage facilities regulatory asset and bandwidth remedy. |
| 02/09 | 2008-00409 Direct | KY | Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative, Inc. | Revenue requirements. |
| 03/09 | ER08-1056 Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Entergy System Agreement bandwidth remedy calculations, including depreciation expense, ADIT, capital structure. |
| 03/09 | U-21453, U-20925 U-22092 (Sub J) Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States Louisiana, LLC | Violation of EGSI separation order, ETI and EGSL separation accounting, Spindletop regulatory asset. |
| 04/09 | Rebuttal |  |  |  |  |
| 04/09 | 2009-00040 Direct-Interim (Oral) | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Emergency interim rate increase; cash requirements. |
| 04/09 | PUC Docket 36530 | TX | State Office of Administrative Hearings | Oncor Electric Delivery Company, LLC | Rate case expenses. |
| 05/09 | ER08-1056 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Entergy System Agreement bandwidth remedy calculations, including depreciation expense, ADIT, capital structure. |
| 06/09 | 2009-00040 Direct- Permanent | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Revenue requirements, TIER, cash flow. |
| 07/09 | 080677-EI | FL | South Florida Hospital and Healthcare Association | Florida Power & Light Company | Multiple test years, GBRA rider, forecast assumptions, revenue requirement, O&M expense, depreciation expense, Economic Stimulus Bill, capital structure. |
| 08/09 | U-21453, U-20925, U-22092 (Subdocket J) Supplemental Rebuttal | LA | Louisiana Public Service Commission | Entergy Gulf States Louisiana, LLC | Violation of EGSI separation order, ETI and EGSL separation accounting, Spindletop regulatory asset. |
| 08/09 | 8516 and 29950 | GA | Georgia Public Service Commission Staff | Atlanta Gas Light Company | Modification of PRP surcharge to include infrastructure costs. |
| 09/09 | 05-UR-104 Direct and Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company | Revenue requirements, incentive compensation, depreciation, deferral mitigation, capital structure, cost of debt. |
| 09/09 | 09AL-299E Answer | CO | CF&I Steel, Rocky Mountain Steel Mills LP, Climax Molybdenum Company | Public Service Company of Colorado | Forecasted test year, historic test year, proforma adjustments for major plant additions, tax depreciation. |
| 09/09 | 6680-UR-117 Direct and Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Power and Light Company | Revenue requirements, CWIP in rate base, deferral mitigation, payroll, capacity shutdowns, regulatory assets, rate of return. |
| 10/09 | 09A-415E Answer | CO | Cripple Creek & Victor Gold Mining Company, et al. | Black Hills/CO Electric Utility Company | Cost prudence, cost sharing mechanism. |
| 10/09 | EL09-50 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Waterford 3 sale/leaseback accumulated deferred income taxes, Entergy System Agreement bandwidth remedy calculations. |
| 10/09 | 2009-00329 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Company, Kentucky Utilities Company | Trimble County 2 depreciation rates. |
| 12/09 | PUE-2009-00030 | VA | Old Dominion Committee for Fair Utility Rates | Appalachian Power Company | Return on equity incentive. |
| 12/09 | ER09-1224 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Hypothetical versus actual costs, out of period costs, Spindletop deferred capital costs, Waterford 3 sale/leaseback ADIT. |
| 01/10 | ER09-1224 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Hypothetical versus actual costs, out of period costs, Spindletop deferred capital costs, Waterford 3 sale/leaseback ADIT. |
| 01/10 | EL09-50 Rebuttal Supplemental Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Waterford 3 sale/leaseback accumulated deferred income taxes, Entergy System Agreement bandwidth remedy calculations. |
| 02/10 | ER09-1224 Final | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Hypothetical versus actual costs, out of period costs, Spindletop deferred capital costs, Waterford 3 sale/leaseback ADIT. |
| 02/10 | 30442 Wackerly-Kollen Panel | GA | Georgia Public Service Commission Staff | Atmos Energy Corporation | Revenue requirement issues. |
| 02/10 | 30442 McBride-Kollen Panel | GA | Georgia Public Service Commission Staff | Atmos Energy Corporation | Affiliate/division transactions, cost allocation, capital structure. |
| 02/10 | 2009-00353 | KY | Kentucky Industrial Utility Customers, Inc., Attorney General | Louisville Gas and Electric Company, Kentucky Utilities Company | Ratemaking recovery of wind power purchased power agreements. |
| 03/10 | 2009-00545 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Ratemaking recovery of wind power purchased power agreement. |
| 03/10 | E015/GR-09-1151 | MN | Large Power Interveners | Minnesota Power | Revenue requirement issues, cost overruns on environmental retrofit project. |
| 04/10 | 2009-00459 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Revenue requirement issues. |
| 04/10 | 2009-00548, 2009-00549 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company, Louisville Gas and Electric Company | Revenue requirement issues. |
| 08/10 | 31647 | GA | Georgia Public Service Commission Staff | Atlanta Gas Light Company | Revenue requirement and synergy savings issues. |
| 08/10 | 31647 Wackerly-Kollen Panel | GA | Georgia Public Service Commission Staff | Atlanta Gas Light Company | Affiliate transaction and Customer First program issues. |
| 08/10 | 2010-00204 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Company, Kentucky Utilities Company | PPL acquisition of E.ON U.S. (LG&E and KU) conditions, acquisition savings, sharing deferral mechanism. |
| 09/10 | 38339 Direct and Cross-Rebuttal | TX | Gulf Coast Coalition of Cities | CenterPoint Energy Houston Electric | Revenue requirement issues, including consolidated tax savings adjustment, incentive compensation FIN 48; AMS surcharge including roll-in to base rates; rate case expenses. |
| 09/10 | EL10-55 | FERC | Louisiana Public Service Commission | Entergy Services, Inc., Entergy Operating Cos | Depreciation rates and expense input effects on System Agreement tariffs. |
| 09/10 | 2010-00167 | KY | Gallatin Steel | East Kentucky Power Cooperative, Inc. | Revenue requirements. |
| 09/10 | U-23327 Subdocket E Direct | LA | Louisiana Public Service Commission | SWEPCO | Fuel audit: S02 allowance expense, variable O&M expense, off-system sales margin sharing. |
| 11/10 | U-23327 Rebuttal | LA | Louisiana Public Service Commission | SWEPCO | Fuel audit: S02 allowance expense, variable O&M expense, off-system sales margin sharing. |
| 09/10 | U-31351 | LA | Louisiana Public Service Commission Staff | SWEPCO and Valley Electric Membership Cooperative | Sale of Valley assets to SWEPCO and dissolution of Valley. |
| 10/10 | 10-1261-EL-UNC | OH | Ohio OCC, Ohio Manufacturers Association, Ohio Energy Group, Ohio Hospital Association, Appalachian Peace and Justice Network | Columbus Southern Power Company | Significantly excessive earnings test. |
| 10/10 | 10-0713-E-PC | WV | West Virginia Energy Users Group | Monongahela Power Company, Potomac Edison Power Company | Merger of First Energy and Allegheny Energy. |
| 10/10 | U-23327 Subdocket F Direct | LA | Louisiana Public Service Commission Staff | SWEPCO | AFUDC adjustments in Formula Rate Plan. |
| 11/10 | EL10-55 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc., Entergy Operating Cos | Depreciation rates and expense input effects on System Agreement tariffs. |
| 12/10 | ER10-1350 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. Entergy Operating Cos | Waterford 3 lease amortization, ADIT, and fuel inventory effects on System Agreement tariffs. |
| 01/11 | ER10-1350 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc., Entergy Operating Cos | Waterford 3 lease amortization, ADIT, and fuel inventory effects on System Agreement tariffs. |
| 03/11 04/11 | ER10-2001 Direct Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc., Entergy Arkansas, Inc. | EAI depreciation rates. |
| 04/11 | U-23327 Subdocket E | LA | Louisiana Public Service Commission Staff | SWEPCO | Settlement, incl resolution of S02 allowance expense, var O&M expense, sharing of OSS margins. |
| 04/11 05/11 | 38306 Direct Suppl Direct | TX | Cities Served by Texas-New Mexico Power Company | Texas-New Mexico Power Company | AMS deployment plan, AMS Surcharge, rate case expenses. |
| 05/11 | 11-0274-E-GI | WV | West Virginia Energy Users Group | Appalachian Power Company, Wheeling Power Company | Deferral recovery phase-in, construction surcharge. |
| 05/11 | 2011-00036 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Revenue requirements. |
| 06/11 | 29849 | GA | Georgia Public Service Commission Staff | Georgia Power Company | Accounting issues related to Vogtle risk-sharing mechanism. |
| 07/11 | ER11-2161 Direct and Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and Entergy Texas, Inc. | ETI depreciation rates; accounting issues. |
| 07/11 | PUE-2011-00027 | VA | Virginia Committee for Fair Utility Rates | Virginia Electric and Power Company | Return on equity performance incentive. |
| 07/11 | 11-346-EL-SSO 11-348-EL-SSO 11-349-EL-AAM 11-350-EL-AAM | OH | Ohio Energy Group | AEP-OH | Equity Stabilization Incentive Plan; actual earned returns; ADIT offsets in riders. |
| 08/11 | U-23327 Subdocket F Rebuttal | LA | Louisiana Public Service Commission Staff | SWEPCO | Depreciation rates and service lives; AFUDC adjustments. |
| 08/11 | 05-UR-105 | WI | Wisconsin Industrial Energy Group | WE Energies, Inc. | Suspended amortization expenses; revenue requirements. |
| 08/11 | ER11-2161 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and Entergy Texas, Inc. | ETI depreciation rates; accounting issues. |
| 09/11 | PUC Docket 39504 | TX | Gulf Coast Coalition of Cities | CenterPoint Energy Houston Electric | Investment tax credit, excess deferred income taxes; normalization. |
| 09/11 | 2011-00161 2011-00162 | KY | Kentucky Industrial Utility Consumers, Inc. | Louisville Gas & Electric Company, Kentucky Utilities Company | Environmental requirements and financing. |
| 10/11 | 11-4571-EL-UNC 11-4572-EL-UNC | OH | Ohio Energy Group | Columbus Southern Power Company, Ohio Power Company | Significantly excessive earnings. |
| 10/11 | 4220-UR-117 Direct | WI | Wisconsin Industrial Energy Group | Northern States Power-Wisconsin | Nuclear O&M, depreciation. |
| 11/11 | 4220-UR-117 Surrebuttal | WI | Wisconsin Industrial Energy Group | Northern States Power-Wisconsin | Nuclear O&M, depreciation. |
| 11/11 | PUC Docket 39722 | TX | Cities Served by AEP Texas Central Company | AEP Texas Central Company | Investment tax credit, excess deferred income taxes; normalization. |
| 02/12 | PUC Docket 40020 | TX | Cities Served by Oncor | Lone Star Transmission, LLC | Temporary rates. |
| 03/12 | 11AL-947E Answer | CO | Climax Molybdenum Company and CF&I Steel, L.P. d/b/a Evraz Rocky Mountain Steel | Public Service Company of Colorado | Revenue requirements, including historic test year, future test year, CACJA CWIP, contra-AFUDC. |
| 03/12 | 2011-00401 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Big Sandy 2 environmental retrofits and environmental surcharge recovery. |
| 4/12 | 2011-00036 Direct Rehearing Supplemental Rebuttal Rehearing | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Rate case expenses, depreciation rates and expense. |
| 04/12 | 10-2929-EL-UNC | OH | Ohio Energy Group | AEP Ohio Power | State compensation mechanism, CRES capacity charges, Equity Stabilization Mechanism |
| 05/12 | 11-346-EL-SSO 11-348-EL-SSO | OH | Ohio Energy Group | AEP Ohio Power | State compensation mechanism, Equity Stabilization Mechanism, Retail Stability Rider. |
| 05/12 | 11-4393-EL-RDR | OH | Ohio Energy Group | Duke Energy Ohio, Inc. | Incentives for over-compliance on EE/PDR mandates. |
| 06/12 | 40020 | TX | Cities Served by Oncor | Lone Star Transmission, LLC | Revenue requirements, including ADIT, bonus depreciation and NOL, working capital, self insurance, depreciation rates, federal income tax expense. |
| 07/12 | 120015-EI | FL | South Florida Hospital and Healthcare Association | Florida Power & Light Company | Revenue requirements, including vegetation management, nuclear outage expense, cash working capital, CWIP in rate base. |
| 07/12 | 2012-00063 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Environmental retrofits, including environmental surcharge recovery. |
| 09/12 | 05-UR-106 | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Electric Power Company | Section 1603 grants, new solar facility, payroll expenses, cost of debt. |
| 10/12 | 2012-00221 2012-00222 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Company, Kentucky Utilities Company | Revenue requirements, including off-system sales, outage maintenance, storm damage, injuries and damages, depreciation rates and expense. |
| 10/12 | 120015-EI Direct | FL | South Florida Hospital and Healthcare Association | Florida Power & Light Company | Settlement issues. |
| 11/12 | 120015-EI Rebuttal | FL | South Florida Hospital and Healthcare Association | Florida Power & Light Company | Settlement issues. |
| 10/12 | 40604 | TX | Steering Committee of Cities Served by Oncor | Cross Texas Transmission, LLC | Policy and procedural issues, revenue requirements, including AFUDC, ADIT – bonus depreciation & NOL, incentive compensation, staffing, self-insurance, net salvage, depreciation rates and expense, income tax expense. |
| 11/12 | 40627 Direct | TX | City of Austin d/b/a Austin Energy | City of Austin d/b/a Austin Energy | Rate case expenses. |
| 12/12 | 40443 | TX | Cities Served by SWEPCO | Southwestern Electric Power Company | Revenue requirements, including depreciation rates and service lives, O&M expenses, consolidated tax savings, CWIP in rate base, Turk plant costs. |
| 12/12 | U-29764 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States Louisiana, LLC and Entergy Louisiana, LLC | Termination of purchased power contracts between EGSL and ETI, Spindletop regulatory asset. |
| 01/13 | ER12-1384 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Gulf States Louisiana, LLC and Entergy Louisiana, LLC | Little Gypsy 3 cancellation costs. |
| 02/13 | 40627 Rebuttal | TX | City of Austin d/b/a Austin Energy | City of Austin d/b/a Austin Energy | Rate case expenses. |
| 03/13 | 12-426-EL-SSO | OH | The Ohio Energy Group | The Dayton Power and Light Company | Capacity charges under state compensation mechanism, Service Stability Rider, Switching Tracker. |
| 04/13 | 12-2400-EL-UNC | OH | The Ohio Energy Group | Duke Energy Ohio, Inc. | Capacity charges under state compensation mechanism, deferrals, rider to recover deferrals. |
| 04/13 | 2012-00578 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Resource plan, including acquisition of interest in Mitchell plant. |
| 05/13 | 2012-00535 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Revenue requirements, excess capacity, restructuring. |
| 06/13 | 12-3254-EL-UNC | OH | The Ohio Energy Group, Inc., Office of the Ohio Consumers’ Counsel | Ohio Power Company | Energy auctions under CBP, including reserve prices. |
| 07/13 | 2013-00144 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Biomass renewable energy purchase agreement. |
| 07/13 | 2013-00221 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Agreements to provide Century Hawesville Smelter market access. |
| 10/13 | 2013-00199 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Revenue requirements, excess capacity, restructuring. |
| 12/13 | 2013-00413 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Agreements to provide Century Sebree Smelter market access. |
| 01/14 | ER10-1350 Direct and Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Waterford 3 lease accounting and treatment in annual bandwidth filings. |
| 02/14 | U-32981 | LA | Louisiana Public Service Commission | Entergy Louisiana, LLC | Montauk renewable energy PPA. |
| 04/14 | ER13-432 Direct | FERC | Louisiana Public Service Commission | Entergy Gulf States Louisiana, LLC and Entergy Louisiana, LLC | UP Settlement benefits and damages. |
| 05/14 | PUE-2013-00132 | VA | HP Hood LLC | Shenandoah Valley Electric Cooperative | Market based rate; load control tariffs. |
| 07/14 | PUE-2014-00033 | VA | Virginia Committee for Fair Utility Rates | Virginia Electric and Power Company | Fuel and purchased power hedge accounting, change in FAC Definitional Framework. |
| 08/14 | ER13-432 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Gulf States Louisiana, LLC and Entergy Louisiana, LLC | UP Settlement benefits and damages. |
| 08/14 | 2014-00134 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Requirements power sales agreements with Nebraska entities. |
| 09/14 | E-015/CN-12-1163 Direct | MN | Large Power Intervenors | Minnesota Power | Great Northern Transmission Line; cost cap; AFUDC v. current recovery; rider v. base recovery; class cost allocation. |
| 10/14 | 2014-00225 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Allocation of fuel costs to off-system sales. |
| 10/14 | ER13-1508 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Entergy service agreements and tariffs for affiliate power purchases and sales; return on equity. |
| 10/14 | 14-0702-E-42T 14-0701-E-D | WV | West Virginia Energy Users Group | First Energy-Monongahela Power, Potomac Edison | Consolidated tax savings; payroll; pension, OPEB, amortization; depreciation; environmental surcharge. |
| 11/14 | E-015/CN-12-1163 Surrebuttal | MN | Large Power Intervenors | Minnesota Power | Great Northern Transmission Line; cost cap; AFUDC v. current recovery; rider v. base recovery; class allocation. |
| 11/14 | 05-376-EL-UNC | OH | Ohio Energy Group | Ohio Power Company | Refund of IGCC CWIP financing cost recoveries. |
| 11/14 | 14AL-0660E | CO | Climax, CF&I Steel | Public Service Company of Colorado | Historic test year v. future test year; AFUDC v. current return; CACJA rider, transmission rider; equivalent availability rider; ADIT; depreciation; royalty income; amortization. |
| 12/14 | EL14-026 | SD | Black Hills Industrial Intervenors | Black Hills Power Company | Revenue requirement issues, including depreciation expense and affiliate charges. |
| 12/14 | 14-1152-E-42T | WV | West Virginia Energy Users Group | AEP-Appalachian Power Company | Income taxes, payroll, pension, OPEB, deferred costs and write offs, depreciation rates, environmental projects surcharge. |
| 01/15 | 9400-YO-100 Direct | WI | Wisconsin Industrial Energy Group | Wisconsin Energy Corporation | WEC acquisition of Integrys Energy Group, Inc. |
| 01/15 | 14F-0336EG 14F-0404EG | CO | Development Recovery Company LLC | Public Service Company of Colorado | Line extension policies and refunds. |
| 02/15 | 9400-YO-100 Rebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Energy Corporation | WEC acquisition of Integrys Energy Group, Inc. |
| 03/15 | 2014-00396 | KY | Kentucky Industrial Utility Customers, Inc. | AEP-Kentucky Power Company | Base, Big Sandy 2 retirement rider, environmental surcharge, and Big Sandy 1 operation rider revenue requirements, depreciation rates, financing, deferrals. |
| 03/15 | 2014-00371 2014-00372 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company and Louisville Gas and Electric Company | Revenue requirements, staffing and payroll, depreciation rates. |
| 04/15 | 2014-00450 | KY | Kentucky Industrial Utility Customers, Inc. and the Attorney General of the Commonwealth of Kentucky | AEP-Kentucky Power Company | Allocation of fuel costs between native load and off-system sales. |
| 04/15 | 2014-00455 | KY | Kentucky Industrial Utility Customers, Inc. and the Attorney General of the Commonwealth of Kentucky | Big Rivers Electric Corporation | Allocation of fuel costs between native load and off-system sales. |
| 04/15 | ER2014-0370 | MO | Midwest Energy Consumers’ Group | Kansas City Power & Light Company | Affiliate transactions, operation and maintenance expense, management audit. |
| 05/15 | PUE-2015-00022 | VA | Virginia Committee for Fair Utility Rates | Virginia Electric and Power Company | Fuel and purchased power hedge accounting; change in FAC Definitional Framework. |
| 05/15 09/15 | EL10-65 Direct, Rebuttal Complaint | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Accounting for AFUDC Debt, related ADIT. |
| 07/15 | EL10-65 Direct and Answering Consolidated Bandwidth Dockets | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Waterford 3 sale/leaseback ADIT, Bandwidth Formula. |
| 09/15 | 14-1693-EL-RDR | OH | Public Utilities Commission of Ohio | Ohio Energy Group | PPA rider for charges or credits for physical hedges against market. |
| 12/15 | 45188 | TX | Cities Served by Oncor Electric Delivery Company | Oncor Electric Delivery Company | Hunt family acquisition of Oncor; transaction structure; income tax savings from real estate investment trust (REIT) structure; conditions. |
| 12/15 01/16 | 6680-CE-176 Direct, Surrebuttal, Supplemental Rebuttal | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Power and Light Company | Need for capacity and economics of proposed Riverside Energy Center Expansion project; ratemaking conditions. |
| 03/16 03/16 04/16 05/16 06/16 | EL01-88 Remand Direct Answering Cross-Answering Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Bandwidth Formula: Capital structure, fuel inventory, Waterford 3 sale/leaseback, Vidalia purchased power, ADIT, Blythesville, Spindletop, River Bend AFUDC, property insurance reserve, nuclear depreciation expense. |
| 03/16 | 15-1673-E-T | WV | West Virginia Energy Users Group | Appalachian Power Company | Terms and conditions of utility service for commercial and industrial customers, including security deposits. |
| 04/16 | 39971 Panel Direct | GA | Georgia Public Service Commission Staff | Southern Company, AGL Resources, Georgia Power Company, Atlanta Gas Light Company | Southern Company acquisition of AGL Resources, risks, opportunities, quantification of savings, ratemaking implications, conditions, settlement. |
| 04/16 | 2015-00343 | KY | Office of the Attorney General | Atmos Energy Corporation | Revenue requirements, including NOL ADIT, affiliate transactions. |
| 04/16 | 2016-00070 | KY | Office of the Attorney General | Atmos Energy Corporation | R & D Rider. |
| 05/16 | 2016-00026 2016-00027 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Need for environmental projects, calculation of environmental surcharge rider. |
| 05/16 | 16-G-0058 16-G-0059 | NY | New York City | Keyspan Gas East Corp., Brooklyn Union Gas Company | Depreciation, including excess reserves, leak prone pipe. |
| 06/16 | 160088-EI | FL | South Florida Hospital and Healthcare Association | Florida Power and Light Company | Fuel Adjustment Clause Incentive Mechanism re: economy sales and purchases, asset optimization. |
| 07/16 | 160021-EI | FL | South Florida Hospital and Healthcare Association | Florida Power and Light Company | Revenue requirements, including capital recovery, depreciation, ADIT. |
| 07/16 | 16-057-01 | UT | Office of Consumer Services | Dominion Resources, Inc. / Questar Corporation | Merger, risks, harms, benefits, accounting. |
| 08/16 | 15-1022-EL-UNC 16-1105-EL-UNC | OH | Ohio Energy Group | AEP Ohio Power Company | SEET earnings, effects of other pending proceedings. |
| 9/16 | 2016-00162 | KY | Office of the Attorney General | Columbia Gas Kentucky | Revenue requirements, O&M expense, depreciation, affiliate transactions. |
| 09/16 | E-22 Sub 519, 532, 533 | NC | Nucor Steel | Dominion North Carolina Power Company | Revenue requirements, deferrals and amortizations. |
| 09/16 10/16 | 15-1256-G-390P (Reopened) 16-0922-G-390P 10-2929-EL-UNC 11-346-EL-SSO 11-348-EL-SSO 11-349-EL-SSO 11-350-EL-SSO 14-1186-EL-RDR | WV OH | West Virginia Energy Users Group Ohio Energy Group | Mountaineer Gas Company AEP Ohio Power Company | Infrastructure rider, including NOL ADIT and other income tax normalization and calculation issues. State compensation mechanism, capacity cost, Retail Stability Rider deferrals, refunds, SEET. |
| 11/16 | 16-0395-EL-SSO Direct | OH | Ohio Energy Group | Dayton Power & Light Company | Credit support and other riders; financial stability of Utility, holding company. |
| 12/16 | Formal Case 1139 | DC | Healthcare Council of the National Capital Area | Potomac Electric Power Company | Post test year adjust, merger costs, NOL ADIT, incentive compensation, rent. |
| 01/17 | 46238 | TX | Steering Committee of Cities Served by Oncor | Oncor Electric Delivery Company | Next Era acquisition of Oncor; goodwill, transaction costs, transition costs, cost deferrals, ratemaking issues. |
| 02/17 | 16-0395-EL-SSO Direct (Stipulation) | OH | Ohio Energy Group | Dayton Power & Light Company | Non-unanimous stipulation re: credit support and other riders; financial stability of utility, holding company. |
| 02/17 | 45414 | TX | Cities of Midland, McAllen, and Colorado City | Sharyland Utilities, LP, Sharyland Distribution & Transmission Services, LLC | Income taxes, depreciation, deferred costs, affiliate expenses. |
| 03/17 | 2016-00370 2016-00371 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company, Louisville Gas and Electric Company | AMS, capital expenditures, maintenance expense, amortization expense, depreciation rates and expense. |
| 06/17 | 29849 (Panel with Philip Hayet) | GA | Georgia Public Service Commission Staff | Georgia Power Company | Vogtle 3 and 4 economics. |
| 08/17 10/17 | 17-0296-E-PC 2017-00179 | WV KY | Public Service Commission of West Virginia Charleston Kentucky Industrial Utility Customers, Inc. | Monongahela Power Company, The Potomac Edison Power Company Kentucky Power Company | ADIT, OPEB. Weather normalization, Rockport lease, O&M, incentive compensation, depreciation, income taxes. |
| 10/17 | 2017-00287 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Fuel cost allocation to native load customers. |
| 12/17 | 2017-00321 | KY | Attorney General | Duke Energy Kentucky (Electric) | Revenues, depreciation, income taxes, O&M, regulatory assets, environmental surcharge rider, FERC transmission cost reconciliation rider. |
| 12/17 | 29849 (Panel with Philip Hayet, Tom Newsome) | GA | Georgia Public Service Commission Staff | Georgia Power Company | Vogtle 3 and 4 economics, tax abandonment loss. |
| 01/18 | 2017-00349 | KY | Kentucky Attorney General | Atmos Energy Kentucky | O&M expense, depreciation, regulatory assets and amortization, Annual Review Mechanism, Pipeline Replacement Program and Rider, affiliate expenses. |
| 06/18 | 18-0047 | OH | Ohio Energy Group | Ohio Electric Utilities | Tax Cuts and Jobs Act. Reduction in income tax expense; amortization of excess ADIT. |
| 07/18 | T-34695 | LA | LPSC Staff | Crimson Gulf, LLC | Revenues, depreciation, income taxes, O&M, ADIT. |
| 08/18 | 48325 | TX | Cities Served by Oncor | Oncor Electric Delivery Company | Tax Cuts and Jobs Act; amortization of excess ADIT. |
| 08/18 | 48401 | TX | Cities Served by TNMP | Texas-New Mexico Power Company | Revenues, payroll, income taxes, amortization of excess ADIT, capital structure. |
| 08/18 | 2018-00146 | KY | KIUC | Big Rivers Electric Corporation | Station Two contracts termination, regulatory asset, regulatory liability for savings |
| 09/18 10/18 | 20170235-EI 20170236-EU Direct Supplemental Direct | FL | Office of Public Counsel | Florida Power & Light Company | FP&L acquisition of City of Vero Beach municipal electric utility systems. |
| 09/18 10/18 | 2017-370-E Direct 2017-207, 305, 370-E Surrebuttal Supplemental Surrebuttal | SC | Office of Regulatory Staff | South Carolina Electric & Gas Company and Dominion Energy, Inc. | Recovery of Summer 2 and 3 new nuclear development costs, related regulatory liabilities, securitization, NOL carryforward and ADIT, TCJA savings, merger conditions and savings. |
| 12/18 | 2018-00261 | KY | Attorney General | Duke Energy Kentucky (Gas) | Revenues, O&M, regulatory assets, payroll, integrity management, incentive compensation, cash working capital. |
| 01/19 | 2018-00294 2018-00295 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company, Louisville Gas & Electric Company | AFUDC v. CWIP in rate base, transmission and distribution plant additions, capitalization, revenues generation outage expense, depreciation rates and expenses, cost of debt. |
| 01/19 | 2018-00281 | KY | Attorney General | Atmos Energy Group | AFUDC v. CWIP in rate base, ALG v. ELG depreciation rates, cash working capital, PRP Rider, forecast plant additions, forecast expenses, cost of debt, corporate cost allocation. |
| 02/19 04/19 | UD-18-17 Direct Surrebuttal and Cross-Answering | New Orleans | Crescent City Power Users Group | Entergy New Orleans, LLC | Post-test year adjustments, storm reserve fund, NOL ADIT, FIN48 ADIT, cash working capital, depreciation, amortization, capital structure, formula rate plans, purchased power rider. |
| 03/19 | 2018-0358 | KY | Attorney General | Kentucky American Water Company | Capital expenditures, cash working capital, payroll expense, incentive compensation, chemicals expense, electricity expense, water losses, rate case expense, excess deferred income taxes. |
| 03/19 | 48929 | TX | Steering Committee of Cities Served by Oncor | Oncor Electric Delivery Company LLC, Sempra Energy, Sharyland Distribution & Transmission Services, L.L.C.., Sharyland Utilities, L.P. | Sale, transfer, merger transactions, hold harmless and other regulatory conditions. |
| 06/19 | 49421 | TX | Gulf Coast Coalition of Cities | CenterPoint Energy Houston Electric | Prepaid pension asset, accrued OPEB liability, regulatory assets and liabilities, merger savings, storm damage expense, excess deferred income taxes. |
| 07/19 | 49494 | TX | Cities Served by AEP Texas | AEP Texas, Inc. | Plant in service, prepaid pension asset, O&M, ROW costs, incentive compensation, self-insurance expense, excess deferred income taxes. |
| 08/19 | 19-G-0309 19-G-0310 | NY | New York City | National Grid | Depreciation rates, net negative salvage. |
| 10/19 | 42315 | GA | Atlanta Gas Light Company | Public Interest Advocacy Staff | Capital expenditures, O&M expense, prepaid pension asset, incentive compensation, merger savings, affiliate expenses, excess deferred income taxes. |
| 10/19 | 45253 | IN | Duke Energy Indiana | Office of Utility Consumer Counselor | Prepaid pension asset, inventories, regulatory assets and labilities, unbilled revenues, incentive compensation, income tax expense, affiliate charges, ADIT, riders. |

VCM26 Report pg. 4, “The in-service date for Unit 3 is projected in the fourth quarter 2022 but could be as late as the first quarter 2023.”  VCM26 Report pg. 5, “The in-service date for Unit 4 is now projected in the third quarter 2023 but could be as late as fourth quarter of 2023.”

Southern Company First Quarter 2022 10-Q, pg. 87.

Total Project Cost is the sum of capital / construction cost and financing cost for Georgia Power.

The $9,094 million capital cost is $11,280 million less $1,492 million Toshiba Parental Guarantee and $694 million the Company has agreed to absorb. These values and $3,384 million finance cost are consistent with VCM 26 table 1.1.

STF-230-10 part c details minor adjustments from load forecasts utilized in the 2022 IRP.

STF 230-6 discusses a change in generic capacity expansion options to include renewables and interim capacity need in years 2023-2024 filled by a short-term procurement assumption.

Table 1.1 of Georgia Power VCM 26 Report at page 11. The construction cost value of $8.4 billion does not reflect the $694 million of capital cost the Company has agreed to absorb so ratepayer exposure would be $7.7 billion through December 31, 2021.  The $2.9 billion in financing cost does not include the additional $840 million gross-up for income tax already charged to ratepayers.

Table 1.1 of Georgia Power VCM 26 Report at page 11.

The $2.0 billion value reflects the difference in the current estimate of the NCCR revenue requirement that customers will have to pay, which is $4.1 billion, and the estimate of $2.1 billion that would have been paid had the Project been completed in 2016/2017 from the original Certification.

The $9.5 billion is the sum of $9.1 billion in capital cost and $0.4 billion deferred financing cost (AFUDC).

These values include the impact on base rate tariff and fuel tariff. There would be an offset of approximately $1.85 per month from lower fuel cost.

Estimated Rate impact in 2018 assuming CWIP in rate base treatment. Certification Docket No. 27800, Hearing Request 1-2 (November 26, 2008)

These results are based on Staff’s Aurora cases using Staff’s gas price forecast and CO2 forecast assumptions, and include combinations of Low, Mod, and High gas forecasts, and $0/Ton, $10/Ton, and $20/Ton CO2 forecasts.

Computed from the Cumulative Revenue Requirements used to derive Figure 1, and the total energy produced by Vogtle Units 3 and 4 over their 60 year lives.

$9.1 billion in Capital / Construction costs and $0.4 billion in deferred financing cost (AFUDC).

See Para 1, 4, and 5 of the Stipulation in the Supplemental Information Review.

See Paragraph 8 of the Stipulation in the Supplemental Information.