Georgia Power Company’s

Solar Quarterly Construction Monitoring Report

Through June 30, 2022

This report is provided in accordance with the Georgia Public Service Commission’s (“Commission”) request for quarterly update reports regarding the solar self-build projects approved by the Commission in Docket Nos. 24505, 39028, and 40161.

Executive Summary

Pursuant to the Commission’s orders in Docket Nos. 24505, 39028 and 40161, Georgia Power Company (the “Company”) has achieved commercial operation and/or commenced design, procurement and construction of the solar self-build projects specified in the table below.  These solar self-build projects provide an economical supply of electric power for the Company’s customers and include projects that either (i) support United States military goals regarding renewable energy, energy resiliency and energy security, and provide a significant investment in Georgia military bases; (ii) provide renewable energy in support of the Company’s community solar program; or (iii) are being completed in conjunction with local state universities.

| Project | Project Size | Commercial Operation Date | Vendor |
| --- | --- | --- | --- |
| Military Portfolio |  |  |  |
| Fort Benning | 30 MWAC | 12/31/2015* | AMEC |
| Fort Gordon | 30 MWAC | 10/4/2016* | PowerSecure |
| Fort Stewart | 30 MWAC | 10/4/2016* | PowerSecure |
| Naval Submarine Base Kings Bay | 30 MWAC | 12/1/2016* | AMEC |
| Marine Corps Logistics Base (MCLB) Albany | 31 MWAC | 2/16/2018* | AMEC |
| April 2017 Portfolio |  |  |  |
| Robins Air Force Base | 128 MWAC | 4/15/2021* | Signal Energy |
| Comer Community Solar | 2 MWAC | 1/5/2018* | URE |
| Guyton Community Solar | 3.6 MWAC | 7/25/2019* | URE |
| Waynesboro Community Solar | 2.4 MWAC | 6/28/19* | URE |
| November 2017 Portfolio |  |  |  |
| Fort Valley State University | 10.8 MWAC | 1/21/2022* | IEA |
| Georgia College & State University | 3.5 MWAC | Q4 2025 | TBD |
| Moody AFB | 49.5 MWAC | 6/23/2020* | AMEC (Wood) |
| June 2018 Portfolio |  |  |  |
| LaGrange Solar | 0.8 MWAC | 2/28/20* | BL Harbert |

* Reflects the date on which the facility achieved commercial operation

Project Activity through June 30, 2022

1.   Military Portfolio

Expenditures on the projects through June 30, 2022 total REDACTED.  The following is a summary of work performed on each project through June 30, 2022:

Fort Benning

The Fort Benning Solar Facility declared commercial operation on December 31, 2015.  Final site stabilization was reached in Q2 2021.

Fort Gordon

The Fort Gordon Solar Facility declared commercial operation on October 4, 2016.  Final site stabilization is expected to be complete in Q3 2022.

Fort Stewart

The Fort Stewart Solar Facility declared commercial operation on October 4, 2016. Final site stabilization was reached in Q4 2018.

MCLB Albany

The Marine Corps Logistics Base Albany Solar Facility declared commercial operation on February 16, 2018.  Final site stabilization was achieved April 2, 2019.

2.   April 2017 Portfolio

Expenditures on the projects through June 30, 2022 total REDACTED. The following is a summary of work performed on each project through June 30, 2022:

Robins Air Force Base

Commercial Operation for the facility was achieved on April 15, 2021. Final site stabilization is expected to be complete in Q4 2022.

Guyton Community Solar (formerly Savannah Community Solar)

The Guyton Community Solar Facility declared commercial operation on July 25, 2019.  Final site stabilization was achieved on April 1, 2021.

Waynesboro Community Solar (formerly Vogtle Community Solar)

Commercial operation for the facility was achieved on June 28, 2019.  Final site stabilization was achieved on January 23, 2020.

3.   November 2017 Portfolio

Expenditures on the projects through June 30, 2022 total REDACTED.  The following is a summary of work performed on each project through June 30, 2022:

Fort Valley State University

The Fort Valley State University project is a 10.8 MWAC fixed tilt solar generation facility.  Commercial Operation for the facility was achieved on January 21, 2022. Georgia Power was selected as the winning bidder for the land lease request for proposal issued by the State of Georgia. A lease agreement for the site has been executed.  A notice to proceed was issued to the engineering procurement and construction contractor, IEA Constructors, on October 12, 2020. In compliance with the Commission order in Docket No. 40161, the Company provided the final engineering, procurement, and construction contract to Staff on November 16, 2020.

Georgia College & State University

The Georgia College & State University (GCSU) project is a 3.5 MWAC fixed tilt solar generation facility. The Company anticipates the project will achieve commercial operation in Q4 of 2025. The Georgia College & State University land RFP to build a solar plant was awarded to Georgia Power on April 20, 2020. However, recent developments with the original site will require GPC to find a new site at GCSU which has changed the expected in-service date.

Moody Air Force Base

Commercial Operation for the facility was achieved on June 23, 2020.  Final site stabilization was achieved December 21, 2020.

4.   June 2018 Portfolio

Expenditures on the projects through June 30, 2022 total REDACTED. The following is a summary of work performed on each project through June 30, 2022:

LaGrange Solar

Commercial operation for the facility was achieved on February 28, 2020.  Final site stabilization was achieved August 31, 2020.

Projected Spending Curve as of June 30, 2022

Table 1 Military Portfolio - Total Projected Spending Curve by Quarter (dollar amounts are reflected in millions)

A projected spending curve by quarter for the Company’s military solar project portfolio is shown below, along with expenditures to date.  The variance is primarily due to a shift in timing of certain expenditures and completion of final punch list items.

|  |  | Cumulative | Cumulative | Cumulative |
| --- | --- | --- | --- | --- |
|  | Projected | Projected | Actual | Variance |
|  | Spend | Spend | Expenditures | To Date |
| Through Q4 – 2014 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2015 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2015 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2015 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2015 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2016 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2016 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2016 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2016 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2022 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2022 | REDACTED | REDACTED | REDACTED | REDACTED |

Table 2 April 2017 Portfolio - Total Projected Spending Curve by Quarter (dollar amounts are reflected in millions)

A projected spending curve by quarter for the Company’s solar self-build April 2017 Portfolio is shown below, along with expenditures to date.  The variance is primarily due to a shift in mobilization and construction for the Robins AFB and community solar projects.

|  |  | Cumulative | Cumulative | Cumulative |
| --- | --- | --- | --- | --- |
|  | Projected | Projected | Actual | Variance |
|  | Spend | Spend | Expenditures | To Date |
| Q1 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2022 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2022 | REDACTED | REDACTED | REDACTED | REDACTED |

Table 3 November 2017 Portfolio - Total Projected Spending Curve by Quarter (dollar amounts are reflected in millions)

A projected spending curve by quarter for the Company’s solar self-build November 2017 Portfolio is shown below, along with expenditures to date.

|  |  | Cumulative | Cumulative | Cumulative |
| --- | --- | --- | --- | --- |
|  | Projected | Projected | Actual | Variance |
|  | Spend | Spend | Expenditures | To Date |
| Q1 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2022 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2022 | REDACTED | REDACTED | REDACTED | REDACTED |

Table 4 June 2018 Portfolio - Total Projected Spending Curve by Quarter (dollar amounts are reflected in millions)

A projected spending curve by quarter for the Company’s solar self-build June 2018 Portfolio is shown below, along with expenditures to date.

|  |  | Cumulative | Cumulative | Cumulative |
| --- | --- | --- | --- | --- |
|  | Projected | Projected | Actual | Variance |
|  | Spend | Spend | Expenditures | To Date |
| Q1 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 – 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 – 2022 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 – 2022 | REDACTED | REDACTED | REDACTED | REDACTED |

Robins Air Force Base

Figure 1 Arial (Q2 2021)

Moody Air Force Base

Figure 1 Array, Substation & Site Stabilization (Q4 2020)

Figure 2 Array & Site Stabilization (Q4 2020)

Guyton Community Solar

Waynesboro Community Solar

LaGrange Solar

Fort Valley Solar