# DIRECT TESTIMONY OF
AARON P. ABRAMOVITZ, JEREMIAH C. HASWELL, AND John B. Williams

# IN SUPPORT OF GEORGIA POWER COMPANY’S

# APPLICATION TO ADJUST RATES TO INCLUDE REASONABLE AND PRUDENT PLANT VOGTLE UNITS 3 AND 4 COSTS

# DOCKET NO. 29849

INTRODUCTION

Q.	PLEASE STATE YOUR NAMEs, TITLEs, AND BUSINESS ADDRESSes.

A.	My name is Aaron P. Abramovitz. I am the Executive Vice President, Chief Financial Officer, and Treasurer for Georgia Power Company (“Georgia Power” or the “Company”). My business address is 241 Ralph McGill Boulevard N.E., Atlanta, Georgia 30308.

My name is Jeremiah C. Haswell. I am the Project Oversight Director at Georgia Power. My business address is 241 Ralph McGill Boulevard, N.E., Atlanta, Georgia 30308.

My name is John B. Williams. I am the Southern Nuclear Operating Company (“Southern Nuclear”) Vice President of Business Operations for Plant Vogtle Units 3 and 4 (the “Project”). My business address is 7825 River Road, Waynesboro, Georgia 30830.

Q. 	Mr. Abramovitz, please summarize your education and professional experience.

A.	I graduated from the University of Georgia with a Bachelor of Business Administration in Finance and Management Information Systems. I joined Southern Company as a contractor in the Financial Strategy and Decision Support organization. This was followed by a series of Financial Analyst roles in various disciplines that included Financial Planning, Financial Analysis, and Regulatory Support. From there I transitioned to Georgia Power to serve as the Coordinator for Forestry and Right of Way services. In 2008, I was assigned to the Kemper Project in Mississippi, where I served in financial leadership roles of increasing responsibility, eventually serving as the Project’s Finance Director, where I was responsible for governance, reporting, regulatory support, and communications to Executives and the Board of Directors. In 2015, I returned to Atlanta to serve as the Director of Investor Relations for Southern Company, where I was responsible for Southern Company’s communications and relationships with the investment community. In 2018, I was named the Southern Nuclear Vogtle Units 3 and 4 Vice President of Business Operations. In this role, I had responsibility for Southern Nuclear’s Project Controls, Risk Management, Budgeting and Reporting, and Commercial Analysis & Controls. I moved to my current role as Executive Vice President, Chief Financial Officer, and Treasurer for Georgia Power in September 2021. I now oversee all accounting and finance functions for the Company including financial reporting, regulatory accounting, financial planning, analysis, and enterprise risk management.

Q.	Mr. Abramovitz, have you previously testified before the Georgia Public Service Commission (“Commission”)?

A.	Yes. I testified in the Vogtle Construction Monitoring (“VCM”) proceeding, Docket No. 29849, regarding the Nineteenth, Twentieth/Twenty-first, Twenty-second, Twenty-third, and Twenty-fourth Semi-annual VCM Reports; the Plant Vogtle Unit 3 and Common Rate Adjustment proceeding in Docket No. 43838 (“Unit 3 Rate Adjustment”); and the Company’s 2022 base rate case proceeding in Docket No. 44280 (“2022 Rate Case”).

Q. 	Mr. Haswell, please summarize your education and professional experience.

A.	I graduated from the University of Alabama at Birmingham with a Bachelor of Science degree in Mechanical Engineering and a Master of Science degree in Civil Engineering (Construction Management focus). I completed a Master of Business Administration at Augusta University and am a licensed Professional Engineer. I joined Southern Company as an Engineer in Southern Company Services Research and Technology Management focusing on new technology deployment in the existing operating fleet. I held multiple Team Leader roles in the areas of Maintenance, Engineering, and Compliance at Alabama Power Company’s Plant Gorgas. In 2012, I moved to Plant Vogtle Units 3 and 4 in the Construction Compliance organization and later to the role of Construction Compliance Supervisor for the Turbine Island and Balance of Plant. I am currently the Project Oversight Director with responsibility for regulatory filings for the Project, compliance with Georgia Power’s loan guarantee with the Department of Energy (“DOE”), Project oversight, risk management, and lead interface with the Commission Public Interest Advocacy Staff (“PIA Staff”), Construction Monitor, and the other Project Owners (Oglethorpe Power Corporation, the Municipal Electric Authority of Georgia, and Dalton Utilities, through the Board of Water, Light and Sinking Fund Commissioners of the City of Dalton) (collectively, the “Co-Owners”).

Q.	Mr. Haswell, have you previously testified before the commission?

A.	Yes. I testified in Docket No. 29849 regarding the Thirteenth, Fourteenth, Fifteenth, Seventeenth, Eighteenth, Nineteenth, Twentieth/Twenty-first, Twenty-second, Twenty-third, Twenty-fourth, Twenty-fifth, Twenty-sixth, Twenty-seventh, and Twenty-eighth Semi-annual VCM Reports.

Q.	Mr. Williams, please summarize your education and professional experience.

A.	I graduated from the Georgia Institute of Technology with a bachelor’s degree in nuclear and radiological engineering. I am currently the Vice President of Business Operations for Southern Nuclear Plant Vogtle Units 3 and 4. I joined Southern Nuclear in 2005 and have more than 20 years of engineering and nuclear fuel experience and have served in several leadership positions throughout the Southern Nuclear organization, including Plant Hatch Engineering Director, Nuclear Fuels and Analysis Director, and Interim Engineering Vice President.

I have represented Southern Nuclear on the DOE Industry Advisory Boards for the Advanced Fuels Campaign and the Nuclear Energy Advanced Modeling and Simulation program. I have also served as the utility lead for the Nuclear Energy Institute’s (“NEI”) Accident Tolerant Fuel Working Group’s Licensing and Safety Benefits Task Force, leading the team that introduced the first Accident Tolerant Fuel into a commercial reactor at Plant Hatch in 2018 and Plant Vogtle in 2019.

Q.	Mr. Williams, have you previously testified before the commission?

A.	Yes. I testified in Docket No. 29849 regarding the Twenty-sixth, Twenty-seventh, and Twenty-eighth Semi-annual VCM Reports.

Q.	What is the purpose of your testimony?

A.	The purpose of our testimony is to support the Company’s Application to Adjust Rates to Include Reasonable and Prudent Vogtle Units 3 and 4 Costs (“Application”) submitted in this docket on August 30, 2023, as well as the Stipulation reached on August 29, 2023. The Application and this testimony are filed to implement the Commission’s January 11, 2018, Order on the Seventeenth Semi-Annual VCM Report in Docket No. 29849 (“VCM 17 Order”), which provided that once fuel load for Unit 4 is reached, the Company may make a filing with the Commission to determine the adjustment to retail base rates necessary to include the remaining amounts for Units 3 and 4 into retail rate base. During review of this Application, the Commission will determine the remaining issues pertaining to the prudence of costs incurred on Vogtle Units 3 and 4. Our testimony is consistent with the Commission’s intent and directives as stated in the VCM 17 Order, the Commission’s January 3, 2017, Supplemental Information Review (“SIR”) Order Adopting Stipulation in Docket No. 29849 (“SIR Final Order”), and the Commission’s November 15, 2021, Order Adopting Stipulation in Docket No. 43838 regarding Georgia Power’s Application to Adjust Rates to Include Certain Plant Vogtle Unit 3 and Common Costs (“Unit 3 Rate Adjustment Order”).

Q.	DESCRIBE THE STIPULATION BETWEEN PIA STAFF, THE COMPANY, AND INTERVENORS IN THIS CASE.

A.	On August 29, 2023, Georgia Power, PIA Staff, the Georgia Association of Manufacturers, Georgia Interfaith Power & Light, Georgia Watch, and Partnership for Southern Equity (the “Stipulating Parties”) signed a stipulated agreement resolving all remaining issues for determination by the Commission regarding the reasonableness, prudence, and cost recovery for the remaining costs associated with the Project (“Stipulation”). The Stipulating Parties agreed that $7.562 billion is a reasonable and prudent total construction and capital cost for the Project to be included in rate base. The agreed-to reduction from Georgia Power’s total construction and capital cost takes into consideration the length of time to construct the Project, replacement energy costs incurred during the extended construction time, and other issues such as the amount of rework required, scheduling of activities, testing, and productivity. The Stipulation addresses the cost recovery of financing costs, projected operation and maintenance (“O&M”) expenses, depreciation expense, nuclear decommissioning accrual, and property taxes, net of projected production tax credits (“PTCs”), as well as nuclear fuel plant and materials and supplies inventory. The Stipulation also addresses the cessation of the Nuclear Construction Cost Recovery (“NCCR”) tariff and what happens if the Units do not initially operate as intended, among other things.

The Company supports the Stipulation as a fair and reasonable resolution of the outstanding issues regarding cost recovery for Vogtle Units 3 and 4. As with any settlement, no single party received everything it sought as a proposed resolution. The Stipulation considers many of the issues raised by PIA Staff and Intervenors in the VCM proceedings throughout the life of the Project. The Stipulating Parties worked hard to look beyond single issues to reach an agreement. The resulting Stipulation strikes an appropriate balance among complex, technical issues and provides for the recovery of reasonable and prudent costs for the Project.

Q.	Please summarize the Company’s request in this case.

    - A.	In compliance with the VCM 17 Order, the SIR Final Order, and the Unit 3 Rate Adjustment Order, the Company seeks Commission approval of the following requests:

- Find the Stipulation to be reasonable and in the best interest of customers;

- Find a total construction and capital cost for Vogtle Units 3 and 4 of $7.562 billion to be reasonable and prudent and approve the additional transfer of $5.462 billion ($7.562 billion less $2.1 billion already reflected in base rates) into the Company’s rate base upon Vogtle Unit 4 achieving Commercial Operation;

- Approve the recovery in rate base of the associated Allowance for Funds Used During Construction (“AFUDC”) financing costs on the construction and capital cost above the $4.418 billion certified cost up to the requested $7.562 billion, which is estimated to be approximately $437 million;

- Approve the recovery in retail base rates of depreciation expense, projected O&M expenses, nuclear decommissioning accrual, and property taxes, net of the projected production tax credits, as reflected in the Company’s Minimum Filing Requirements (“MFRs”);

- Approve the recovery of projected nuclear fuel plant and materials and supplies inventory in rate base as reflected in the MFRs, as well as the deferred interest on nuclear fuel;

- Approve the recovery in retail base rates of any deferred depreciation and deferred financing related to Unit 3 and Common facilities accumulated since Unit 3 was placed in service;

- Approve the transfer to rate base of the regulatory assets related to the deferred depreciation and deferred financing of Unit 3 and Common facilities accrued since Unit 3 was placed in service and the deficient accumulated deferred income taxes (“ADITs”) associated with Vogtle Units 3 and 4 resulting from the Tax Cuts and Jobs Act (“TCJA”);

- Consistent with O.C.G.A. § 46-2-25(c), approve the continued collection of financing costs through the NCCR tariff until the effective date of the Unit 3 and 4 rate adjustment, at which point such financing costs would be collected through the Company’s general revenue requirements in retail base rates;

- Adjust retail base rates by $729 million on an annual basis effective the first month following Vogtle Unit 4 achieving Commercial Operation; and

- Following the final order in this Docket, approve the tariffs designed to collect the retail base rate adjustment.

### Q.	How is your testimony organized?

A. 	The remainder of our testimony is organized as follows:

- Section II outlines the overview of the Company’s request for cost recovery.

- Section III discusses the prudence and reasonableness of the total construction and capital cost for the Project based on the following:

  - Total construction and capital cost projected to be incurred ($10.188 billion)

  - Total reasonable construction and capital cost recoverable from customers ($8.826 billion)

  - Total construction and capital cost stipulated to be recovered ($7.562 billion)

- Section IV discusses the financing costs the Company seeks to add to rate base and the treatment of the NCCR tariff.

- Section V discusses the operating expenses the Company seeks to include in rate base.

- Section VI discusses replacement fuel costs.

- Section VII discusses the appropriate retail base rate adjustments to recover the Vogtle Units 3 and 4 costs.

- Section VIII discusses Commercial Operation.

- Section IX discusses additional provisions agreed to by the Stipulating Parties.

OVERVIEW

Q.	WHAT HAS BEEN THE COMPANY’S NUMBER ONE PRIORITY WITH THE PROJECT?

A.	Since the Project’s inception, safety has been the number one priority in the design and construction of Vogtle Units 3 and 4. Throughout construction, the Project maintained an OSHA Recordable Incidence Rate below the heavy construction industry average. Also, throughout construction of the Project, the Company has been inspected under the Nuclear Regulatory Commission’s (“NRC”) Construction Reactor Oversight Process – an in-depth oversight and review process that enables the NRC to confirm the reactors are built according to NRC design and allows the NRC to objectively evaluate Southern Nuclear’s effectiveness in assuring construction quality while communicating performance assessment results to the public. As discussed in the Application and numerous VCM proceedings, the Company ensured that the priorities of safety, quality, and compliance were never outweighed by factors such as cost or schedule. As the Units transition to operation, safety and quality will remain the top priority, consistent with Southern Nuclear and Georgia Power’s industry-leading operational standards.

Q.	PLEASE DESCRIBE THE VOGTLE UNITS 3 AND 4 COSTS THE COMPANY IS SEEKING TO RECOVER.

A.	Georgia Power requests recovery of the reasonable and prudent construction and capital cost, financing costs, and operating costs associated with the completion of Vogtle Units 3 and 4 and Common facilities. While all the costs incurred to complete Vogtle Units 3 and 4 were prudent and reasonable, the Company decided to forego recovery of some costs from customers. As shown in Georgia Power’s Application, the Company supports that $8.826 billion in total construction and capital cost is reasonable to recover from customers. However, as stated in the Stipulation, the Company, PIA Staff, and the other Stipulating Parties have agreed that the Company is requesting to recover $7.562 billion in total construction and capital cost, along with the accompanying AFUDC financing costs and operating costs, among other things. Georgia Power is seeking recovery of $2.626 billion less than the Company’s projected total construction and capital cost for the Project.

Figure 1 below is a graphical representation of the Project costs and the portions of those costs already found to be reasonable or prudent, what amount the Company elected to forego recovery of from customers, and what amount was agreed to in the Stipulation to be recovered from customers.

Figure 1: Total Project Construction and Capital Cost

Table 1 below takes into account the amounts agreed to in the Stipulation and summarizes the Company’s request of total construction and capital, financing, and operating costs for Vogtle Units 3 and 4. Table 1 represents the total Project costs for which Georgia Power seeks a Commission finding of reasonableness and prudence. As approved in the Unit 3 Rate Adjustment Order, $2.1 billion of the $7.562 billion is already being recovered in current rates for Unit 3 and Common construction and capital cost along with Unit 3 operating costs. For this proceeding, the base rate increase requested only reflects the incremental costs not reflected in current rates.

Table 1: Summary of Request

| Capital Cost Requested for Recovery | Amount (millions) 13-Month Average |
| --- | --- |
| Construction and Capital Cost | $7,562 |
| AFUDC Financing Costs | 437 |
| (less) Capital Accumulated Reserve | (131) |
| Nuclear Fuel (net of Accumulated Reserve) | 232 |
| Regulatory Assets | 215 |
| Spare Parts Inventory | 54 |
| Accumulated Deferred Income Taxes | 212 |
| Total | $8,580 |

Note – Details may not add to total due to rounding.

| Operating Expense Requested for Recovery | Amount (millions) |
| --- | --- |
| O&M Expense | $155 |
| Depreciation Expense | 134 |
| Property Taxes | 58 |
| Nuclear Decommissioning | 15 |
| Regulatory Assets Amortization | 23 |
| (less) Production Tax Credits | (137) |

Q.	WHY IS IT APPROPRIATE FOR CUSTOMERS TO PAY FOR THE COSTS ASSOCIATED WITH VOGTLE UNITS 3 AND 4?

- A.	Upon Commercial Operation, Unit 4 will be placed into service and join Unit 3 in operations for the benefit of Georgia Power’s retail customers. With Units 3 and 4 in commercial service as used and useful, the cost to construct, finance, and operate Units 3 and 4 are reasonable and prudent costs incurred by the Company to serve customers and are appropriate costs to be recovered from customers.

Q.	HOW WILL GEORGIA POWER’S CUSTOMERS BENEFIT FROM UNITS 3 AND 4 GOING INTO SERVICE?

A.	At Georgia Power, customers are at the center of everything we do, and we are unwavering in our commitment to meet the energy needs of our 2.7 million customers and the communities we are privileged to serve. Vogtle Units 3 and 4 will add two reliable, carbon-free, baseload units to the Georgia Power generation fleet and will serve Georgia Power customers for the next 60 to 80 years. Notwithstanding the high upfront capital costs, nuclear energy remains one of the lowest-cost and most reliable energy sources for our state and our customers. Vogtle Units 3 and 4 will provide necessary baseload energy for our customers along with fuel diversity to help protect customers from unpredictable fluctuations in fuel prices. Once completed, Vogtle Units 1 through 4 are expected to produce more carbon-free electricity each year than any other energy facility currently operating in the United States.

Q.	WHAT ARE THE BENEFITS TO THE STATE OF GEORGIA FROM UNITS 3 AND 4 GOING INTO SERVICE?

A.	As Georgia’s economy and population continue to grow and thrive, Vogtle Units 3 and 4 will be critical to Georgia Power’s ability to continue meeting the evolving energy needs of customers and this state. Georgia is one of the fastest growing states in the country, driven in large part by Georgia’s position as one of the best states in the nation in which to do business. The addition of these Units will provide businesses and industries with the confidence to stay, expand, or locate in our state, which will help ensure Georgia’s economy continues to grow.

Georgia Power engaged NEI to analyze the economic impact of the Project and to help illustrate the numerous benefits of the Project to the state. A copy of the NEI Study is provided as Exhibit 1 to this testimony. The NEI Study estimates that from 2009 through March 2023, construction of Vogtle Units 3 and 4 supported an average of nearly 16,800 direct and secondary jobs in Georgia alone and created significant economic benefits for the state: $46.9 billion in economic benefit from construction; $27.2 billion increase in gross state product; and $31 billion in disposable personal income. The Project produced benefits outside the state of Georgia as well, supporting an average of more than 4,300 jobs annually during the same time period, and $17.9 billion in economic benefit from construction for the rest of the country. Once both Units are operational, the Project will provide more than 800 permanent jobs to the local community and provide an average annual economic benefit of $2.5 billion.

In support of a growing Georgia, the new Vogtle Units play a vital role in meeting customers’ evolving expectation that a larger portion of their energy needs be served by carbon-free, emission-free energy. Nuclear units like Vogtle 3 and 4 generate large amounts of electricity without emitting greenhouse gases and are an essential source of safe, reliable electricity that meets both environmental needs and the demand for electricity. Vogtle Units 3 and 4 are expected to generate over 281 million megawatt-hours and avoid more than 103 million metric tons of carbon dioxide by 2057. The Project has and will provide significant economic benefits for the state and will provide substantial carbon-free energy with low fuel costs throughout the life of the Units.

PRUDENCE AND REASONABLENESS OF PROJECT CONSTRUCTION AND CAPITAL COST

Standard for Cost Recovery

Q.	WHAT COSTS CAN BE INCLUDED FOR RECOVERY FROM CUSTOMERS IN BASE RATES?

A.	The Company may recover costs incurred in the construction of the Project in base rates if they are found to be both prudent and reasonable. We are here to testify regarding the decisions and actions that make these costs appropriate for recovery.

Q.	WHAT IS THE STANDARD FOR PRUDENCY, AS YOU UNDERSTAND IT?

A.	We understand that the prudency standard in Georgia evaluates whether decisions and actions were reasonable under the circumstances, given the facts and circumstances that were known or should have been known at the time the decision was made, without the benefit of hindsight. Essentially, this standard asks the Commission to put itself in the shoes of the Vogtle Project managers at the time critical decisions were being made, and ask itself “what would a reasonable manager have done, and was what the Vogtle Project managers did within an acceptable zone of reasonableness?” In addition to what has been conveyed to this Commission through the VCM process and through the Application, we are here to testify as to the prudence of the decisions and actions on the Project for which costs were incurred and are sought for recovery.

Q. 	WHAT STANDARD OF CARE IS APPLIED WHEN EVALUATING PRUDENCY?

A.	When evaluating prudency, the “reasonable manager” standard of care is applied. Under this standard, decisions are assessed based on what a reasonable manager would have done under the same or similar circumstances. Given this standard, a reasonable manager is one who is qualified by education, training, and experience to make the decision or take the action, using the information available and applying logical reasoning processes.

Witnesses Miller and Skaggs have submitted testimony as to the reasonable manager standard based on their industry experience, including their time as executives at Duke Energy and Tennessee Valley Authority (“TVA”), respectively.

Q.	WHAT IS THE STANDARD FOR REASONABLENESS?

A.	As we understand it, reasonableness goes to the cost associated with prudent decisions and comes into play when a utility seeks to add costs over the certified amount to rate base. The Company must not only establish that the costs above the certified amount are the product of prudent decision-making, but also demonstrate that the amounts of those costs are reasonable. In other words, while the decision to incur a certain cost may have been prudent, the amount of that cost may be excessive or unreasonable and therefore not appropriately chargeable to customers.

Q. 	WHAT STANDARD OF CARE IS APPLIED WHEN EVALUATING REASONABLENESS?

Reasonableness, like prudency, is also satisfied by the reasonable manager standard of care. As discussed above, the testimony of witnesses Miller and Skaggs will discuss the reasonable manager standard as it applies to prudency and reasonableness based on their extensive industry experience.

Total Construction and Capital Cost Projected to be Incurred

Q.	WHAT IS GEORGIA POWER’S SHARE OF THE TOTAL PROJECT COST?

A.	As of the Company’s VCM 29 filing, Georgia Power’s projected total Project construction and capital cost is expected to be $10.188 billion, which includes $33 million for PIA Staff’s construction monitoring fees and after accounting for the Toshiba Parent Guaranty funds, net of customer refunds, which are applied to reduce the capital cost. As of June 30, 2023, Georgia Power’s total Project construction and capital cost was $9.823 billion, including $25 million expended for PIA Staff’s construction monitoring fees and after accounting for the Toshiba Parent Guaranty funds.

Q.	DOES THE PROJECTED TOTAL CONSTRUCTION AND CAPITAL COST OR ACTUAL CONSTRUCTION AND CAPITAL COST INCURRED TO DATE INCLUDE COSTS ASSOCIATED WITH THE COST-SHARING AND TENDER PROVISIONS WITH THE CO-OWNERS?

A.	No. The $10.188 billion projection excludes approximately $407 million of costs associated with the cost-sharing and tender provisions of the joint ownership agreement for which Georgia Power will not seek recovery from retail customers. Of this estimated $407 million, $121 million was incurred as of June 30, 2023, related to Georgia Power’s cost-sharing with Oglethorpe Power Corporation and Dalton Utilities and the September 29, 2022, settlement agreement with Municipal Electric Authority of Georgia (“MEAG”) Power.

Q.	IS THE CONSTRUCTION AND CAPITAL COST INCURRED BY THE COMPANY PRUDENT AND REASONABLE?

A.	Yes. All construction and capital cost incurred to date on Units 3 and 4 were prudently and reasonably incurred. All costs incurred on the Project to date were necessary to complete construction and bring Units 3 and 4 online and in service for Georgia Power’s customers.

Total Reasonable Construction and Capital Cost Recoverable from Customers

Q.	IS THE COMPANY REQUESTING RECOVERY OF ALL ITS PRUDENT AND REASONABLE PROJECTED TOTAL CONSTRUCTION AND CAPITAL COSTS FROM CUSTOMERS?

A.	No. Of the $10.188 billion in total construction and capital cost that the Company expects to incur, the Company has put forth the necessary support in its prudence request to justify the reasonableness, prudence, and recovery of $8.826 billion in total construction and capital cost. As described in the Application, the Company elected to forego recovery of $1.362 billion in reasonable and prudent construction and capital cost incurred to bring Vogtle Units 3 and 4 through construction, testing, startup and into operations to serve our 2.7 million customers. This amount includes the $694 million in increased projected total Project costs the Company stated in VCM 19 that it would not seek to recover from customers following the cost reforecast conducted in 2018. Importantly, as we will discuss later in our testimony, in total and as a part of the Stipulation with the PIA Staff and other Stipulating Parties, Georgia Power has agreed to not request recovery of $2.626 billion in construction and capital cost from customers.

Q.	IS THE COMPANY’S DECISION NOT TO REQUEST RECOVERY OF CERTAIN COSTS AN ADMISSION OF IMPRUDENCE?

A.	Absolutely not. The decision to forego recovery of certain costs is not an admission of imprudence or a declaration that such costs were unreasonable. While all the construction and capital cost incurred for Units 3 and 4 were both prudent and reasonable, as described further below, Georgia Power decided to forego seeking recovery of costs above $8.826 billion for the benefit of customers.

Included Costs

Q.	WHAT COSTS ARE INCLUDED IN THE $8.826 BILLION THE COMPANY ESTIMATES IS REASONABLE AND PRUDENT TO RECOVER FROM CUSTOMERS?

A.	Georgia Power’s Application and the VCM record support the reasonableness and prudence of $8.826 billion of total Project construction and capital cost for Vogtle Units 3 and 4. For the avoidance of doubt, the Company is not requesting Commission approval to recover $8.826 billion – the Company is requesting recovery of the $7.562 billion agreed to in the Stipulation. The Company presents the breakout of reasonable and prudent construction and capital cost included up to $8.826 billion as additional support for the costs that are being requested for recovery. The construction and capital cost included within the $8.826 billion are identified in Table 2 and described below were all reasonable and prudent costs necessary to complete the Project.

Table 2: Reasonable and Prudently Incurred Costs Included in the $8.826 Billion

| Cost | Amount (millions) |
| --- | --- |
| VCM 17 Previously Deemed Reasonable Amount | $7,293 |
| COVID-19 Costs (Schedule and Mitigation) | $200 |
| Change in Scope | $142 |
| Procurement of Materials and Equipment | $105 |
| Additional Engineering Resources (headcount and duration) | $48 |
| Direct Construction Productivity/Performance | $413 |
| Schedule Changes (non-COVID) Driven by Scope Increases | $517 |
| Miscellaneous (Taxes, Regulatory Support Costs, and IT) | $75 |
| Construction Monitor | $33 |
| Total | $8,826 |

Q.	PLEASE DESCRIBE THE COMPANY’S DECISION TO START WITH $7.293 BILLION IN ITS DETERMINATION OF REASONABLE AND PRUDENTLY INCURRED COSTS.

A.	In VCM 17, the Commission approved the revised construction and capital cost forecast of $7.3 billion and found that any costs spent up to the revised cost forecast were deemed reasonable. Through the VCM process, the Commission has verified and approved all expenditures up to the revised, approved construction and capital cost of $7.3 billion and has reviewed, but not verified and approved, all expenditures above that amount. Considering the robust process and record created through the VCM process, it made sense to build the Company’s reasonable request by starting with the $7.293 billion the Commission has already deemed reasonable.

Q.	WHAT COSTS ARE CAPTURED IN THE COVID-19 SCHEDULE AND MITIGATION COSTS?

A.	The impacts from the COVID-19 pandemic were the result of circumstances outside of the Company and the Project Team’s direct control. The Company acted prudently in its management of the COVID-19 pandemic and was able to keep the Project moving forward while keeping the safety of the workforce at the forefront of all decisions. The Company incurred approximately $40 million in direct costs related to mitigation measures implemented to keep the workforce safe and healthy (e.g., onsite medical village, vaccines, testing, masking, hand sanitizer and cleaning stations). The Company also incurred approximately $160 million in schedule impacts due to productivity challenges from higher-than-normal absenteeism for craft and non-manual personnel, social distancing requirements, and disruption to planned and ongoing work (direct construction, subcontracts, testing) due to mandatory isolation restrictions. Finally, the Project’s estimated COVID costs also incorporate the impacts from the Project’s reduction in force measures taken at the onset of the pandemic to create greater physical separation and less workspace congestion on site.

Q.	WHAT COSTS ARE REQUESTED RELATED TO CHANGE IN SCOPE?

A.	Following the Westinghouse Electric Company (“WEC”) Bankruptcy and Southern Nuclear’s transition to site leadership, it became clear that prior estimates for certain scopes of work were inadequately estimated. In response, Southern Nuclear routinely led walkdowns of the entire site to evaluate progress, status, and work to be completed, and used this information to reforecast the work scopes for Bechtel and other subcontractors to account for the differences observed. For example, the Company identified increases in civil construction, subcontractor, and unscheduled electrical commodity installation scope during the VCM 20/21 reporting period and again following a quantity verification effort during the May 2019 schedule re-baseline. Southern Nuclear also adjusted scope estimates for coatings and fireproofing, concrete and rebar commodity increases for building completion, instrumentation in the plant, and various commodity fabrication. The addition of quantities (scope) and corresponding manhours to complete the required scope for the Project is a reasonable and prudent cost necessary to complete the Project.

Q.	WHY IS IT APPROPRIATE FOR THE COMPANY TO RECOVER COSTS RELATED TO PROCUREMENT OF MATERIALS AND EQUIPMENT ABOVE WHAT WAS PREVIOUSLY DEEMED REASONABLE?

A.	Procurement needs varied greatly over the course of the Project. As the Project progressed, design specifications and field routing estimates changed, which resulted in revised procurement needs and cost estimates for additional materials and equipment. The estimated $105 million in additional procurement costs were required to complete the Project and are prudent and reasonable costs to recover from customers.

Q.	WHAT COSTS ARE INCLUDED IN THE ADDITIONAL ENGINEERING RESOURCES CATEGORY?

A.	Additional engineering resources beyond those forecasted in VCM 17 were required to support documentation closeout for the Inspection, Test, Analysis, and Acceptance Criteria (“ITAAC”), Engineering Service Requests, and Non-Conformances among other requirements. The Project’s engineering estimates were adjusted, as needed, throughout the construction, testing, and startup process as more resources were required to ensure both Units would operate as designed, as well as to ensure successful completion of construction, documentation closure, and necessary testing. These costs are reasonable and prudent as they were necessary to ensure the plant was built in accordance with design and licensing basis requirements and would operate safely for the benefit of customers.

Q.	PLEASE DESCRIBE THE DIRECT CONSTRUCTION PRODUCTIVITY/ PERFORMANCE COST CATEGORY.

A.	The Direct Construction Cost Performance Index (“CPI”) is relevant to Bechtel Direct Construction scope of work and measures the ratio of hours spent on an activity relative to hours earned. CPI is a measure of cost efficiency whereby a CPI above 1.0 indicates that the Project is spending more hours than planned to complete a task and a CPI below 1.0 indicates that the Project is spending fewer hours than planned to complete a task. The cumulative Bechtel Direct Construction CPI for the Project at the end of direct construction was approximately 1.66. The Project undertook several mitigation actions such as changing craft staffing levels, minimizing non-productive work, and improving first time quality in an effort to mitigate productivity challenges with the goal of achieving a CPI of closer to 1.0. Southern Nuclear also conducted multiple craft productivity assessments and held site-wide staff stand downs related to productivity, production, and quality improvements. While performance was not consistent with the VCM 17 or 19 estimates, given the first of a kind nuclear construction for this Project and the evolution of the craft labor workforce, the incremental costs incurred for direct construction productivity and performance is reasonable and prudent.

Q.	PLEASE DESCRIBE THE NON-COVID SCOPE DRIVEN SCHEDULE CHANGE COSTS.

A.	As previously discussed, additional scope for civil construction and unscheduled electrical commodity installation was added to the Project after Southern Nuclear took over site leadership. As the schedule was extended to account for these increases in scope, the Project Team faced increases in cost that were dependent on the time added to the schedule as well as external factors in the economy that increased labor rates, such as competition and availability of skilled resources. Simply put, when more work needs to be done than originally planned, it takes more time to complete the work and, in turn, costs more to keep the right people on site to complete the work. The increases in manhours and time to complete were necessary for completion of the scope changes, and the costs associated with these scope-driven schedule changes are reasonable and prudent.

Q.	WHAT COSTS FALL INTO THE MISCELLANEOUS CATEGORY?

A.	This cost category includes costs for local Ad Valorem tax assessments as the installed cost of the Project increased, regulatory support cost increases, and Information Technology (“IT”) infrastructure cost increases. These cost increases are the time-related cost from Ad Valorem tax being capitalized and regulatory support resources being utilized for a longer period of time that are associated with the other reasonable and prudent costs previously described above and are reasonable and prudent ancillary costs to complete the Project.

Q.	ARE THE CONSTRUCTION MONITORING COSTS REASONABLE AND PRUDENT?

A.	Yes. In fact, the VCM 19 Stipulation approved by the Commission provided that the annual allowance for Construction monitoring is reasonable and prudent and not charged against or assumed to be within the $7.3 billion previously deemed reasonable in VCM 17.

Excluded Costs

Q.	WHAT COSTS WERE EXCLUDED FROM THE COMPANY’S CALCULATION OF THE $8.826 BILLION CONSTRUCTION AND CAPITAL COST?

A.	The Company and Southern Nuclear conducted a review of expenditures, and the Company decided to forego requesting recovery from customers for certain Project costs. The reasonable and prudent construction and capital cost incurred on the Project that are not included in the $8.826 billion identified by the Company are included in Table 3 and described below.

Table 3: Excluded Cost Categories

| Cost | Amount (millions) |
| --- | --- |
| VCM 19 Reforecast | $694 |
| Schedule Changes |  |
| Rework Driven (Electrical and Inspection Record Backlog) | $165 |
| Rework |  |
| Electrical Quality Issues (IEEE 384) | $8 |
| Inspection Records Backlog | $22 |
| Construction work performed before Bechtel | $12 |
| Penetration Seal Breaches and Re-seals | $2 |
| Non-Segregated Busbar Rework/Redesign | $21 |
| Valve rework | $11 |
| Extraction steam piping rework | $4 |
| Other tracked rework items identified by Staff or GPC | $22 |
| Project Performance Costs Above Best Sustained Productivity | $319 |
| Lost and Damaged Items | $28 |
| Miscellaneous – Testing Support Labor & Other | $54 |
| Total | $1,362 |

Q.	PLEASE EXPLAIN THE COMPANY’S DECISION NOT TO REQUEST COSTS RELATED TO THE VCM 19 REFORECAST.

A.	In the VCM 19 reforecast, Georgia Power’s projected share of the total cost increased from $7.3 billion to $8.4 billion. This increase of approximately $1.1 billion included $694 million in base capital forecast and a Project contingency estimate of $366 million. The Company determined that it was in the best long-term interests of customers, investors, and other stakeholders to maintain Project momentum by electing not to seek approval of the base capital cost increase so soon after receiving Commission approval in the VCM 17 Order to continue with the Project. Consistent with Georgia Power’s position since VCM 19, the Company is not requesting recovery of the $694 million in base capital cost increase that resulted from the VCM 19 reforecast.

Q.	PLEASE EXPLAIN THE CHALLENGES WITH REWORK ON THE PROJECT.

A.	A certain amount of rework and remediation is normal and expected on a project the size of Vogtle Units 3 and 4. As discussed in detail in the Application, there were several instances in which rework was greater than anticipated, even on a project of this size. Rework on the Project was driven in part by the workforce’s limited experience with the nuclear design requirements for the Project and the Project’s transition through multiple contractors, among other factors. In addition, the Company proceeded with construction of the Units under the NRC’s new Part 52 licensing process and new modularization approach to nuclear plant construction. As the Project moved through construction on Unit 3, Southern Nuclear was nonetheless able to apply lessons learned from rework required on Unit 3 to minimize the amount of rework required for Unit 4. For example, the rework required because of the spent fuel pool leak and resulting repairs, as well as the rework associated with the IEEE 384 cable separation issues, all fall into the category of rework over and beyond what was anticipated, and the Company is not seeking recovery for these costs.

Q.	WHY HAS THE COMPANY MADE THE DECISION TO NOT SEEK CERTAIN REWORK ITEMS?

A.	As stated previously, while there is a certain amount of rework anticipated on a megaproject like Vogtle Units 3 and 4, the amount experienced on the Project was larger than expected. While the Company believes that all the costs to remediate work on the Project were reasonable and prudently incurred, it has decided not to ask customers to bear such costs.

Q.	PLEASE DESCRIBE THE REWORK-DRIVEN SCHEDULE CHANGE COSTS THAT THE COMPANY IS NOT SEEKING TO RECOVER.

A.	In addition to costs directly associated with redoing work—for example, costs such as labor and equipment—rework also requires additional time in the schedule to re-complete activities prior to continuing to later-sequenced activities already included in the schedule. For example, milestones were pushed to accommodate completion of rework to acceptable standards. In addition to delaying the completion of physical work on site, rework caused delays in closing ITAACs that were required to load fuel. At the time, the critical path for the Project was driven through ITAAC completion. Therefore, delays in rework for challenges such as the IEEE 384 electrical cable separation issues delayed ITAAC closure, which caused delays in progress to the critical path. Southern Nuclear’s analysis on the delay associated with IEEE 384 remediation was the basis for the amounts captured by the “Rework Driven Schedule Change” costs.

To calculate the schedule-driven costs related to rework, Southern Nuclear identified items needing rework and had Bechtel and other subcontractors track and report the manhours spent on these rework tasks. The time to address the items requiring rework was then identified in the schedule as reflected in ITAAC milestones. The delay and cost associated with the identified rework was then calculated based on the time to complete the rework in the schedule.

Q.	WHY IS THE COMPANY NOT SEEKING RECOVERY OF THESE SCHEDULE-DRIVEN COSTS?

A.	As previously discussed, the schedule-driven delays resulted from the amount of time required to remediate items requiring rework. Although addressing these items was necessary to successfully meet the technical specifications and testing to bring the Units online, the Company is not seeking recovery of the costs associated with these schedule delays because of (1) the underlying causes of the rework and (2) the extensive schedule impacts it caused.

Q.	WHAT TYPES OF COSTS ARE INCLUDED IN THE CATEGORY OF “CONSTRUCTION WORK PERFORMED BEFORE BECHTEL?”

A.	Four construction contractors performed work on the Project, three of which preceded Bechtel’s tenure as primary contractor. Once onsite, Bechtel was better able to review work completed, or assumed completed, in their initial estimates. In some cases, this review identified necessary remediation of work previously completed by other contractors, including installation of electrical, concrete, rebar, and other commodities. Deficient construction costs such as these would have been included in the fixed price contract previously in effect under prior constructors. Post WEC bankruptcy, however, the costs to correct these issues had to be borne by the Company. These corrections were necessary to support the testing or technical specifications required to complete the Units as designed.

Q.	PLEASE EXPLAIN THE “PROJECT PERFORMANCE COSTS ABOVE BEST SUSTAINED PRODUCTIVITY” CATEGORY AND HOW IT WAS CALCULATED.

A.	As described previously, CPI is a cost efficiency measure calculated by determining the ratio of hours spent on an activity relative to the hours earned. A CPI greater than 1.0 indicates that the Project spent more hours than planned to complete a task. After VCM 17, when Southern Nuclear took over responsibility for Project construction, Southern Nuclear analyzed historical performance measures on the Project after incorporating common unit rates in the project control tools and accounting for expected deviations in CPI that were documented in the Company’s VCM 17 Estimate to Complete and accompanying Cost and Schedule Assessment. In addition to the expected deviations in CPI, Southern Nuclear also analyzed comparative performance and productivity on Unit 4 compared to Unit 3 to establish improved performance to account for improvements in execution and lessons learned from the leading Unit. The Company calculated the difference between the best sustained productivity on the Project as seen through historical performance and other experienced productivity measures on Vogtle Units 3 and 4 to determine the Project cost related to poor productivity. This difference is not being sought for recovery from customers.

Q.	WHY ARE LOST AND DAMAGED ITEMS EXCLUDED FROM THE COMPANY’S REQUEST?

A.	Lost and damaged material is a common component of a large and complex construction project. Vogtle Units 3 and 4 were not immune to this. On this Project, some of the lost or damaged materials had specific purposes and had to be replaced by materials that met the same design and quality requirements as the original. For example, after installation, level transmitters were damaged and had to be replaced and reinstalled to complete construction. Southern Nuclear tracked the material replacements and these costs are represented within this cost category. Considering the timing of some of the events and causes in which some of the lost and damaged items materialized, the Company decided to forego recovery of these costs.

Q.	WHAT TYPES OF COST FALL INTO THE MISCELLANEOUS CATEGORY OF COSTS?

A.	This cost category primarily includes staff labor hours for testing support. This support staff was mainly comprised of personnel from the maintenance organization and included contractors.  The support staff tested systems and equipment, as well as performed operational testing.

Q.	WITH THESE CATEGORIES OF COSTS EXCLUDED, DOES THE COMPANY BELIEVE $8.826 BILLION IN COSTS SHOULD BE RECOVERED FROM CUSTOMERS?

A.	Yes. Based on the Company’s assessment of the total construction and capital cost incurred on the Project, the Company estimated that $8.826 billion of prudent and reasonable costs should be recovered from customers and the Company should forgo $1.362 billion in prudently incurred construction and capital cost. The Company’s Application, along with the record in this Docket No. 29849 established over the course of 14 years of VCM proceedings, supports the recoverability of $8.826 billion. As discussed below, a portion of these total Project costs have already been determined to be reasonable and prudent. Importantly, per the Stipulation executed between the Company, PIA Staff, and several intervenors on August 29, 2023, the Company will forego an additional $1.264 billion. In total, Georgia Power has agreed to forego recovery of $2.626 billion in construction and capital cost and seeks to collect $7.562 billion in construction and capital cost from customers.

Amounts Already Determined to be Reasonable and Prudent

Q.	HAS THE COMMISSION PREVIOUSLY FOUND ANY PORTION OF THE PROJECT’S CONSTRUCTION AND CAPITAL COST TO BE REASONABLE AND PRUDENT?

A.	Yes. At various points throughout the construction of Units 3 and 4, and as part of the VCM proceedings in Docket No. 29849, the Commission has found that certain categories of costs were reasonable or prudently incurred:

- As part of the SIR Final Order, the Commission deemed prudent the $3.569 billion incurred by Georgia Power on the Project through the VCM 14 Reporting Period ending December 31, 2015 (including settlement costs paid or to be paid to Westinghouse).

- Also, in the SIR Final Order, the Commission found that costs up to $5.68 billion were presumed prudent, thereby shifting the evidentiary burden to intervening parties to show that costs incurred over $3.569 billion and up to $5.68 billion were not prudently incurred.

- In VCM 17, the Commission deemed that construction and capital cost up to $7.3 billion were deemed reasonable.

- In VCM 19, the Commission found that all construction monitoring costs are reasonable and prudent.

Through the VCM process, the Commission has verified and approved all expenditures up to the revised, approved construction and capital cost of $7.3 billion and has reviewed, but not verified and approved, all expenditures above that amount.

Q.	HOW MUCH OF THE CONSTRUCTION AND CAPITAL COST MUST THE COMPANY DEMONSTRATE TO BE REASONABLE IN THIS PROCEEDING?

A.	Consistent with the Commission’s prior findings and based on the $8.826 billion the Company has determined to be recoverable from customers, the Company would need to show that $1.5 billion in construction and capital cost are reasonable. However, considering that the Stipulation limits recovery for the Project to $7.562 billion, Georgia Power must only demonstrate reasonableness of $236 million in construction and capital cost above the $7.3 billion previously deemed reasonable, as illustrated in Table 4:

Table 4: Costs Remaining to be Determined Reasonable

| Remaining Construction and Capital Cost to be Determined Reasonable: | Amount (in millions) |
| --- | --- |
| Stipulated Amount | $7,562 |
| VCM 17 Order | ($7,293) |
| VCM 19 – CM Fees | ($33) |
| Total Remaining | $236 |

Q.	HOW MUCH OF THE STIPULATED REQUESTED RECOVERY AMOUNT MUST THE COMPANY DEMONSTRATE TO BE PRUDENT IN THIS PROCEEDING?

A.	Consistent with the Commission’s prior findings and based on the $8.826 billion the Company has determined to be recoverable from customers, the Company would need to show that $3.113 billion in construction and capital cost are prudent. However, given the Stipulation limits recovery for the Project to $7.562 billion, the Company has the burden to show that $1.849 billion in construction and capital cost are prudent. Table 5 below illustrates Georgia Power’s burden of proof as to the prudence of the remaining construction and capital cost:

Table 5: Costs Remaining to be Determined Prudent

| Remaining Construction and Capital Cost to be Determined Prudent: | Amount (in millions) |
| --- | --- |
| Stipulated Amount | $7,562 |
| Presumed Prudent in SIR Final Order | ($5,680) |
| VCM 19 – CM Fees | ($33) |
| Total Remaining | $1,849 |

Q.	WHAT COSTS ARE INCLUDED IN THE AMOUNTS GREATER THAN THE $5.68 BILLION PRESUMED PRUDENT AND UP TO THE $8.826 BILLION THE COMPANY BELIEVES IS RECOVERABLE FROM CUSTOMERS?

A.	The construction and capital cost between $5.68 billion and $8.826 billion were generally incurred after the WEC Bankruptcy and SIR Final Order (2016) through the VCM 27 reporting period (June 2022). These costs include the Project’s transition following the WEC Bankruptcy, loss of the protection of a fixed price contract, the reforecasting of the cost to complete, Southern Nuclear’s management of a new primary contractor and subcontractors on the Project, and completion of construction on Unit 3.

Reasonableness and Prudence of Project Decisions at Issue

Q.	WHAT ACTIONS AND DECISIONS ARE REFLECTED IN THE COSTS INCURRED BETWEEN THE SIR FINAL ORDER IN 2016 AND MID-2022?

A.	Several of the Company’s decisions that have received significant attention from PIA Staff and intervenors in the VCM proceedings were made following the SIR Final Order in 2016 and when the Company spent up to $8.826 billion in June 2022, including but not limited to: tracking performance using CPI rather than adjusting unit rates; managing to an aggressive site work plan; and implementing a partial release to test approach.

Q.	WHY DID THE COMPANY ELECT TO USE CPI TO TRACK PERFORMANCE RATHER THAN UPDATING UNIT RATES WHEN IT TOOK OVER CONTROL OF PROJECT CONSTRUCTION?

A.	Following Southern Nuclear’s transition after VCM 17, the Company elected to maintain the unit rates from their initial inclusion in the project control tools to establish a consistent baseline from which to measure performance. If Southern Nuclear had adjusted unit rates over time, there would not be a consistent baseline of performance, which would decrease the value of real-time performance indicators. Rather than adjust unit rates, the Company measured performance using actual experienced CPIs in project management, manpower loading, and schedule adjustments.

Q.	WHY DID THE COMPANY CHOOSE TO MANAGE TO AN AGGRESSIVE SITE WORK PLAN?

A.	When Southern Nuclear took over Project construction after the WEC Bankruptcy, the Company re-estimated the Project cost and schedule. The Company understood the need for a schedule to be realistic and achievable, and the Company was cognizant of the fact that often, if you give a team more time to do something, they are likely to use all their allotted time. After assuming control of the planning process, and to improve production and provide schedule margin, Southern Nuclear planned to complete the Project ahead of the regulatory-approved in-service dates of November 2021 and November 2022 for Units 3 and 4, respectively. Southern Nuclear continually acknowledged that this site working schedule was aggressive and believed working towards a challenging schedule was necessary to help the Project Team maintain focus and drive toward completion of the Project. The Project team used this method as a project management tool and motivator to get the Project done as expeditiously as possible in a safe and quality manner. In addition, by using an aggressive schedule, it allowed the earlier identification of potential risks in testing that otherwise would have been identified later in the project.

Q.	HOW CAN THE USE OF AN AGGRESSIVE SITE WORK PLAN HAVE BEEN REASONABLE IF IT WAS NEVER MET?

A.	As a part of its Integrated Project Schedule, Southern Nuclear used the aggressive site schedule as a management tool. The aggressive Site Work Plan worked as intended. as it helped drive the Project forward, identifying risks early and allowing the Project to pivot when a roadblock or barrier halted work on one critical path. The Company recognized that the dynamic nature associated with the aggressive Site Work Plan made reporting to its stakeholders challenging, and as a complement to the aggressive Site Work Plan, the Company developed the risk-adjusted schedule for tracking and reporting purposes. Used in conjunction with the site’s more aggressive working schedule, these risk-adjusted schedules provided points of comparison and valuable risk management for the site working schedule. The risk-adjusted schedules also provided forecasted production levels needed to meet the regulatory-approved and risk-adjusted in-service dates. By creating and reviewing these benchmark schedules, the Project Team, Co-Owners, and PIA Staff were able to compare the production levels and milestone dates forecasted to meet the in-service dates beyond the site working schedule.

Q.	WHY DID THE COMPANY IMPLEMENT A PARTIAL RELEASE TO TEST (“PRT”) APPROACH?

A.	The aggressive site work plan not only enabled the Project Team to gain a better understanding of the risks that were in front of them, but also helped identify those risks earlier than they otherwise would have. A key process for identifying risks sooner rather than later was the Partial Release to Test (“PRT”) approach, which provided Initial Test Program (“ITP”) personnel with access to early testing of components and equipment. As construction on Unit 3 progressed, rather than derail the Project’s testing schedule, site leadership decided to subdivide systems and structures into subcomponents for testing purposes. This approach allowed the Project to get components and partial systems in front of the testing organization as quickly as possible. As with the aggressive schedule, the Company implemented PRTs to identify as much risk as possible to adjust and provide needed flexibility in progressing toward completion.

Q.	WAS IT REASONABLE AND PRUDENT TO IMPLEMENT PRT ON THE PROJECT?

A.	Yes. It was appropriate to use PRTs on Unit 3 (the first of the two Units to be completed) simply to learn more, more quickly. By testing early and finding potential shortcomings earlier, the Project was able to apply lessons learned from Unit 3 to Unit 4 sooner than would have otherwise been the case had the Company not used a PRT approach. Unit 4 construction progressed significantly more quickly than Unit 3 in large part because of the decision to use PRT on Unit 3. The Project was able to identify numerous operational risks as fast as possible, which in turn led to better implementation on Unit 4.

Q.	DOES THE COMPANY BELIEVE THAT THE COSTS RELATED TO THESE DECISIONS WERE REASONABLE AND PRUDENT?

A.	Yes.

Total Construction and Capital Cost Stipulated to be Recovered

Q.	HOW DID THE STIPULATING PARTIES DETERMINE THAT $7.562 BILLION WAS AN APPROPRIATE TOTAL CONSTRUCTION AND CAPITAL COST FOR THE COMPANY TO RECOVER?

A.	As described in the Stipulation, the agreed to reduction in the construction and capital cost from the total projected construction and capital cost expected to be spent takes into consideration the extended length of time to construct the Project, replacement energy costs incurred during the prolonged construction time, and other issues of concern such as the amount of rework required, scheduling of activities, testing, and productivity.

Q.	WHAT HAPPENS IF UNIT 4 IS DELAYED OR THE COMPANY INCURS ADDITIONAL CONSTRUCTION AND CAPITAL COST TO FINISH THE PROJECT?

A.	As provided by the Stipulation, the $7.562 billion of total construction and capital cost amount is a limit on the amount the Company can recover for the Project. Any additional construction and capital cost incurred prior to Commercial Operation will be the responsibility of the Company not customers. If Unit 4 does not achieve Commercial Operation by March 31, 2024, the Company’s return on equity (“ROE”) used to calculate both the NCCR tariff revenue requirement and the AFUDC will be reduced to zero until Unit 4 reaches Commercial Operation.

Q.	HOW MUCH HAS THE COMPANY AGREED TO FOREGO IN COST RECOVERY?

A.	If the Stipulation is approved, the Company will forgo recovery of a total of $2.626 billion in prudently incurred costs to bring Vogtle Units 3 and 4 through construction, testing, and startup and into operations to serve our 2.7 million customers.

FINANCING COSTS

Q.	HOW HAS THE COMPANY RECOVERED FINANCING COSTS FROM CUSTOMERS DURING CONSTRUCTION?

A.	Pursuant to O.C.G.A. § 46-2-25(c.1), the Company recovers from customers the financing costs on the certified construction and capital cost of Vogtle Units 3 and 4 through the NCCR Tariff, which permits recovery of financing costs during construction of the Units. Financing costs incurred on the construction and capital cost above the $4.418 billion certified amount are accrued through AFUDC to be included in rate base and recovered from customers upon Commercial Operation of Unit 4.

Q.	ARE THERE GROUNDS FOR DISALLOWING ANY FINANCING COSTS, WHETHER COLLECTED THROUGH THE NCCR TARIFF OR AFUDC?

A.	No. The financing costs incurred and accrued through the NCCR Tariff and AFUDC are a direct byproduct of the construction and capital cost incurred on the Project. Therefore, reasonable and prudent capital costs during construction will result in corresponding AFUDC financing costs, which should also be deemed prudent and reasonable and appropriately recovered from customers.

Q,	HOW DID THE COMPANY CALCULATE THE REQUESTED AFUDC INCLUDED IN THIS FILING?

A.	The Company included the actual and projected AFUDC accrued on the construction and capital cost above the certified amount of $4.418 billion up to the stipulated $7.562 billion and excluded any construction and capital cost above the stipulated amount from its AFUDC calculation. The AFUDC financing costs align with the construction and capital amount requested in this filing and the Stipulation. The cost of capital applied to AFUDC is consistent with the ROE reductions implemented by the Commission in the SIR Final Order and again in the VCM 17 Order.

Q.	WHY IS IT APPROPRIATE FOR FINANCING COSTS TO FOLLOW THE CONSTRUCTION AND CAPITAL COST FOR WHICH THEY WERE INCURRED?

A.	The accounting for financing costs in conjunction with the construction and capital cost for which they were incurred is in accordance with US Generally Accepted Accounting Principles (“GAAP”), FERC, and general utility ratemaking. Traditional utility ratemaking, as well as US GAAP and FERC, consider financing costs to be a cost of construction and necessary to bring an asset to the condition and location necessary for its intended use. The treatment of financing costs should follow the treatment of the underlying construction and capital cost.

Q.	WHAT WILL HAPPEN TO COLLECTIONS UNDER THE NCCR TARIFF WHEN UNIT 4 REACHES COMMERCIAL OPERATION?

A.	On the effective date of the rate adjustment following Commercial Operation of Unit 4 the Company will cease collecting financing costs through the NCCR tariff and those financing costs will be included in Georgia Power’s general revenue requirements and collected through base rates.

Q.	WHAT WILL HAPPEN TO ANY OVER OR UNDER RECOVERY REMAINING WHEN THE COMPANY CEASES COLLECTING FINANCING COSTS UNDER THE NCCR TARIFF?

A.	Any over or under-recovered balance resulting from the NCCR tariff at its termination date will be included in rate base and addressed in the next base rate case.

OPERATING COSTS

# Q.	PLEASE DESCRIBE THE OPERATING COSTS THE COMPANY SEEKS TO RECOVER FROM CUSTOMERS.

A.	The Company has included depreciation expenses, O&M expenses, property tax expenses, and nuclear decommissioning expenses as part of the operating expenses to be included in the revenue requirement to be recovered from customers upon Commercial Operation of Unit 4. The Company has also included operating costs for nuclear fuel plant and materials and supplies inventory in the projected rate base, which are both necessary costs of operating Units 3 and 4. The projected operating cost profile and ultimate costs to customers will be significantly reduced thanks to the benefit of the PTCs related to the Company’s share of Vogtle Unit 3 and 4’s generation output. The Company proposes to provide the full benefit of the PTCs generated by Units 3 and 4 to customers through an offset to operating expenses in the revenue requirement.

# Q.	SHOULD THERE BE ANY DISALLOWANCES, ADJUSTMENTS, OR OTHER LIMITATIONS ON THESE OPERATING AMOUNTS INCLUDED IN REVENUE REQUIREMENTS?

A.	No. When Units 3 and 4 achieve Commercial Operation, they will be fully dispatchable baseload generation available to serve customers with the generation output of the Company’s ownership in Units 3 and 4 serving customers as a certified generating resource. The Stipulation with PIA Staff and several other intervenors provides for full recovery of the operating amounts included in the revenue requirement. Under typical regulatory accounting treatment, operating costs are either included in rates once a unit is placed in service or deferred for future recovery until the regulatory review process for the capital cost of the unit is completed. This regulatory proceeding completes the regulatory review process for all of Unit 3 and 4 costs. It would be inappropriate for the Commission to disallow recovery of operating costs for a certified generation facility that is in service.

REPLACEMENT FUEL COSTS

Q.	WHAT IS THE COMPANY’S ESTIMATE OF REPLACEMENT FUEL COSTS?

A.	The Company calculated replacement fuel costs as directed by the VCM 12 order in all VCM proceedings following the initial certification dates of the Project. The Company’s replacement energy cost analysis is found in Table 1.2 of each VCM report starting in VCM 15 and, to show the net cost picture, includes not only the deferred benefits of replacement energy costs and PTCs but also the deferred operating expenses that customers would be paying if the Units were in operation. The updated Company analysis presented in Table 5 of the Company’s Application to Adjust Rates accounts for the Commercial Operation dates of November 2021 for Unit 3 and November 2022 for Unit 4 found reasonable in the VCM 17 Order. The updated regulatory-approved dates are the appropriate benchmark since the Project was holistically reviewed in a ‘Go’/‘No-Go’ decision and the option selected was to continue construction under a new project structure versus selecting an alternate option to meet the growing load demand.

Q.	IS THERE A FUEL COST BENEFIT TO THE NEW NUCLEAR UNITS?

A.	Yes, nuclear energy has historically provided a benefit to customers in the form of lower fuel costs as compared to other generating options. When the Units achieve Commercial Operation, they are dispatchable and capable of ramping up and down to follow load, and typically dispatch at 100% power, 24 hours a day, seven days a week as a baseload resource due to their lower operating and fuel costs compared to other resources on the system.

Q.	DOES THE COMPANY’S CURRENT FUEL COST RECOVERY (“FCR”) TARIFF CAPTURE THE IMPACT OF VOGTLE UNITS 3 AND 4 ACHIEVING COMMERCIAL OPERATION?

A.	Yes. The Company’s FCR-26 rates currently in place anticipated Vogtle Units 3 and 4 achieving Commercial Operation in March and December 2023, respectively. Based on the estimates available from the previous VCM 28 filing, the Units are expected to provide approximately $289 million of projected fuel cost savings for the 24-month test period ending March 2025. Prior to Commercial Operation, during testing, the cost of the fuel consumed is capitalized and included as construction cost, and the kilowatt hours generated during the testing period are available for retail customers and included in the Company’s FCR calculations.

RETAIL BASE RATE ADJUSTMENT

Q.	PLEASE DESCRIBE THE COMPANY’S REQUEST TO ADJUST BASE RATES ONCE UNIT 4 ACHIEVES COMMERCIAL OPERATION.

A.	The Company requests to increase base rates by $729 million effective the first day of the month following Unit 4 achieving Commercial Operation.

Q.	HOW IS THE COMPANY PROPOSING TO ALLOCATE THE REQUESTED INCREASE IN BASE RATES?

A.	The proposed increase will be allocated equally across all base tariffs consistent with how the Unit 3 rate adjustment was designed and ultimately approved by the Commission. The Company will design the remaining Vogtle Unit 3, Unit 4, and Common facilities price changes after completing the rate design for the October 1, 2023, rate case compliance filing as specified in the Commission’s Order in Docket No. 44280.

Q.	HOW DID THE COMPANY DETERMINE THE RETAIL REVENUE DEFICIENCY FOR THE REMAINING AMOUNT OF VOGTLE UNITS 3 AND 4 FOR THIS PROCEEDING?

A.	To derive the incremental retail revenue deficiency for the remaining amount of Vogtle Units 3 and 4, the Company calculated the total revenue requirement for Vogtle Units 3 and 4 for the twelve-month period ending March 31, 2025, and subtracted the base rate increase amount approved in the Vogtle Unit 3 Rate Adjustment Order, which went into effect on August 1, 2023. The resulting revenue deficiency represents the cost of Vogtle Units 3 and 4 that has not been contemplated in base rates.

Q.	PLEASE DESCRIBE THE DEVELOPMENT OF THE RETAIL REVENUE DEFICIENCY AMOUNT FOR THE TWELVE-MONTH PERIOD ENDING MARCH 31, 2025.

A.	The calculation in Figure 2 below presents a revenue deficiency of $729 million for the period ending March 31, 2025, to be collected through base rates beginning April 2024, the month following Unit 4’s anticipated Commercial Operation. The calculations are consistent with those used in the Company’s base rate proceedings. The requested financing costs reflect the Company’s cost of capital requirements, which are weighted by the mix of long-term debt and common equity to produce an overall rate of return. This rate of return is then applied to the rate base to yield the Company’s earnings requirement. The Company is also requesting to collect the related operating expenses including: (1) depreciation expense; (2) O&M expenses; (3) property taxes; and (4) nuclear decommissioning costs, as well as return the full benefits of the PTCs related to Georgia Power’s ownership in Units 3 and 4 to customers, which will offset a portion of the operating expenses.

The earnings requirement is then compared to earnings available for return to determine the amount of retail earnings deficiency during the recovery period being considered. This earnings deficiency is then adjusted to cover income taxes by using an “income expansion factor.” This factor, 74.596%, reflects a federal income tax rate of 21% and a state income tax rate of 5.75%. The income expansion factor also includes a reduction for uncollectible accounts, slightly offset by compensation for collection of sales tax. The income expansion factor used in this filing is the factor approved by the Commission in the 2022 base rate case. The retail earnings deficiency is then divided by the income expansion factor to determine the total revenue deficiency from retail customers. Finally, the base rate increase amount approved by the Commission in the Unit 3 Rate Adjustment Order is subtracted from the total to arrive at the incremental revenue deficiency requested in this filing.

Q.	WHAT COMPONENTS MAKE UP THE RETAIL RATE BASE AMOUNT PRESENTED IN FIGURE 2 UPON WHICH THE COMPANY IS BASING ITS REVENUE DEFICIENCY FOR THE TWELVE-MONTH PERIOD ENDING MARCH 31, 2025?

A.	The components are provided in Figure 3 below.

Q.	PLEASE DESCRIBE HOW THE COMPANY’S REQUESTED RATE OF RETURN IS CALCULATED.

A.	The Company’s 7.78% requested rate of return is based on the 13-month average of the estimated capitalization from March 2024 through March 2025. The long-term debt proportion of capitalization is multiplied by its average estimated embedded cost for each month through March 2025. The cost of common equity represents the 10.5% ROE approved in the Company’s 2022 base rate case proceeding. Figure 4 below shows the capital structure components for the 13-month period, together with associated costs.

Q.	PLEASE IDENTIFY WHICH LINE(S) AND AMOUNTS OF OPERATING EXPENSES AND PRODUCTION TAX CREDITS ARE INCLUDED IN THE REVENUE DEFICIENCY CALCULATION PRESENTED IN FIGURE 2.

A.	The after-tax (earnings) impact of the operating expenses and the PTCs are summed and presented on Figure 2, line 4, “Earnings Available for Return.” The calculation of earnings available for return for the twelve-month period ending March 2025 is presented in Figure 5 below.

Q.	WHAT DEPRECIATION RATE HAS THE COMPANY APPLIED TO THE VOGTLE UNITS 3 AND 4 FACILITIES PLACED IN PLANT-IN-SERVICE TO CALCULATE THE AMOUNT OF DEPRECIATION EXPENSE REQUESTED TO BE RECOVERED?

A.	As provided in the Stipulation, the Company applied an annual depreciation rate of 1.677% for Vogtle Units 3 and 4 and Common Nuclear Production Plant-in-Service as approved in the Unit 3 Rate Adjustment Order in Docket No. 43838. This depreciation rate assumed a 60-year operating life for Vogtle Units 3 and 4. The depreciation rate for Vogtle Units 3 and 4 and Common facilities will be reevaluated in the Company’s depreciation study in its next base rate case.

Q.	WHAT IS INCLUDED IN THE NUCLEAR DECOMMISSIONING ACCRUAL PROPOSED IN THIS FILING?

A.	The Company included the license termination and the spent fuel management components of nuclear decommissioning for Vogtle Unit 3 and 4 in this filing and excluded site restoration costs. For license termination, the Company used the NRC minimum calculation. For the spent fuel management component, the Company used the projected costs from the site-specific study for Vogtle Units 3 and 4 performed by TLG Services, Inc. The current 40-year operating license was used to derive the estimates as required by the NRC to satisfy funding assurance for nuclear decommissioning.

Q.	ARE THERE SPECIFIC NRC REGULATIONS REGARDING THE CALCULATION AND FUNDING OF NUCLEAR DECOMMISSIONING COSTS?

A.	Yes, 10 CFR Part 50.75 defines the nuclear decommissioning calculation and funding requirements to ensure funding is available upon the current license termination date, or 40 years for Vogtle Units 3 and 4, to decommission the radioactive components of the Units.

Q.	WERE THE ESTIMATED VOGTLE UNITS 3 AND 4 NUCLEAR DECOMMISSIONING COSTS REQUESTED IN THIS PROCEEDING CALCULATED IN ACCORDANCE WITH THE NRC REQUIREMENT?

A.	Yes.

Q.	HAS THIS COMMISSION HISTORICALLY PROVIDED FOR THE RECOVERY OF NUCLEAR DECOMMISSIONING COSTS FOR LICENSE TERMINATION CALCULATED USING THE NRC MINIMUM METHODOLOGY AND COSTS FOR SPENT FUEL MANAGEMENT FROM THE SITE-SPECIFIC STUDY?

A.	Yes.

Q.	HOW ARE THE PROJECTED PROPERTY TAXES CALCULATED IN THIS FILING?

A.	The projected property taxes are based on the amount estimated to be remitted to the taxing authorities, which is consistent with the state-required method of valuation for public utilities.

Q.	ARE THE PROPERTY TAXES DEPENDENT ON THE AMOUNT OF CONSTRUCTION AND CAPITAL COST APPROVED FOR RECOVERY FROM CUSTOMERS?

A.	No. The property taxes required by the taxing authorities are based on the total construction and capital cost spent by the Company on the Project. Therefore, as provided in the Stipulation, the Company appropriately included the total projected construction and capital cost in its calculation of the property taxes in this filing to most accurately reflect the estimated property tax to be paid.

Q.	IS THE COMPANY ALSO PROPOSING TO PROVIDE 100% OF ITS OWNERSHIP BENEFIT OF THE PTCs TO CUSTOMERS?

A.	Yes. The Company has included its full annual amount allowed under the IRS regulations as an offset to the operating costs.

Q.	IS THE COMPANY SEEKING RECOVERY OF PREVIOUSLY DEFERRED COSTS ASSOCIATED WITH VOGTLE UNITS 3 AND 4?

### A.	Yes. As agreed in the Stipulation, the Company is seeking to recover (i) the deferred depreciation related to Unit 3 and Common facilities incurred since Unit 3 was placed in service, (ii) the deferred financing costs of Unit 3 and Common facilities accrued since Unit 3 was placed in service, (iii) the deficient ADITs resulting from TCJA, and (iv) the deferred interest on nuclear fuel accrued in accordance with prior Commission order (Docket No. 3397).

### Q.	PLEASE DESCRIBE THE RECOVERY OF DEFERRED DEPRECIATION PROPOSED IN THIS FILING.

### A.	As approved in the Unit 3 Rate Adjustment Order, the Company is deferring to a regulatory asset the depreciation of Unit 3 and Common facilities above the $2.1 billion of construction and capital cost approved for inclusion in rate base upon Commercial Operation of Unit 3. The deferred depreciation is calculated based on the 1.677% depreciation rate approved in the Unit 3 Rate Adjustment Order through the Commercial Operation of Unit 4. The Stipulation provides for the amortization of the deferred depreciation the month after Unit 4 Commercial Operation ratably over a 10-year period.

### Q.	PLEASE DESCRIBE THE RECOVERY OF DEFERRED FINANCING COSTS PROPOSED IN THIS FILING.

### A.	As approved in the Unit 3 Rate Adjustment Order, the Company is deferring to a regulatory asset the financing costs of Unit 3 and Common facilities above the $2.1 billion of construction and capital cost approved for inclusion in rate base upon Commercial Operation of Unit 3. The cost of equity incorporated in the deferred financing costs is the Company’s average cost of long-term debt as approved in the Unit 3 Rate Adjustment Order through Commercial Operation of Unit 4. Since the Company cannot defer the equity return for GAAP financing reporting purposes, the Company will defer the debt return to the regulatory asset for GAAP and will defer the equity return to the regulatory asset for regulatory reporting purposes only. The Stipulation provides for the amortization of the deferred financing costs, both debt and equity, the month after Commercial Operation of Unit 4 ratably over a 10-year period.

### Q.	PLEASE DESCRIBE THE RECOVERY OF DEFICIENT ADITS REGULATORY ASSET INCLUDED IN THE STIPULATION.

### A.	As a result of the TCJA in December 2017, the Company recorded a regulatory asset of $145.5 million associated with the deficient ADITs for Vogtle Units 3 and 4. The Stipulation provides for the Company to amortize the deficient ADITs the month after Unit 4 Commercial Operation ratably over a 10-year period.

### Q.	PLEASE DESCRIBE THE RECOVERY OF DEFERRED INTEREST ON NUCLEAR FUEL INCLUDED IN THE STIPULATION.

### A.	In accordance with the prior Commission order in Docket No. 3397, the Company is deferring interest costs on Vogtle Units 3 and 4 nuclear fuel to a deferred asset account through their respective Commercial Operation dates. The Stipulation provides for the deferred interest on nuclear fuel to be amortized through fuel expense over the respective fuel cycles of Vogtle Units 3 and 4.

COMMERCIAL OPERATION

Q.	WHEN DID UNIT 3 ACHIEVE COMMERCIAL OPERATION?

A.	Unit 3 achieved Commercial Operation on July 31, 2023.

Q.	HAS UNIT 3 PERFORMED AS EXPECTED SINCE ACHIEVING COMMERCIAL OPERATION?

A.	Yes. Since July 31, 2023, Unit 3 has remained operational and dispatchable, serving Georgia customers with 24-hour a day, 7-day a week carbon-free electricity.

Q.	WHAT PROCESS DOES THE COMPANY PROPOSE TO DETERMINE THAT UNIT 4 HAS ACHIEVED COMMERCIAL OPERATION?

A.	Commercial Operation is defined in the SIR Stipulation as “fully dispatchable on demand at the stated Net Electrical Output of 1,102 MWe.” Utilizing the same process as Unit 3, at the conclusion of its testing and start-up procedures, Southern Nuclear will determine when Unit 4 is “fully dispatchable on demand at the stated Net Electrical Output of 1,102 MWe.” Once this determination is made, the Company, along with the other Vogtle Co-Owners, will declare that Unit 4 has achieved Commercial Operation, will turn over Unit 4 to Fleet Operations, and will notify the Commission of that declaration.

Q.	WHAT FORM OF NOTIFICATION DOES THE COMPANY NEED TO PROVIDE TO THE COMMISSION WHEN UNIT 4 HAS ACHIEVED COMMERCIAL OPERATION?

A.	A simple notification process whereby the Company notifies the Commission when Unit 4 is fully dispatchable at the stated Net Electrical Output is all that is necessary for the Commission to determine that Unit 4 has achieved Commercial Operation. This process is consistent with the notification process used for Unit 3 Commercial Operation.

ADDITIONAL PROVISIONS INCLUDED IN THE STIPULATION

Q.	DID THE STIPULATING PARTIES AGREE TO OTHER PROVISIONS IN THE STIPULATION FOR THE BENEFIT OF CUSTOMERS?

A.	Yes. As part of the Stipulation, Georgia Power agreed to three additional provisions for customers’ benefit:

(1)	Georgia Power agreed to propose in the 2025 Integrated Resource Plan (“IRP”) and Demand Side Management (“DSM”) Certification dockets a base case of DSM performance savings targets up to .75% of annual retail sales, reserving the right for Stipulating Parties to advocate for different savings targets.

(2) 	Effective when rates are adjusted the month after Unit 4 achieves Commercial Operation, Georgia Power agreed to expand the current Income Qualified Senior Discount to: (a) all seniors who live in a household with a combined income that is 200% or less of the federal poverty level, adjusted for household size; (b) individuals who receive Social Security Disability Income assistance or Supplemental Security Income; and (c) customers who participate in the federal Housing Choice Voucher Program (HUD Section 8). The Stipulating Parties agree that Georgia Power plans to implement this change by adding up to 96,000 participants over the next three years (approximately 32,000 per year). This will be paid for by residential customers and will be limited to approximately $1 per month per customer (or approximately $28 million annually) to cover the resulting anticipated cost shift from this provision.

(3) 	Georgia Power agreed to continue to evaluate the expansion of renewable resources and to expand renewable programs in the 2025 IRP to the extent they are beneficial to customers. Further, Georgia Power agreed to support any applications by the appropriate state agency to the Inflation Reduction Act’s “Solar for All” program and, to the extent the state of Georgia is selected, Georgia Power will support the use of these funds through Commission-approved Georgia Power solar programs for the benefit of customers.

Q.	WHY ARE THESE PROVISIONS REASONABLE?

A.	While none of the Stipulating Parties received everything they would have requested in this proceeding in the absence of a settlement agreement, the agreed to terms of the Stipulation are a reasonable and balanced resolution of the outstanding prudence, reasonableness, and cost recovery issues for the Project and offer additional benefits to customers. The Stipulation is fair and reasonable and should be approved by the Commission.

CONCLUSION

Q.	Does this conclude your testimony?

A.	Yes.

All dollars represent Georgia Power’s share of Project costs.

All dollars represent Georgia Power’s share of Project costs.

All dollars represent Georgia Power’s share of Project costs.

IEEE stands for the Institute of Electrical and Electronics Engineers.