Georgia Power Company’s

Grid Investment Plan Semi-Annual Report

Reporting Period: January 1 - December 31, 2023

This second Grid Investment Plan (“GIP”) Semi-Annual update is provided in accordance with the Georgia Public Service Commission’s (“Commission”) Final Order in the 2022 Base Rate Case proceeding in Docket No. 44280, which requires Georgia Power Company (“Georgia Power” or the “Company”) to file semi-annual reports. This GIP Semi-Annual Report covers the reporting period of January 1, 2023 through December 31, 2023 (the “Reporting Period”).  Following the Commission’s Final Order, Georgia Power is reporting on the approved capital expenditures amount of $1.38 billion for the three-year period beginning on January 1, 2023 and ending December 31, 2025.

# Grid Investment Plan

The GIP is a multi-year initiative focused on improving reliability for customers and replacing aging assets across the system. For Distribution, the Company is making targeted investments through projects such as undergrounding, adding new sectionalizing devices, and creating and strengthening circuit ties. For Transmission, the Company is replacing substation and transmission line equipment through various investment packages outlined within the GIP.

# Completion of Targeted Projects

During the Reporting Period, the Company was successful in placing over 90% of targeted Distribution and Transmission projects in service. The Company successfully placed 61 of the 67 targeted Distribution projects in service and 32 of the 36 targeted Transmission projects in service. Additionally, 3 Transmission projects originally targeted for 2024 completion were successfully placed in service ahead of schedule. Each of these projects play an important role in achieving the objective of the GIP to improve reliability and replace aging system assets.

# Capital Spending

As a result of the Commission Order, the Company continues to report on the portfolio of both Distribution and Transmission projects to a set of projects with estimated expenditures totaling approximately $1.38 billion target in the 2023 – 2025 time frame.  For the Reporting Period, the GIP capital spending was $568 million relative to the targeted spend of $571 million.

## Total GIP

|  | Actual Spend Jan - Jun | Actual Spend Jul - Dec | Actual Spend Jan - Dec | Annual Budget |
| --- | --- | --- | --- | --- |
| 2023 | $343 | $225 | $568 | $571 |
| 2024 |  |  |  | $392 |
| 2025 |  |  |  | $414 |
| Total | $343 | $225 | $568 | $1,377 |

## Distribution

|  | Actual Spend Jan - Jun | Actual Spend Jul - Dec | Actual Spend Jan – Dec | Annual Budget |
| --- | --- | --- | --- | --- |
| 2023 | REDACTED | REDACTED | REDACTED | REDACTED |
| 2024 |  |  |  | REDACTED |
| 2025 |  |  |  | REDACTED |
| Total | REDACTED | REDACTED | REDACTED | REDACTED |

## Transmission

|  | Actual Spend Jan – Jun | Actual Spend Jul - Dec | Actual Spend Jan-Dec | Annual Budget |
| --- | --- | --- | --- | --- |
| 2023 | REDACTED | REDACTED | REDACTED | REDACTED |
| 2024 |  |  |  | REDACTED |
| 2025 |  |  |  | REDACTED |
| Total | REDACTED | REDACTED | REDACTED | REDACTED |

Details of the Grid Investment Plan capital spend are provided in Public Disclosure (“PD”) Attachment: “PSC Grid Reporting Template December 2023”.