## Arkwright
PUBLIC DISCLOSURE
Arkwright
Table 11. Arkwright Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Arkwright AP-1,2,3,Landfill | Closure by removal and consolidation to permitted landfill | 61.0228 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 61.0228 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 12. Arkwright Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 61022771.842 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $22.9 million consist primarily of detailed design, front-end planning, and landfill maintenance in addition to early site work, mobilization of water management activities and maintenance activities at AP-1. Activities expected during 2024 include continued design work, early site work, ongoing site maintenance, and permitting activities.

## Bowen
PUBLIC DISCLOSURE
Bowen
Table 13. Bowen Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Advanced closure in place with liner | 248.7583 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Bowen CCR Landfill | Active landfill / closure in place | 0.0023909 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 248.7607 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 14. Bowen Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 248760706.8797 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $78.2 million consist primarily of structural fill, liner system construction, material delivery and stockpiling, construction of Bowen Landfill Cell 5 and 6, and construction of the on-site beneficial use facility. Activities expected during 2024 include continued excavation of AP-1 CCR, completion of Landfill Cells 5 and 6 construction, and start of beneficial use production.

## Branch
PUBLIC DISCLOSURE
Branch
Table 15. Branch Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-A | Closure by removal to permitted landfill | 1.2727 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-B | Closure by removal to permitted landfill | 20.9624 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-C | Closure by removal to permitted landfill | 23.697 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-D | Closure by removal to permitted landfill | 15.3986 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-E | Closure by removal to permitted landfill | 130.7203 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill | Closure in place | -1e-08 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 192.0509 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 16. Branch Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 192050515.8183 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $65.3 million consist primarily of contractor mobilizations, on-going water management/dewatering, landfill construction, laydown area development and beneficial use design, procurement, and initial construction activities. Activities expected during 2024 include front end planning, procurement, permitting activities, landfill cell construction, and beneficial use facility construction.

## Hammond
PUBLIC DISCLOSURE
Hammond
Table 17. Hammond Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 27.8914 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-2 | Closure by removal to permitted landfill | 43.3609 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-3 | Advanced closure in place | 26.4335 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-4 | Closure by removal to permitted landfill | 30.3014 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Huffaker Road CCB Facility | Closure in place | 10.2604 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 138.2476 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 18. Hammond Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 138247116.9702 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $30.1 million consist primarily of continued AP-1 and AP-2 ash excavation activities and initial procurement of streambank mitigation credits for Huffaker landfill expansion in support of ash pond closure, as well as dewatering and water management activities and AP-4 permitting support. Additionally, this included final cover liner material purchased ahead of schedule due to availability of reduced material pricing. Activities expected during 2024 include AP-1/AP-2 ash excavation activities, procurement of remaining streambank mitigation credits for Huffaker landfill expansion in support of ash pond closure, and AP-4 and Huffaker Cells E & F detailed design.

## Kraft
PUBLIC DISCLOSURE
Kraft
Table 19. Kraft Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 8.4459 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Grumman Road Landfill | Closure in place | 18.5742 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 27.0201 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 20. Kraft Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 27020132.1224 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $3.3 million consist primarily of groundwater monitoring activities and associated oversight costs, and maintenance and construction activities. Activities expected during 2024 include continued groundwater monitoring, continued maintenance and construction activities, and program management.

## McDonough
PUBLIC DISCLOSURE
McDonough
Table 21. McDonough Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Advanced closure in place | 33.5325 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-2 | Closure by removal | 17.9449 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-3 | Advanced closure in place | 40.5159 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-4 | Advanced closure in place | 52.2868 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 144.2801 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 22. McDonough Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 144280064.9842 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $16.1 million consist primarily of water treatment activities, AP-1 civil works scope, final stack and cover for AP-4, as well as groundwater monitoring costs for all four ash ponds, permitting support, execution of the AP-4 grouting scope, AP-2 final restoration, and demobilization of the prime contractor. Activities expected during 2024 include completion of additional excavation scope on AP-2/3/4 and permitting activities. The installation of the AP-1 barrier wall included in the 2024 forecast will ultimately coincide with the EPD’s review of the engineering plans.

## McIntosh
PUBLIC DISCLOSURE
McIntosh
Table 23. McIntosh Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 21.9243 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill 3 | Closure in place | 2.8374 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill 4 | Closure in place | 9.2325 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 33.9942 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 24. McIntosh Current Estimated Cost by Executive Cost Code
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 33993610.2225 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $2.7 million consist primarily of ash pond/landfill dike and dam maintenance, continued groundwater monitoring and associated oversight, and program management. Activities expected during 2024 include continued groundwater monitoring, maintenance, and program management.

## McManus
PUBLIC DISCLOSURE
McManus
Table 25. McManus Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Closure by removal to permitted landfill | 108.7523 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 108.7523 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 26. McManus Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 108752297.7037 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $2.8 million consist primarily of groundwater monitoring, pond dike and dam maintenance, and program management. Activities expected during 2024 include continued groundwater monitoring, pond maintenance, and program management.

## Mitchell
PUBLIC DISCLOSURE
Mitchell
Table 27. Mitchell Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-A | Closure by removal to permitted landfill and beneficial reuse | 2.3579 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-1 | Closure by removal to permitted landfill and beneficial reuse | 57.986 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-2 | Closure by removal to permitted landfill and beneficial reuse | 68.7101 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 129.054 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 28. Mitchell Current Estimated Cost by Executive Cost Code
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 129054115.5778 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $36.3 million consist primarily of AP-1/AP-2 CCR excavation, stacking, and truck and rail car loading. The cost of these activities is partially offset by beneficial use sales proceeds. Activities expected during 2024 include continued excavation of AP-1/AP-2 and activities associated with the transport and beneficial use of CCR.

## Scherer
PUBLIC DISCLOSURE
Scherer
Table 29. Scherer Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Advanced closure in place | 19.9777 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill | Active landfill / closure in place | 0.0071294 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 19.9848 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 30. Scherer Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 19984846.0847 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $5.9 million consist primarily of procurement and installation of piping and electrical materials to support dewatering, procurement and installation of dewatering equipment, groundwater monitoring, and completion of the early site work construction package. Activities expected during 2024 include completion of dewatering equipment installation, commencement of water treatment, permitting support, and the start of ash movement activities onsite.

## Wansley
PUBLIC DISCLOSURE
Wansley
Table 31. Wansley Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Closure by removal | 34.986 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Landfill | Closure in place | -0.007644 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total |  | 34.9783 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 32. Wansley Current Estimated Cost by Executive Cost Code
($ in Millions)
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 34979549.6619 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $10.8 million consist primarily of review and technical support for Wansley AP-1 permit, continued front-end planning activities, and continued dewatering system commissioning activities, and procurement of streambank mitigation credits for landfill expansion in support of ash pond closure. Activities expected during 2024 include detailed design, permitting support, commencement of construction activities for the following: Landfill Cells 1-3, haul road, stream culvert foundation, and final commissioning of the dewatering system.

## Yates
PUBLIC DISCLOSURE
Yates
Table 33. Yates Current Estimated Cost by Ash Pond / Landfill
($ in Millions)
Ash Pond / Landfill | Closure Method | Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
AP-1 | Closure by removal | 17.3082 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-2 | Closure by removal | 121.6312 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-3 | Advanced closure in place | 84.7919 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-A | Closure by removal | 17.1964 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-B | Closure by removal | 16.8682 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
AP-B' | Advanced closure in place | 12.5351 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Gypsum Landfill | Inactive landfill / closure by removal to permitted landfill and beneficial reuse | 4.4441 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
R6 Landfill | Inactive landfill / closure in place | 33.7544 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
|  | 308.5295 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Table 34. Yates Current Estimated Cost by Executive Cost Code
| Project to Date Actuals Through Dec 2023 | 2024 Forecast | 2025 Forecast | 2026-2028 Forecast | 2029-2031 Forecast | 2032-2079 Forecast | Total
Previous Closure Cost | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Program Management | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Front End Planning | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Detailed Engineering Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Construction | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Post Closure Costs | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Total | 308529454.9766 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
Retail Cost Estimates
*Project-to-Date Actuals represent costs incurred from January 1, 2003 through December 31, 2023
Note: Details may not add to totals due to rounding
Notes:
2023 actuals through December of $25.5 million consist primarily of excavation, stacking of CCR and installation of the cover system. The site also continues to progress final site restoration/backfill activities. Activities expected during 2024 include AMA cap and cover completion, prime contractor demobilization, transition into IPCC, and permitting support activities.