BEFORE THE PUBLIC SERVICE COMMISSION

STATE OF GEORGIA

In Re:						   :

:

CAPACITY AND ENERGY PAYMENTS			DOCKET NO.: 4822

TO COGENERATORS UNDER PURPA	   :

:

EMERGENCY PETITION OF RGP BOWMAN SOLAR, LLC

FOR EXTENSION OF TIME

AND

PETITION FOR DECLARATORY RULING ON INTERCONNECTION COSTS FOR A QUALIFYING FACILITY

Comes now, RGP BOWMAN SOLAR, LLC (“Bowman”), Petitioner, and pursuant to O.C.G.A. § 50-13-11, Commission Utility Rules 515-2-1-.04(3), 515-2-1-.12 and the Georgia Public Service Commission’s (“Commission”) Order (the “Order”) in the above styled docket files its “Emergency Petition for Extension of Time and Petition for Declaratory Ruling on Interconnection Costs for A Qualifying Facility” (“Emergency Petition” or “Petition”), seeking the following relief:

a.  an emergency extension of time (as needed to resolve the interconnection issues raised in this Petition) to execute a State-jurisdictional Transmission Qualifying Facility (“QF”) Interconnection Agreement (“QFIA”) with Georgia Power Company (“Georgia Power” or the “Company”) for the interconnection of a 76.53 MW solar photovoltaic (“PV”) generation facility (the “QF Facility”)  and 9.72 MVA Battery Energy Storage System (“BESS”) located at 2375 Georgia Highway 172, Bowman, Elbert County, Georgia   30624 (Latitude 34.236284; Longitude 82.998566) consisting of approximately 342 acres (the “Subject Property”), the execution of which Georgia Power currently requires on or before April 27, 2024;

b.  a declaratory ruling that Georgia Power’s requirement that Bowman ----REDACTED-------REDACTED----REDACTED------REDACTED----REDACTED---- Georgia Power for estimated installation costs for affected system network upgrades to the Georgia Transmission Corporation (“GTC”) system, which the Company contends is required to interconnect the QF Facility to the GTC electric system, the required payment of which to the Company violates the Commission’s Order, the Qualifying Facilities Transmission Generator Interconnection Procedures (“QF-TGIP”) and pertinent provisions of the QFIA, and is further unjust and unreasonable;

c.  a declaratory ruling that Georgia Power’s requirement that Bowman ----REDACTED----REDACTED---REDACTED---REDACTED- which the Company contends are required for interconnection of the QF Facility to the Company’s electric system, the required payment of which is an unreasonable interconnection cost in violation of the Commission’s Order, the QF-TGIP and pertinent provisions of the QFIA, and is further unjust and unreasonable;

d. a declaratory ruling that the Company’s requirement that Bowman make ----REDACTED--REDACTED--REDACTED--REDACTED---REDACTED---- for interconnection facilities for its QF Facility are not based on the Company’s actual cost to provide O&M services, and are otherwise unreasonable and violate the Commission’s Order, the QF-TGIP and QFIA;

e.  a declaratory ruling that Bowman has timely provided the Company with acceptable ICF Site control documents and all necessary Property Rights documents to develop the QF Facility on the Subject Property substantially in the Company’s standard form and in conformance with the Company’s standard requirements; and

f.  enter a Procedural and Scheduling Order by which the Commission will take evidence on this Petition and issue its final decision.

INTRODUCTION

Georgia Power acknowledges its urgent need for new generation capacity to meet its customers’ growing needs.  Bowman seeks to develop its 76.53 MW QF Facility, along with a 9.72 MVA BESS in Elbert County, Georgia to provide the Company with new, clean, affordable generation that will help the Company meet an explosive and unexpected increase in customer demand.  The BESS will have storage duration of four (4) hours and a capacity of 40 MW.  The cost of the QF Facility is approximately $150 million, including BESS.  Bowman’s QF Facility will sell power to Georgia Power at avoided cost which will put additional downward pressure on customer rates.   Hopefully, Bowman’s QF Facility can be online by January 1, 2027.  The Company designated the QF Facility as GPCQF-1034.

Bowman recognizes its responsibility to pay reasonable interconnection costs to allow its QF Facility to interconnect with Georgia Power’s electric system for transmission of its generation to locations that need power.  Bowman is willing to pay reasonable interconnection costs for that purpose.  However, Bowman has no legal responsibility to pay unreasonable costs simply because they are required by the Company.

Here, Georgia Power’s assessment of interconnection costs for Bowman’s QF Facility are unreasonable.  In the QFIA, Georgia Power requires Bowman to pay or provide security for the payment of interconnection costs in the total -----REDACTED----.  Broken down, Georgia Power requires payment or security for affected system network upgrades to GTC’s electric system --- REDACTED and --       --REDACTED-------REDACTED----REDACTED------REDACTED----REDACTED--.  Some of these upgrades may be unnecessary, and some of the estimated costs may be significantly overstated.

The imposition of such costs creates a multi-million-dollar roadblock to the development of Bowman’s QF Facility.  To put the Company’s assessed interconnection costs in proper context, the Company requires Bowman to pay or provide security for more than one-half of the total cost of the QF Facility to interconnect and be on the grid.  The magnitude of the interconnection costs assessed by the Company will prevent the construction of the QF Facility, at the very time that the Company needs a massive amount of new generation accompanied with new BESS.  As shown below and as Bowman expects to establish through evidence in support of this Petition, the Company’s interconnection charges are unreasonable, violate the Commission’s Order, the QF-TGIP and QFIA.  The Commission should grant the relief requested by Bowman.

JURISDICTION OF THE COMMISSION

This Commission has jurisdiction to oversee the valuation of renewable energy generation resources.  It has general regulatory authority over electric utilities in Georgia pursuant to O.C.G.A. §§ 46-2-20, 46-2-21 and 46-2-23, and it is responsible for administration of the Integrated Resources Planning Act, O.C.G.A. § 46-3A-1, et seq.  This Commission has jurisdiction to implement the provisions of the Public Utilities Regulatory Policy Act of 1978 (“PURPA”), and pursuant thereto, this Commission in its Order reserved “the right to determine the reasonableness of any State-jurisdictional interconnection costs assigned to a QF through a QFIA or a negotiated QF Standard Offer Contract.”  Pursuant to O.C.G.A. § 50-13-11 and Commission Utility Rule 515-2-1-.12, this Commission may issue a declaratory ruling in any matter in which the petitioner is uncertain or insecure with respect to its rights.

STATEMENT OF FACTS

Bowman is a Georgia limited liability company created on December 1, 2021, Control No.:  21299366.   Bowman maintains its principal place of business at 1131 Tanglebrook Drive, Athens, Clarke County, Georgia   30606.  Bowman was organized to develop a QF Facility and enter into a “Standard Contract for the Purchase of Non-Firm Energy from a Qualifying Facility” (the “Standard QF PPA”) with Georgia Power by which the Company will purchase the electricity generated by the QF Facility.

Development of Bowman’s QF Facility progressed pursuant to the QF-TGIP approved by this Commission for QFs, as follows:

- Bowman entered into a QF Interconnection Study Agreement for GPCQF-1034 (the “Study Agreement”) on December 15, 2022;

- Pursuant to the Study Agreement, Section 1.1, Southern Company Services (“SCS”) performed the QF Interconnection Study on behalf of the Company;

- The QF Study – Phase I (“Phase I”), completed on March 24, 2023, required submission of additional information. (Exhibit “A,” attached hereto).

- Upon submission, a revised QF Study – Phase I v.2 (“Phase I v.2”) was completed on March 30, 2023. (Exhibit “B,” attached hereto).

- Initially, Phase I found that the Bowman QF Facility ----REDACTED-------REDACTED----------.

- Upon receipt of Phase I and Phase I v.2, Bowman determined ----REDACTED-------REDACTED-REDACTED--REDACTED--REDACTED- during the review process.

- When Bowman entered the required data in the Company’s SIMPL program, the QF Facility’s data was compliant ----REDACTED------REDACTED, but the same data was not compliant with ----REDACTED-------REDACTED----REDACTED---------, in other words, the --REDACTED—REDACTED----- during the Company’s evaluation.

- Working with Staff (and by agreement of the Company and Bowman), the QF Facility was resubmitted for analysis on September 15, 2023.

- The ---REDACTED------ the QF Facility remained constant through the subsequent analysis, and Bowman’s QF Facility passed Phase I, and it  proceeded to Phase II.

- Phase I v.2 imposed ----REDACTED-------REDACTE           D----REDACTED and ----REDACTED---REDACTED---REDACTED------REDACTED----REDACTED.  Affected System Interconnection Utility Upgrades were identified for GTC’s system, and other possibly affected systems were identified, including South Carolina Public Service Authority, Dominion Energy South Carolina (“DESC”), Duke Energy Carolinas and the U.S. Army Corps of Engineers.

- GTC conducted a Facilities Study Report based on Phase I and identified upgrade costs required on its system of $1,603,000. (Exhibit “C,” attached hereto).

- Subsequently, the Company conducted the QF Study -- Phase II (“Phase II”), the results of which were provided to Bowman on January 8, 2024. (Exhibit “D,” attached hereto).

- Phase II identified substantially increased interconnection costs. ----REDACTED-------REDACTED----REDACTED------REDACTED---- REDACTED--------REDACTED-------REDACTED----REDACTED-.  Affected System Interconnection Utility Upgrades for GTC were identified for the first time ----REDACTED-------REDACTED;

- Upon receipt of Phase II, DESC conducted an interconnection study and found no upgrades were required. (Exhibit “E,” attached hereto).

- Between Phase I v.2 and Phase II, Bowman’s total interconnection costs increased by ----REDACTED-------REDACTED-------, such increase accounting for 61% of the total interconnection cost.

- The Company disputed Bowman’s site control documentation, and Bowman responded to the Company on March 20, 2024.

- Rather than fully resolve the site control issues it raised, Georgia Power tendered Bowman a draft QFIA on March 27, 2024 with execution required on or before April 27, 2024, preserving its right to challenge site control later.

- The ----REDACTED-------REDACTED---------are the basis for the Company’s demand for payment or security in the QFIA.

- Simultaneously with execution of the QFIA, Bowman must provide the Company with a Notice to Proceed (“NTP”), and within ten (10) days after providing the NTP, Bowman must ----REDACTED-------REDACTED----REDACTED---REDACTED.

- If Bowman fails to execute the QFIA, provide the NTP and pay or provide security identified above, Bowman’s QF Facility will lose its place in the Company’s interconnection queue, and its application and approval process must start completely over (if at all).

Given these facts, Bowman will be unable to challenge the interconnection costs identified in Phase II, and it must pay and/or provide security to the Company as required in the QFIA if timing relief is not granted to execute the QFIA.   Otherwise, Bowman must either start over or terminate development of its QF Facility.

I.

REQUEST FOR EMERGENCY RELIEF

Bowman seeks emergency relief to maintain the status quo pending execution of the QF Facility’s QFIA and to hold its position in the Company’s interconnection queue pending Commission resolution of the interconnection issues raised herein.  Bowman’s request for emergency relief to extend the time to execute the QFIAs should be granted, during which time this Commission can exercise its authority to determine whether the interconnection costs imposed on the QF Facility are reasonable – and thereby compliant with its Order.

Commission Utility Rule 515-2-1-.04(3) allows the Commission to approve emergency relief in its discretion.  Requests for emergency or expedited relief to this Commission are rare.  However, emergency relief is appropriate when the facts so require, as they do here.  The issues raised by Bowman in this Petition are important to both the parties and the public, and they require resolution by the Commission.  It is proper and appropriate for the Commission to maintain the status quo until these issues can be resolved.  Bowman’s request for relief is also necessary to preserve the Commission’s jurisdiction to resolve these matters, and it is consistent with past Commission action on QF interconnection issues.

II.

REQUEST FOR DECLARATORY RELIEF

Pursuant to O.C.G.A. § 50-13-11 and Commission Utility Rule 515-2-1-.12, Bowman requests that the Commission issue a declaratory ruling as to its rights and obligations under the QF Facility’s QFIA pertaining to interconnection costs assessed by the Company.  In compliance therewith, Bowman shows the Commission, as follows:

a.  Petitioner’s name and address:

RGP Bowman Solar, LLC

c/o Mr. Neville A. Anderson

1131 Tanglebrook Drive

Athens, Georgia   30606

b.  The full text of the statute, rule or order upon which a ruling is requested:

- “Order;” In re: Capacity and Energy Payments to Cogenerators Under PURPA; Docket 4822 (March 11, 2021) https://psc.ga.gov/search/facts-document/?documentId=184684;

- “Order Approving Qualifying Facility Interconnection Procedures and Interconnection Agreement Documents;” Docket 4822 (May 24, 2022) https://psc.ga.gov/search/facts-document/?documentId=190208; and

3.  Georgia Power Company’s QF Guidelines (as applicable), Docket 4822 (April 8. 2022) https://psc.ga.gov/search/facts-document/?documentId=189524.

c.  Paragraph statement of pertinent and existing facts necessary to determine the applicability of the quoted statute or rule:

Refer to Statement of Facts, supra and Argument and Citation of Authorities, infra.

d.   Statement of Petitioner’s interest in the matter and why Petitioner is uncertain with respect to its rights:

Refer to Statement of Facts, supra.

(e).  Petitioner’s contention with citation of legal authorities to support a decision in accordance therewith:

Refer to Argument and Citation of Authorities, infra.

- The Commission should declare that the interconnection costs for upgrades on GTC’s system are unreasonable and that “Affected System-Interconnection Utility Upgrades” issues should be resolved between Bowman and GTC.

1.  Georgia Power’s determination of the network upgrade costs

on GTC’s transmission system are unreasonable.

It does not matter how the Company defines the interconnection costs and Network Upgrades because the costs and security requirement imposed by the Company on Bowman are unreasonable under any definition.  The requirement of -------REDACTED----REDACTED-- which are 61% of total project costs should raise red flags to this Commission.

Inconsistencies in the descriptions, classifications and requirements for interconnection are also problematic.  In Phase I, the Company required ----REDACTED-------REDACTED----REDACTED------REDACTED----REDACTED----,” GTC’s study did not include -----REDACTED and therefore imposed no additional costs for it.  In Phase II, Georgia Power included the ----REDACTED-------REDACTED----REDACTED------REDACTED----REDACTED--------REDACTED---------.”  But, it identified them as “TBD by GTC” – even though both are included with a price in GTC’s Study.  The Company did not include the previously identified ----REDACTED-------REDACTED----REDACTED---.”  Instead, Georgia Power for the first time ----REDACTED-------REDACTED----REDACTED------R-.  The Company erroneously stated GTC’s estimated cost of ---REDACTED- the Vanna Primary Substation, when it was only $193,000.

These discrepancies raise important and significant questions as to:   whether the network upgrades are actually needed and whether the Company’s cost estimates are accurate.  If the answer to either is “no,” the obligation imposed on Bowman by the Company to pay for them is unreasonable, and the costs are being improperly allocated to Bowman’s QF Facility.  Ultimately, the reasonableness of interconnection costs presents a fact question for resolution by the Commission. The reasonableness of these costs can only be established through the presentation of testimony and evidence before the Commission.

2.  The upgrades identified by the Company in Phase II

are “Affected System-Interconnection Utility Upgrades.”

The Company’s Phase II study requires Bowman to ----REDACTED-------REDACTED----REDACTED for upgrades to GTC’s transmission system, specifically for the following:

----REDACTED-------REDACTED

----REDACTED------REDACTED--.

----REDACTED-------REDACTED

----REDACTED------REDACTED----REDACTED----.

Under Federal Energy Regulatory Commission (“FERC”) precedent, each upgrade identified by the Company is a Network Upgrade, which is defined as being all facilities “at or beyond the point where the Interconnection Customer’s Generating Facility interconnects to the Transmission Provider’s Transmission System.”  FERC precedent distinguishes Network Upgrades by using a “simple test for distinguishing Interconnection Facilities from Network Upgrades,” with Interconnection Facilities being designated at or near the Point of Interconnection (“POI”).

FERC’s common-sense distinction has been recognized and applied by other state tribunals seeking to “distinguish interconnection costs from network upgrade costs, rather than jumbling their meanings, because they express two distinct concepts.” CED Wheatland Wind LLC v. Montana Department Of Public Service Regulation, 509 P.3d 19 (MT 2022).  Therefore, any required improvement on GTC’s transmission system (which plainly occurs beyond the POI) is a Network Upgrade, the definition of which is found in the QF-TGIP as an “Affected System-Interconnection Utility Upgrade.  Under that definition, it is governed by QF-TGIP, Paragraph 15 (“Paragraph 15").

- QF-TGIP, Paragraph 15 requires Bowman and GTC

to negotiate and contract directly for

“Affected System-Interconnection Utility Upgrades.”

Paragraph 15 (“Paragraph 15”) instructs Bowman and GTC to discuss interconnection directly, with little or no role for Georgia Power to play.  Specifically, Paragraph 15 provides:

If GPC identifies any potential Affected System-Interconnection Utility, GPC will provide contact information to enable Generator to engage directly with the Affected System-Interconnection Utility to determine the need for an Affected System-Interconnection Utility study; Generator will be responsible for paying the Affected System-Interconnection Utility for any study deemed necessary by that utility. The Affected System-Interconnection Utility will identify any Affected System-Interconnection Utility Upgrades necessary for safe and reliable interconnection and operation of its Electric System during parallel operation of the QF. (Emphasis added)

Pursuant to the Company’s own QF-TGIP, Bowman had to contact GTC directly to request an interconnection study (which it did), and GTC had to determine the costs of the required network upgrades (which it did, as well) for its own system resulting from Bowman’s QF Facility.

Paragraph 15 also requires that Bowman and GTC enter into a separate agreement from the QFIA, stating:

Any upgrade identified for an Affected System-Interconnection Utility (including, if applicable, with a GPC affiliate or an ITS Participant) must be facilitated under a separate agreement between Generator and the Affected System-Interconnection Utility, which agreement will address, inter alia, scope of the Affected System-Interconnection Utility Upgrades, costs to be paid by Generator, and anticipated schedule for the upgrades. Any question regarding scope, cost, or schedule for the Affected System-Interconnection Utility Upgrades must be resolved between Generator and the Affected System-Interconnection Utility.  (Emphasis added).

Once GTC is identified as an Affected System-Interconnection Utility, Paragraph 15 requires Bowman and GTC to be responsible for the study, planning, construction and testing for necessary upgrades, as follows:

Generator and the Affected System-Interconnection Utility will be responsible for managing all engineering, procurement, construction, and testing necessary for completion of all Affected System-Interconnection Utility Upgrades work.  Before the Facility can be allowed to synchronize, any Affected System Interconnection Utility must provide written verification to GPC that all necessary project work and appropriate mitigation has been completed.

As a result, the Company’s involvement is limited solely to the receipt of written verification of the completion of any upgrade.

FERC precedent, should be applied to all upgrades required to GTC’s system pursuant to Paragraph 15.  After Bowman engaged GTC to conduct an interconnection study of the required Network Upgrades indicated in Phase I v.2 on its affected system and after GTC’s study was completed on August 24, 2023 and its findings were presented to Bowman, Bowman could reasonably believe that its responsibility to pay for Network Upgrades to GTC was $1,603,000.  For certain, GTC notified Bowman that: “The final step would then be for GTC to prepare an Affected Systems Agreement (“ASA”) for execution by GTC and Bowman which both parties stood ready to do.   GTC’s study did not mention the line -------REDACTED-------REDACTED---------, and Bowman could not possibly have foreseen that Phase II would require----REDACTED-------REDACTED--REDACTED---REDACTED--REDACTED.

- Only GTC can direct Bowman’s

payment of GTC’s Network Upgrade costs.

Pursuant to Paragraph 15, the impact of Bowman’s QF Facility on GTC’s transmission network must be resolved between them.  Because it is GTC’s system, Georgia Power cannot assess Network Upgrade costs (as it did for ---REDACTED)---------- receive payments for required Network Upgrades on GTC’s system.  Bowman’s obligation to pay for Network Upgrades on GTC’s transmission system can only be fully negotiated and resolved by Bowman and GTC, giving Georgia Power (other than having SCS identify the possible upgrade itself) no further role to play.

- In its QF-TGIP and QFIA, Georgia Power differentiates between

Network Upgrades without a rational basis.

Georgia Power’s QF-TGIP and QFIA differentiate Network Upgrades, without any technical basis.  For example, Phase I identified four (4) GTC system Network Upgrades and separately classified them, as follows:

“Affected System-Interconnection Utility Upgrades:”

-----REDACTED-----------------

-----REDACTED-------------------.

“Affected System Owned Interconnection Facilities (Coordinated by GPC):”

---------REDACTED----------------

----REDACTED-------REDACTED----REDACTED------REDACTE D----REDACTED----

“Affected System-Interconnection Utility Upgrades,” are defined in QF-TGIP, Paragraph 15 as:

An Affected System utility or electric facility owner whose facilities require additions, modifications, or upgrades that are necessary for safe and reliable operation of the Electric System during parallel operation of the QF, other than those required due [to GPC’s designation of the QF’s output to serve GPC’s Native Load, as referenced in the Study Report.

Applying Georgia Power’s terminology, this definition isthe equivalent of Network Upgrades, based on FERC precedent.  Phase I correctly identified the ----REDACTED-------REDACTED--------------- as Affected System-Interconnection Utility Upgrades.  Therefore, it was appropriate for Bowman to request a cost study from GTC.

The ----REDACTED-------REDACTED----REDACTED--- also Network Upgrades under FERC precedent.  But, Georgia Power delineates them as “Affected System Owned Interconnection Facilities (Coordinated by GPC)” in Phase I.  However, it is unclear what they are because “Affected System Owned Interconnection Facility" is not defined in either the QF-TGIP or the QFIA.  The QF-TGIP also incorporates the provisions of the SCS’s State-Jurisdictional Qualifying Facility Transmission Generator Interconnection Study Process (“SJQF-TGISP”), and “Affected System Owned Interconnection Facility” is also not defined there.   While an ”Affected System Owned Interconnection Facility” is not a term defined in any Georgia Power or Southern Company document, the basis for Georgia Power’s differentiation is clear:  these Network Upgrades will be “coordinated” by the Company.

“Coordinated” by the Company means that Georgia Power assumes responsibility for virtually all facets of interconnection for Bowman’s QF Facility.  Georgia Power’s “Coordination” seems to supersede the authority of the affected system, here, GTC.  Phase II, Section D.2.2 states that:

Georgia Power Company will contact the potential Electric System utilities … or an electric facility owner that is impacted by the Generator’s proposed QF interconnection and are identified below.  GPC will coordinate with these Affected System(s) to identify the cost and timing of any Affected System owned Interconnection Facilities required to allow interconnected operation of the QF with the Electric System as indicated in this Study Report.

QFIA, Section 1.5(F) gives Georgia Power the obligation to design and construct the network upgrades on GTC’s system.  Therefore, Georgia Power will tell GTC what upgrades are needed on its system, set the cost (which Bowman will have to pay or for which it will have to provide security to Georgia Power) and schedule construction of the upgrade.

Under the Company’s delineation, it becomes the contractor and the bank.  It collects payments or holds an LC as long-term security for network upgrades to GTC’s affected system.  The actual processes the Company will use in its banker role are not stated in the QFIA, and no procedures therefor have been approved by this Commission.  For example, the Company states that it will ----REDACTED-------REDACTED----REDACTED------REDACTED----------------------------.  redacted must be provided promptly, even though project construction may occur years later.

GTC is not a party to the QFIA which requires Bowman to pay or post security to the Company in order to interconnect with GTC’s system.  Bowman knows of no document confirming GTC’s agreement to the provisions of Phase II, Section D.2.2 allowing the Company to unilaterally make its interconnection decisions.  If Bowman pays interconnection costs up front, there is (to Bowman’s knowledge) no document governing how the Company will hold the funds, which entity is entitled to interest that should accrue or a process for its release if the cost of construction does not deplete the funds.

Bowman is not aware of any document between Georgia Power, Bowman and GTC which sets the procedures by which the Company (as a third party) may hold or release security for the Network Upgrade, and (on information and belief) no such document has been approved by the Commission for use by the Company as part of the QF-TGIP.  The QFIA gives no direction as to whom the -------REDACTED------------, nor does it address the terms or procedures by which funds should be held, when it can be drawn down or released upon payment, etc.  Indeed, no thought or oversight appears to have been given to address the legalities or mechanics of an overwhelming credit facility being held for Georgia Power’s (and not GTC’s) benefit. However, the obligation to pay the Company or provide security will unequivocally and significantly adversely affect Bowman’s ability to capitalize the project.

The Company does not distinguish between Network Upgrades because of different technology or because a specific upgrade may require a different means of interconnection.  Instead, the Company distinguishes between Network Upgrades based on by Georgia Power’s designated use of the QF’s electricity.  The Company created its own authority by adding an exclusion in its definition of “Affected System-Interconnection Utility” in the QF-TGIP and the QFIA.  In both documents, an “Affected System-Interconnection Utility” is defined as:

An Affected System utility or electric facility owner whose facilities require additions, modifications, or upgrades that are necessary for safe and reliable operation of the Electric System during parallel operation of the QF, other than those required due to GPC’s designation of the QF’s output to serve GPC’s Native Load, as referenced in the Study Report. (Emphasis Added)

It would appear that the designated Native Load exclusion operates to remove most Network Upgrades from the jurisdiction of the other “affected systems.”

Here, The Company designated Bowman’s QF Facility as Native Load in Phases I and II by requiring the QF to provide “firm delivery of the QF’s output to GPC Native Load.”   As applied, virtually all interconnection requirements on GTC’s system (including Bowman’s) now fall under Paragraph 16, rather than Paragraph 15 of the QF-TGIP because they are no longer Affected System-Interconnected Utility Upgrades due solely to the Company’s exclusion in the definition.  With its designation, Georgia Power determined that a Network Upgrade is really not a network upgrade, allowing Georgia Power to control of all facets of QF interconnection, irrespective of FERC precedent.

The Company’s differentiation between network upgrades certainly conflicts with FERC’s precedent.  It is also possible that this arrangement discriminates against Bowman’s QF Facility, vis a vis the Company’s RFP solicitation programs.  If the Company imposes different rules for QFs, than it does for RFP projects, the Company’s QF-TGIP and QFIA may violate PURPA.  If so, the Company’s differentiation of network upgrades should be disregarded and the Commission should follow common-sense FERC precedent.

B.  The Commission should declare that the interconnection costs for network upgrades on the Georgia Power/Southern Company transmission system are unreasonable.

Similarly, the interconnection costs on the Company’s system identified in Phase II are also unreasonable.  Phase II identified more -------REDACTED-------REDACTED------REDACTED---REDACTED- on the Southern Company’s transmission system.  This amount is alarming for interconnecting a QF Facility that is estimated to increase the load on existing lines by approximately one per cent (1%).   The QFIA (based on Phase II) requires Bowman (and Bowman alone) -------REDACTED-------REDACTED------REDACTED------- the Southern Company system.

The upgrades to Southern Company’s transmission system identified in Phase II raise three important questions:

- whether it is proper to impose these costs on Bowman alone, when others will  benefit from the upgrade upon completion;

- whether the upgrades identified in Phase II are actually required; and

- whether the costs of the upgrades calculated in Phase II are reasonable.

Bowman seeks permission to present evidence on each of these issues, and its request falls squarely within the Commission’s jurisdiction set forth in the Order.

1.  Allocating the cost ----REDACTED----REDACTED-----REDACTED---------------------

is unreasonable, discriminatory, and contrary to FERC precedent and

foundational ratemaking principles.

FERC precedent concerning both the allocation of costs for transmission system upgrades, the assignment of upgrade costs to interconnection customers and long-standing ratemaking principles preclude allocating the full costs of -------REDACTED-------REDACTED-----------solely to Bowman’s QF Facility.  The QF-TGIP definition of Interconnection Facility is limited to “the physical facilities necessary to permit interconnected operations” as “consistent with PURPA and 18 C.F.R. § 292.101(b)(7).”  That federal regulation, in turn, limits costs to the “reasonable costs” of interconnection “directly related” to physical facilities “necessary to permit interconnected operations with a qualifying facility,” and only to the extent such costs exceed the costs which the utility “would have incurred if it had not engaged in interconnected operations.”

The impact of Bowman’s QF Facility on these lines is trivial.  Bowman’s QF Facility will contribute a de minimis amount of power to lines that are already over 95% loaded.  When an existing line is already loaded at 95-100% of its capacity and with expectation of some annual load growth, these lines should have already been identified for upgrades in the Company’s planning.  FERC precedent requires that the cost upgrades for the lines in Southern Company’s system be allocated to beneficiaries “in a way that is roughly commensurate with the benefits received,” which “precludes an allocation where the benefits received are trivial in relation to the costs to be borne.”

-------REDACTED-------REDACT already loaded without Bowman’s QF Facility, and the benefits of the rebuild overwhelmingly inure to others.  Imposing the cost to --------REDACTED solely because of Bowman’s QF Facility is inconsistent with fundamental principles of cost causation.  As a QF Facility, it will pay its share of the costs of each project through transmission rates.    Therefore, allocating the costs -------REDACTED-------REDACTED--- violates FERC precedent and requires Bowman to pay unreasonable interconnection costs in violation of the Final Order.

2.  Phase II does not state why the network upgrades are required.

Even assuming the existing lines are at 95% capacity, Phase II did not explain why the addition of a de minimis amount of power ------REDACTED-REDACTED --. Table d.3.a identifies the required interconnection facilities for Bowman’s QF Facility, and Table d.3.b. identifies upgrades to the Southern Company Transmission System.  Phase II provides no explanation why the addition of approximately 1% load requires that the -------REDACTED-------REDACTED--------------------------REDACTED--------------------.   Some basis or explanation for the redacted-- requirement should be provided in Phase II to assess the reasonableness of the required upgrades and whether they are needed.

3.  The costs for the interconnection facilities in Phase II are not explained.

In Phase II, the Company provides no data and makes no effort to justify or substantiate its cost calculations for the interconnection facilities and system upgrades.  For transmission upgrades on the Southern Company transmission system, the Phase II study only gives Bowman the direction -----------REDACTED-------REDACTED---------- and a final price.  No components of the upgrades are identified, and no costs for such components are stated for them.  Furthermore,  Phase II fails to indicate whether the dated –redacted-- has been depreciated by the Company, nor does it provide a credit for the present value of the depreciation dollars collected by the Company from ratepayers over the years for the book life of redacted, creating a potential “double dip” where the Company has the money itself for --redacted but charge full cost to the QF Facility for its REDACTED--.  Notwithstanding the above, with the results of Phase II, the Company requires that Bowman pay for transmission upgrades that --REDACTED with the expectation that the Company’s price estimate will simply be accepted.  Bowman should be allowed to challenge the reasonableness of the costs of the required upgrades through evidence presented to the Commission.

Phase II does identify the components for the interconnection facilities.   For example, the Company determined that a -------REDACTED-------REDACTED----------REDACTED-------, and the mechanical components/requirements are set out.  However, the costs for the components of the substation are not set out.  The component costs are lumped together into one price.  This still provides no basis by which Bowman can assess their reasonableness.  Again, Bowman should be allowed to challenge the reasonableness of the interconnection facilities’ costs through evidence presented to the Commission to determine whether the costs satisfy the reasonableness standard in the Commission’s Order.  For these reasons, the Commission upon hearing testimony and taking evidence from the parties should declare that the Company’s imposed interconnection costs are unreasonable and consequently violate the Order and FERC precedent.

C.  The Commission should declare that the O&M costs

assigned to Bowman’s QF Facility are unreasonable.

The Commission should declare that the required O&M expenses imposed on Bowman’s QF Facility by the Company are unreasonable.  The Bowman QFIA requires payment of REDACTED----REDACTED---REDACTED.   This figure is unreasonably high and significantly exceeds O&M costs in analogous scenarios.  While Bowman will pay fair and reasonable O&M costs, the imposition of very high fees impedes the development of cost-effective new energy generation plants in Georgia.  Alternatively, computation of O&M fees should be based on a transparent formula based on known and verifiable factors that capture likely O&M expenses, checked by a true-up process to ensure that neither generators, the Company, nor ratepayers are overcharged.

D.   The Commission must declare that Bowman has established site control.

The Commission should declare that Bowman’s documentation of site control over both the Subject Property, the ICF site (where the Company’s interconnection facilities will be located) and right of way between them established site control required by the Company.  Site control is defined as: “[t]he right to develop real property for purposes of constructing and operating the QF or for the ICF Site, as applicable.”  The ICF Site is defined as: “[t]he real property, acceptable to GPC, where designated GPC-owned Interconnection Facilities are or will be located, and specifically including the Access Route” – the POI.  The QFIA requires Bowman to establish its legal authority to construct the QF Facility on the Subject Property, to secure easement rights to transmit electricity generated by the QF Facility to the POI and to access the real property on which the POI is located.

The Company’s QF Procedures recognize that site control will be an ongoing requirement after the QF Facility’s interconnection request is received, stating:

Recognizing that Generator may be in initial project planning stages at the time of QF Interconnection Request submission, Generator may or may not yet have full Site Control or ICF Site Control.  Accordingly, GPC requests that Generator, as part of its application, provide details regarding the status of its Site/ICF Site Control. See also Section 8.B (Performance of Study; Site Visit) below for additional Site Control documentation requirements.

QFIA, Section 1.3(B) directs that “each property rights document” must be substantially in compliance with the Company’s standard form, standard requirements and acceptable to the Company and agreed upon in a timely manner.

Bowman provided the Company with the following documents related to site control for its QF Facility:

a.  Option for Lease of the Subject Property;

b.  Warranty Deed for the property on which the POI will be located;

c.  Evidence of support from Elbert County and Hart County for use of the public right of way as the access route for the Company’s activities required in QFIA, Section 1.4;

d.  “site plan layout sketch” for the location of the Tie-Line and POI; and

e. the Interconnection Site Property Rights Affidavit, executed by Neville A. Anderson.

Bowman’s site control documentation satisfies the Company’s requirements, and this Commission should so declare.

III.

PROCEDURE FOR REVIEW

In its Order, the Commission confirmed its jurisdiction to review interconnection costs.  Therein, it reserved “the right to determine the reasonableness of any State-jurisdictional interconnection costs assigned to a QF through a QFIA or a negotiated QF Standard Offer Contract.”  However, the Commission has not established a procedure or precedent by which interconnection costs imposed on a QF, such as Bowman, will be considered.

The Commission has not formally considered an interconnection dispute between a QF Facility and the Company.  Here, Bowman asks the Commission to resolve QF interconnection issues regarding:

- whether it is proper to impose these costs on Bowman’s QF Facility alone, when others will benefit from the upgrade upon completion;

- whether the upgrades identified in Phase II are actually required; and

- whether the costs of the upgrades calculated in Phase II are reasonable.

This request applies to interconnection costs on both the Company’s and GTC’s systems. Resolution of these issues requires the presentation of testimony from witnesses and introduction of documentary evidence as to whether the interconnection requirements imposed by the Company on Bowman’s QF Facility are reasonable.

While this Commission has not conducted a full evidentiary hearing on interconnection of a QF Facility into the Company’s system, the Commission has significant experience in resolving interconnection issues. This Commission considered numerous interconnection issues between telecommunications carriers, and it set an established procedure for resolving them.  The procedures used by the Commission are instructive here.  Likewise, very simple and basic standards for calculating interconnection costs were set:  interconnection costs must be based on the cost to the carrier (without regard to a rate of return) and applied in a non-discriminatory manner.   Bowman requests that the Commission issue a Procedural and Scheduling Order setting forth a procedure and timeline (in consultation with the parties) and setting a standard for evaluation of interconnection costs to resolve the issues raised in this Petition.

CONCLUSION

For the above and foregoing reasons, the Emergency Petition of RGP Bowman Solar, LLC for an Extension of Time and Petition for Declaratory Ruling on Interconnection Costs for Qualifying Facilities must be granted.

This 26th day of April, 2024.

GALLOWAY & LYNDALL, LLP

Counsel for RGP BOWMAN SOLAR, LLC

/s/Newton M. Galloway___________________

Newton M. Galloway

Georgia Bar No.:  283069

Terri M. Lyndall

Georgia Bar No.: 462235

The Lewis-Mills House

406 North Hill Street

Griffin, GA  30223

(770) 233-6230 telephone

(770) 233-6231 facsimile

ngalloway@gallyn-law.com

tlyndall@gallyn-law.com

CULHANE MEADOWS, PLLC

/s/Jeffrey Paul Lutz______________________

Jeffrey Paul Lutz 
Georgia Bar No.:   670646

Culhane Meadows PLLC

1626 Frederica Road Suite 201
Saint Simons Island, GA 31522

(404) 606-1650 telephone

jlutz@cm.law

CERTIFICATE OF SERVICE

I hereby certify that I have this day served a copy of the within and foregoing EMERGENCY PETITION FOR EXTENSION OF TIME AND COMMISSION REVIEW OF INTERCONNECTION COSTS FOR A QUALIFYING FACILITY upon the following persons by causing electronic copies of the same to be transmitted to each interested party that has supplied a valid email address and by first class mail with adequate postage affixed thereon and deposited in the United States Mail addressed to interested parties that have not supplied a valid email address as follows:

Ms. Sallie Tanner

Executive Secretary

Georgia Public Service Commission

244 Washington Street, First Floor

Atlanta, Georgia 30334

Mr. Preston Thomas

Georgia Public Service Commission

244 Washington Street, First Floor

Atlanta, Georgia 30334

pthomas@psc.ga.gov

Ms. Jamie Barber

Georgia Public Service Commission

244 Washington Street, First Floor

Atlanta, Georgia 30334

jamieb@psc.ga.gov

Mr. Steven J. Hewitson

Troutman Pepper Hamilton Sanders, LLP

Bank of America Plaza

600 Peachtree Street, N.E.

Suite 3000

Atlanta, Georgia  30308-2216

steven.hewitson@troutman.com

This 26th day of April 2024.

GALLOWAY & LYNDALL, LLP

Counsel for RGP BOWMAN SOLAR, LLC

/s/Newton M. Galloway___________________

Newton M. Galloway

“Order;” In re: Capacity and Energy Payments to Cogenerators Under PURPA; Docket 4822 (March 11, 2021).

QFIA, Exhibit A, Costs to be Paid by Generator, ¶ 1.

Id.

“Georgia Power 2023 Integrated Resource Plan Update – Main Document;” In re: Georgia Power Company’s 2023 Integrated Resources Plan Update; Docket 55387 (October 27, 2023).

“Stipulation;” Docket 55387 (March 27, 2024) (“The Company … will ensure the incremental revenue from new large load customers has downward pressure of at least $2.89 per month to the typical residential customer…”)

“Order;” Docket 4822, at Ordering Paragraph L, p. 27 (March 11, 2021).  The Company requested that the Commission review interconnection network upgrade costs for two solar projects:  CPV Five Bridges and Heelstone Alligator Creek.  (See: “Letter from Mr. Sean Finnerty to Chair Pridemore;” Docket 4822 (December 2, 2021)(CPV Five Bridges); “Letter from Newton M. Galloway to Chair Pridemore;” Docket 4822 (December 16, 2021)(Heelstone Alligator Creek)).

“Letter from Steven J. Hewitson to Mr. Reece McAlister;” Docket 4822 (March 2, 2021), conveying Georgia Power’s QF Standard Offer Contracts which were approved by the Commission.

“Order Approving Qualifying Facility Interconnection Procedures and Interconnection Agreement Documents;” Docket 4822 (May 24, 2022).

QF Study – Phase I, pp. 4 (Reactive Power), 7 (RVC).

QF Study – Phase I v.2 (March 30, 2023).

QF Study – Phase I, pp. 4 (Reactive Power), 7 (RVC).

Email: William Houser, Manager, Project Manager, Renewable Development to Neville Anderson, September 11, 2023.

Email: Susan Chin, Supervisor, PD Interconnections and Planning to Neville Anderson, October 19, 2023.

QF Study Phase I v.2, p. 14 (March 23, 2023).

Id., at 15.

Id., at 15-16.

Facilities Study Report for Affected System Upgrades (Final), RGP Bowman Solar Affected System Project AS-111, Georgia Transmission Corporation (August 24, 2023).

QF Study Phase II, p. 14 (January 8, 2024).

Id., at 15.

Id.

Dominion Energy South Carolina Affected System Cluster 23-2; System Impact Study Report; Revision 0 (January 26, 2024).

Email, Newton M. Galloway to Steven J. Hewitson (March 20, 2024).

QFIA, Exhibit A, Costs to be Paid by Generator, ¶ 1.

QF Study Phase II, p. 11 (January 8, 2024).

See, e.g.:  Emergency Joint Petition of Marketer Group for Expedited Establishment of COVID-19 Natural Gas Assurance Program; Docket 43115 (April 7, 2020); In re: Global NAPS Georgia, Inc Emergency Petition for Declaratory Ruling Concerning Threatened Denial of Service by BellSouth Telecommunications, Inc.; Docket 16200 (November 6, 2002);

QF Study -- Phase I, Table d.3.d, p. 16.

QF Study – Phase II, Table d.3.c, p. 14.

GTC Study, pp. 2-3.

QF Study -- Phase II, Table d.3.d, p.15.

Id.

QF Study – Phase I, Table d.3.c, p. 15.

QF Study – Phase II, p. 15.  Phase I and Phase I v.2 are silent on this --redacted.

Order No. 2003, 104 FERC ¶ 61,103,  P 21; see also id. at PP 65-66 (explaining that determining whether a facility is a Network Upgrade “does not require a case-specific determination that all users benefit from [the] Network Upgrade” because FERC instead looks only at “whether the upgrade is at or beyond the Point of Interconnection”); Nat’l Ass’n of Regulatory Util. Comm’rs v. FERC, 475 F.3d 1277, 1284 (D.C. Cir. 2007) (reaffirming FERC’s at-or-beyond rule); Entergy Servs. v. FERC, 391 F.3d 1240, 1247-51 (D.C. Cir. 2004) (affirming FERC’s at-or-beyond rule for identifying network upgrades and rejecting utility’s attempt to circumvent it based on the fact that an interconnection customer benefited from the upgrades at issue); Ill. Power Co., 103 FERC ¶ 61,032, at P 5 (2003) (rejecting proposed allocation of system upgrade cost to interconnection customer because the upgrade was at or beyond the point of interconnection).

Facilities Study Report for Affected System Upgrades (Final), RGP Bowman Solar Affected System Project AS-111, Georgia Transmission Corporation (August 24, 2023).

Accord:  QFIA, Section 1.2.C (“If the Study Report indicates that QF Interconnection Service requires modification of the facilities of an Affected System-Interconnection Utility, GPC cannot provide QF Interconnection Service unless and until the Affected System-Interconnection Utility modifies its facility, which is not within GPC’s control. Generator must coordinate with each Affected System-Interconnection Utility to conduct any appropriate study and to accomplish the necessary modification.”).

Facilities Study Report for Affected System Upgrades (Final), RGP Bowman Solar Affected System Project AS-111, Georgia Transmission Corporation (August 24, 2023).

Email:  Keith Martin, E-IV System Services, GTC to Neville Anderson (October 12, 2023).

QF Study – Phase I, Table d.3.c, p. 15.

QF-TGIP, Schedule of Defined Terms, p. 3.

See:  QF-TGIP, Definitions, Exhibit A (p. 10).

See:  QFIA, Schedule of Defined Terms,

QF-TGIP, III. QF Interconnection Study Process, Section 6 (p. 5).

See:  SJQF-TGISP, Part 1, Section 1.1 (p. 3).

QF Study – Phase II, p. 12.

QFIA, Exhibit A, Costs to Be Funded by Generator, Section 1. (In QFIA, Section 2.6 (Security for Upgrade Project(s) Identified for Future Years), the Company allows Bowman to substitute cash prior to any draw upon the LC).

QF-TGIP, p. 10; QFIA, p. 3.

QF Study – Phase I, Section A.1, p.1; QF Study – Phase II, Section A.1, p. 1.

However, the Company’s terminology is still inconsistent .  ----------REDACTED-------------REDACTED------------------REDACTED-------------------REDACTED-------------REDACTED--------------REDACTED-------------------REDACTED-------------------------REDACTED

-------REDACTED---------REDACTED--------

-----REDACTED------REDACTED

----------REDACTED-------------REDACTED------------------REDACTED-------------------REDACTED-------------REDACTED--------------REDACTED-------------------REDACTED-------------------------REDACTED

QF Study – Phase II, GPCQF-1034, January 8, 2024, pp. 13-14.

----------REDACTED-------------REDACTED------------------REDACTED-------------------REDACTED-------------REDACTED--------------REDACTED-------------------REDACTED-------------------------REDACTED.

Order 1000, 136 FERC ¶ 61,051 at p. 639.

See K N Energy, Inc. v. FERC, 968 F.2d 1295, 1300 (D.C. Cir. 1992) (“[I]t has been traditionally required that all approved rates reflect to some degree the costs actually caused by the customer who must pay them.”); Alabama Elec. Coop., Inc. v. FERC, 684 F.2d 20, 27 (D.C. Cir. 1982) (“Properly designed rates should produce revenues from each class of customers which match, as closely as practicable, the costs to serve each class or individual customer.”); see also Tenaska Clear Creek Wind, LLC v. Sw. Power Pool, Inc., 180 FERC ¶ 61,160, at P 99 (2022) (accepting the establishment of a minimum impact threshold “so that interconnection customers do not bear cost responsibility for de minimis impacts on transmission facilities”).

See S.C. Pub. Serv. Auth. v. FERC, 762 F.3d at 85 (affirming FERC Order 1000 and reiterating the court’s endorsement of “assigning the costs of system-wide benefits to all customers on an integrated transmission grid”) (quoting W. Mass. Elec. Co. v. FERC, 165 F.3d at 927).

QF Study – Phase II, pp. 14-15.

QF Study – Phase II, Table d.3.a (Interconnection Facilities), p. 13.

QFIA, Schedule of Defined Terms, p. 6.

QFIA, Schedule of Defined Terms, p. 4.

QF Interconnection Procedures Section II(4)(B), 2d Paragraph.

QFIA, Section 1.3(A).

QFIA, Exhibit A, Attachment 3.

Id., at Ordering Paragraph L, p. 27.

See:  O.C.G.A. § 46-5-164 (requiring:  “All local exchange companies shall permit reasonable interconnection …” and “The rates, terms, and conditions for such interconnection services shall not unreasonably discriminate between providers …”).

See, e.g.: “Procedural and Scheduling Order;” In re:  Petition of Charter Fiberlink – Georgia for Arbitration of Rates, Terms and Conditions of Interconnection with Windstream Georgia, LLC, et al.; Docket 27830 (October 9, 2008).

47 U.S.C. § 252(d).

Bowman does not seek discovery rights, which were commonly made a part of interconnection disputes between telecommunications carrier.