Georgia Power Company’s

Quarterly Renewable Demonstration Projects Monitoring Report

Through September 30, 2024

This report is provided in accordance with the Georgia Public Service Commission’s (“Commission”) Final Order in the 2016 Integrated Resource Plan (“IRP”) proceeding in Docket No. 40161.  The Final Order requires Georgia Power Company (“Georgia Power” or the “Company”) to provide quarterly reports regarding the Closed Ash Pond Solar Demonstration Project approved by the Commission in Docket No. 40161.

Project Scope Summary

Closed Ash Pond Solar – The Closed Ash Pond Solar Demonstration Project allows the Company to develop up to 10 MW of solar generation projects on closed coal ash ponds at Company-owned generating facilities.  The project may include the evaluation of different technologies such as traditional and non-traditional racking systems and solar energy covers.  The energy output of the project will be tied to the site’s existing infrastructure (including existing transmission assets to the extent possible) and will serve Georgia Power customers.  The project will provide the Company with a hands-on, detailed understanding of what is required to permit and build solar generation facilities on top of closed solid waste facilities and/or underdeveloped plant properties.

Actual Expenditures through September 30, 2024

Closed Ash Pond Solar – Expenditures thus far have totaled REDACTED.  The Company has chosen Plant McIntosh to build the 10 MW Solar Facility and has finalized plans for the project taking into account both state and federal CCR rules.  The Company has completed the installation of the project, and the project obtained commercial operation on 7/09/2024.  During Q1 of 2019, a 38 kW demonstration project was installed on the slope of the closed Plant McDonough Ash Pond.

Major Contracts

There is a Demonstration Project Agreement between Southern Company Services, Inc., and  Watershed Geosynthetics LLC.

There is a Labor Contract for Civil Sitework Construction between Georgia Power Company and The McGraley Company LLC.

There is a Labor Contract for Prime Install Construction between Georgia Power Company and Vanguard Energy Partners LLC.

Procurement Status of Significant Components

During the 1st quarter of 2023, procurement activites started with competitively bidding modules,  inverters, fixed tilt racking, combiner boxes, and string harnesses.  As a result of the bids, subsequent evaluations and awards, purchase orders have been issued to the following suppliers during the 2nd quarter 2023:

- Modules – JA Solar

- Inverters – SMA

- Fixed Tilt Racking – Gamechange Solar

- Combiner Boxes – Olson

- String Harnesses – Voltage

Construction Status

During the 4th quarter of 2023, design activities completed and construction activities started.  The McGraley Company mobilized in October 2023 for civil sitework activities which include drainage, access roads, and stormwater management.  Vanguard Energy Partners mobilized in November 2023 for prime construction activities which include electrical, racking and module installation.

During the 1st quarter of 2024, construction activities continued with underground electrical, racking and module installation.  McGraley finished the majority of the civil sitework scope and continues to work on punchlist items.  Vanguard installed inverter station, DC feeders, racking, module, harness cabling and AC feeders.

Projected Spending Curve through September 30, 2024

A quarterly spending curve for the demonstration projects is set forth below, reflecting projected and actual expenditures to date.  The projected spending curve is based upon the Company’s Budget 2016.

Closed Ash Pond Solar - Total Projected Capital Spending Curve by Quarter

| Time Period | Projected Spend | Cumulative Projected Spend | Cumulative Actual Spend | Cumulative Variance To Date |
| --- | --- | --- | --- | --- |
| Through Q4 - 2016 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 - 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 - 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 - 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 - 2017 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 - 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 - 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 - 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 - 2018 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 - 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 - 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 - 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 - 2019 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 - 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 - 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 - 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 - 2020 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 - 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 - 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 - 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 - 2021 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 - 2022 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 - 2022 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 - 2022 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 - 2022 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 - 2023 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 - 2023 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 - 2023 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q4 - 2023 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q1 - 2024 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q2 - 2024 | REDACTED | REDACTED | REDACTED | REDACTED |
| Q3 - 2024 | REDACTED | REDACTED | REDACTED | REDACTED |