## Main
[10 empty] | Load Ramp | [15 empty] | Change in
Project Name | CITY | COUNTY | GPS COORDINATES | CLASS | SEGMENT | TERRITORY | Project Stage | Announced Load* | Initial In Service Date | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | New Project? | Announced Load | Load Ramp | Project Stage | Initial Service Date
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 1000 | Q2 2026 |  |  |  | 200 | 350 | 500 | 600 | 700 | 800 | 900 | 1000 | 1000 | 1000 | 1000 | 1000 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 725 | Q1 2025 |  |  | 5 | 77 | 245 | 365 | 485 | 605 | 725 | 725 | 725 | 725 | 725 | 725 | 725 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 910 | Q4 2026 |  |  |  | 100 | 370 | 550 | 730 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 901 | Q2 2027 |  |  |  |  | 120 | 342 | 588 | 823 | 901 | 901 | 901 | 901 | 901 | 901 | 901 |  | Y | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Outside | Contract for Electric Service | 180 | Q1 2026 |  |  |  | 40 | 110 | 175 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 |  |  |  | Y | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 360 | Q2 2027 |  |  |  |  | 72 | 120 | 168 | 216 | 288 | 360 | 360 | 360 | 360 | 360 | 360 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 300 | Q3 2026 |  |  |  | 100 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 780 | Q1 2026 |  |  |  | 15 | 195 | 390 | 585 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 250 | Q4 2026 |  |  |  | 10 | 125 | 200 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 480 | Q4 2026 |  |  |  | 10 | 143 | 244 | 345 | 447 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 693 | Q2 2025 |  |  | 2 | 10 | 87 | 173 | 260 | 347 | 433 | 520 | 606 | 693 | 693 | 693 | 693 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 481 | Q4 2027 |  |  |  |  | 14 | 118 | 261 | 404 | 481 | 481 | 481 | 481 | 481 | 481 | 481 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Other | Inside | Technical Review | 150 | Q1 2024 |  | 25 | 25 | 50 | 50 | 100 | 100 | 125 | 125 | 150 | 150 | 150 | 150 | 150 | 150 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 651 | Q1 2027 |  |  |  |  | 74 | 149 | 223 | 307 | 419 | 530 | 642 | 651 | 651 | 651 | 651 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 365 | Q2 2025 |  |  | 5 | 125 | 245 | 365 | 365 | 365 | 365 | 365 | 365 | 365 | 365 | 365 | 365 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 144 | Q2 2027 |  |  |  |  | 36 | 72 | 108 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 567 | Q2 2025 |  |  | 2 | 81 | 162 | 243 | 324 | 405 | 486 | 567 | 567 | 567 | 567 | 567 | 567 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Contract for Electric Service | 182 | Q2 2026 |  |  |  | 72 | 128 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Contract for Electric Service | 216 | Q3 2025 |  |  | 6 | 30 | 90 | 150 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 600 | Q2 2026 |  |  |  | 1 | 10 | 200 | 400 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Contract for Electric Service | 324 | Q2 2026 |  |  |  | 94 | 159 | 213 | 256 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Technical Review | 60 | Q4 2026 |  |  |  | 30 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 648 | Q4 2026 |  |  |  | 2 | 10 | 216 | 432 | 648 | 648 | 648 | 648 | 648 | 648 | 648 | 648 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 311 | Q2 2025 |  |  | 2 | 6 | 104 | 208 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 |  |  | Y | Y | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Outside | Technical Review | 240 | Q4 2027 |  |  |  |  | 80 | 80 | 160 | 160 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 470 | Q1 2027 |  |  |  |  | 75 | 157 | 259 | 371 | 470 | 470 | 470 | 470 | 470 | 470 | 470 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 243 | Q3 2027 |  |  |  |  | 39 | 63 | 115 | 167 | 208 | 243 | 243 | 243 | 243 | 243 | 243 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Clean Energy Tech | Outside | Contract for Electric Service | 207 | Q1 2024 |  | 61 | 96 | 132 | 148 | 184 | 196 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 |  | Y | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 240 | Q4 2026 |  |  |  | 40 | 80 | 120 | 160 | 200 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 163 | Q4 2026 |  |  |  | 80 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 200 | Q4 2027 |  |  |  |  | 40 | 80 | 160 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 455 | Q2 2025 |  |  | 5 | 95 | 185 | 275 | 365 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 872 | Q4 2026 |  |  |  | 1 | 10 | 300 | 372 | 672 | 872 | 872 | 872 | 872 | 872 | 872 | 872 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 200 | Q1 2027 |  |  |  |  | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 1200 | Q1 2026 |  |  |  | 250 | 500 | 750 | 1000 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 130 | Q2 2024 |  | 5 | 5 | 68 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 500 | Q4 2026 |  |  |  | 75 | 150 | 250 | 350 | 450 | 500 | 500 | 500 | 500 | 500 | 500 | 500 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Outside | Contract for Electric Service | 192 | Q4 2023 | 1 | 10 | 30 | 100 | 150 | 175 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 |  | Y | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Contract for Electric Service | 240 | Q1 2025 |  |  | 30 | 100 | 150 | 175 | 200 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 162 | Q1 2028 | [5 empty] | 50 | 100 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Outside | Technical Review | 130 | Q1 2029 | [6 empty] | 30 | 80 | 130 | 130 | 130 | 130 | 130 | 130 | 130 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 910 | Q4 2026 |  |  |  | 25 | 350 | 550 | 750 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Contract for Electric Service | 180 | Q3 2026 |  |  |  | 120 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Other | Outside | Technical Review | 300 | Q3 2025 |  |  | 50 | 50 | 100 | 100 | 100 | 100 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 1000 | Q2 2026 |  |  |  | 200 | 350 | 500 | 600 | 700 | 800 | 900 | 1000 | 1000 | 1000 | 1000 | 1000 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Technical Review | 100 | Q4 2025 |  |  | 10 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 150 | Q1 2027 |  |  |  |  | 75 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Other | Multiple Sites | Technical Review | 245 | Q3 2026 |  |  |  | 85 | 85 | 245 | 245 | 245 | 245 | 245 | 245 | 245 | 245 | 245 | 245 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 250 | Q4 2026 |  |  |  | 125 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Technical Review | 80 | Q4 2024 |  | 5 | 5 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 500 | Q4 2027 |  |  |  |  | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 151 | Q2 2028 | [5 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Multiple Sites | Technical Review | 360 | Q3 2027 |  |  |  |  | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Other | Multiple Sites | Technical Review | 110 | Q2 2028 | [5 empty] | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Technical Review | 146 | Q4 2027 |  |  |  |  | 74 | 74 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 |  | Y | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 656 | Q2 2026 |  |  |  | 52 | 126 | 209 | 304 | 353 | 407 | 461 | 503 | 536 | 581 | 623 | 656
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Other | Inside | Technical Review | 65 | Q1 2025 |  |  | 1 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Outside | Technical Review | 250 | Q4 2026 |  |  |  | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Outside | Technical Review | 600 | Q3 2025 |  |  | 10 | 120 | 312 | 505 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Other | Multiple Sites | Technical Review | 118 | Q1 2027 |  |  |  |  | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | 118 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Outside | Technical Review | 50 | Q1 2026 |  |  |  | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Other | Multiple Sites | Technical Review | 300 | Q4 2026 |  |  |  | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 400 | Q2 2027 |  |  |  |  | 100 | 200 | 300 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Request for Electric Service | 105 | Q2 2027 |  |  |  |  | 5 | 91 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 216 | Q3 2026 |  |  |  | 36 | 108 | 180 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 250 | Q1 2026 |  |  |  | 75 | 150 | 200 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 1000 | Q1 2025 |  |  | 5 | 15 | 250 | 500 | 750 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Clean Energy Tech | Inside | Technical Review | 717 | Q3 2025 |  |  | 5 | 5 | 5 | 540 | 717 | 717 | 717 | 717 | 717 | 717 | 717 | 717 | 717
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Outside | Request for Electric Service | 79 | Q4 2027 |  |  |  |  | 26 | 47 | 47 | 64 | 64 | 79 | 79 | 79 | 79 | 79 | 79 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Clean Energy Tech | Inside | Request for Electric Service | 90 | Q1 2024 |  | 61 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 432 | Q1 2028 | [5 empty] | 72 | 216 | 216 | 216 | 288 | 360 | 432 | 432 | 432 | 432 |  |  | Y | Y | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Outside | Contract for Electric Service | 1429 | Q2 2024 |  | 81 | 400 | 768 | 975 | 1054 | 1429 | 1429 | 1429 | 1429 | 1429 | 1429 | 1429 | 1429 | 1429
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Clean Energy Tech | Inside | Contract for Electric Service | 126 | Q2 2023 | 10 | 24 | 71 | 87 | 95 | 106 | 115 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Technical Review | 49 | Q2 2027 |  |  |  |  | 12 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 600 | Q4 2026 |  |  |  | 10 | 163 | 294 | 425 | 557 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 650 | Q1 2026 |  |  |  | 120 | 191 | 247 | 303 | 359 | 415 | 471 | 527 | 583 | 650 | 650 | 650 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 432 | Q4 2027 |  |  |  |  | 10 | 60 | 108 | 216 | 324 | 432 | 432 | 432 | 432 | 432 | 432 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 365 | Q4 2026 |  |  |  | 10 | 124 | 196 | 269 | 341 | 365 | 365 | 365 | 365 | 365 | 365 | 365 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 321 | Q1 2025 |  |  | 25 | 120 | 209 | 301 | 321 | 321 | 321 | 321 | 321 | 321 | 321 | 321 | 321 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Outside | Request for Electric Service | 240 | Q4 2025 |  |  | 15 | 155 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 225 | Q4 2027 |  |  |  |  | 75 | 150 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 |  | Y | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 600 | Q2 2027 |  |  |  |  | 150 | 300 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 285 | Q2 2027 |  |  |  |  | 100 | 200 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285 | 285
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 180 | Q2 2028 | [5 empty] | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Contract for Electric Service | 150 | Q4 2024 |  | 20 | 140 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 597 | Q4 2024 |  | 2 | 10 | 119 | 239 | 358 | 477 | 597 | 597 | 597 | 597 | 597 | 597 | 597 | 597 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 533 | Q4 2027 |  |  |  |  | 10 | 107 | 213 | 320 | 427 | 533 | 533 | 533 | 533 | 533 | 533 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Request for Electric Service | 502 | Q1 2028 | [5 empty] | 184 | 253 | 309 | 387 | 441 | 480 | 502 | 502 | 502 | 502 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Technical Review | 271 | Q1 2027 |  |  |  |  | 33 | 48 | 79 | 97 | 140 | 179 | 233 | 255 | 271 | 271 | 271 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center | Inside | Contract for Electric Service | 145 | Q4 2028 | [5 empty] | 97 | 104 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 |  |  |  |  | Y
*Announced load as of 2037

## Load Change
Project name | Q3 2024 | Q2 2024 | Change
REDACTED | 225 | 300 | -75
REDACTED | 192 | 200 | -8
REDACTED | 207 | 202 | 5
REDACTED | 146 | 115 | 31
REDACTED | 901 | 720 | 181

## Ramp Change
| Q3 2024 | [14 empty] | Q2 2024 | [14 empty] | Change
Project Name | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
REDACTED | [5 empty] | 72 | 216 | 216 | 216 | 288 | 360 | 432 | 432 | 432 | 432 | 0 | 0 | 0 | 0 | 72 | 216 | 288 | 360 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 0 | 0 | 0 | 0 | -72 | -144 | -72 | -144 | -216 | -144 | -72 | 0 | 0 | 0 | 0
REDACTED |  |  | 2 | 6 | 104 | 208 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 0 | 2 | 10 | 104 | 208 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 0 | -2 | -8 | -98 | -104 | -103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 10 | 107 | 213 | 320 | 427 | 533 | 533 | 533 | 533 | 533 | 533 | 0 | 0 | 0 | 10 | 107 | 213 | 320 | 427 | 533 | 533 | 533 | 533 | 533 | 533 | 533 | 0 | 0 | 0 | -10 | -97 | -106 | -107 | -107 | -106 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | [5 empty] | 184 | 253 | 309 | 387 | 441 | 480 | 502 | 502 | 502 | 502 | 0 | 0 | 24 | 63 | 119 | 184 | 253 | 309 | 387 | 441 | 480 | 502 | 502 | 502 | 502 | 0 | 0 | -24 | -63 | -119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 14 | 118 | 261 | 404 | 481 | 481 | 481 | 481 | 481 | 481 | 481 | 0 | 0 | 14 | 118 | 261 | 404 | 481 | 481 | 481 | 481 | 481 | 481 | 481 | 481 | 481 | 0 | 0 | -14 | -118 | -247 | -286 | -220 | -77 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 10 | 60 | 108 | 216 | 324 | 432 | 432 | 432 | 432 | 432 | 432 | 0 | 0 | 0 | 60 | 108 | 216 | 324 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 0 | 0 | 0 | -60 | -98 | -156 | -216 | -216 | -108 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  | 25 | 120 | 209 | 301 | 321 | 321 | 321 | 321 | 321 | 321 | 321 | 321 | 321 | 0 | 3 | 25 | 120 | 209 | 301 | 321 | 321 | 321 | 321 | 321 | 321 | 321 | 321 | 321 | 0 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 75 | 150 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 0 | 0 | 0 | 0 | 75 | 150 | 225 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75 | -75 | -75 | -75 | -75 | -75 | -75 | -75
REDACTED |  |  | 6 | 30 | 90 | 150 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 0 | 0 | 0 | 30 | 90 | 150 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  | 61 | 96 | 132 | 148 | 184 | 196 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 0 | 60 | 113 | 144 | 162 | 192 | 197 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 0 | 1 | -17 | -12 | -14 | -8 | -1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
REDACTED | 1 | 10 | 30 | 100 | 150 | 175 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 0 | 0 | 10 | 30 | 60 | 90 | 130 | 180 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 1 | 10 | 20 | 70 | 90 | 85 | 62 | 12 | -8 | -8 | -8 | -8 | -8 | -8 | -8
REDACTED | [5 empty] | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 36 | 108 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | 0 | -36 | -108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  | 120 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | 2 | 60 | 60 | 120 | 120 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | -2 | 60 | 120 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  | 80 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 0 | 0 | 5 | 80 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 0 | 0 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | [5 empty] | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | 0 | 126 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 0 | 0 | 0 | 0 | -126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 36 | 72 | 108 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 0 | 0 | 0 | 36 | 72 | 108 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 0 | 0 | 0 | -36 | -36 | -36 | -36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 10 | 24 | 71 | 87 | 95 | 106 | 115 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 10 | 50 | 73 | 87 | 95 | 106 | 115 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 0 | -26 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 74 | 74 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 146 | 0 | 0 | 0 | 48 | 97 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 0 | 0 | 0 | -48 | -23 | -41 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
REDACTED |  |  |  |  | 5 | 91 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | 5 | 91 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | -5 | -91 | -100 | -14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 26 | 47 | 47 | 64 | 64 | 79 | 79 | 79 | 79 | 79 | 79 | 0 | 0 | 26 | 47 | 47 | 64 | 64 | 64 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 0 | 0 | -26 | -47 | -21 | -17 | -17 | 0 | -15 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 12 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 0 | 0 | 0 | 12 | 12 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 0 | 0 | 0 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED |  |  |  |  | 120 | 342 | 588 | 823 | 901 | 901 | 901 | 901 | 901 | 901 | 901 | 0 | 0 | 0 | 0 | 90 | 285 | 510 | 695 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 0 | 0 | 0 | 0 | 30 | 57 | 78 | 128 | 181 | 181 | 181 | 181 | 181 | 181 | 181
REDACTED |  |  | 30 | 100 | 150 | 175 | 200 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 0 | 0 | 10 | 30 | 60 | 100 | 140 | 190 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 0 | 0 | 20 | 70 | 90 | 75 | 60 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stage Change
Project Name | Q3 2024 | Q2 2024
REDACTED | Request for Electric Service | Technical Review
REDACTED | Request for Electric Service | Technical Review
REDACTED | Contract for Electric Service | Request for Electric Service

## Initial Service Change
Project Name | Q3 2024 | Q2 2024 | Change (Months)
REDACTED | Q1 2026 | Q2 2026 | -3
REDACTED | Q3 2026 | Q2 2026 | 3
REDACTED | Q1 2026 | Q2 2026 | -3
REDACTED | Q2 2025 | Q4 2025 | -6
REDACTED | Q4 2027 | Q4 2025 | 24
REDACTED | Q1 2027 | Q2 2027 | -3
REDACTED | Q2 2025 | Q4 2025 | -6
REDACTED | Q2 2027 | Q2 2026 | 12
REDACTED | Q3 2025 | Q2 2026 | -9
REDACTED | Q4 2026 | Q2 2026 | 6
REDACTED | Q2 2025 | Q4 2024 | 6
REDACTED | Q3 2027 | Q2 2027 | 3
REDACTED | Q1 2024 | Q2 2024 | -3
REDACTED | Q4 2026 | Q2 2025 | 18
REDACTED | Q4 2027 | Q2 2027 | 6
REDACTED | Q2 2025 | Q4 2025 | -6
REDACTED | Q2 2024 | Q4 2024 | -6
REDACTED | Q4 2026 | Q2 2026 | 6
REDACTED | Q4 2023 | Q1 2025 | -15
REDACTED | Q1 2028 | Q2 2028 | -3
REDACTED | Q1 2029 | Q2 2029 | -3
REDACTED | Q3 2026 | Q4 2025 | 9
REDACTED | Q1 2027 | Q2 2027 | -3
REDACTED | Q3 2026 | Q2 2026 | 3
REDACTED | Q4 2026 | Q2 2026 | 6
REDACTED | Q4 2027 | Q2 2027 | 6
REDACTED | Q2 2028 | Q2 2027 | 12
REDACTED | Q4 2027 | Q2 2026 | 18
REDACTED | Q4 2026 | Q2 2026 | 6
REDACTED | Q1 2026 | Q2 2026 | -3
REDACTED | Q2 2027 | Q2 2025 | 24
REDACTED | Q3 2026 | Q2 2026 | 3
REDACTED | Q1 2026 | Q2 2026 | -3
REDACTED | Q1 2025 | Q4 2025 | -9
REDACTED | Q4 2027 | Q2 2025 | 30
REDACTED | Q1 2024 | Q3 2024 | -6
REDACTED | Q1 2028 | Q2 2027 | 9
REDACTED | Q2 2023 | Q3 2023 | -3
REDACTED | Q2 2027 | Q2 2026 | 12
REDACTED | Q1 2026 | Q2 2026 | -3
REDACTED | Q4 2027 | Q2 2026 | 18
REDACTED | Q1 2025 | Q4 2024 | 3
REDACTED | Q4 2025 | Q2 2025 | 6
REDACTED | Q4 2027 | Q2 2027 | 6
REDACTED | Q2 2028 | Q2 2026 | 24
REDACTED | Q4 2024 | Q2 2024 | 6
REDACTED | Q4 2027 | Q2 2026 | 18
REDACTED | Q1 2028 | Q4 2025 | 27
REDACTED | Q1 2027 | Q2 2027 | -3
REDACTED | Q4 2028 | Q2 2028 | 6

## Removed Projects
Project Name | Announced Load (MW) in 2Q Update | Reason for Removal
REDACTED | 52 | See Note 1
REDACTED | 1280 | Selected alternative state
REDACTED | 460 | Project Cancelled
REDACTED | 200 | Project Cancelled
REDACTED | 180 | Project Cancelled
REDACTED | 192 | Project Cancelled
REDACTED | 115 | See Note 2
REDACTED | 53 | Selected alternative state
REDACTED | 135 | Selected alternative state
REDACTED | 335 | Project Cancelled
Note 1 - Project still active but load now falls below 45 MW threshold for Industrial Large Load Customer.
Note 2 - Project still active but load now falls below 115 MW threshold for Commercial Large Load Customer.

## Projects Added
Project Name | Announced Load*
REDACTED | 1000
REDACTED | 725
REDACTED | 910
REDACTED | 360
REDACTED | 250
REDACTED | 480
REDACTED | 150
REDACTED | 567
REDACTED | 600
REDACTED | 648
REDACTED | 240
REDACTED | 470
REDACTED | 240
REDACTED | 872
REDACTED | 200
REDACTED | 1200
REDACTED | 910
REDACTED | 300
REDACTED | 1000
REDACTED | 100
REDACTED | 360
REDACTED | 110
REDACTED | 65
REDACTED | 600
REDACTED | 118
REDACTED | 300
REDACTED | 400
REDACTED | 600
REDACTED | 365
REDACTED | 597
*Announced load as of 2037