# Q4 2024 Large Load Economic Development Report

February 21, 2025

Docket No. 55378

# Introduction

Georgia Power has a responsibility to serve the needs of its customers — today and for generations to come. Our long-term integrated resource planning processes, along with the Georgia Public Service Commission’s triennial Integrated Resource Plan proceedings, serve as the foundation of our ability to provide clean, safe, reliable, and affordable energy to Georgians and to serve the state’s growing economy. Georgia is the number one state to do business due in large part to the effectiveness of this planning process that ensures we are able to meet energy demands today and in the future.

Since the Company’s last large load quarterly report in November, Georgia’s economy continues to prosper. And as the state’s economic prospects remain bright, the trends leading up to the 2023 IRP Update filing remain consistent, having now continued for more than a year.

The latest data continue to support Georgia Power’s expectation for continued and robust economic growth in Georgia and the timing of new large load customers. As illustrated in this report, the following growth trends continue:

- The pipeline of committed and potential economic development projects continues to grow.

  - As of December 31, 2024, the total pipeline of economic development projects through the mid-2030s has increased by 9,600 MW to 46,100 MW. Of this, 44,200 MW represent large load economic development projects.

  - For the near-term winter of 2028/2029, the large load economic development pipeline has increased by 1,400 MW to 21,300 MW.

- Just as the total and large load economic development pipelines have grown and strengthened, so has the size of commitments from large load customers for reliable service from Georgia Power.

  - As of December 31, 2024, the portfolio of large load customers committed to receiving service from Georgia Power has grown by 228 MW, reaching a total of 8,274 MW across 26 customers. By the winter of 2028/2029, these customers represent a load of 4,885 MW. All of these customers have initial in-service dates of Q4 2028 or sooner.

- Large load customers continue to materialize and progress with construction.

  - In the near-term, projects that have broken ground represent 2,951 MW of the total 4,885 MW of customer commitments for the winter of 2028/2029.

  - Table 1 in this report provides a summary of the construction status of the 26 large load projects that have executed a Request for Electric Service (“RFS”) as of December 31, 2024. Thirteen of these projects have broken ground, and thirteen are pending construction.

This Large Load Economic Development Report is provided in accordance with the Order Adopting Stipulated Agreement issued by the Georgia Public Service Commission (the “Commission”) approving the Stipulation in Georgia Power Company’s (“Georgia Power” or the “Company”) 2023 Integrated Resource Plan (“IRP”) Update in Docket No. 55378. To keep the Commission informed during this period of extraordinary economic growth, Item 2 from the Stipulation requires the Company to file quarterly reports that include information identified in Attachment A of the Stipulation and any other pertinent information about large load economic development activity in the 2023 IRP Update Load Forecast and any changes since the previous update. Details about the existing, new, and former projects in the pipeline are provided in the attachment to this report.

# Changes in the Economic Development Pipeline

Since the third quarter 2024 report, as of December 31, 2024, the total pipeline of economic development projects through the mid-2030s has increased from 36,500 MW to 46,100 MW – an increase of 9,600 MW. Of the 46,100 MW in the total pipeline, 44,200 MW represent large load economic development projects. The large load projects have increased by a net 9,500 MW, resulting from the following changes since the last report:

- 12,200 MW that entered the pipeline;

- 1,700 MW that exited the pipeline; and

- A net decrease of 1,000 MW for projects in the pipeline that decreased their projected load.

Since our last report, in the near-term (winter of 2028/2029), the total pipeline of projects has increased by 1,500 MW to 23,100 MW, while the large load economic development pipeline has increased by 1,400 MW to 21,300 MW. Further details about the existing, new, and former projects in the pipeline are provided in the attachment to this report.

# Changes in Commitments from Large Load Customers

Just as the total and large load economic development pipelines have grown and strengthened, so has the size of commitments to Georgia Power for service from large load customers. As of December 31, 2024, Georgia Power’s committed large customer portfolio has grown by 228 MW to 8,274 MW, representing 26 committed large load projects. This reflects an increase of one committed large load project. By the winter of 2028/2029, these projects represent a load of 4,885 MW. All of these projects have initial in-service dates of Q4 2028 or sooner.

Table 1 below provides a summary of the construction status of the 26 committed large load projects, all of which have executed an RFS with Georgia Power. Thirteen of these projects have broken ground, and thirteen are pending construction. This evidence clearly indicates that these large load customers are materializing and making progress without material delays. In the near-term, projects that have broken ground represent 2,951 MW of the total 4,885 MW of customer commitments for the winter of 2028/2029.

Table 1. Summary of Committed Customers

Table 2 below provides a summary of the changes in the economic development pipeline, commitments from large load customers, and announced load ramps for projects that have broken ground.

Table 2. Summary of Pipeline Changes (approximate MW)

| Date | October 2023 |  | Q3 2024 |  | Q4 2024 |  | Change from Q3 2024 |  | Change since October 2023 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2028/ 2029 | Mid-2030s | 2028/ 2029 | Mid-2030s | 2028/ 2029 | Mid-2030s | 2028/ 2029 | Mid-2030s | 2028/ 2029 | Mid-2030s |
| Total Pipeline | 11,600 | 17,000 | 21,600 | 36,500 | 23,100 | 46,100 | 1,500 | 9,600 | 11,500 | 29,100 |
| Large Load Pipeline | 10,500 | 16,000 | 19,900 | 34,600 | 21,300 | 44,200 | 1,400 | 9,500 | 10,800 | 28,200 |
| Commitments | 2,700 | 3,600 | 4,900 | 8,000 | 4,900 | 8,300 | 0 | 200 | 2,200 | 4,700 |
| Broken Ground | 2,000 | 2,900 | 3,000 | 3,700 | 3,000 | 3,700 | 0 | 0 | 1,000 | 800 |

# Conclusion

Since September 2024:

- The total economic development pipeline has expanded from approximately 36,500 MW to approximately 46,100 MW through the mid-2030s, representing an increase of 9,600 MW;

- Near-term 2028/2029 large loads have increased by 1,400 MW; and

- Customer commitments have expanded from 8,046 MW to 8,274 MW, representing an additional 228 MW.

Since the filing of the 2023 IRP Update in October 2023:

- The total economic development pipeline has expanded from approximately 17,000 MW to approximately 46,100 MW through the mid-2030s, representing an increase of 29,100 MW;

- Near-term 2028/2029 large loads have increased by approximately 10,800 MW; and

- Customer commitments have expanded from 3,612 MW to 8,274 MW, representing an increase of 4,662 MW.

This information evidences that Georgia Power’s load forecast is materializing and that the constructive outcome of the 2023 IRP Update is supportive of economic growth in Georgia.

The Company will continue to monitor economic growth and will keep the Commission apprised of large load activity consistent with the requirements of the Commission’s Order Adopting Stipulated Agreement in the 2023 IRP Update.

Large load economic development projects represent those above the Company’s organic load growth thresholds for commercial and industrial load.