## 3. WBS Report
23-047 Bowen ELG - Screening | [7 empty] | 5/23/2023
DIVISION OF WORK (DOW)
PRELIMINARY ESTIMATE - REVIEW & SIGN-OFF REQUIRED
Item Description | Qty | Unit | Labor Hours | Labor Total | Matl Total | Subs Hours | Subs Total | Engr Total | Engr Exp Total | Total Costs
Front End Planning | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN289 - SCS Front End Planning | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN292 - Outsourced - Front End Planning | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 0 | HR |  | 0 | 0 | 0 | 0 | 22206278.0452 | 0 | 22206278.0452
CECEN283 - Design & Technical Services - Start-Up Support | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN284 - Design & Technical Services - Construction Support | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN285 - Design & Technical Services - Detailed Engineering | 0 | HR |  | 0 | 0 | 0 | 0 | 5706278.0452 | 0 | 5706278.0452
CECEN291 - Outsourced Detailed Engineering | 0 | HR |  | 0 | 0 | 0 | 0 | 16500000 | 0 | 16500000
CECEN293 - Portfolio Unassigned Liabilities/Accruals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN294 - Portfolio Retention |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN296 - Outsourced - Construction Support | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN280 - Engineering Procured |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN281 - Major Equipment (New Gen Only) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN282 - Gas Conditioning Station |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 0 | HR | 17499.862 | 1995156.9617 | 200722169.1924 | 0 | 114956035 | 8151825.7789 | 4891095.4673 | 330716282.4002
COCIN150 - T&PS - Construction Management | 0 | HR |  | 0 | 0 | 0 | 0 | 8151825.7789 | 0 | 8151825.7789
COCIN151 - Temporary Construction | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 4891095.4673 | 4891095.4673
COCIN152 - Construction Unassigned Liabilities/Accruals | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCIN153 - Construction Retention | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCIN154 - OCIP & Builders Risk Insurance |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCIN155 - Outsourced Construction Management | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSCFS875 - Civil Field Services | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSCFS877 - Drilling Services - Civil Field Services | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK001 - Underground Investigations / Site Work |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK002 - OPEN - Future |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK003 - Deep Foundations |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK004 - Foundations and Structural Concrete |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK005 - Structural Steel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK006 - Mechanical |  |  | 17499.862 | 1077314.9617 | 187539681.1924 | 0 | 94956035 | 0 | 0 | 283573031.1541
COCPK007 - Electrical |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK008 - Instrumentation & Controls |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK009 - Insulation, Coatings & Linings |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK010 - OPEN - Future |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK011 - Fuel Receiving, Storage and Handling |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK012 - Demolition |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK013 - Water Treatment & Cooling |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK014 - Material Handling, Storage & Shipping |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK015 - Site Work Restoration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK016 - Permanent Fencing, Parking, Roadways & Related Lighting |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK017 - Buildings / Architectural |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK018 - Off-site Pipelines, Equipment, & Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK019 - SOCO Installed Permanent IT & Communications Facilities |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK020 - Switchyard, Distribution & Transmission |  |  | 0 | 0 | 0 | 0 | 20000000 | 0 | 0 | 20000000
COCPK021 - Underground Mechanical & Electrical |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK022 - Fire Protection |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK023 - Fire Detection |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK024 - Corrective Action |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK025 - Cells, Ponds and Landfills |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK026 - CCR Advanced Engineering Methods |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK027 - Lead and Asbestos Abatement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK028 - Large Cranes and Heavy Hauls |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK029 - Scaffolding |  |  | 0 | 129277.8 | 0 | 0 | 0 | 0 | 0 | 129277.8
COCPK030 - Contractor Indirects |  |  | 0 | 788564.2 | 13182488 | 0 | 0 | 0 | 0 | 13971052.2
COCPK031 - OPEN - Future |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COCPK032 - OPEN - Future |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Start Up | 0 | HR | 0 | 0 | 0 | 0 | 0 | 9260730.3115 | 0 | 9260730.3115
CPCOC310 - Plant Costs - Start-Up | 0 | HR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TSSUC750 - Start-up and Commissioning | 0 | HR | 0 | 0 | 0 | 0 | 0 | 3260730.3115 | 0 | 3260730.3115
TSSUC751 - Start-up - Craft Labor and Materials |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TSSUC752 - Outsourced Start-Up and Commissioning | 0 | HR | 0 | 0 | 0 | 0 | 0 | 6000000 | 0 | 6000000
Project Management | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN286 - Project Management | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN287 - SCS Project Support | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CECEN297 - Outsourced Project Support | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Owner | 0 | HR | 0 | 68627.116 | 6904209.0388 | 0 | 3954124.7577 | 1362762.8417 | 168238.2459 | 12457962
CECEN290 - Allocated EWO's |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPCOC301 - E&S |  |  |  | 68627.116 | 6904209.0388 |  | 3954124.7577 | 1362762.8417 | 168238.2459 | 12457962
CPCOC302 - Asset Purchase |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPCOC303 - OPCO Costs | 0 | HR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPCOC308 - Plant Costs | 0 | HR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPCOC309 - Non Billable |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPCOC311 - Project Credits |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPCOC312 - Owners Cost |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Escalation and Contingency |  |  |  | 717376.8178 | 72171465.1804 | 0 | 41333478.7033 | 14245308.9739 | 1758637.4681 | 130226267.1434
CPCOC304 - Escalation |  |  |  | 118829.6074 | 11954814.6282 |  | 6846668.2033 | 2359658.7332 | 291308.8279 | 21571280
CPCOC305 - Contingency |  |  |  | 598547.2104 | 60216650.5522 |  | 34486810.5 | 11885650.2407 | 1467328.6402 | 108654987.1434
CPCOC306 - Management Reserve |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPCOC313 - Corrective Action |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Removal | 0 | HR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPCOC307 - Retirement Cost |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AFUDC |  |  |  | 431819.5301 | 43443065.6342 | 0 | 24880373.7559 | 8574855.6052 | 1058598.4746 | 78388713
CPCOC300 - AFUDC/IDC |  |  |  | 431819.5301 | 43443065.6342 |  | 24880373.7559 | 8574855.6052 | 1058598.4746 | 78388713
TOTAL PROJECT COST | 0 | HR | 17499.862 | 3212980.4255 | 323240909.0458 | 0 | 185124012.2169 | 63801761.5564 | 7876569.6559 | 583256232.9004
[5 empty] | Total Craft Hours | 17499.862

## 11. Cash Flow - AFUDC
23-047 Bowen ELG - Screening |  |  |  |  | 5/23/2023
AFUDC CASH FLOW
PRELIMINARY ESTIMATE - REVIEW & SIGN-OFF REQUIRED
DOW Code Annual Summary
Additions |  | 2024 | 2025 | 2026 | 2027 | 2028 | Total
CECEN285 - Design & Technical Services - Detailed Engineering |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 5706278.0452
CECEN291 - Outsourced Detailed Engineering |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 16500000
COCIN150 - E&CS Construction Management |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 8151825.7789
COCIN151 - Temporary Construction |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 4891095.4673
COCPK006 - Mechanical |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 283573031.1542
COCPK020 - Switchyard, Distribution & Transmission |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 20000000
COCPK029 - Scaffolding |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 129277.7954
COCPK030 - Contractor Indirects |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 13971051.9258
CPCOC305 - Contingency |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 108654987.1435
TSSUC750 - Start-up and Commissioning |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 3260730.3115
Additions Escalation |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 21571280.4688
Additions E&S Adders |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 12457961.8197
AFUDC |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 78388713.4634
Total Additions |  | 18960199.5065 | 36966312.1384 | 225875747.6956 | 218352727.9363 | 83101246.0969 | 583256233.3737
Removals |  | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Removals Escalation |  | 0 | 0 | 0 | 0 | 0 | 0
Removals E&S Adders |  | 0 | 0 | 0 | 0 | 0 | 0
Total Removals |  | 0 | 0 | 0 | 0 | 0 | 0
GPC Actuals To Date | 0 | [5 empty] | 0
OPCO 2 Actuals To Date | 0 | [5 empty] | 0
Total Project Period Annual | 0 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 583256233.3737
Total Project Cumulative Annual | 0 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | TRUE