## JKA-2-13 Attachment
Project | Plant/Unit | Compliance Measure | Status of Compliance | Compliance Due Date | Cost | Status of PSC Approval | Timeline
Bottom Ash Closed Loop – Remote Submerged Chain Conveyor | Gaston 1-4 | 2020 ELG10 Supplemental Rule | In progress | 2025-12-31 | REDACTED | Approved in 2022 IRP14 | To meet 2020 ELG Rule general applicable limitations of zero discharge, Gaston plans to continue use of a remote submerged chain conveyor system currently in operation but will require additional piping/pump installations for these units. Procurement of equipment began in November 2024. Construction and installation of this project will be completed by the compliance deadline of December 31, 2025.
316(b) Intake Studies & Screen Modifications | Gaston 1-4 | 316(b) rule of the Clean Water Act | Awaiting permit | To be provided in permit issuance | REDACTED | Approved in 2022 IRP | The Company has submitted the required 316(b) studies in accordance with Gaston's current National Pollutant Discharge Elimination System ("NPDES") permit and are waiting on a renewed permit. The final 316(b) compliance strategy will be determined through the NPDES permit process by the Alabama Department of Environmental Management (“ADEM”). The timing of the installation is site-specific and dependent on the permit issuance. Preliminary engineering has begun, but once the permit is issued, the remaining engineering will be completed and the permit will list the required compliance date.
FGD1 WWT2 Phys-Chem-Bio3 Treatment | Bowen 1-4 | 2020 ELG Reconsideration Rule | In progress | 2025-12-31 | REDACTED | Approved in 2022 IRP | Construction began in August 2023 and the project is currently in the start-up and commissioning phase. The project is projected to end this phase and begin performance testing in June 2025. The project is projected to be completed by the compliance due date of December 31, 2025
FGD WWT– ZLD4 | Bowen 1-4 | 2024 ELG Supplemental Rule | Awaiting PSC13 approval | 2029-12-31 | REDACTED | Awaiting approval in 2025 IRP | See the Company's response to STF-JKA-2-11
FGD WWT – VIP5 Subcategory | Scherer 1 & 2 (Scherer 3 option) | 2020 ELG Reconsideration Rule | In progress | 2028-12-31 | REDACTED | Approved in 2022 IRP | The Company began engineering and procurement in third quarter of 2024. Construction has begun in first quarter of 2025. Startup and commissioning is projected to begin first quarter of 2027 and completed by the compliance due date of December 31, 2028.
CRL6 WWT – ZLD | Bowen 1-4 | 2024 ELG Supplemental Rule | Awaiting PSC approval | 2029-12-31 | REDACTED | Awaiting approval in 2025 IRP | See the Company's response to STF-JKA-2-11
CRL WWT – ZLD | Scherer 1-3 | 2024 ELG Supplemental Rule | Awaiting PSC approval | 2029-12-31 | REDACTED | Awaiting approval in 2025 IRP | See the Company's response to STF-JKA-2-11
PM7 CEMS8 Replacement | Bowen 1-4 | 2024 MATS11 Rule | Awaiting PSC approval | July 2027 | REDACTED | Awaiting approval in 2025 IRP | See the Company's response to STF-JKA-2-12
PM CEMS Replacement | Scherer 1-3 | 2024 MATS Rule | Awaiting PSC approval | July 2027 | REDACTED | Awaiting approval in 2025 IRP | See the Company's response to STF-JKA-2-12
Operational CCR9 Landfill Cell Development | Scherer Landfill Cell 3 | CCR | In progress | N/A | REDACTED | Approved in 2022 IRP | The additional landfill capacity is projected to be ready in June 2027 with construction currently underway.
Boiler Studies | Bowen | 111 GHG12 Rule | In progress | 1/1/2030 (co-fire natural gas) | REDACTED | Awaiting approval in 2025 IRP | See the Company's response to STF-PIA-4-14. The boiler studies are expected to completed in 2025.
Boiler Studies | Scherer | 111 GHG Rule | In progress | 1/1/2030 (co-fire natural gas) | REDACTED | Awaiting approval in 2025 IRP | See the Company's response to STF-PIA-4-14. The boiler studies are expected to completed in 2025.
Operational CCR Landfill Cell Development | Bowen Landfill Cells 7&8 | CCR | Awaiting PSC approval | N/A | REDACTED | Awaiting approval in 2025 IRP | The Company will conduct engineering and construction to support an in service date of landfill cells 7 and 8 in 2031.
1FGD = Flue Gas Desulfurization |  | 8CEMS = Continuous Emissions Monitoring System
2WWT = Wastewater Treatment |  | 9CCR = Coal Combustion Residual
3Phys-Chem-Bio = physical, chemical, and biological treatment |  | 10ELG = Effluent Limitations Guidelines
4ZLD = Zero Limits Discharge |  | 11MATS = Mercury and Air Toxics Standards
5VIP = Voluntary Incentives Program |  | 12GHG = Greenhouse Gas
6CRL = Combustion Residual Leachate |  | 13PSC= Public Service Commission
7PM = Particulate Matter |  | 14IRP = Integrated Resource Plan