## STF-JKA-2-29 Attachment J
Estimated Hydro Modernization Schedule of All Projects
Plant | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033
North: Terrora | ENG | UNIT 2 | UNIT 1
North: Tugalo |  | SCOPING | ENG | ENG | UNIT 1/2 | UNIT 3 | UNIT 4
North: Nacoochee |  |  | SCOPING | SCOPING | ENG | ENG/UNIT 1 | UNIT 2
North: Burton |  |  |  |  | SCOPING | ENG | ENG/ UNIT 2 | UNIT 1
North: Tallulah Falls | [7 empty] | SCOPING | ENG | UNIT 1 | UNIT 2/3 | UNIT 4/5 | UNIT 6
North: Yonah | [8 empty] | SCOPING | ENG | UNIT 1/2 | UNIT 2/3
Chattahoochee: Bartletts Ferry 1-4 |  | SCOPING | ENG | ENG | UNIT 1 | UNIT 1 | UNIT 1/3 | UNIT 4/2
Chattahoochee: Oliver |  |  |  | SCOPING | ENG | ENG | UNIT 1 | UNIT 4 | UNIT 2/3
Chattahoochee: Bartletts Ferry 5-6 | [11 empty] | SCOPING | ENG | UNIT 5 | UNIT 6
Chattahoochee: Goat Rock | [8 empty] | SCOPING | ENG | UNIT 3/4 | UNIT 4/5 | UNIT 5/6 | UNIT 6 7/8 BOP
Chattahoochee: North Highlands | [6 empty] | SCOPING | ENG | UNIT 1 | UNIT 2 | UNIT 3 | UNIT 4
Central: Sinclair | [5 empty] | SCOPING | ENG | UNIT 1 | UNIT 2
Central: Lloyd Shoals | [6 empty] | SCOPING | ENG | UNIT 1/3 | UNIT 4/5 | UNIT 2/6
Central: Wallace | [7 empty] | SCOPING | ENG | ENG | UNIT 1 | UNIT 2/5 | UNIT 6/3 | UNIT 4
Other: Flint River | [10 empty] | SCOPING | ENG | BOP
Other: Morgan Falls | [9 empty] | SCOPING | ENG | UNIT 1/2 | UNIT 3/4 | UNIT 5/6 | UNIT 7
Notes:
ENG = engineering
This table reflects the years in which activities are expected to begin.
Plant names in bolded text were approved in the 2019 or 2022 IRPs.
Plant Terrora & Plant Tugalo Units 1-3 represent the actual schedule for those modernization projects.
The Company will continue to evalue the schedules of these modernization projects to optimize resources and address any changes at the sites with the most pressing need of maintenance to mitigate extended unit outages, thereby benefiting the overall hydro modernization schedule.