STF-PIA-32-3

Question:

As it pertains to Bartletts Ferry Units 1-4, what led to the completion date being moved to December 2026 from March 2028 in the February 2025 report?

Response:

Several factors originally contributed to the delay of the Bartletts Ferry Units 1-4 project including Unit 1 bearing rework, Unit 3 generator rotor shaft and stator machining work, and Units 2-4 replacement components. Based on the as-found condition of Unit 1, Georgia Power Company (“GPC”) decided to procure new parts instead of rehabilitating the existing parts. The procurement of new parts (across multiple units) led to the removal of a significant amount of shop and field rehabilitation times. During this time, GPC also created a revised logistics plan that allows for the disassembly of multiple units simultaneously. Combined, these two decisions led to the schedule decrease.