STF-PIA-32-4

Question:

All plants except Bartletts Ferry Units 1-4 are experiencing 1–3-month delays in project completion. For each plant and unit, identify the underlying cause or causes for the delays. Does the Company have the ability or expectation that these delays can be mitigated? If so, please describe the mitigation strategy for each unit.

Response:

See the table below that identifies variances and explanations by unit for each plant.

| Plant | Unit | Explanation of Variances to Unit Online Dates From the 12-30-2024 to 6-30-2025 PSC Report |
| --- | --- | --- |
| Oliver | 1 | The variance is REDACTED on this unit. The date came in to finish REDACTED. |
| Oliver | 2 | The variance is REDACTED on this unit. The date came in to finish REDACTED. |
| Oliver | 3 | The REDACTED to unit online was caused by the updated delivery date for REDACTED REDACTED. |
| Oliver | 4 | The variance is REDACTED on this unit. The date came in to finish REDACTED. |
| Burton | 1 | The variance is REDACTED on this unit. The date came in to finish REDACTED. |
| Burton | 2 | The REDACTED to unit online was caused by REDACTED REDACTED REDACTED REDACTED. |
| Nacoochee | 1 | The REDACTED to unit online was caused by REDACTED REDACTED REDACTED REDACTED REDACTED REDACTED. |
| Nacoochee | 2 | The REDACTED to unit online was caused by REDACTED REDACTED. |
| Tugalo | 4 | Unit 4 online was 4-17-25. The -17 day push to unit online was caused by delays on receiving the generator to port and the high lift system, additional work on the generator bearing pads, and additional time needed to complete the 4 wire test on the turbine. There were zero variances to units 1-3, as they were previously completed at the time of this report. |
| Sinclair | All Units | Schedule is a level 0. No baseline yet. Zero variances. |

The mitigation strategy for discovery work is procuring more replacement components instead of refurbishment, which helps to avoid extensive and uncertain rehabilitation scopes.