**GEORGIA POWER COMPANY**

**Docket No. 55931**

**Yates Units 8-10 Construction Monitoring**

**Data Request No. STF-PIA-3-1**

**STF-PIA-3-R1-1d**

Question:

Please consider this data request to be recurring and submit the information below at one time, each month by the 25th following the month the information relates to. As new information becomes available Staff may request additional information to be filed as part of this DR group, and as the Project progresses, Staff and the Company can re-visit each of these requests for relevance.

* All available reports associated with Consortium, GSU scope, Gas Lateral scope, Transmission Line scope issued – Daily, Weekly, Monthly or any other frequency in PDF and native file format if available (a complete reporting list from the Company, if available, can be marked-up, however, a limited sample of such reports are listed below):

1. P6 XER files,
2. Risk Registers (GPC and Contractors’),
3. Level 1, Level 2, Level 3 schedules (3 week lookahead, 3-month lookahead, Critical Path(s), major cranes/lift schedule, full schedule),
4. Payment Milestone Schedule (including paid, projected to be paid),
5. Force Report,
6. Commodity curves,
7. Acumen Fuse Analyses,
8. Schedule Adherence Report (Planned, Planned Not Complete, Planned Complete, Unplanned Complete - activity counts),
9. Scope change log,
10. Skyline (for Startup System Turnover),
11. Startup System Walkdown Tracker,
12. Weekly Progress Reports,
13. Presentation slides from Yates Management Review Board,
14. All official letters from directors or above (notices, impact, delay, claim, performance, backcharges, etc.) issued – by Consortium or their Subcontractors or GSU scope, Gas Lateral scope, Transmission Line scope performing entities to Georgia Power Company or any of its affiliates,
15. All official letters from directors or above (notices, impact, delay, claim, performance, backcharges, etc.) issued – from Georgia Power Company, or any of its affiliates, to the Consortium, GSU scope, Gas Lateral scope and Transmission Line scope performing entities
16. Any audits, quality assurance findings, corrective actions, lessons learned, ad hoc reviews,
17. Monthly Consortium, GSU scope, Gas Lateral scope, Transmission Line scope Status Report.
18. Company project controls means and methods, and the work product developed to perform cost/schedule analyses, forecasts and reporting for the Project Cost and Schedule (for all scope associated with Plant Yates 8 – 10). Please provide Staff with a copy of each work product (in native format and PDF as appropriate).  Please include a narrative explaining the purpose of each work product.
19. Earned Value Management System (EVMS) work product to track the Project percent complete in a manner consistent with the contract terms for the Prime Contract and work self-performed by Southern Company personnel.  Please provide Staff a copy of the percent complete information and all data that rolls ups to derive that figure.

Response:

Please see the response below for each subsection.

1. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-i for Consortium October 2025 xer files and Owner’s schedule xer files.
2. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-ii for October 2025 update to GPC’s Risk Register. The company is not provided with a copy of the contractor risk register.
3. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-i for October 2025 Consortium Level 1, Level 2, and Level 3 schedules.
4. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-iv for Payment Milestone Schedule.
5. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-v for October 2025 Update to Daily Force Report on 10-31-2025.
6. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-vi for October 2025 update to commodity curves.
7. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-vii for October 2025 update to Acumen Fuse Analyses.
8. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-vii for October 2025 update to for Schedule Adherence Report.
9. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-ix for October 2025 update to Scope Change Log.
10. Skyline (for Startup System Turnover) is not available at this time. The Company will provide the document once it is available.
11. Startup System Walkdown Tracker is not available at this time. The Company will provide the document once it is available.
12. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-xii for October 2025 Weekly Progress Reports.
13. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-xiii for October 2025 Yates MRB.
14. No update for the month of October 2025.
15. No update for the month of October 2025.
16. No update for the month of October 2025.
17. Please see the electronic Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-xvii for the October 2025 POND reports associated with the gas lateral scope. The reporting on GSU scope and Transmission Line is included in the weekly progress reports. The monthly Consortium Reports are provided in the Monthly Status Report.
18. Please see Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-vii and STF-PIA-3-R1-1d-xii for the Yates 8 – 10 Simple Cycle Project Schedule and Trade Secret (“TS”) Attachment STF-PIA-3-R1-1d-xviii for the Yates 8 – 10 Simple Cycle Project Schedule Cost.
19. Trade Secret (“TS) Attachment STF-PIA-3-R1-1d-xix for October 2025 EVMS will be provided once available.

Contact: Frederick Willis