Georgia Power Company’s

Bi-Annual Hydro Modernization Update

For the Period Ending December 31, 2025

This Hydro Modernization Update (“Update”) is provided in accordance with the Order Adopting Stipulation as Amended (the “Order”) issued by the Georgia Public Service Commission (the “Commission”) in the matter of Georgia Power Company’s 2019 Integrated Resource Plan (“IRP”) under Docket No. 42310.  As such, it provides information to allow the Commission to monitor Georgia Power Company’s (“Georgia Power” or the “Company”) modernization efforts at Plant Terrora, Plant Tugalo, Plant Bartletts Ferry 1-4, Plant Nacoochee, and Plant Oliver.

This report also includes updates on the modernization projects at Plants Burton and Sinclair, 
in accordance with the Order for Georgia Power’s 2022 IRP under Docket No. 44160. As well as Plants Bartletts Ferry 5–6, North Highlands, Tallulah Falls, and Yonah, in accordance with the Order for Georgia Power’s 2025 IRP under Docket No. 56002.

Summary of Work Performed by Site

Plant Bartletts Ferry Units 1-4

Plant Bartletts Ferry Units 1-4 are part of the Chattahoochee hydro group. These units began commercial operation at varying times as shown below:

- Bartletts Ferry Units 1-2 in 1926

- Bartletts Ferry Unit 3 in 1928

- Bartletts Ferry Unit 4 in 1951

Summary of Scope of Work: The scope of work is limited to Plant Bartletts Ferry Units 1-4. The work on these units includes generator rewinds, turbine replacements, and replacement of the Balance of Plant (BOP) systems, such as lubricating oil, service water systems, 480V switchgear, and the plant control system. Plant Bartletts Ferry Units 5-6 are not included in this scope of work.

Project Status: Unit 1 began generating on July 14, 2025. Demolition of Unit 3 turbine, generator, and BOP disassembly complete. Unit 3 assembly is ongoing. Unit 2 turbine fabrication is in progress. Unit 2 demolition is in progress. Unit 4 BOP, generator, and turbine demolition are complete.   Unit 4 assembly is ongoing. Unit 1, 2, 3, and 4 headworks have been completed and commissioned.

Plant Nacoochee Units 1-2

Plant Nacoochee Units 1-2 are part of the North Georgia hydro group.  These units began commercial operation in 1926.

Summary of Scope of Work: The scope of work expected for Plant Nacoochee Units 1-2 includes generator replacements, turbine replacement on both units, and replacement of the BOP systems, such as lubricating oil, service water systems, 480V switchgear, and the plant control system.

Project Status: The generator, turbine, and BOP procurement packages have been awarded. Engineering design is complete. Unit 1 assembly complete; unit started generating November 21, 2025. Unit 2 generator and turbine fabrication are in progress.

Plant Oliver Units 1-4

Plant Oliver Units 1-4 are part of the Chattahoochee hydro group.  These units began commercial operations in 1959.

Summary of Scope of Work: The scope of work expected for Plant Oliver Units 1-4 includes turbine replacements and replacement of the BOP systems, such as lubricating oil, service water systems, 480V switchgear, and the plant control system. Additionally, generator replacements will be performed on Units 3 and 4. Generator rewinds were previously completed for Units 1 and 2 during their maintenance cycles in 2015 and 2016, respectively.

Project Status: The turbine, generator, and BOP packages have been awarded. Engineering design packages are complete. Units 1 and 4, turbine and generator demolition are complete. Unit 4 demolition of BOP is in progress and Unit 1 BOP demolition is complete. Unit 1 turbine fabrication is complete.

Plant Burton Units 1-2

Plant Burton Units 1-2 are part of the North Georgia hydro group.  These units began commercial operation in 1927.

Summary of Scope of Work: The scope of work expected for Plant Burton Units 1-2 includes generator rewinds/replacement, turbine replacements, and replacement of the BOP systems, such as lubricating oil, service water systems, 480V switchgear, the plant control system, and spillway gates.

Project Status: Turbine and generator packages have been awarded. Engineering design packages are complete. The demolition of Unit 2 BOP, turbine, and generator is completed. Unit 2 assembly is ongoing. Unit 1 demolition is complete.

Plant Sinclair Units 1-2

Plant Sinclair Units 1-2 are part of the Central Georgia hydro group.  These units began commercial operation in 1953.

Summary of Scope of Work: The scope of work expected for Plant Sinclair Units 1-2 includes generator rewinds/replacement, turbine replacements, and replacement of the BOP systems, such as lubricating oil, service water systems, 480V switchgear, and the plant control system.

Project Status: Engineering and procurement activities are ongoing. The turbine and generator packages have been awarded. The site preparation planning for the project is complete.

Plant Bartletts Ferry Units 5-6

Plant Bartletts Ferry Units 5-6 are part of the Chattahoochee hydro group. These units began commercial operations in 1984.

Summary of Scope of Work: Project kick off meeting is scheduled for 3rd Quarter of 2026.

Plant North Highlands Units 1-4

Plant North Highlands Units 1-4 are part of the Chattahoochee hydro group. These units began commercial operations in 1899. Georgia Power refurbished Plant in 1962.

Summary of Scope of Work: Project kick off meeting was held in October 2025.  Scope is currently being finalized.

Plant Tallulah Falls Units 1-6

Plant Tallulah Falls Units 1-6 are part of the North Georgia hydro group. Construction of the Tallulah development began in 1911 with Unit 1 operational in 1913, followed by Units 2-5 began commercial operational in 1914 and Unit 6 began commercial operational in 1920.

Summary of Scope of Work: The scope of work expected for Plant Tallulah Falls Units 1-6 includes turbine and generator replacements, and replacement of the BOP systems, such as lubricating oil, service water systems, 480V switchgear, and the plant control systems.

Project Status: Engineering and procurement activities are ongoing. Site preparation is ongoing. Turbine and generator packages are out for bid.

Plant Yonah Units 1-3

Plant Yonah Units 1-3 is part of the North Georgia hydro group. Construction began in 1924 with the installation of the three generating units completed in late 1925 and the units put into service in January of 1926.

Summary of Scope of Work: Project kick off meeting is scheduled for 3rd Quarter of 2026.

Summary of Sites with Modernization Complete

Plant Tugalo Units 1-4

Plant Tugalo Units 1-4 are part of the North Georgia hydro group. Plant Tugalo Units 1-2 began commercial operation in 1923. Plant Tugalo Units 3-4 began commercial operation in 1924.

Summary of Scope of Work: The scope of work for Plant Tugalo Units 1-4 includes generator replacements, turbine replacements, and replacement of the BOP systems, such as lubricating oil, service water systems, 480V switchgear, and the plant control system.

Project Status: Work scope complete for all units. Unit 1 began generating on October 10, 2023. Unit 2 began generating on December 7, 2023. Unit 3 began generating on October 8, 2024. Unit 4 began generating on April 17, 2025, and all spillway gates have been commissioned.

Plant Terrora Units 1-2

Plant Terrora Units 1-2 are part of the North Georgia hydro group.  These units began commercial operation in 1925.

Summary of Scope of Work: The scope of work for Plant Terrora Units 1-2 included generator rewinds, turbine replacements, and the replacement of the BOP systems, such as lubricating oil, service water systems, 480V switchgear, and the plant control system.

Project Status:  Modernization work at Plant Terrora is complete. Unit 1 was returned to normal operation on November 19, 2021. Unit 2 was returned to normal operation on December 30, 2020.