## Summary
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Total Project
($1,000s)
|  | 2019 IRP | [9 empty] | 2022 IRP |  |  |  | 2025 IRP
Year | Period Ending | Terrora Actuals | Terrora Project Forecast* | Tugalo Actuals | Tugalo Project Forecast* | Bartletts Ferry 1-4 Actuals | Bartletts Ferry 1-4 Project Forecast* | Nacoochee Actuals | Nacoochee Project Forecast* | Oliver Actuals | Oliver Project Forecast* | Sinclair Actuals | Sinclair Project Forecast* | Burton Actuals | Burton Project Forecast* | Bartletts Ferry 5-6 Actuals | Bartletts Ferry 5-6 Project Forecast* | North Highlands Actuals | North Highlands Project Forecast* | Tallulah Falls Actuals | Tallulah Falls Project Forecast* | Yonah Actuals | Yonah Project Forecast* | Total Actuals | Total Project Forecast*
2019 | 2020-06-30 | 1041.8486 | 260.4158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 1041.8486 | 260.4158
2019 | 2020-12-31 | 3429.6734 | 1848.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 3429.6734 | 1848.093
2020 | 2020-06-30 | 9855.3482 | 10687.3078 | 628.8861 | 623.5072 | 683.1847 | 683.1847 | 33.8242 | 33.8242 | 434.24 | 434.2395 | 0 |  | 0 | 0 | [8 empty] | 11635.4832 | 12462.0635
2020 | 2020-12-31 | 15497.8001 | 18624.3918 | 5507.5219 | 5442.7172 | 1733.8484 | 1733.8484 | 6.4437 | 6.4437 | 3.14 | 3.14 | 0 |  | 0 | 0 | [8 empty] | 22748.7542 | 25810.5412
2021 | 2020-06-30 | 8060.1643 | 8180.7575 | 2188.3582 | 2187.4721 | 3405.1118 | 3405.1118 | 344.7118 | 344.7118 | 480.206 | 480.2063 | 0 |  | 0 | 0 | [8 empty] | 14478.552 | 14598.2596
2021 | 2020-12-31 | 8449.4292 | 7693.7221 | 18029.6887 | 17472.8391 | 11287.421 | 11315.421 | 1352.0203 | 1352.0203 | 521.084 | 521.0852 | 0 |  | 0 | 0 | [8 empty] | 39639.6432 | 38355.0877
2022 | 2020-06-30 | 863.3334 | 750 | 6805.6451 | 13466.6798 | 6375.0951 | 4671.91 | 677.453 | 677.453 | 240.5546 | 240.5551 | 0 |  | 0 | 0 | [8 empty] | 14962.0813 | 19806.5979
2022 | 2020-12-31 | -166.4205 | 0 | 19110.9071 | 19761.8337 | 13844.3996 | 14461 | 2922.9958 | 2922.9958 | 4953.6748 | 4953.6755 | 683.1719 |  | 1299.9293 | 1299.9293 | [8 empty] | 42648.6579 | 43399.4343
2023 | 2020-06-30 |  |  | 11342.4459 | 11032.993 | 17428.8617 | 18095.7 | 2509.5553 | 2292.9644 | 1979.5166 | 1979.5171 | 172.7342 |  | 152.2287 | 152.2287 | [8 empty] | 33585.3423 | 33553.4032
2023 | 2020-12-31 |  |  | 22510.2495 | 7858.4967 | 20761.5151 | 14532.3 | 7300.4088 | 10066.5289 | 14252.6601 | 14252.6615 | 131.284 |  | 3274.2254 | 3274.2254 | [8 empty] | 68230.343 | 49984.2125
2024 | 2020-06-30 |  |  | 11649.7178 | 11712.5592 | 18253.5253 | 12223.68 | 5120.6075 | 14051.3996 | 6424.5803 | 11798.6282 | 328.8083 |  | 1111.1531 | 1111.1531 | [8 empty] | 42888.3922 | 50897.4201
2024 | 2020-12-31 |  |  | 14407.7729 | 7964.6128 | 22470.5493 | 13242.32 | 4931.0943 | 12805.6534 | 19460.1043 | 19768.2141 | 4936.5944 |  | 6059.8504 | 6059.8504 | 0 |  | 1.2776 |  | 0 |  | 0 |  | 72267.2431 | 59840.6507
2025 | 2020-06-30 |  |  | 9150.6339 | 10098.0501 | 19945.967 | 11814.675 | 5129.2079 | 6515.2896 | 12203.2755 | 25355.2395 | 2328.7624 |  | 7779.6092 | 9412.0556 | 0 |  | 1123.9895 |  | 0 |  | 0 |  | 57661.4454 | 63195.3098
2025 | 2020-12-31 |  |  | 1153.1367 | 7670.0805 | 27677.703 | 12996.1425 | 11735.273 | 465.1862 | 24104.7543 | 34223.6738 | 17957.59 |  | 13672.9639 | 14976.7237 | 275.8992 |  | 832.4019 |  | 991.2683 |  | 750.3108 |  | 99151.3011 | 70331.8067
2026 | 2020-06-30 |  |  | 0 | 3.4752 | 0 | 13695 | 0 |  | 0 | 17567.2988 | 0 |  | 0 | 9549.3488 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 40815.1228
2026 | 2020-12-31 |  |  |  |  | 0 | 11205 | 0 |  | 0 | 17230.5655 | 0 |  | 0 | 15656.9864 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 44092.5519
2027 | 2020-06-30 |  |  |  |  | 0 | 0 |  |  | 0 | 4233.2106 | 0 |  | 0 | 2495.0166 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6728.2272
2027 | 2020-12-31 |  |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 1910.9849 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1910.9849
2028 | 2020-06-30 | [8 empty] | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
2028 | 2020-12-31 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
2029 | 2020-06-30 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
2029 | 2020-12-31 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
2030 | 2020-06-30 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
2030 | 2020-12-31 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
TOTAL |  | 47031.1767 | 48044.688 | 122484.9637 | 115295.3168 | 163867.1818 | 144075.2933 | 42063.5957 | 51534.471 | 85057.7907 | 153041.9107 | 26538.9451 | 0 | 33349.96 | 65898.5028 | 275.8992 | 0 | 1957.669 | 0 | 991.2683 | 0 | 750.3108 | 0 | 524368.761 | 577890.1827
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
*Added once Project Forecast estimates are updated and approved. Currently includes Plant Terrora Project Forecast that was developed 1Q 2021, Plant Tugalo 3Q 2021, Bartletts 1-4 4Q 2021, Nacoochee 2Q 2023, Oliver 1Q 2024, Burton 1Q 2025
Measured against Total IRP Budgets = $1,183,449. 2019 IRP Budget - $446,618; 2022 IRP Budget - $145,760 (Burton & Sinclair); 2025 IRP Budget -$591,071 (Bartlets 5-6, North Highlands, Tallulah Falls, & Yonah)
REDACTED

## Bartletts 1-4
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Bartletts Ferry 1-4
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Unit 4 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 683.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683.1847 | 683.1847 | 0%
2020 | 2020-12-31 | 1733.8484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1733.8484 | 1733.8484 | 0%
2021 | 2020-06-30 | 2885.6318 | 0 | 0.763 | 0 | 0 | 0 | 518.717 | 0 | 0 | 0 | 0 | 0 | 3405.1118 | 3405.1118 | 0%
2021 | 2020-12-31 | 1931.456 | 175.273 | 3397.978 | 1995.152 | 43.14 | 632.91 | 817.141 | 44.246 | 598.139 | 904.89 | 60.27 | 686.826 | 11287.421 | 11315.421 | -0.2474%
2022 | 2020-06-30 | 2215.7115 | 238.7545 | 3219.871 | 205.274 | 38.6038 | 58.87 | 176.324 | 36.108 | 61.9404 | 88.578 | 2.721 | 32.339 | 6375.0951 | 4671.91 | 36.46% | B
2022 | 2020-12-31 | 3349.6801 | 939.0034 | 6972.5584 | 23.3581 | 661.7316 | 162.679 | 0.43809 | 675.2071 | 160.9914 | 41.5784 | 726.3531 | 130.8208 | 13844.3996 | 14461 | -4.264%
2023 | 2020-06-30 | 5825.553 | 3173.691 | 6580.9189 | 196.2819 | 37.6299 | 241.3939 | 730.0735 | 37.8381 | 254.2321 | 42.6498 | 39.8318 | 268.7678 | 17428.8617 | 18095.7 | -3.685%
2023 | 2020-12-31 | 4899.4362 | 1818.9075 | 9683.2923 | 103.7633 | 26.8188 | 387.997 | 945.0582 | 89.0408 | 193.5288 | 2234.702 | 28.213 | 350.7571 | 20761.5151 | 14532.3 | 42.86%
2024 | 2020-06-30 | 5172.742 | 1174.7312 | 6122.0382 | 214.3912 | 34.8551 | 74.4588 | 971.798 | 1445.2583 | 2674.3521 | 196.883 | 95.7898 | 76.2276 | 18253.5253 | 12223.68 | 49.33%
2024 | 2020-12-31 | 3895.0714 | 420.4666 | 8868.9808 | 823.2497 | 124.6806 | 1141.251 | 1949.6581 | 121.0873 | 1721.9525 | 2235.4061 | 137.7831 | 1030.962 | 22470.5493 | 13242.32 | 69.69%
2025 | 2020-06-30 | 3071.442 | 345.4024 | 4289.0138 | 371.6112 | 1178.2701 | 292.5502 | 3757.6508 | 2127.7075 | 674.3929 | 1416.5813 | 298.7445 | 2122.6002 | 19945.967 | 11814.675 | 68.82%
2025 | 2020-12-31 | 4378.1343 | 123.4202 | 7903.9401 | 614.8185 | 296.9105 | 1284.6144 | 3924.9377 | 2178.8439 | 436.137 | 1280.6804 | 3981.2812 | 1273.9848 | 27677.703 | 12996.1425 | 113%
2026 | 2020-06-30 | [12 empty] | 0 | 13695
2026 | 2020-12-31 | [12 empty] | 0 | 11205
2027 | 2020-06-30
2027 | 2020-12-31
TOTAL |  | 40041.8914 | 8409.6497 | 57039.3545 | 4547.9 | 2442.6405 | 4276.7242 | 13791.7963 | 6755.337 | 6775.6662 | 8441.9491 | 5370.9875 | 5973.2852 | 163867.1818 | 144075.2933 | 42.4% | A,C
[13 empty] | Current Estimate at Completion |  | 205156.7967 | Increase from $191M at last submittal
Sums and percentages may not add due to rounding.
Notes on Variances
A | Increase from IRP submittal to current forecast driven by turbine, generator, GSU, and electrical equipment pricing.
B | Accounting system adjustments during period ending December 31, 2022.
C | Challenges associated with supply chain issues and identification of more equipment wear and damage than anticipated during the discovery process, are expected to result in overall increased cost.
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast developed Q4 2021.
Measured against 2019 IRP Budget - $114,763

## Nacoochee
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Nacoochee
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 0 | 0 | 0 | 33.8242 | 0 | 0 | 33.8242 | 33.8242 | 0%
2020 | 2020-12-31 | 0 | 0 | 0 | 6.4437 | 0 | 0 | 6.4437 | 6.4437 | 0%
2021 | 2020-06-30 | 0 | 0 | 0 | 344.7118 | 0 | 0 | 344.7118 | 344.7118 | 0%
2021 | 2020-12-31 | 0 | 0 | 627.8157 | 724.2046 | 0 | 0 | 1352.0203 | 1352.0203 | 0%
2022 | 2020-06-30 | 0 | 0 | 269.4713 | 407.9817 | 0 | 0 | 677.453 | 677.453 | 0%
2022 | 2020-12-31 | 0 | 0 | 1716.1745 | 1062.3142 | 0 | 144.5071 | 2922.9958 | 2922.9958 | 0%
2023 | 2020-06-30 | 0 | 0 | 377.1041 | 2115.8357 | 0 | 16.6154 | 2509.5553 | 2292.9644 | 9.446% | B
2023 | 2020-12-31 | 1054.4324 | 1000 | 2244.1849 | 2731.2763 | 260 | 10.5151 | 7300.4088 | 10066.5289 | -27.48% | C
2024 | 2020-06-30 | 1199.5088 | -987.7204 | 3113.4998 | 1572.8604 | 25.4481 | 197.0109 | 5120.6075 | 14051.3996 | -63.56% | C
2024 | 2020-12-31 | 1429.9675 | 153.7207 | 1332.6376 | 1718.8377 | 24.4548 | 271.476 | 4931.0943 | 12805.6534 | -61.49% | C
2025 | 2020-06-30 | 1507.8475 | 253.9548 | 1916.3588 | 1113.517 | 26.2518 | 311.2781 | 5129.2079 | 6515.2896 | -21.27% | C
2025 | 2020-12-31 | 3778.996 | 505.814 | 5462.875 | 1481.182 | 16.766 | 489.64 | 11735.273 | 465.1862 | 2423% | C
2026 | 2020-06-30 | [6 empty] | 0 | 0
2026 | 2020-12-31 | [6 empty] | 0 | 0
2027 | 2020-06-30
2027 | 2020-12-31
TOTAL |  | 8970.7522 | 925.7692 | 17060.1217 | 13312.9894 | 352.9207 | 1441.0426 | 42063.5957 | 51534.471 | -9.883e-14% | A
[7 empty] | Current Estimate at Completion |  | 51534.471 | No change from last submittal
Sums and percentages may not add due to rounding.
Notes on Variances
A | Increase from IRP submittal to current forecast driven by GSU, trash racks, and labor costs.
B | Corrected Unit 2 turbine total for accounting system change of previous posted actuals.
C | Actual expenditures occurring later than assumed in the project forecast.
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast developed Q2 2023.
Measured against 2019 IRP Budget - $44,117

## Oliver
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Oliver
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Unit 4 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 434.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434.24 | 434.2395 | 0.0001105%
2020 | 2020-12-31 | 3.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.14 | 3.14 | 0%
2021 | 2020-06-30 | 480.206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480.206 | 480.2063 | 0%
2021 | 2020-12-31 | 521.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521.084 | 521.0852 | 0%
2022 | 2020-06-30 | 240.5546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240.5546 | 240.5551 | 0%
2022 | 2020-12-31 | 4017.3837 | 0 | 454.9296 | 0 | 0 | 154.1035 | 0 | 0 | 161.3575 | 0 | 0 | 165.9006 | 4953.6748 | 4953.6755 | 0%
2023 | 2020-06-30 | 1439.7506 | 0 | 443.4237 | 1.9717 | 0 | 35.2489 | 0 | 0 | 29.0311 | 0 | 0 | 30.0905 | 1979.5166 | 1979.5171 | 0%
2023 | 2020-12-31 | 2860.7067 | 0.37279 | 5438.8976 | 2400.7393 | 0.19242 | 51.2493 | 2473.514 | 0 | 46.9526 | 923.9494 | 0 | 56.0859 | 14252.6601 | 14252.6615 | 0%
2024 | 2020-06-30 | 2290.4399 | 1.5114 | 1195.335 | 163.0015 | 1.3843 | 212.3314 | 1141.842 | -16.1542 | 120.5993 | 910.0754 | 356.1772 | 48.0372 | 6424.5803 | 11798.6282 | -45.55%
2024 | 2020-12-31 | 3879.1042 | 37.5336 | 5903.5663 | 2479.6737 | 24.5272 | 118.7663 | 1425.3879 | 3344.3326 | 236.6898 | 1239.8627 | 560.6795 | 209.9805 | 19460.1043 | 19768.2141 | -1.559% | B
2025 | 2020-06-30 | 5166.2629 | 118.8456 | 4094.4511 | 253.489 | 86.9905 | 311.6545 | 282.158 | 141.8583 | 47.5297 | 823.0899 | 568.9489 | 307.9972 | 12203.2755 | 25355.2395 | -51.87%
2025 | 2020-12-31 | 4668.5427 | 95.8544 | 11538.2259 | 1764.7235 | 45.0627 | 305.9047 | 1658.1911 | 197.7838 | 280.8039 | 1952.9733 | 981.8171 | 614.8711 | 24104.7543 | 34223.6738 | -29.57%
2026 | 2020-06-30 | [12 empty] | 0 | 17567.2988
2026 | 2020-12-31 | [12 empty] | 0 | 17230.5655
2027 | 2020-06-30 | [12 empty] | 0 | 4233.2106
2027 | 2020-12-31 | [12 empty] | 0 | 0
2028 | 2020-06-30 | [12 empty] | 0 | 0
TOTAL |  | 26001.4153 | 254.1177 | 29068.8292 | 7063.5987 | 158.1572 | 1189.2586 | 6981.0931 | 3667.8204 | 922.964 | 5849.9507 | 2467.6227 | 1432.9631 | 85057.7907 | 153041.9107 | 1.522e-06% | A
[13 empty] | Current Estimate at Completion |  | 153041.9131 | No change from last submittal
Sums and percentages may not add due to rounding.
Notes on Variances
A | Increase from IRP submittal to current forecast driven by labor and material costs.
B | Propane generator costs under Unit 1 moved from Generator to appropriate BOP category.
C
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast expected Q3 2023.
Measured against 2019 IRP Budget - $119,842

## Sinclair
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Sinclair
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022 | 2020-12-31 | 150.8892 | 0 | 379.4143 | 0 | 0 | 152.8683 | 683.1719 | 0
2023 | 2020-06-30 | 59.037 | 0 | 105.1855 | 0 | 0 | 8.5117 | 172.7342 | 0
2023 | 2020-12-31 | 24.1551 | 0 | 101.5007 | 0 | 0 | 5.6282 | 131.284 | 0
2024 | 2020-06-30 | 64.6974 | 0 | 257.0298 | 0 | 0 | 7.081 | 328.8083 | 0
2024 | 2020-12-31 | 1840.1873 | 0 | 3089.0297 | 0 | 0 | 7.3774 | 4936.5944 | 0 |  | A
2025 | 2020-06-30 | 859.8837 | 0 | 1453.4513 | 5.0295 | 0 | 10.3979 | 2328.7624 | 0
2025 | 2020-12-31 | 7113 | 0 | 3760.59 | 6936 | 0 | 148 | 17957.59 | 0
2026 | 2020-06-30 | [6 empty] | 0 | 0
2026 | 2020-12-31 | [6 empty] | 0 | 0
2027 | 2020-06-30 | [6 empty] | 0 | 0
2027 | 2020-12-31 | [6 empty] | 0 | 0
2028 | 2020-06-30 | [6 empty] | 0 | 0
TOTAL |  | 10111.8497 | 0 | 9146.2013 | 6941.0295 | 0 | 339.8646 | 26538.9451 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A | Propane generator costs under Unit 1 moved from Generator to appropriate BOP category.
B
C
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast expected Q1 2026.
Measured against 2022 IRP Budget - $85,405

## Burton
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Burton
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2020 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2021 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2021 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2022 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2022 | 2020-12-31 | 423.7767 | 0 | 722.6852 | 0 | 0 | 153.4674 | 1299.9293 | 1299.9293 | 0%
2023 | 2020-06-30 | 29.4972 | 0 | 116.6981 | 0 | 0 | 6.0334 | 152.2287 | 152.2287 | -3.734e-14%
2023 | 2020-12-31 | 2410.9948 | 0 | 857.9003 | 0 | 0 | 5.3304 | 3274.2254 | 3274.2254 | 1.389e-14%
2024 | 2020-06-30 | 317.5503 | 37.0162 | 734.3376 | 0 | 0.25331 | 21.9957 | 1111.1531 | 1111.1531 | 2.046e-14%
2024 | 2020-12-31 | 1569.2262 | 12.5104 | 4259.3194 | 0 | 1.1576 | 217.6368 | 6059.8504 | 6059.8504 | 6.003e-14% | B
2025 | 2020-06-30 | 166.5588 | 313.2914 | 2808.1636 | 2741.101 | 900.8812 | 849.6133 | 7779.6092 | 9412.0556 | -17.34%
2025 | 2020-12-31 | 2814.3126 | 453.5691 | 4927.013 | 2165.9834 | 734.861 | 2577.2248 | 13672.9639 | 14976.7237 | -8.705%
2026 | 2020-06-30 | [6 empty] | 0 | 9549.3488
2026 | 2020-12-31 | [6 empty] | 0 | 15656.9864
2027 | 2020-06-30 | [6 empty] | 0 | 2495.0166
2027 | 2020-12-31 | [6 empty] | 0 | 1910.9849
TOTAL |  | 7731.9165 | 816.3872 | 14426.1173 | 4907.0844 | 1637.1531 | 3831.3016 | 33349.96 | 65898.5028 | 0% | A
[7 empty] | Current Estimate at Completion |  | 65898.5028 | No change from last submittal
Sums and percentages may not add due to rounding.
Notes on Variances
A | Increase from IRP submittal to current forecast driven by scope change for civil infrastructure.
B | Propane generator costs under Unit 1 moved from Generator to appropriate BOP category.
C
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast expected Q1 2025.
Measured against 2022 IRP Budget - $60,355
REDACTED

## Bartletts 5-6
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Bartletts 5-6
Actuals ($1,000s)
Year | Period Ending | Unit 5 |  |  | Unit 6 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP
2024 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 2020-12-31 | 275.8992 | 0 | 0 | 0 | 0 | 0 | 275.8992 | 0
2026 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 275.8992 | 0 | 0 | 0 | 0 | 0 | 275.8992 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast expected Q2 2029.
Measured against 2025 IRP Budget - $92,222

## North Highlands
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant North Highlands
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Unit 4 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2023 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 | 2020-12-31 | 0 | 0 | 1.2776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2776 | 0
2025 | 2020-06-30 | 0 | 0 | 618.3142 | 0 | 0 | 0 | 0 | 0 | 505.6753 | 0 | 0 | 0 | 1123.9895 | 0
2025 | 2020-12-31 | 715.8252 | 0 | 90.3695 | 0 | 0 | 0 | 0 | 0 | 26.2073 | 0 | 0 | 0 | 832.4019 | 0
2026 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 715.8252 | 0 | 709.9613 | 0 | 0 | 0 | 0 | 0 | 531.8825 | 0 | 0 | 0 | 1957.669 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast expected Q3 2026.
Measured against 2025 IRP Budget - $189,819

## Tallulah Falls
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Tallulah Falls
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Unit 4 |  |  | Unit 5 |  |  | Unit 6 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2024 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 2020-12-31 | 572.9571 | 0 | 418.3112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991.2683 | 0
2026 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 572.9571 | 0 | 418.3112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991.2683 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast expected Q2 2026.
Measured against 2025 IRP Budget - $178,323

## Yonah
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Yonah
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2024 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 2020-12-31 | 750.3108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750.3108 | 0
2026 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | 2020-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | 2020-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 750.3108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750.3108 | 0
Sums and percentages may not add due to rounding.
Notes on Variances
A
B
C
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast expected Q2 2027
Measured against 2025 IRP Budget - $130,707

## Major Contracts
PUBLIC DISCLOSURE
Major Contracts
Project Monitoring Report thru December 31, 2025
Major Contracts | Type | PO 1 | Estimated Amount (1000$)2 | Initial Contract Amount (1000$) | Current Contract Amount (1000$)3 | % Variance4 | Notes
Terrora
Turbine | Supply, remove and install | GPC10980282 / GPC6429-0009 | REDACTED | REDACTED | REDACTED | REDACTED | A, B, P
Generator | Supply, remove and install | GPC65084-0001 | REDACTED | REDACTED | REDACTED | REDACTED | A, C
General Contractor Unit 2 | Install | GPC65147-0001 | REDACTED | REDACTED | REDACTED | REDACTED | A, D
General Contractor Unit 1 | Install | GPC69749-0001 | REDACTED | REDACTED | REDACTED | REDACTED | A, G
Trash Racks | Supply, remove and install | GPC67622-0001 | REDACTED | REDACTED | REDACTED | REDACTED | A
Governor HPU Skids | Supply | GPC10982009 | REDACTED | REDACTED | REDACTED | REDACTED | A
Station Service Transformers | Supply | GPC10977336 | REDACTED | REDACTED | REDACTED | REDACTED | A
Switchgear | Supply | GPC11053203 | REDACTED | REDACTED | REDACTED | REDACTED | A
Lube Oil Skids | Supply | GPC10982036 | REDACTED | REDACTED | REDACTED | REDACTED | A, E
Batteries | Supply | GPC11020730 | REDACTED | REDACTED | REDACTED | REDACTED | A
Generator Step Up Transformer | N/A | N/A | REDACTED | REDACTED | REDACTED
DCS | Supply | GPC10990070 | REDACTED | REDACTED | REDACTED | REDACTED | A, F
Totals |  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Tugalo
Turbine/Generator LNTP | Supply, remove and install | GPC69300-0001 | REDACTED | REDACTED | REDACTED | REDACTED | H, I
Turbine/Generator U1 | Supply, remove and install | GPC69300-0001 | REDACTED | REDACTED | REDACTED | REDACTED | I,J
Turbine/Generator U2 | Supply, remove and install | GPC69300-0002 | REDACTED | REDACTED | REDACTED | REDACTED | I,J
Turbine/Generator U3 | Supply, remove and install | GPC69300-0003 / GPC69300-0013 | REDACTED | REDACTED | REDACTED | REDACTED | I,J
Turbine/Generator U4 | Supply, remove and install | GPC69300-0004 / GPC69300-0012 | REDACTED | REDACTED | REDACTED | REDACTED | I,J
General Contractor U1 | Install | GPC83925-0002 | REDACTED | REDACTED | REDACTED | REDACTED
General Contractor U2 | Install | GPC83925-0004 | REDACTED | REDACTED | REDACTED | REDACTED
General Contractor U3 - Original | Install | GPC83925-0005 | REDACTED | REDACTED | REDACTED | REDACTED | Q
General Contractor U4 - Original | Install | GPC83925-0006 | REDACTED | REDACTED | REDACTED | REDACTED | Q
General Contractor U3 - New contract | Install | GPC93088-0004 | REDACTED | REDACTED | REDACTED | REDACTED | Q
General Contractor U4 - New contract | Install | GPC93621-0001 | REDACTED | REDACTED | REDACTED | REDACTED | Q
Trash Racks | Supply, remove and install | GPC64556-0007 | REDACTED | REDACTED | REDACTED | REDACTED | N
Governor HPU Skids U1 | Supply | GPC69389-0007 / GPC18391-0388 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids U2 | Supply | GPC69389-0008 / GPC18391-0390 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids U3 | Supply | GPC69389-0009 / GPC18391-0386 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids U4 | Supply | GPC69389-0010 / GPC18391-0389 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply | GPC68066-0007 | REDACTED | REDACTED | REDACTED | REDACTED
Switchgear | Supply | GPC63594-0009 | REDACTED | REDACTED | REDACTED | REDACTED
Lube Oil Skids | N/A | N/A | REDACTED | REDACTED | REDACTED | REDACTED
Batteries | Supply | GPC72032-0001 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Step Up Transformers | Supply | GPC70844-0002 | REDACTED | REDACTED | REDACTED | REDACTED | L
DCS Unit 1 | Supply | GPC11121719 | REDACTED | REDACTED | REDACTED | REDACTED | O
DCS Unit 2 | Supply | GPC18391-0383 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 3 | Supply | GPC18391-0419 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 4 | Supply | GPC18391-0421 | REDACTED | REDACTED | REDACTED | REDACTED
Spillway Gates | Supply | GPC64556-0007 | REDACTED | REDACTED | REDACTED | REDACTED | K
Totals |  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Bartletts Ferry 1-4
Turbine Common | Supply, remove and install | GPC69087-0001 | REDACTED | REDACTED | REDACTED | REDACTED | H
Turbine Unit 1 | Supply, remove and install | GPC68064-0005 | REDACTED | REDACTED | REDACTED | REDACTED | M
Turbine Unit 2 | Supply, remove and install | GPC68064-0002 / GPC11503034 | REDACTED | REDACTED | REDACTED | REDACTED | M
Turbine Unit 3 | Supply, remove and install | GPC11485430 / GPC68064-0003 | REDACTED | REDACTED | REDACTED | REDACTED | M
Turbine Unit 4 | Supply, remove and install | GPC68064-0004 | REDACTED | REDACTED | REDACTED | REDACTED | M
Generator Unit 1 | Supply, remove and install | GPC74379-0002 | REDACTED | REDACTED | REDACTED | REDACTED | H
Generator Unit 2 | Supply, remove and install | GPC74379-0005 | REDACTED | REDACTED | REDACTED | REDACTED | H
Generator Unit 3 | Supply, remove and install | GPC74379-0003 | REDACTED | REDACTED | REDACTED | REDACTED | H
Generator Unit 4 | Supply, remove and install | GPC74379-0004 / GPC69855-0016 / GPC96961-0004 | REDACTED | REDACTED | REDACTED | REDACTED | H
General Contractor - All Units | Install | Multiple | REDACTED | REDACTED | REDACTED | REDACTED
Trash Racks | Supply Only | GPC64556-0019 | REDACTED | REDACTED | REDACTED | REDACTED | N
Governor HPU Skids Unit 1 | Supply | GPC73295-0001 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 2 | Supply | GPC73295-0003 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 3 | Supply | GPC73295-0002 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 4 | Supply | GPC73295-0004 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply | GPC68066-0012 | REDACTED | REDACTED | REDACTED | REDACTED
Switchgear | Supply | GPC67910-0006 | REDACTED | REDACTED | REDACTED | REDACTED
Lube Oil Skids | Supply | GPC66641-0008 | REDACTED | REDACTED | REDACTED | REDACTED | O
Generator Step Up Transformer U1 | Supply | GPC70844-0029 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Step Up Transformer U2 | Supply | GPC70844-0004 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Step Up Transformer U3 | Supply | GPC70844-0030 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Step Up Transformer U4 | Supply | GPC70844-0006 | REDACTED | REDACTED | REDACTED | REDACTED
DCS U1 | Supply | GPC71804-0010 | REDACTED | REDACTED | REDACTED | REDACTED
DCS U2 | Supply | GPC18391-0422 | REDACTED | REDACTED | REDACTED | REDACTED
DCS U3 | Supply | GPC18391-0413 | REDACTED | REDACTED | REDACTED | REDACTED
DCS U4 | Supply | GPC18391-0420 | REDACTED | REDACTED | REDACTED | REDACTED
|  |  | REDACTED | REDACTED | REDACTED | REDACTED
Totals |  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Nacoochee
Turbine Unit 2 | Supply, remove and install | GPC69300-0008 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Unit 2 | Supply, remove and install | GPC69300-0014 | REDACTED | REDACTED | REDACTED | REDACTED
Turbine and Generator Unit 1 | Supply, remove and install | GPC69300-0015 | REDACTED | REDACTED | REDACTED | REDACTED
General Contractor U1 | Install | GPC97256-0001 / GPC73295-0011 | REDACTED | REDACTED | REDACTED | REDACTED
General Contractor U2 | Install | GPC97256-0002 / GPC73295-0008 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 1 | Supply | GPC73295-0011 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 2 | Supply | GPC73295-0008 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply | GPC83584-0004 | REDACTED | REDACTED | REDACTED | REDACTED
Switchgear | Supply | GPC54530-0019 | REDACTED | REDACTED | REDACTED | REDACTED
Lube Oil Skids | N/A | N/A | REDACTED | REDACTED | REDACTED | REDACTED
Batteries | Supply | GPC72032-0003 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Step Up Transformer | Supply | GPC70844-0014 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 1 | Supply | GPC18391-0362 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 2 | Supply | GPC18391-0363 | REDACTED | REDACTED | REDACTED | REDACTED
Bulk Heads | Supply | GPC64556-0010 | REDACTED | REDACTED | REDACTED | REDACTED
Trash Racks | Supply Only | GPC64556-0018 | REDACTED | REDACTED | REDACTED | REDACTED
Head Gates | Supply and install | GPC64556-0018 | REDACTED | REDACTED | REDACTED | REDACTED
Totals |  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Oliver
Turbine Unit 1 | Supply, remove and install | GPC64290-0016 | REDACTED | REDACTED | REDACTED | REDACTED
Turbine Unit 2 | Supply, remove and install | GPC64290-0014 | REDACTED | REDACTED | REDACTED | REDACTED
Turbine & Generator Unit 3 | Supply, remove and install | GPC64290-0033 / GPC64290-0015 | REDACTED | REDACTED | REDACTED | REDACTED
Turbine & Generator Unit 4 | Supply, remove and install | GPC64290-0020 | REDACTED | REDACTED | REDACTED | REDACTED
General Contractor - Unit 1, 3 & 4 | Install | Multiple | REDACTED | REDACTED | REDACTED | REDACTED
Trash Racks | Supply | GPC89056-0004 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 1 | Supply | GPC73295-0016 / GPC73295-0009 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 2 | Supply | GPC73295-0005 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 3 | Supply | GPC73295-0006 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 4 | Supply | GPC73295-0007 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply | GPC83584-0008 | REDACTED | REDACTED | REDACTED | REDACTED
Switchgear Buses | Supply | GPC67910-0035 | REDACTED | REDACTED | REDACTED | REDACTED
Lube Oil Skids | Supply
Batteries | Supply | GPC72032-0007 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Step Up Transformer | Supply | GPC70844-0021 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 1 | Supply | GPC71804-0002 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 2 | Supply | GPC71804-0003 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 3 | Supply | GPC71804-0004 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 4 | Supply | GPC71804-0005 | REDACTED | REDACTED | REDACTED | REDACTED
Depressing Air Compressor | Supply | GPC68851-0143 | REDACTED | REDACTED | REDACTED | REDACTED
Headgates | Supply | GPC94852-0032 / GPC89056-0002 | REDACTED | REDACTED | REDACTED | REDACTED
|  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Sinclair
Turbine U1 | Supply, remove and install | GPC64290-0030 | REDACTED | REDACTED | REDACTED | REDACTED
Turbine U2 | Supply, remove and install | GPC64290-0035 | REDACTED | REDACTED | REDACTED | REDACTED
Generator U1 | Supply, remove and install | GPC64290-0034 | REDACTED | REDACTED | REDACTED | REDACTED
Generator U2 | Supply, remove and install | GPC64290-0036 | REDACTED | REDACTED | REDACTED | REDACTED
General Contractor - Unit 2 | Install
Trash Racks | Install
Governor HPU Skids Unit 1 | Supply | GPC73295-0013 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids Unit 2 | Supply | GPC73295-0012 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply | GPC83584-0012 | REDACTED | REDACTED | REDACTED | REDACTED
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer | Supply | GPC70844-0025 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 1 | Supply | GPC18391-0359 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 2 | Supply | GPC18391-0361 | REDACTED | REDACTED | REDACTED | REDACTED
Bulk Heads | Supply
Trash Racks | Supply Only
|  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Burton
Turbine LNTP | Supply, remove and install | GPC69300-0016 | REDACTED | REDACTED | REDACTED | REDACTED
Turbine/Generator U1 | Supply, remove and install | GPC69300-0016 | REDACTED | REDACTED | REDACTED | REDACTED
Turbine/Generator U2 | Supply, remove and install | GPC69300-0017 | REDACTED | REDACTED | REDACTED | REDACTED
General Contractor - Unit 2 | Install | GPC98936-0001 | REDACTED | REDACTED | REDACTED | REDACTED
Trash Racks | Supply and install | GPC89056-0017 | REDACTED | REDACTED | REDACTED | REDACTED
Governor HPU Skids | Supply | GPC73295-0010 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply | GPC83584-0010 | REDACTED | REDACTED | REDACTED | REDACTED
Switchgear | Supply | GPC54530-0028 | REDACTED | REDACTED | REDACTED | REDACTED
Lube Oil Skids | Supply
Batteries | Supply | GPC72032-0008 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Step Up Transformer | Supply | GPC70844-0015 | REDACTED | REDACTED | REDACTED | REDACTED | O
DCS Unit 1 | Supply | GPC18391-0358 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Unit 2 | Supply | GPC18391-0360 | REDACTED | REDACTED | REDACTED | REDACTED
Bulk Heads | Supply
|  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Bartletts 5-6
Turbine | Supply, remove and install
Generator | Supply, remove and install
General Contractor | Install
Trash Racks | Supply, remove and install
Governor HPU Skids U1-4 | Supply
Station Service Transformers | Supply
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer | Supply
DCS U1-4 | Supply
Spillway Gates | Supply
|  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
North Highlands
Turbine | Supply, remove and install
Generator | Supply, remove and install
General Contractor | Install
Trash Racks | Supply, remove and install
Governor HPU Skids Common | Supply | GPC73295-0020 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer U1&2 | Supply | GPC70844-0033 | REDACTED | REDACTED | REDACTED | REDACTED
Generator Step Up Transformer U3&4 | Supply | GPC70844-0031 | REDACTED | REDACTED | REDACTED | REDACTED
DCS Common | Supply | GPC18391-0502 | REDACTED | REDACTED | REDACTED | REDACTED
Spillway Gates | Supply
|  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Tallulah Falls
Turbine | Supply, remove and install
Generator | Supply, remove and install
General Contractor | Install
Trash Racks | Supply, remove and install
Governor HPU Skids Common | Supply | GPC73295-0018 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer | Supply
DCS Common | Supply | GPC18391-0500 | REDACTED | REDACTED | REDACTED | REDACTED
Spillway Gates | Supply
|  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
Yonah
Turbine | Supply, remove and install
Generator | Supply, remove and install
General Contractor | Install
Trash Racks | Supply, remove and install
Governor HPU Skids | Supply | GPC73295-0019 | REDACTED | REDACTED | REDACTED | REDACTED
Station Service Transformers | Supply
Switchgear | Supply
Lube Oil Skids | Supply
Batteries | Supply
Generator Step Up Transformer | Supply
DCS Common | Supply | GPC18391-0501 | REDACTED | REDACTED | REDACTED | REDACTED
Spillway Gates | Supply
|  |  | REDACTED | REDACTED | REDACTED | REDACTED
Sums and percentages may not add due to rounding.
1 PO's included when contract value exceeds $100k following award of contract and issuance of PO.
2 Estimated amount from Project Estimate
3 This reflects change orders to the contract/purchase order
4 From Initial Contract Amount to Current Amount
Notes on Variances
A | Variances between the Estimated Amount and the Initial Contract Amount are the result of the differences between the screening level Estimated Amount compared to the actual contract that was procured and is reflected as the Initial Contract Amount.
B | Additional work related to rehabilitation and replacement of components not included in base scope.
C | Additional rotor stability frame due to safety concerns. Additional cleaning and handling of the generator rotor.
D | Documents issued for bid vs documents issued for construction.
E | Additional valve, differential pressure transmitters, and lifting frame modification.
F | Power and water cybersecurity suite equipment, operation station, and additional start up support.
G | "Estimated Amount" included in General Contractor Unit 2 value. Shown in Cell E9.
H | Limited Notice to Proceed - contract negotiations completed
I | Turbine and Generator scope issued a single contract due to an alternate bid
J | Transferred braking/jacking and vibration monitoring scope to vendor, added scope for online brush removal and terminal blocks.
K | Estimate includes supply and install. Originally estimated as Obermeyers, current strategy is replace in kind.
L | Includes U1 and U3 transformers
M | Steel indices
N | Storage Fees
O | Part associated with completing the final design.
P | Accounting system adjustments during period ending December 31, 2022.
Q | New contracts due to replacement of General Contractor for finishing BOP work for Units 3 & 4.

## Change Orders
PUBLIC DISCLOSURE
Project Change Orders
Project Monitoring Report thru December 31, 2025
Material Change Orders (>$100k)
Terrora
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
2020-01-30 | Controls | REDACTED | 2020-05-13
2020-01-30 | Penstock manholes/platforms, turb/gen platform, air reciever tank, control room access | REDACTED | 2020-05-13
2020-05-14 | Unit 1/2 Turbine Increases. | REDACTED | 2020-05-14
2020-05-14 | Night Shift Coordinator | REDACTED | 2020-05-18
2020-06-23 | Terrora Isolation Valves | REDACTED | 2020-07-23
2020-10-19 | Terrora Overhead Crane uprate | REDACTED | 2020-10-19
2020-11-10 | Equipment and Startup support | REDACTED | 2020-11-24
2020-11-24 | Operations Procedures | REDACTED | 2020-11-24
2021-03-29 | Terrora Phase 2 Startup Support | REDACTED | 2021-04-12
2021-09-09 | Terrora Unit 1 & 2– New Lower Generator Guide Bearing Oil Basin Cover Proposal for Turbine Contractor | REDACTED | 2021-09-09
2021-09-09 | Terrora Unit 1– LGGB Housing and Bridge Fit Reconditioning for Turbine Contractor | REDACTED | 2021-10-08
| 34 Other Change Orders (<$100k) | 936 | Multiple
| Total | 936
Tugalo
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
2021-10-14 | Online Brush Removal, Vibration Sensors, Braking/Jack System, and Terminal Blocks | REDACTED | 2021-11-30
2022-03-24 | Additional Electrical Hours Required | REDACTED | 2022-03-24
2022-03-24 | Tugalo Unit 1 sole plate, draft tube, and wheel pit repairs | REDACTED | 2022-03-24
2022-03-17 | By-Pass for the Temperature Control Valves | REDACTED | 2022-09-29
2022-07-08 | Tugalo Trash Rack and Structural Steel temporary Storage | REDACTED | 2022-09-29
2022-11-21 | GSU PO Reconciliation | REDACTED | 2022-11-21
2023-01-25 | GSU Concrete Pad install | REDACTED | 2023-06-29
2023-03-15 | Sheave Wheel Bracket Modifications (28 Sheave Wheel Brackets) | REDACTED | 2023-06-29
2023-03-31 | Turbine Unit 2&3 Draft Tube Repairs | REDACTED | 2023-06-29
2023-05-26 | Turbine Contractor Unit 2 Expedited delivery | REDACTED | 2023-08-25
2024-06-24 | General Contractor scope additions for various Field Work Authorizations | REDACTED | 2024-06-25
2025-11-11 | Final agreement on changes of quantities for civil infrastructure project | REDACTED | 2025-01-22
2025-05-02 | Scroll Case Coating: Unit 3 | REDACTED | 2025-06-23
| 21 Other Change Orders (<$100k) | 679.537 | Multiple
| Total | 679.537
Bartlett's Ferry 1-4
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
2021-08-31 | Additional Options and Engineering Studies | REDACTED | 2021-09-07
2022-02-05 | CPI increase in raw steel Price vs the Post-adjustment price for Headcover | REDACTED | 2022-04-05
2022-02-05 | CPI increase in raw steel Price vs the Post-adjustment price for Runner | REDACTED | 2022-04-05
2022-03-08 | Bartletts U1-4 Powerhouse Crane Cost Change | REDACTED | 2022-04-21
2022-07-06 | Lifting and Handling Devices for Unit dis-assembly and re-assembly | REDACTED | 2022-08-30
2022-04-15 | Trash Gate Actuator Variance Post-Control | REDACTED | 2022-08-30
2022-08-18 | Additional Hours Needed to complete Mechanical Design | REDACTED | 2022-08-30
2022-05-16 | I&C Variance for years 2023 thru 2026 | REDACTED | 2022-10-06
2022-09-02 | Generator Bearings | REDACTED | 2022-11-22
2022-11-17 | U1 and U2 Baffling in Thrust Tub | REDACTED | 2022-12-14
2022-08-30 | Log Powerhouse Crane – LCP (Lead Containing Paint) Removal and Storage | REDACTED | 2022-12-02
2023-02-08 | GSU PO Reconciliation - Pricing Index Increase | REDACTED | 2023-02-16
2022-06-03 | Bartlett's Ferry Units 1-4 Shear Pin Detection system | REDACTED | 2023-04-17
2023-01-11 | Bartletts Shear Pin Monitoring Panel Unit 3 | REDACTED | 2023-04-18
2023-03-03 | Replacement Stem Nuts for Head Gate Actuators | REDACTED | 2023-04-18
2023-04-27 | Switchyard Relocation - Install of New GSU's (U1 &U3) | REDACTED | 2023-04-27
2023-05-12 | Vertical Generator Shaft Bearing Journals Replacement | REDACTED | 2023-05-25
2022-07-06 | Headcover Sump and Piping Removal | REDACTED | 2023-05-25
2022-08-18 | Tail Race Stop Log | REDACTED | 2023-05-25
2023-03-08 | Spillway Gantry Cranes Upgrade from 575v to 480v | REDACTED | 2023-05-25
2023-05-24 | Turbine Thrust Runner Repair | REDACTED | 2023-06-14
2023-06-20 | Turbine Steel Price Adjustment | REDACTED | 2023-06-20
2023-06-23 | Draft Tube Installation and Wheel Pit Blasting | REDACTED | 2023-06-23
2023-06-13 | New turbine operating rings at Bartletts Units 1 & 2 | REDACTED | 2023-06-28
2023-06-21 | Fans and Louvers | REDACTED | 2023-07-27
2023-08-25 | Stator Rewind, Restack, Rotor Pole Refurbishment U1 Frame Modifications | REDACTED | 2023-08-25
2023-08-03 | Generator Contractor Finger Flanges Change Order for the Stator Rewind, Restack, Rotor Pole Refurbishment | REDACTED | 2023-08-22
2022-04-14 | Head Gates Drive System Change from Manual to Automatic Actuator | REDACTED | 2023-09-29
2023-11-15 | Replacement of upper and lower generator guide bearings | REDACTED | 2023-11-16
2023-07-14 | Rotor cleaning and Abatement Removal | REDACTED | 2023-11-16
2023-11-15 | Replacement of Operating Ring | REDACTED | 2023-11-16
2023-11-16 | Stator Reposition | REDACTED | 2023-11-16
2023-12-18 | Civil Infrastructure Contractor - Trash Rack Beam, Trash Rack Guides and Intake cover for priming valve | REDACTED | 2024-01-29
2023-12-18 | Turbine Contractor Remob & Stay Vanes | REDACTED | 2024-01-29
2023-12-18 | Upper Guide & Lower Guide Modification and Thrust Bearing | REDACTED | 2024-01-29
2024-04-17 | Replacement Thrust Shoes | REDACTED | 2024-04-24
2024-05-22 | Thrust Runner | REDACTED | 2024-05-24
2024-05-08 | Civil Contractor - Draft Tube Stop Logs in Tail Race Units 1-4, Additional Trash Rack Channel Guide Modifications for Units 2-4, and Headgate Stem Guides | REDACTED | 2024-05-24
2024-04-17 | Generator Delay due to Discovery Effort from June 23 to Nov 23. | REDACTED | 2024-05-24
2024-06-20 | Covers of the Headgate Actuators | REDACTED | 2024-07-30
2024-10-11 | Line Boring, Rotor Fans, & Isolator Bushings | REDACTED | 2024-12-10
2024-09-12 | 2nd Fabrication Set (Gearbox Assembly) Rework | REDACTED | 2024-12-11
2025-01-23 | Additional Replacement Parts | REDACTED | 2025-02-27
2025-03-06 | Unit 2 Head Gate Gear Box Rework | REDACTED | 2025-04-02
2025-03-25 | Work - Stop Logs, Stem and Beam Repair, Actuator | REDACTED | 2025-04-02
2025-03-26 | New Clamping Flange Finger for U4 | REDACTED | 2025-04-02
2025-04-02 | Unit 2 Actuator Rework | REDACTED | 2025-04-02
2025-04-02 | U2 Actuator Standy-by and Re-Install | REDACTED | 2025-04-02
2025-04-15 | Building Lean To | REDACTED | 2025-05-08
05/27/2025 | Generator Work Platform Unit 3 | REDACTED | 2025-06-27
05/27/2025 | Unit 3 Wheel Pit and Stay Vane Blast and Repaint and Rotor Blast and Repaint | REDACTED | 2025-06-27
05/27/2025 | Water Quality Monitoring | REDACTED | 2025-06-27
2025-09-03 | U4 Fan Blade Refurbishment U3 Endplate Replacement | REDACTED | 2025-09-19
2025-09-03 | U1 Additional Commissioning Support | REDACTED | 2025-09-19
2025-09-03 | U3 Additional Work | REDACTED | 2025-09-19
2025-08-19 | U3 Generator Work | REDACTED | 2025-10-15
2025-08-19 | U3 Thrust Pot Rehab | REDACTED | 2025-10-15
2025-08-19 | HCMS U3 Support | REDACTED | 2025-10-15
2025-11-11 | Headworks & U3 Rotor Removal | REDACTED | 2025-11-17
2025-11-12 | Discovery Work***--U1 and U2 | REDACTED | 2025-11-17
2025-11-12 | Discovery Work**BF--U3 | REDACTED | 2025-11-17
2025-11-12 | Unit 4 Bar Align. Stator Key | REDACTED | 2025-11-17
2025-11-13 | U4 Role Deformity Repair & U4 Stator House Refurb. | REDACTED | 2025-11-17
2025-11-13 | Removing & Installing Stop Logs & Fab of U2 | REDACTED | 2025-11-17
2025-11-13 | Unit 3 Thrust Runner & Block Replacement | REDACTED | 2025-11-17
2025-11-13 | Core #2 Provide and Install Temp Shoring U3 | REDACTED | 2025-11-17
2025-11-13 | Unit 3 Shaft Removal | REDACTED | 2025-11-17
| 48 Other Change Orders (<$100k) | 1734.9378 | Multiple
| Total | 1734.9378
Nacoochee
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
2024-05-17 | Contractor Unit 1 Delays and Rework | REDACTED | 2024-05-17
2024-08-06 | Delays and rework during Nacoochee Unit 1 head gate replacement | REDACTED | 2024-08-12
2024-08-20 | Unit 1-2 Exciters | REDACTED | 2024-12-12
2025-01-12 | Unit 1 replace generator sole plates | REDACTED | 2025-01-21
2025-03-17 | Auxillary Loads | REDACTED | 2025-04-14
2025-03-25 | Unit 1 Draft Tube Repairs | REDACTED | 2025-04-14
2025-10-10 | Turbine & Generator spare parts | REDACTED | 2025-10-28
2025-10-10 | Additional costs to comply with PWA | REDACTED | 2025-10-28
2025-10-30 | Lighting - Receptacles - Full Package | REDACTED | 2025-12-19
2025-10-30 | U1 & BOP Added-Deleted Circuits | REDACTED | 2025-12-19
| 29 Other Change Orders (<$100K) | 759 | Multiple
| Total | 759
Oliver
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
2024-05-15 | Contractor Generator Unit 3 New Scope Additions | REDACTED | 2024-05-24
2024-04-17 | Oliver Unit 1 New Inner-Outer-Intermediate Headcovers | REDACTED | 2024-05-09
2023-12-14 | Oliver Simulator | REDACTED | 2024-05-24
08/09/2024 | Discovery Unit 1 bottom ring replacement | REDACTED | 12/10/2024
2024-11-21 | New Headcovers and Bottom Rings | REDACTED | 2025-01-13
2024-11-21 | New Turbine Shafts for U1-3 | REDACTED | 2025-01-13
2024-10-11 | Units 1-3 Greaseless Bushings and Wear pads with optional spares | REDACTED | 2024-12-11
2024-06-17 | Auxiliary Loads Rewiring | REDACTED | 2024-12-06
2025-02-06 | Discovery Work--Ditch Fill, Grounding Grid, Temp office trailers, grounding for fence | REDACTED | 2025-02-07
2025-02-06 | Discover Work-- Static Excitation | REDACTED | 03/17/2025
2025-03-26 | Discovery-- U1-2 Nut Guards | REDACTED | 2025-04-02
2024-05-24 | GSU Transformers x (3) | REDACTED | 2025-06-09
2025-11-11 | Unit 1-3 Discharge Rings | REDACTED | 2025-12-16
2025-11-11 | U1 Discharge Ring Ribs, U3 RTD, U-4 Servo Frame | REDACTED | 2025-12-16
2025-11-11 | Headworks Cable Tray | REDACTED | 2025-12-16
| 12 Other Change Orders (<$100k) | 502 | Multiple
| Total | 502
Sinclair
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
0 Other Change Orders (<$100k)
| Total | 0
Burton
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
2025-04-02 | Stop Logs - Design, Fabricate, and Ship to Burton | REDACTED | 2025-05-09
2025-04-02 | Sluice Gate Sealing | REDACTED | 2025-05-09
2025-10-24 | Unit 1/2 Additional Site Machining | REDACTED | 2025-12-18
2025-10-28 | Unit 1/2 Spare Parts | REDACTED | 2025-12-09
2025-10-29 | Penstock infill and sluice gate sealing | REDACTED | 2025-10-30
| 5 Other Change Orders (<$100k) | 194.336 | Multiple
| Total | 194.336
Bartletts Ferry 5-6
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
0 Other Change Orders (<$100k)
| Total | 0
North Highlands
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
0 Other Change Orders (<$100k)
| Total | 0
Tallulah Falls
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
0 Other Change Orders (<$100k)
| Total | 0
Yonah
Date CO Submitted | Description of Change Order Request | Dollar Amount Requested (1000$) | Date Approved
0 Other Change Orders (<$100k)
| Total | 0

## Procurement
PUBLIC DISCLOSURE
Procurement Status of Significant Components -- All Received
Project Monitoring Report thru December 31, 2025
See separate GPC Hydro Modernization Procurement Summary attachment.

## Tugalo (Complete)
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Tugalo
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Unit 3 |  |  | Unit 4 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP | Turbine | Generator | BOP
2020 | 2020-06-30 | 623.5072 | 0 | 5.3789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628.8861 | 623.5072 | 0.8627%
2020 | 2020-12-31 | 1870.5049 | 54.2629 | 91.121 | 1165.174 | 0 | 0 | 1164.9735 | 0 | 0 | 1161.4857 | 0 | 0 | 5507.5219 | 5442.7172 | 1.191%
2021 | 2020-06-30 | 1108.9637 | 164.872 | 551.4867 | 132.3773 | 0 | 3.4759 | 110.7911 | 0 | 3.4759 | 109.4395 | 0 | 3.4759 | 2188.3582 | 2187.4721 | 0.04051%
2021 | 2020-12-31 | 4496.8564 | 1727.4895 | 7002.4199 | 1231.3596 | 0 | 117.9769 | 1270.2663 | 0 | 731.1155 | 1330.2843 | 0 | 121.9202 | 18029.6887 | 17472.8391 | 3.187%
2022 | 2020-06-30 | 3263.2449 | 159.5937 | 3051.6997 | 121.4756 | 0 | 27.2134 | 115.4002 | 0 | -10.6336 | 118.357 | 0 | -40.7058 | 6805.6451 | 13466.6798 | -49.46%
2022 | 2020-12-31 | 3125.5259 | 2788.734 | 6589.4657 | 1308.603 | 1701.7617 | 96.1494 | 1039.6256 | 156.0131 | 2124.2975 | 156.1454 | 8.8873 | 15.6984 | 19110.9071 | 19761.8337 | -3.294%
2023 | 2020-06-30 | 3354.112 | 720.5781 | 3445.9873 | 873.6754 | 133.9481 | 55.8233 | 445.842 | 1627.7778 | 352.0699 | 222.5328 | 61.0332 | 49.066 | 11342.4459 | 11032.993 | 2.805%
2023 | 2020-12-31 | 3532.3592 | 897.917 | 6957.2576 | 1176.6895 | 3796.0778 | 1234.4633 | 929.9204 | 182.2276 | 755.7797 | 1555.3062 | 1184.829 | 307.4222 | 22510.2495 | 7858.4967 | 186.4% | B
2024 | 2020-06-30 | -2673.974 | 53.5618 | 3430.4996 | 4165.9857 | 455.8315 | 163.8969 | 1152.5481 | 1377.0222 | 1647.4741 | 851.3767 | 409.3267 | 616.1687 | 11649.7178 | 11712.5592 | -0.5365% | D
2024 | 2020-12-31 | -3701.7428 | 630.1543 | 5605.7412 | -2413.1601 | 1744.586 | 1518.7206 | 2556.4276 | 2935.5474 | 1932.4373 | 1201.4734 | 1792.7866 | 604.8012 | 14407.7729 | 7964.6128 | 80.9% | C
2025 | 2020-06-30 | 2.2803 | 0 | 2089.2272 | 0.25716 | 1.0228 | 27.7852 | 368.1463 | 74.9933 | 102.5033 | 3209.5876 | 2591.0122 | 683.8185 | 9150.6339 | 10098.0501 | -9.382%
2025 | 2020-12-31 | 0 | 0 | 22.8642 | 0 | 0 | 0 | 29.7955 | 0 | 0 | 500.9866 | 577.4326 | 22.0578 | 1153.1367 | 7670.0805 | -84.97%
2026 | 2020-06-30 | [12 empty] | 0 | 3.4752
2026 | 2020-12-31
2027 | 2020-06-30
2027 | 2020-12-31
TOTAL |  | 15001.6377 | 7197.1633 | 38843.1491 | 7762.4371 | 7833.2278 | 3245.505 | 9183.7368 | 6353.5814 | 7638.5195 | 10416.9751 | 6625.3075 | 2383.7232 | 122484.9637 | 115295.3168 | 6.174% | A
[13 empty] | Current Estimate at Completion |  | 122414.221 | Increase from $121M from last submittal
Sums and percentages may not add due to rounding.
Notes on Variances
A | Increase from IRP submittal to current forecast driven by turbine pricing, generator replacement, GSU pricing, and trash racks scope.
B | Project proceeded ahead of the previous schedule, with the actual online dates advancing for Unit 1 to October 2023 from projected December 2023 and for Unit 2 to December 2023 from projected August 2024. Therefore, more costs occurred during the period ending December 31, 2023, than the project forecast due to project proceeding ahead of schedule, which translates to a decrease in the Current Estimate at Completion of around $3 million from the June 2023 report to the December 2023 report.
C | Project continues to proceed ahead of schedule used to create Final Project Forecast, leading to earlier actual spend. Also, increase to Current Estimate at Completion in period ending December 31, 2024 due to change of General Contractor to finish Unit 3 & 4 BOP work.
D | Corrected Unit 1 BOP total for accounting system change of previous posted actuals.
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast developed Q3 2021.
Measured against 2019 IRP Budget - $109,736
REDACTED

## Terrora (Complete)
PUBLIC DISCLOSURE
Hydro Modernization Cost Report
Project Monitoring Report thru December 31, 2025
Plant Terrora
Actuals ($1,000s)
Year | Period Ending | Unit 1 |  |  | Unit 2 |  |  | Actuals | Project Forecast* | % Variance (against Project Forecast) | Notes
|  | Turbine | Generator | BOP | Turbine | Generator | BOP
2019 | 2019-06-30 | 0 | 0 | 0 | 594.2607 | 30.8366 | 416.7513 | 1041.8486 | 260.4158 | 300.1%
2019 | 2019-12-31 | 0 | 0 | 0 | 1677.5296 | 302.9649 | 1449.1789 | 3429.6734 | 1848.093 | 85.58%
2020 | 2020-06-30 | 1777.5108 | 0 | 12.4613 | 3948.8911 | 1582.1272 | 2534.3578 | 9855.3482 | 10687.3078 | -7.785%
2020 | 2020-12-31 | 972.1517 | 1551.0082 | 802.1557 | 4512.0184 | 2647.9997 | 5012.4663 | 15497.8001 | 18624.3918 | -16.79%
2021 | 2020-06-30 | 3221.7034 | 1276.5857 | 2666.3232 | 498.3993 | 2.5907 | 394.562 | 8060.1643 | 8180.7575 | -1.474%
2021 | 2020-12-31 | 4970.2956 | 920.5226 | 2069.6412 | 129.0723 | 0 | 359.8975 | 8449.4292 | 7693.7221 | 9.822%
2022 | 2020-06-30 | 564.1607 | 27.7352 | 91.8525 | 191.7345 | 0 | -12.1495 | 863.3334 | 750 | 15.11%
2022 | 2020-12-31 | -151.2073 | -19.1042 | 3.3008 | 0.59021 | 0 | 0 | -166.4205 | 0 | N/A | B
TOTAL |  | 11354.615 | 3756.7476 | 5645.7347 | 11552.496 | 4566.5191 | 10155.0643 | 47031.1767 | 48044.688 | -2.11% | A
Sums and percentages may not add due to rounding.
Notes on Variances
A | Variance based on total actuals in this report versus total project forecast.
B | Accounting system adjustments during period ending December 31, 2022.
C
Notes:
*Added once Project Forecast estimates are updated and approved. Final Project Forecast developed Q1 2021.
Measured against 2019 IRP Budget - $58,160
Unit 1 returned to normal operation on November 19, 2021. Unit 2 returned to normal operation on December 30, 2020.
This report reflects actuals for the two semiannual periods following the return to normal operation of the last unit in the project (i.e., Unit 1) to reflect applicable invoiced costs but does not include any ordinary accounting adjustments made to close out the project, as applicable, after December 31, 2022.