BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S 2022 RATE CASE: STORM DAMAGE RECOVERY APPLICATION | DOCKET NO. 44280 |
| --- | --- |

|  | DIRECT TESTIMONY |  |
| --- | --- | --- |
|  | AND EXHIBITS |  |
|  | OF |  |
|  | TOM NEWSOME, PE, CFA LANE KOLLEN, CPA, CMA, CGMA RANDY A. FUTRAL |  |

|  | ON BEHALF OF THE |  |
| --- | --- | --- |

|  | GEORGIA PUBLIC SERVICE COMMISSION |  |
| --- | --- | --- |
|  | PUBLIC INTEREST ADVOCACY STAFF |  |

PUBLIC DISCLOSURE VERSION

|  | April 17, 2026 |  |
| --- | --- | --- |

TABLE OF CONTENTS

I.   	QUALIFICATIONS AND SUMMARY	1

II. 	The Company’s Planning for and Management of Its RESPONSE TO THESE STORMS FAILED TO EMPLOY INDUSTRY BEST PRACTICES	18

III. 	The COMPANY OVERSTATED THE STORM COST REGULATORY ASSET BECAUSE IT FAILED TO EXCLUDE COSTS ALREADY RECOVERED THROUGH BASE REVENUES	29

IV. The Company Overstated The Storm cost Regulatory Asset BECAUSE IT FAILED TO REMOVE ALL CAPITAL COSTS THAT INSTEAD SHOULD HAVE BEEN RECORDED TO PLANT IN SERVICE	36

A.	Overview Of Capital Cost And The Errors That Overstated The Storm Cost Regulatory Asset And Understated Plant In Service	36

B.	Calculation Error That Understated Labor Cost Included In Capital Cost 
Credit	43

C.	Conceptual And Calculation Error That Understated Labor Cost Included In Capital Cost Credit	46

D.	Conceptual And Calculation Error That Understated External Contractor Cost Included In Capital Cost Credit	47

V. 	The Company’s Documentation, Review, and Approval Process WAS GENERALLY adequate; HOWEVER, IMPROVEMENTS ARE NECESSARY	49

VI. 	The Commission Should deny The Company’s PROPOSAL to Increase The Storm Cost Regulatory Asset INCLUDED IN RATE BASE FOR ESTIMATED STORM COSTS AFTER December 31, 2025	61

VII.	The Commission Should deny The Company’s Request To Recover A Return On The Storm COST Regulatory Asset At Its grossed-up Weighted average Cost of Capital	65

VIII.	The Storm Cost Regulatory Asset Recovery PERIOD Should Be EXTENDED AND THE REVENUE RECOVERY SHOULD BE LEVELIZED	67

IX. 	The Company’s Definition of A Storm Event Reflects An Inordinately Low Threshold of $50,000	72

X. 	The Commission Should Deny The Company’s Request to Increase The Storm Expense Accrual For Future Storms By $69.835 Million In This Proceeding And Address ChangEs In FUTURE COMPREHENSIVE BASE RATE PROCEEDINGS	76

# QUALIFICATIONS AND SUMMARY

Q.	Please state your names, positions, employers, and business addresses.

A.	My name is Tom J. Newsome. I am the Director of Utility Finance with the Georgia Public Service Commission (“Commission”). My business address is 244 Washington St., Atlanta, Georgia, 30334.

My name is Lane Kollen. I am a Vice President and Principal of J. Kennedy and Associates, Inc.  My business address is 570 Colonial Park Drive, Suite 305, Roswell, Georgia, 30075.

My name is Randy A. Futral. I am a Director, Consulting with J. Kennedy and Associates, Inc. My business address is 570 Colonial Park Drive, Suite 305, Roswell, Georgia, 30075.

Q. 	Mr. Newsome, please describe your primary responsibilities with the Commission Staff.

A. 	I am responsible for economic, financial, and cost of equity analyses and evaluations at the Commission.

Q.	Mr. Kollen and Mr. Futral, please describe your responsibilities with Kennedy and Associates.

A.	Mr. Kollen and Mr. Futral provide consulting services to state and local government agencies and large customers taking regulated electric, natural gas, water, and sewer utility service. These services include accounting, ratemaking, finance, taxes, planning, operations, storm costs, and other issues.

Q.	Describe your education and experience.

A.	We each provide a description of our education and experience, a list of our professional certifications and affiliations, and a list of our testimony appearances on Exhibit STF-NKF-1 (Mr. Newsome), Exhibit STF-NKF-2 (Mr. Kollen), and Exhibit STF-NKF-3 (Mr. Futral).

Q.	Provide an overview of Georgia Power Company’s request to increase base revenues in this proceeding.

A.	Georgia Power Company (“the Company”) seeks to increase base revenues on a net basis by $269.622 million calculated using a forecast test year ending May 31, 2027. The Company’s request consists of three separate requests, only the first two of which are related to storm costs and result in increases in base revenues. The Company’s first request is to increase base revenues by $290.030 million to recover the storm cost regulatory asset at December 31, 2025 for past storms over a four-year amortization and recovery period. The first request also includes a return on the storm cost regulatory asset less accumulated amortization and less accumulated deferred income taxes (ADIT) estimated at May 31, 2026 at the Company’s grossed-up weighted average cost of capital (WACC).

The Company’s second request is to increase base revenues by $69.835 million to reflect an increase in the storm expense accrual for future storms. This second request for an increase to preemptively recover unknown costs that have not yet been incurred for future storms is separate and independent of the Company’s first request for recovery of known costs that were actually incurred for past storms.

The Company’s third request is to reduce base revenues by $90.203 million to amortize and refund 25% of a Production Tax Credit (PTC) regulatory liability and refund the return on the PTC regulatory liability less accumulated amortization less the related ADIT at the Company’s grossed-up WACC.

The following table summarizes each of these three requests and the net base revenue increase requested in this proceeding.

Q.	Describe the purpose of your testimony.

A.	The purpose of our testimony is to address and make recommendations regarding the first two of the Company’s requests shown on the preceding table. We do not further address the Company’s third request in our testimony because it is not directly related to the recovery of the storm cost regulatory asset, but we do not oppose it.

With respect to the Company’s first request, we address and make recommendations in each of the following areas: 1) the Company’s planning for and management of its response to these storms, including the resources mobilized and the technology tools used for these purposes; 2) the Company’s accounting for the storm costs, including differentiating the costs incurred between incremental costs (recoverable as storm costs) and non-incremental costs (not recoverable as storm costs because they already are recovered through base revenues); 3) the manner and extent to which the costs were or should have been capitalized to plant and recovered as plant costs starting in the next base rate proceeding, instead of being deferred to the storm cost regulatory asset and included for recovery as storm costs in this proceeding; 4) the extent to which the invoiced costs for third party services were properly reviewed and approved prior to payment, including authorizations for the services, service contracts, contract rates, and all other required support for the amounts invoiced; 5) whether the storm cost regulatory asset included in rate base should be limited to the actual storm costs incurred through December 31, 2025 in this proceeding in accordance with the Commission’s Order describing the scope of this proceeding; 6) whether a return at the Company’s WACC or at some other cost of capital should be added to the allowed storm cost regulatory asset; and 7) whether the Company’s calculation of the ratemaking recovery is reasonable or should be modified to ensure there is no overrecovery.

With respect to the Company’s second request, we address the Company’s request to recover an increase in the storm damage expense accrual for future storms in this proceeding in lieu of requesting a change in the expense in a future comprehensive rate proceeding where all base revenues, expenses, and rate base costs are considered at the same time in the determination of the base revenue requirement.

Q.	Provide a summary of your conclusions and recommendations.

A.	We recommend a reduction of $269.932 million in the Company’s requested base revenue increase of $269.662 million, or a net reduction in present base revenues of $0.270 million. The net reduction is based on an increase in base rates of $89.932 million for the recovery of and on the storm cost regulatory asset, no increase above present recoveries in base rates for unknown future storm costs storm, and the Company’s request to reduce base revenues by $90.203 million for the amortization and refund of the PTC regulatory liability. We summarize the effects of our recommendations on the Company’s claimed base revenue requirement and requested base rate increase on the following table.

The following table shows the effects of the Staff adjustments on the storm cost regulatory asset, starting with the Company’s request and ending with the Staff recommendation.

We provide the following summary of our conclusions and recommendations in the same sequence that we address each area in our testimony.

The Company’s Planning For And Management Of Its Response To These Storms Failed To Employ Industry Best Practices

The Company’s planning and management of its response to these storms failed to employ industry best practices and planning and resource management technology tools to determine the optimal quantities and mix of resources acquired, manage the resources acquired to restore service in a reasonable timeframe against reasonable performance metrics, and minimize the costs of those resources. The Company’s failures in these areas likely led to excessive costs due to unnecessary and inefficient resourcing, although Staff was not able to quantify the excessive costs. The Staff did not perform a comprehensive prudence or operations review, but reviewed the Company’s emergency response plan, planning and resource management systems and technology that were in place when these storms occurred, the Company’s limited critique of its performance in response to Hurricane Helene, changes that have been implemented and changes that are in progress in these areas since Hurricane Helene, among other information.

We recommend the Commission direct the Company to study industry practices to identify the best of those industry practices, integrate those best practices into its planning, resource acquisition, and resource management, and adopt and use modern information technology and modeling tools, optimize the quantities and mix of resources, and manage those resources to reasonably balance the resources and time required to restore service with the costs incurred to restore service. We recommend the Commission direct the Company to complete this initial study, develop an action plant to implement these industry best practices, begin implementing those best practices by the end of 2026, and adopt and begin implementing modern information technology and modeling tools by the end of 2026. We recommend the Commission direct the Company to file quarterly detailed status reports with the Commission describing its progress on these activities starting in September 2026.

We also recommend the Commission direct the Company to critique its performance after each major storm to identify areas for improvement and then apply the lessons learned to continuously improve its restoration and cost performance in its responses to future storms. We recommend the Commission direct the Company to file these critiques, action plans, and detailed status reports with the Commission starting three months after each storm and continuing each quarter thereafter for at least one year after each storm.

In addition, we recommend the Commission consider these facts in conjunction with our other recommendations, including the amounts that Staff had to estimate because of the Company’s inability and/or unwillingness to quantify and exclude non-incremental costs already recovered through base revenues and the amounts that Staff had to estimate because of the Company’s flawed accounting and failure to correctly calculate the costs capitalized and recorded to plant in service instead of to the storm cost regulatory asset.

The Company Overstated The Storm Cost Regulatory Asset Because It Failed To Exclude Costs Already Recovered Through Base Revenues

The Company’s accounting for storm costs is based on incorrect assumptions that do not accurately differentiate between incremental costs and non-incremental costs. The accounting for storm costs is important and relevant because it ultimately affects how these costs are recovered from ratepayers. The Company’s accounting incorrectly assumes that all overtime labor costs and all external contractor costs are incremental, despite the fact that some of these internal and external resources were redeployed from their activities under “business as normal” (also referred to as “blue sky”) conditions and the fact those costs already were recovered in base revenues collected from ratepayers. The costs of the redeployed resources under “business as normal” conditions were and are not incremental, were and are already being recovered in base revenues, and should not have been and should not be deferred to the storm cost regulatory asset for recovery a second time. In addition, due to limitations in its accounting and reporting systems, the Company claims that it cannot readily identify and quantify the cost of the internal and external resources that were redeployed from “business as normal” activities to storm response activities necessary to avoid recovering these costs twice through the ratemaking process.

We recommend the Commission disallow the overtime labor and all outside services contractor costs for resources redeployed from “business as normal” activities that were not incremental and already were recovered through base revenues.

We also recommend the Commission direct the Company to improve its accounting and reporting systems so that it can accurately differentiate and quantify the incremental and non-incremental costs and exclude the costs for redeployed resources that are already recovered through base revenues, including overtime labor and external contractor costs, from the costs deferred for future storms.

The Company Overstated The Storm Cost Regulatory Asset Because It Failed To Remove All Capital Costs That Instead Should Have Been Recorded to Plant In Service

The Company overstated the storm cost regulatory asset because it did not remove all capital costs and record those costs to plant in service. Initially, the Company records all storm costs to the storm cost regulatory asset, and then credits (reduces) the regulatory asset to remove costs that should be capitalized to plant in service. The Company uses a formulaic standard cost methodology to quantify the costs capitalized to plant in service. The Company’s methodology is flawed and failed to correctly remove all relevant capital costs, including external line crew, vegetation management, and staging contractor costs. This fundamental flaw significantly overstated the amounts remaining in the storm cost regulatory asset and significantly understated plant in service. In addition, the Company made other errors in the calculation of the capital cost credit that further overstated the storm cost regulatory asset and understated plant in service.

We recommend the Commission include additional capital costs in the capital cost credit, reduce the storm cost regulatory asset, and increase plant in service. The increase in the capital cost credit does not result in a disallowance of storm costs; rather, it correctly excludes the costs from the storm cost regulatory asset and instead includes the costs in plant in service. The costs correctly included in plant in service will be recovered consistent with the manner in which it recovers all other capital costs included in plant in service. The Company may fully recover these costs regardless of whether they are recorded in a storm cost regulatory asset or plant in service, provided they were reasonable and prudent.

We also recommend the Commission direct the Company to modify the formulaic standard cost methodology it presently uses to remove all capital costs from the storm cost regulatory asset and record the additional capital costs in plant in service.

The Company’s Documentation, Review, and Approval Process Was Generally Adequate; However, Improvements Are Necessary

Staff performed an audit using stratified statistical sampling of invoice costs and related contracts for each of the storms. The audit was focused primarily on invoices submitted by external line and vegetation management contractors, external mutual assistance company contractors, staging site contractors, and other contractors, as these contractor costs made up the vast majority of the storm costs incurred. The sample size of invoices for Hurricane Helene was larger than that for the other storms due to magnitude of the costs incurred to respond to that storm.

With certain exceptions that we subsequently describe, the invoice costs associated with external contractors were incurred to repair damages and restore service for storm events and properly deferred to the storm cost regulatory asset, before reductions for capital cost credits, the line item cost rates matched contract pricing when applicable, the total invoice costs matched the amounts recorded to the general ledger, and there were no duplications of invoice costs included in the storm cost regulatory asset and various storm cost summaries. We also concluded that the sample invoice support requested by Staff in discovery was complete and well organized for review. We recommend no disallowance of costs related to our audit of the external contractor invoices.

In addition, we reviewed the contract provisions and rates for each vendor. We found there were numerous unorganized files for multiple vendors provided in a single folder. In many cases, the Company failed to provide copies of the vendor contracts. We recommend the Company improve the access and organization of these vendor files to ensure all costs are properly verified on a timely basis prior to approving invoices for payment.

The Commission Should Deny The Company’s Proposal to Increase The Storm Cost Regulatory Asset Included In Rate Base For Estimated Storm Costs After December 31, 2025

The Company improperly increased the storm cost regulatory asset to reflect estimated increases in storm costs after December 31, 2025. The Company’s request violates the Stipulation to Extend the Alternate Rate Plan approved by the Commission in Docket 44280 approved by the Commission in its Order dated July 31, 2025 (Stipulation) wherein the recovery of the storm cost regulatory asset in this proceeding was expressly limited to the costs incurred through December 31, 2025. The Company should only be allowed to recover actual costs incurred rather than estimates of costs that have not yet been incurred.

In addition, the Company’s methodology used to calculate the return on the storm cost regulatory asset in this proceeding improperly commingles the regulatory asset at December 31, 2025, the amortization and recovery of the regulatory asset at December 31, 2025, the estimated storm costs after December 31, 2025, the requested storm expense accruals for future storms, and the calculation of the requested return on rate base.

We recommend the Commission deny the Company’s request to recover a return on estimated storm costs incurred after December 31, 2025. We recommend the Commission limit the return on the storm cost regulatory asset to the costs incurred through December 31, 2025, consistent with the Stipulation approved by the Commission last year.

The Commission Should Deny The Company’s Request To Recover A Return On The Storm Cost Regulatory Asset At Its Grossed-Up Weighted Average Cost of Capital

The Company requests a return on the storm cost regulatory asset at its grossed-up WACC. One alternative to the Company’s request is to deny any return on the storm cost regulatory asset. That would maintain the status quo. The Company presently earns neither a current return nor a deferred return on the storm cost regulatory asset. Another alternative is to authorize a debt only rate of return on the storm cost regulatory asset.

We recommend the Commission authorize a debt only rate of return on the storm cost regulatory asset. This is an approximate midpoint between the status quo of no return on the storm cost regulatory asset and the Company’s request for a grossed-up rate of return. We note the Company has the option of actually financing the asset with debt only, such as term loans, which is lower cost and could be structured to match the limited amortization and recovery period for the storm cost regulatory asset. In addition, the debt only rate of return reflects the lower financial and regulatory risk from recovery of a defined financial asset and amount compared to physical assets and operating expenses. Further, the debt only rate of return redresses, albeit indirectly, the Company’s overrecovery of the storm cost regulatory asset due to growth in sales and other billing determinants between base rate proceedings.

We also recommend that the return on be applied only to the storm cost regulatory asset at December 31, 2025 less accumulated amortization and related ADIT as the regulatory asset is amortized and recovered from customers.

The Storm Cost Regulatory Asset Recovery Period Should Be Extended And The Revenue Recovery Should Be Levelized

The Company’s calculation of the proposed base revenue increase and the proposed recovery will result in excessive recovery of the storm costs. The Company’s requested recovery is based on the revenue requirement calculated for a forecast test period from June 1, 2026 through May 31, 2027, representing only the first 12 months of the Company’s proposed amortization and recovery period of 48 months. The Company’s request fails to reflect the decline in the storm cost revenue requirement as the regulatory asset is amortized and the return on the regulatory asset continues to decline each month after May 31, 2027. In addition, the Company’s proposed amortization and recovery period is unnecessarily and unduly short. Further, the Company’s proposed amortization and recovery period is not aligned with the Commission’s recent history of setting the Company’s base revenues every three years pursuant to a sequence of alternative rate plans.

We recommend the recovery of the storm cost regulatory asset be calculated on a levelized (annuitized) basis, similar to the calculation of payments for a home mortgage loan, using an amortization and recovery period of 103 months timed to coincide with the Company’s historic pattern of base rate proceedings every three years. The recovery will remain the same for each of the 103 months until the storm cost regulatory asset is fully amortized and recovered. The recovery should remain a separate component within the base revenue requirement in future base rate proceedings to facilitate review by Staff and other parties.

The Company’s Definition of A Storm Event Reflects An Inordinately Low Threshold of $50,000

The Company’s definition of a storm event reflects a dollar threshold of $50,000, which results in the deferral of costs to respond to minor and unnamed storms that are both frequent and recurring. These costs are more appropriately considered as routine operating expenses to streamline the response to and accounting for these events, in contrast to less frequent and more severe storms with greater physical, customer, and cost impacts. The $50,000 threshold is extremely low.  A more appropriate dollar threshold would be $2 million.

We recommend the Commission modify the definition of a storm event to reflect a minimum dollar threshold of $2 million per storm event before the Company is allowed to defer the costs over that threshold to the storm reserve/storm cost regulatory asset.

The Commission Should Deny the Company’s Request to Increase The Storm Expense Accrual For Future Storms By $69.835 Million In This Proceeding And Address Changes In The Storm Expense Accrual for Future Storms In Future Comprehensive Base Rate Proceedings

The Company seeks to expand the limited scope of this proceeding approved by the Commission last year to increase the storm expense accrual for future storm costs and the base revenue recovery from the $31.419 million presently recovered in base revenues to $101.254 million effective June 1, 2026, an increase of $69.835 million annually, or an increase in base revenue recoveries from customers of $180.407 million from June 1, 2026 through December 31, 2028 when the present three year alternative rate plan expires.

We recommend the Commission deny the request to increase the storm expense accrual for future storm costs and the base revenue recovery in this proceeding. This request is outside the limited scope of this proceeding and is properly addressed in the context of a future comprehensive base rate proceeding wherein all revenues and all costs are considered on a comprehensive basis, rather than seeking to increase the recovery of a single expense on a selective basis.

II. The Company’s Planning for and Management of Its Response to These Storms failed to employ industry best practices

Q.	Describe briefly the Company’s planning for and response to severe weather events to repair damage to its system and restore service.

A.	The Company’s planning for and response to severe weather events is described in its Storm Response Plan, its responses to Staff discovery, and in the Direct Testimony of Company witnesses Cleve Fann, Josh Stallings, and Matthew Berrigan.

The process starts with the identification of a potential storm event based on meteorological data. The process continues with the identification of the potential location(s) and timing of the geographic areas that will be affected, assessment of potential impacts, continuous monitoring, acquisition and positioning of resources (line crews, vegetation management crews, damage assessors, flaggers, stating, etc.) in the geographic areas that likely will be impacted, post-storm assessment of actual damages, clearance of vegetation and other debris, repair of the system and restoration of service to customers, demobilization of external contractor resources, and return of internal resources and external resources temporarily redeployed to storm activities back to their “business as normal” activities.

Q.	Describe how the Company determines the resources necessary to respond to a storm event.

A.	The Company provided the following description in response to Staff discovery.

For pre-storm planning, the Company uses meteorological data from both contract meteorologists and the National Weather Service (NWS). The information is then compared to previous storms and historical data is used from the Distribution Resource Management tracking application to determine resource needs. For post-storm response, the Company uses intelligence from field and regional resources including events, customer outages, and the causes of outages to determine the necessary resources.

Q.	Describe the information and other technology tools used by the Company in this process.

A.	In response to Staff discovery, the Company stated:

The Company currently does not have storm modeling tools. However, as described and referred to in later data request responses, the Company is in the process of developing and evaluating multiple tools to aid in storm preparation, resource allocation, and mobilization.

These tools will utilize the following inputs:

- Historical outage data

- Historical forecast data

- Geospatial data

- Customer location and density

- Asset location data

- Historical vegetation management data

- Crew resource data

The outputs from these tools will include:

- Predicted incident counts

- Predicted customer impacts

- Hourly timing predictions

- Geospatial impact predictions (with varying resolutions down to workgroup level)

- Forecasted weather metrics

Q.	Did the Company utilize a decision matrix or probability distribution to measure and/or compare potential damages to varying resource quantities in order to make its resource, mobilization, and staging location decisions?

A.	No. Staff asked the Company in discovery if it utilized a probability distribution or matrix to measure and/or compare potential damage against resources required and, if so, to describe how the Company factored this distribution or matrix into the resourcing and mobilization decisions, including, but not limited to, the various storm response logistics modeling tools. The Company stated in response:

The Company currently does not have a probability distribution or matrix developed. However, the Company is in the process of developing and evaluating multiple tools to aid in storm preparation.

Q.	Did the Company utilize a decision matrix or probability distribution to measure and/or compare potential resources against outage times in order to make its resource and mobilization decisions?

A.	No. Staff asked the Company in discovery if it utilized a probability distribution or matrix to measure and/or compare potential resources against outage times and, if so, to describe how the Company factors this distribution or matrix into its resourcing and mobilization decisions, including, but not limited to, the various storm response logistics modeling tools. The Company stated in response:

The Company currently does not have a probability distribution or matrix for this issue. However, it does have an Estimated Restoration Time (ERT) measure, which will be incorporated into the tools it is developing and evaluating to aid in storm preparation, resource allocation, and mobilization. Please see the Company’s response to STF-PIA-29-3 for potential tool functionality the Company is planning to implement.

Q.	Did the Company utilize target metrics or quantitative goals for outage restoration times that were factored directly or indirectly into the number and type of resources acquired and/or the various storm response logistics modeling tools?

A.	No.  Staff asked the Company in discovery if it had one or more target metrics or quantitative goals for outage restoration times that was factored directly or indirectly into the number and type of resources acquired and/or the various storm response logistics modeling tools and, if so, to identify and describe each such target metric or quantitative goal and describe the manner in which it is used to determine the number and type of resources acquired, including, but not limited to, the various storm response logistics modeling tools. The Company stated in response:

The Company does not have specific metrics or quantitative goals for outage restoration times that factor into the number and type of resources needed for initial preparations of the storm response. Once the initial storm event has occurred and damage for various areas has been assessed by the Company, it assigns an outage event level from 1 through 4, which can be used as an input for resourcing decisions.  The outage event level also helps determine an Estimated Restoration Time (ERT) to track restoration times for customers.

The Staff also requested a listing and description of each goal or measure used by the Company to assess the effectiveness of its storm planning and response process and to provide documentation of these goals and measures and how they were used during and after Hurricane Helene, including in the various storm response logistics modeling tools. In response, the Company stated:

There are no specific metrics or documented goals for Hurricane Helene restoration efforts; however, the primary aim during any storm event is to safely and efficiently restore electric service to all affected customers as quickly as possible.

Q.	Does the historic lack of decision tools, including technology tools, to assist in planning and executing the response to the storms included in the storm cost regulatory asset support the Company’s claim that it utilized “industry best practices” or demonstrate a focus on optimizing resourcing and minimizing costs in response to those storms?

A.	No. The Company failed to use industry best practices to plan or execute its responses to the storms included in the storm cost regulatory asset. This led to inefficiencies and likely excessive costs. The Company relied on its historic practices, but such practices have no inherent benefit other than as guides to rough estimates of resourcing based on prior resourcing decisions for other storms. Of course, those prior storms were resourced in the same manner and without the benefit of modern decision tools, including technology tools, essentially a circular process that embedded and perpetuated historic rule of thumb practices and the inherent inefficiencies in those practices.

The Company also lacks an overall approach to storm response that incorporates quantitative performance objectives and metrics and allows it to assess the tradeoffs among the number and mix of resources available compared to outage restoration times and costs in order to achieve reasonable restoration times at the least reasonable cost. This led to inefficiencies and likely excessive costs. An overall approach that incorporates various performance objectives and metrics allows the utility to make decisions based on data and to test the outcomes using technology tools.

Generally, the more resources that are acquired, the shorter the time, on average, required to restore service, but the greater the cost to do so. The use of decision matrices and technology tools would allow the Company to more efficiently deploy resources so that restoration times are reduced and less cost is incurred.

Other utilities are much further developed in their planning and execution and have implemented technology tools that allow them to more precisely forecast potential damages based on system asset inventories, vegetation coverage, other potential causes of damage, and that allow them to acquire the resources correlated to the expected potential damages, and to manage the resources and transitions from higher to lower priority locations, to timely demobilize resources as damage is repaired and service is restored, and to minimize the costs to respond to the storm or other emergency event.

The Company has been slow to identify and implement best practices. After Hurricane Helene, the Company recognized that improvements in planning and execution were necessary to optimize resources and minimize costs, including the use of technology tools in this process. The Company’s failure to implement industry best practices and to integrate relevant technology tools to assess and set performance objectives and outage metrics necessarily led to excess resourcing, inefficiencies, and excessive costs imposed on customers, although the excessive costs cannot be directly quantified in retrospect.

Q.	Since Hurricane Helene has the Company acquired or developed new technology tools to improve its performance?

A.	Yes. The Company’s response to Staff discovery previously cited included its assessment of the functionality and the use of new technology tools. The Company’s response to additional Staff discovery identified new technology tools it has implemented and described the functionality of those tools as follows:

The Company implemented a storm modeling tool, Storm Prediction, Estimated Restoration Times and Reporting (“SPEAR”), in July 2025. This storm analytics tool delivers:

- Predicted incident counts;

- Forecasted customer impacts;

- Hourly timing estimates;

- Geospatial impact forecasts, both at the state and region levels; and

- Weather metric predictions.

As part of the SPEAR application, the Company also recently implemented a manpower tracking tool called GridCritical, which will be used to efficiently onboard, track, and accommodate resources assigned to restorations efforts.  This information will feed directly into the SPEAR application to assist in customer restoration times.

In addition to SPEAR, the Company is currently testing two additional modeling tools (StormImpact Prediction Models and WeatherSentry) to use for benchmarking purposes.

- StormImpact: Provides proprietary weather and hurricane models that are customized with Georgia Power’s historical storm effects to predict infrastructure damage and outages for any scale event.

- WeatherSentry: Robust platform that provides insights from proprietary weather prediction models on storm impacts using historical data to show damage, outages, and flooding. Among other capabilities, this system also provides data on traffic and evacuation routes to route restoration crews if necessary.

Q.	Did the Company critique its performance after each of the storms to determine its strengths and successes as well as its weaknesses and areas to develop and apply lessons learned for improved performance in response to future storms?

A.	No. The Company did not perform any documented critique of its performance after any storm, except for a limited critique after Hurricane Helene. In response to Staff discovery, the Company described this critique as follows.

Following the Company’s response to Hurricane Helene, a cross functional team was brought together to review the Company’s storm response process. As a result of this qualitative review, the Company identified eight areas for assessment and, where appropriate, further action. The Company is currently addressing these areas and anticipates completion later in 2025.

- Develop a base camp playbook for leaders to utilize to successfully run a base camp.

- Update the Significant Event Level Estimated Restoration Time Management document to better accommodate needs for restoration events with a 1 to 2 week duration.

- Determine a process for assigning storm roles to every new and existing employee at the Company and providing necessary training for the newly assigned roles.

- Develop a process for hosting an annual Company-wide storm drill and include a scenario of a severe hurricane impacting the whole state, including Metro Atlanta, in the first drill.

- Standardize the Company’s approach to local (county/city) communication during major storm events.

- Evaluate and update the safety onboarding process for off-system personnel.

- Develop a standardized process for damage assessment data collection and delivery.

- Refresh storm preparedness checklists included in all region Storm Emergency Response Plans.

Q.	Is that limited effort sufficient to identify areas of improvement through lessons learned and to apply those lessons to improve performance, including reduced outage times at lower costs?

A.	No. None of the eight areas reviewed addressed performance metrics, quantities and mix of resources, effective management of the resources acquired, reductions in outage times, or reductions in costs, all of which are at the very core of the Company’s storm response and the costs incurred.  Such self-critiques are essential to achieving improvements in the areas that matter the most to customers.

In addition, the lack of any specific performance metrics or documented goals for restoration efforts limits the opportunities for the Company and its leadership to assess performance and intentionally and continuously improve performance using those metrics.

Q.	What are your recommendations?

A.	We recommend the Commission direct the Company to study industry practices to identify the best of those industry practices, integrate those best practices into its planning, resource acquisition, and resource management, and adopt and use modern information technology and modeling tools, optimize the quantities and mix of resources, and manage those resources to reasonably balance the resources and time required to restore service with the costs incurred to restore service. We recommend the Commission direct the Company to complete this initial study, develop an action plant to implement these industry best practices, begin implementing those best practices by the end of 2026, and adopt and begin implementing modern information technology and modeling tools by the end of 2026. We recommend the Commission direct the Company to file quarterly detailed status reports with the Commission describing its progress on these activities starting in September 2026.

We also recommend the Commission direct the Company to critique its performance after each major storm to identify areas for improvement and then apply the lessons learned to continuously improve its restoration and cost performance in response to future storms. We recommend the Commission direct the Company to file these critiques, action plans, and detailed status reports with the Commission starting three months after each storm and continuing each quarter thereafter for at least one year after each storm.

In addition, we recommend the Commission consider these facts in conjunction with our other recommendations, including the amounts that Staff had to estimate because of the Company’s inability and/or unwillingness to quantify and exclude non-incremental costs already recovered through base revenues and the amounts that Staff had to estimate because of the Company’s flawed accounting and failure to correctly calculate the costs capitalized and recorded to plant in service instead of to the storm cost regulatory asset.

III. The COMPANY OVERSTATED THE STORM COST REGULATORY ASSET BECAUSE IT FAILED TO EXCLUDE COSTS ALREADY RECOVERED THROUGH BASE REVENUES

Q.	Describe briefly the Company’s accounting for storm costs.

A.	The Company describes its accounting for storm costs in “Accounting for Storm Damage & Other Emergencies,” which it provided in response to Staff discovery. These accounting guidelines apply to “major storms” and other emergency situations, including localized storms not meeting the requirements to be classified as a major storm, among others.

The costs for each storm or emergency situation are charged to a unique project activity code. The costs charged to the project activity code are debited to the “storm reserve” account, which if it is an asset balance, is referred to as a storm cost regulatory asset. There may be multiple storm cost regulatory assets in the future depending on the form of recovery adopted in this proceeding. At this time, the Company simply aggregates all storm cost regulatory assets. However, other utilities segregate their regulatory assets based on the form of ratemaking recovery and the timing of that recovery. We address this latter issue in the ratemaking section of our testimony.

The Company’s accounting guidelines specify which costs are to be charged to the project activity code. For example, all straight-time labor and related costs are considered “base charges,” meaning these costs are not incremental and already are recovered in present base revenues. These costs are not charged to the project activity code and are not included in the storm cost regulatory asset. All overtime labor and related costs and all contractor costs are considered “reserve charges,” meaning these costs are considered by the Company to be incremental. These costs are charged to the project activity code and are included in the storm cost regulatory asset.

The Company’s accounting guidelines also require the transfer of capital costs from the storm cost regulatory asset to plant in service accounts. The Company describes its accounting for the capital costs in other accounting guidelines provided in response to Staff discovery.

Q.	What are the threshold requirements for deferral of storm costs to a storm cost regulatory asset and recovery of those costs?

A.	First, the costs must be incremental, meaning they are costs that would not have been incurred but for the storm and are not already recovered through present base revenues. Second, the costs deferred to the storm cost regulatory asset should exclude all costs that are capital in nature and properly recorded in the plant in service accounts. The capital costs are incurred for the replacement of physical assets that have physical service lives and should be recovered from customers over their service lives in the same manner the costs of all other physical assets are recovered.

Q.	Does the Company agree conceptually with these threshold requirements?

A.	Yes. The Company agrees that only incremental costs should be deferred to the storm cost regulatory asset. It also agrees that capital costs should be recorded to the plant in service accounts and excluded from the storm cost regulatory asset, which it records through the capital cost credit. We address the capital cost credit in more detail in the following section of our testimony.

Q.	Did the Company actually restrict the costs included in the storm cost regulatory asset to only incremental costs?

A.	No. The Company improperly included costs that were not incremental and that already were recovered through present base revenues (rates). More specifically, the Company deferred all overtime labor costs for the internal resources that were redeployed from “business as normal” activities to storm activities and charged to the storm activity code for accounting purposes. The deferral of these costs to the storm cost regulatory asset is based on the assumption the entirety of these costs was incremental. That assumption is incorrect. The Company already recovers overtime labor costs for these redeployed resources through base revenues for “business as normal” activities. It does not incur those costs a second time for resources that were or are redeployed from those “business as normal” activities to storm response activities.

Similarly, the Company deferred all external contractor costs for external resources that were redeployed from “business as normal” activities to storm activities and charged to the storm activity code for accounting purposes. The deferral of these costs to the storm cost regulatory asset is based on the assumption that the entirety of these costs was incremental. That assumption is incorrect. The Company already recovers external contractor costs for these redeployed resources through base revenues for “business as normal.” It does not incur those costs a second time for resources that were or are redeployed from those “business as normal” activities to storm response activities.

Q.	Did Staff request the Company provide the labor and external contractor costs already included in and recovered through base revenues under “business as normal” activities for internal and external resources that are redeployed to storm response activities?

A.	Yes. The Company refused to provide this information in response to multiple Staff discovery requests or in the Minimum Filing Requirements (MFR) schedules despite Staff comments requesting that this information be provided for the costs of each storm included in the storm cost regulatory asset.

In response to one of the Staff discovery requests, the Company asserted that it “does not maintain a breakdown of contract labor and other outside services” into “electric line contractors and equipment,” “vegetation management contractors and equipment,” and “other contractors, e.g., flaggers, hydraulic pumping, etc., and equipment.” In response to Staff comments regarding the Company’s draft MFR schedules, the Company stated “During a storm, all outside services are charged to the respective storm number using a single resource type. The Company's reporting system does not track costs by vendor type.”

Q.	Regardless of the Company’s refusal to provide the information requested by Staff, is this information available from the Company’s records?

A.	Yes. The Company maintains accounting records that include the information necessary to quantify the information requested by the Staff necessary to correctly calculate the incremental and non-incremental costs. These records include the Company’s Contractor Application for Time and Expense Entry (CATEE) and Job Estimating and Tracking System (JETS) reporting systems and the invoices from each vendor for the specific external contractor resources that were redeployed from “business as normal” or activities to storm response activities, and the Company’s scheduling records.

Since Hurricane Helene, the Company has developed and/or implemented other technology tools that could provide this information. Staff was able to obtain a list of invoices by external contract providers from the Company and sort the providers into “vegetation management contractors and equipment,” “staging contractors,” and all other contractor and equipment for each of the storms based on the contract and invoice data. The Company could have done the same thing Staff did for the other named and un-named storms, but would not. We note the Company subsequently provided additional detail in response to Staff discovery for Hurricane Helene. Again, the Company could have provided this additional detail for the other named and un-named storms, but would not.

Q.	Are other utilities able to provide this information or proxies for this information?

A.	Yes.

Q.	In the absence of information that only the Company can provide, is there another approach the can use to quantify the costs of internal and external resources already recovered in base revenues?

A.	Yes. The Commission can use informed judgment to approximate the percentage of internal and external resources that were redeployed from “business as normal” activities to storm response activities and the related costs already included and recovered in base revenues as a rebuttal presumption. The Company then can decide whether to do its own analyses or not.

Q.	What is your recommendation?

A.	We recommend the Commission disallow all overtime labor and all outside services contractor costs for resources that were redeployed from “business as normal” activities that already are recovered through base revenues. In the absence of more detailed information that only the Company can provide, we recommend that 20% of the daily overtime labor and external contractor costs incurred during the post-storm restoration period be disallowed from the storm cost regulatory asset, which the Company can refine on rebuttal if it chooses to do so, subject to Staff review and Staff supplemental testimony as appropriate.

We also recommend the Commission direct the Company to improve its accounting and reporting systems so that it can differentiate between and correctly quantify the incremental and non-incremental costs and exclude the non-incremental costs for redeployed internal and external resources already recovered through base revenues, including overtime labor and external contractor costs.

Q.	What is the effect of your recommendation?

A.	The effect is an incremental reduction of $3.173 million in the requested base revenue increase due to a reduction of $10.083 million in the storm cost regulatory asset. The reduction in the storm cost regulatory asset for this disallowance is less than 1% of the total storm costs incurred by the Company.

IV. The Company Overstated The Storm cost Regulatory Asset BECAUSE IT FAILED TO REMOVE ALL CAPITAL COSTS THAT INSTEAD SHOULD HAVE BEEN RECORDED TO PLANT IN SERVICE

A.	Overview Of Capital Cost And The Errors That Overstated The Storm Cost Regulatory Asset And Understated Plant In Service

Q.	Describe the physical damage to the system from these storms using the Company’s description of the damage caused by Hurricane Helene.

A.	The Company’s witnesses describe the extent of the physical damage to the system from Hurricane Helene as follows:

Hurricane Helene was the most damaging storm in the Company’s history, impacting nearly 1.6 million customers and causing extreme infrastructure damage, including 12,239 broken poles and more than 20,000 spans of wire downed. For comparison, Hurricane Helene had more broken poles and downed spans of wire than Hurricanes Matthew, Irma, Michael, Zeta, and Idalia combined. In response, Georgia Power mobilized more than 20,000 personnel, including crews from over 35 partner companies, to repair or replace poles, lines, and transformers, and in some cases, rebuild portions of the power grid from the ground up.

Q.	Describe the two categories of costs incurred to respond to a storm.

A.	The first category of costs are the costs to replace and/or substantially rebuild physical assets that have been damaged. These costs are accounted for as capital costs because they are costs incurred for physical assets that have physical lives and provide service to customers over many decades.

The second category of costs are the costs to repair minor damage to assets and restore service to customers, such as retensioning conductor or replacing hardware items that are not units of property. These costs are accounted for as operation and maintenance (O&M) expenses and deferred to the storm cost regulatory asset, which generally are recovered over a period much shorter than the service lives of physical assets.

In response to storm events, costs are incurred that cannot be directly categorized as either capital or O&M expense because they were incurred for both activities. All such costs should be properly allocated between capital (plant in service) and O&M expense (storm cost regulatory asset), not simply assigned to O&M expense.

Q.	Describe the Company’s accounting for the storm cost regulatory asset and how capital amounts are removed from regulatory asset and recorded to plant in service.

A.	The Company initially records all storm costs to the storm cost regulatory asset. It then determines the costs that should be removed from the storm cost regulatory asset and instead recorded to plant in service using a formulaic standard cost methodology. The standard cost methodology for capital costs is triggered only for the removal of damaged existing plant assets and the installation of new plant assets that are eligible and/or required to be capitalized to the plant in service accounts for accounting and reporting purposes.

The standard cost methodology for each asset starts with a calculation of the capital costs under “business as normal” conditions. It includes the inventory cost; an inventory stores cost load; straight time labor based on a standard number of manhours times a straight time average hourly rate; a standard labor cost load; a standard fleet cost load; a supervision and engineering (S&E) cost load; an administrative and general (A&G) cost load; and other cost loads.

The Company then modifies the standard cost methodology for each asset to include additional costs in the capital cost credit under “storm event” conditions. More specifically, the Company applies a 125% “multiplier” to the standard straight time labor cost under “business as normal” conditions to calculate the labor cost included in the capital cost credit under “storm event” conditions.  The Company developed the 125% multiplier based on the assumption that the labor cost consists of straight time labor at 100% for half of the standard manhours and the overtime labor cost at 150% of the straight time labor cost for the other half of the standard manhours.

The Company does not directly measure either the straight time or the overtime labor charged to the storm cost regulatory asset for the capital cost credit. As we noted previously, the Company does not record straight time labor to the storm cost regulatory asset, except for excess straight time labor and affiliate straight time labor.

The Company calculates the equipment costs included in the capital cost credit as 25% of the labor costs.

The Company calculates the cost of inventory included in the capital cost credit based on an average of the standard costs under normal site conditions and the higher standard costs under inaccessible site conditions, and switches and switching cubicles based on the higher standard cost under inaccessible conditions.

The Company calculates the cost of certain contractor costs included in the capital cost credit at 100% for hydrovac contractors, 25% for traffic control contractors, 15% for data analytics and technology (DTA) contractors, 100% for crew support contractors, and 25% for miscellaneous repair contractors, but does not calculate the capital portion of other external contractor costs.

Q.	Did the Company correctly capitalize and include in the capital cost credit all capital costs related to the removal and replacement of damaged physical assets?

A.	No. The Company incurred significant other external contractor costs to remove and replace damaged physical assets. Yet, the Company did not and does not capitalize any of these other external contractor costs, exclude these costs from the storm cost regulatory asset through the capital cost credit, or correctly record the costs in the plant in service accounts. More specifically, the Company did not and does not capitalize and include in the capital cost credit any of the external line contractor costs, the single largest category of external contractor costs. Nor does the Company capitalize and include in the capital cost credit any of the external vegetation management contractor costs. Nor does the Company capitalize and include in the capital cost credit any of the staging costs. The entirety of these external contractor costs remains in the storm cost regulatory asset after the capital cost credit for other external contractor costs removes those costs from the storm cost regulatory asset.

Q.	What percentage of the storm costs were capitalized to plant in service for each of the named storms and for the un-named storms in the aggregate by the Company?

A.	The following table shows the percentage of the storm costs capitalized to plant in service for each of the named storms and for the un-named storms by the Company.

Q.	Are these capitalization amounts and percentages reasonable?

A.	No. They are remarkably low for the majority of the named storms, but especially low for Hurricane Helene, especially given the magnitude of the physical damage to the system for that storm described by the Company’s witnesses in their direct testimony that we previously cited and quoted in part.

In addition, we are aware from publicly available information that Duke Energy Carolinas, LLC. capitalized approximately 42% of its Hurricane Helene storm costs, or approximately five times more than the 8.2% the Company capitalized for the same storm.

Q.	Explain why it matters whether the costs are recorded to capital or remain in the storm cost regulatory asset.

A.	It matters from an accounting and ratemaking perspective. As we previously noted, capital costs incurred for physical assets are properly recorded in plant in service accounts, included in the base revenue requirement, and recovered from customers over the service lives of the assets. In contrast, the costs recorded to the storm cost regulatory asset are included in the base revenue requirement and recovered from customers generally over a shorter period than the capital costs, at a lower rate of return, and/or in a different form if the recovery is levelized.

Q.	Describe the Staff’s investigation into the Company’s accounting and methodologies that it used to calculate the capital cost credit.

A.	Given the Company’s extremely low percentages of storm costs capitalized to plant in service for the majority of the named storms and the fact the Company capitalized only 8.2% of the costs of Hurricane Helene compared to the 42% capitalized by Duke Energy Carolinas, LLC. for the same storm, we carefully reviewed and assessed the Company’s accounting and the methodologies it used to calculate the capital cost credits recorded to plant in service.

In our review and assessment, we identified conceptual and calculation errors that caused the capital costs to be understated, not only for Hurricane Helene, but also for the other storms.

We subsequently address each of these conceptual and calculation errors. The errors include a conceptual and calculation error the Company acknowledged in response to Staff discovery that understates the labor cost included in the capital cost credit, a conceptual error that further understated the labor cost included in the capital cost credit, and a conceptual error that understated the external contractor costs included in the capital cost credit.

As we previously noted, an increase in the capital cost credit does not result in a disallowance of storm costs; rather, it transfers the costs from the storm cost regulatory asset to plant in service costs, which then will be included in the Company’s base revenue requirement in the next base rate proceeding and recovered in that manner.

B.	Calculation Error That Understated Labor Cost Included In Capital Cost Credit

Q.	Describe the calculation error that understated the labor cost included in the capital cost credit for Hurricane Helene.

A.	The Company’s original calculation of this removal was incorrectly based on a percentage of costs applied not only to its own labor, but also to specialized external contract labor for such things as hydro-vac services, special equipment operation, assessor fees, and engineering services. In response to Staff discovery after a Teams meeting with the Company’s subject matter experts, the Company confirmed there was an error in its calculations and that approximately $8 million more should have been capitalized for Hurricane Helene as follows:

In responding to this request, the Company recognized that the specialized contract labor in the estimated labor basis from JETS was not deducted prior to the application of labor adder deduction since contractors are not applied labor adders. This correction is reflected in the tab ‘STF-SCR-1-17_Recalculation’ within “PSC Staff Follow Up – 4.3.26” and results in an increase of approximately $8 million to the amount that were previously capitalized. The Company will make this adjustment during its final true-up to reflect this change.

The Company utilizes its JETS application to calculate the capital cost credit for plant in service costs using a standard cost methodology. It uses a standard cost methodology for “business as normal” conditions and the same standard cost methodology with modifications for storm conditions.  One difference in the standard cost methodology under storm conditions is the addition of a 25% adder, applied as a 125% multiplier, to the standard cost labor rates used under “business as normal” conditions in an attempt to recognize that it includes only overtime labor costs in the storm cost regulatory asset.

The Company provided examples of the JETS output used to record distribution capitalized costs for Hurricane Helene in response to discovery, that appeared to reflect errors resulting in an inordinately low level of capitalized costs for Hurricane Helene. Staff participated with Company subject matter experts in a Teams meeting on March 26, 2026 to review the various inputs and components of the JETS output for capitalization and to explain its concerns with the Company’s calculations.

According to the Company, the JETS labor rates also factor in all labor overhead loaders such as benefits, incentive costs, and payroll taxes. These overhead loaders in JETS amounted to 99.86% of in-house labor applicable to Hurricane Helene and represent the overhead percentages applicable to straight-time pay. Since only overtime pay was included in the Company’s incremental storm costs to be capitalized, the overhead loader amounts had to be removed from the JETS output to determine the incremental distribution costs to be capitalized.

Q.	Does this error in the calculation of the capital cost credit for Hurricane Helene extend to the other storms?

A.	We believe it does, but were not able to confirm this on the expedited schedule for this proceeding. We believe the Company used the same calculation methodology for the other storms in the absence of any information to the contrary.

Q.	What is your recommendation?

A.	We recommend the Commission correct this error that understated the capital cost credit for all storm costs in this proceeding. As we noted, the Company agrees the error should be corrected for Hurricane Helene. We recommend the Company provide the amounts necessary to correct this error for the other storms or provide evidence that the error did not extend to the other storms. We also recommend the Commission direct the Company to correct this error going forward for all future storms.

Q.	What is the effect of your recommendation?

A.	The effect is an incremental reduction of $2.578 million in the requested base revenue increase based on a reduction of $8.192 million in the storm cost regulatory asset, solely related to the Hurricane Helene costs after consideration of the prior adjustments that we recommend. We were not able to quantify the effects on the requested base revenue increase related to the other storms. However, the Commission should incorporate the correction of this error related to the other storms after the Company confirms this error exists as well for those storms and provides the quantifications necessary to correct those errors.

C.	Conceptual And Calculation Error That Understated Labor Cost Included In Capital Cost Credit

Q.	Did the Company correctly calculate the labor cost included in the capital cost credit?

A.	No. The Company’s calculation understates the capital cost credit because it incorrectly assumes that the labor costs are half straight time labor and half overtime labor. This assumption is inherently incorrect because the Company does not and did not record any straight time labor to the storm cost regulatory asset. Indeed, the Company recorded and continues to record for this purpose only overtime labor, all of which has a 50% premium over straight time labor, under the assumption that the manhours are the same under storm conditions as under business as normal conditions. The capital cost credit should not reflect in any manner the lower straight time labor costs that were not recorded to the storm cost regulatory asset. The capital cost credit should reflect only overtime labor because only overtime labor is recorded to the storm cost regulatory asset.

Q.	How can the Commission correct this error?

A.	The error can be corrected by increasing the straight time labor cost “multiplier” to 150% from the Company’s present multiplier of only 125% so that the labor costs excluded from the storm cost regulatory asset to plant in service through the capital cost credit are properly matched to the labor costs recorded to the storm cost regulatory asset.

Q.	What is your recommendation?

A.	We recommend the Commission correct this conceptual and calculation error that understated the capital cost credit for the storm costs in this proceeding. We also recommend the Commission direct the Company to correct this error going forward for all future storms.

Q.	What is the effect of your recommendation?

A.	The effect is an incremental reduction of $1.279 million in the requested base revenue increase based on a reduction of $4.066 million in the storm cost regulatory asset balance after consideration of the prior adjustments that we recommend.

D.	Conceptual And Calculation Error That Understated External Contractor Cost Included In Capital Cost Credit

Q.	Does the Company’s standard cost methodology used for the capital cost credit correctly calculate the external contractor capital costs that should be excluded from the storm cost regulatory asset and instead recorded to plant in service?

A.	No. The Company’s methodology also understates the external contractor costs in the calculation of the capital cost credit. The Company’s methodology incorrectly excludes all external line contractor costs, all external vegetation management contractor costs, and all staging costs from the capital cost credit, thus overstating the costs in the storm cost regulatory asset and understating the costs recorded to plant in service.

Q.	Is it reasonable to exclude all external contractor costs from the costs included in the capital cost credit?

A.	No. These external contractor costs were incurred to repair all damage to the system necessary to restore service, which include both the capital cost activities necessary to remove existing assets that were damaged and install replacement assets (units of property) and O&M expense cost activities (not tied to units of property) necessary to restore service. External contractor costs were the single largest category of costs incurred in response to each of the storms.

The portion of the costs necessary to remove existing assets that were damaged and install replacement assets are capital costs and should have been included in the capital cost credit, excluded from the storm cost regulatory asset, and included in plant in service.

Q.	What is your recommendation?

A.	We recommend the Commission correct the Company’s standard cost methodology used to calculate the capital cost credit and increase the capital costs recorded to plant in service to include external line contractor costs, external vegetation management contractor costs, and external staging contractor costs.

We recommend that a minimum of 20% of these external contractor costs be included in the capital cost credit in the absence of more detailed information that only the Company can provide, but refused to do so in response to Staff discovery. We note this 20% is less than half of the 42% capitalization percentage calculated by Duke Energy Carolinas for Hurricane Helene. The Company can refine this percentage on rebuttal if it chooses to do so in response to our recommendation, although we reserve the right to review and supplement our direct testimony in response to any Company information provided for the first time in rebuttal testimony.

We also recommend the Commission direct the Company to utilize the corrected standard cost methodology to calculate the capital cost credit for storm costs incurred in the future.

Q.	What is the effect of your recommendation?

A.	The effect is an incremental reduction of $68.948 million in the requested base revenue increase based on a reduction of $219.119 million in the storm cost regulatory asset after consideration of the prior adjustments that we recommend.

V. The Company’s Documentation, Review, and Approval Process WAS GENERALLY adequate; HOWEVER, IMPROVEMENTS ARE NECESSARY

Q.	Describe the focus of the Staff audit of third party invoices.

A.	We focused our audit primarily on external contractor invoices submitted by line and vegetation management contractors, mutual assistance companies, staging site contractors, and other contractors, as these contractor vendor costs comprise almost 94% of the storm costs incurred. The MFRs submitted with the Company’s application categorizes these costs all as outside services. The Company groups all of these costs together generically as outside services for deferral to the storm cost regulatory asset and does not distinguish by the services provided.

Q.	What level of invoice and contract support was requested by Staff through discovery?

A.	Staff sought through discovery copies of sample invoices for the outside services contractors (line, vegetation management, mutual assistance, and other) as well as the other outside services vendors (staging and other) related to Georgia Power’s response to each storm for which recovery is being requested. Staff also sought copies of all vendor contracts associated with those same outside services contractors and other vendors.  All contract copies were required in advance to be able to review once sample invoice copies were identified and provided for review.

Q.	Describe the samples of invoices that were reviewed for the storms.

A.	In response to Staff discovery, the Company provided lists for each storm of all invoices for its outside services vendors in the form of confidential Excel spreadsheets that were sourced from its accounting records. The lists included each vendor’s name, invoice number, and invoice amount sorted in descending order from highest amount to lowest. Based on these lists, we developed a stratified sampling by including invoice amounts in dollar range buckets. Then we developed a systematic sampling of each bucket by testing each nth invoice in each bucket based on selecting varying percentages of invoices in each bucket. The buckets and each nth sample selections were different in some respects for each of the storms based primarily on the amount of invoices in each of the dollar range buckets. Since Hurricane Helene was responsible for the highest number of individual invoices and with the highest dollar amounts by far, a greater number of those invoices were selected. The table below shows the sampling technique utilized for the Hurricane Helene invoices. The sampling technique was developed from the original list of 6,421 invoices provided by the Companies that were posted through March 2025.

This sampling technique was also utilized for the additional set of 1,287 Hurricane Helene invoices processed after March 2025.

A similar sampling technique was utilized for each of the other individual storms.  Due to size, similar tables for each of the other storms are attached as Exhibit STF-NKF-6.

Q.	Identify the major components verified in your review of the invoices for each of the storms.

A.	Below we have identified in bullet point format the major components we sought to verify in review of the invoice copies for each outside services vendor.

- Whether invoice copy support was provided by Georgia Power through discovery for each individual invoice sought as part of the samples of invoice copies requested;

- Whether the total costs of each sample invoice matched the total amounts for each invoice included in the confidential Excel workbook lists of invoices that were provided by the Company;

- Whether there were any apparent duplications of invoice costs requiring further investigation.

- Whether the invoice copy support that was provided by Georgia Power included the proper timesheet, cost per hour, and cost extension data necessary for verification purposes, such as dates and daily hours of work performed as well as location of work performed;

- Whether the number of hours invoiced matched the number of hours summarized on each of the timesheets;

- Whether supporting timesheet data was applicable, given the nature of the invoiced costs;

- Whether further discovery was required for cost verification purposes;

- Whether the hourly labor and equipment rates for each data line on the invoices matched the contracted regular, overtime, and double-time rates for all labor and equipment distinctions (service items);

- Whether the hourly labor rates included in the contracts and charged on the invoices appeared reasonable in comparison to those of other contractors;

- Whether there were days in which more than the contracted and standard International Brotherhood of Electrical Workers (“IBEW”) 16 hours in a day were charged for either overhead line or vegetation management contractors;

- Whether each regular working day for each individual line item was charged with at least 8 hours of regular time before overtime rates were charged;

- Whether the working day rates for overtime and double-time were appropriately charged for any weekend days or holidays;

- Whether the timesheet dates for each individual line item on the timesheets for mobilization, demobilization, and regular working hours matched a reasonable range of dates for actual storm restorations for each individual event; and

- Whether there were any other cost items that appeared out of the ordinary.

Q.	Describe the various forms of invoice support provided by the Company in response to Staff discovery utilized in your review.

A.	Invoice support was similar for the non-Helene storms and much more diverse for Hurricane Helene due to the much larger scope of work being performed by many additional outside contractor crews. Georgia Power utilized its CATEE application to process the largest portion of the invoices for line and vegetation management contractors.

The invoice support requested through discovery was well organized and complete for review. Georgia Power supplied electronic folders for each sample invoice selected for review without exception. The folders were identified by vendor and invoice number and contained copies of either the CATEE generated invoice or the normal vendor generated invoice, timesheet data, expense reimbursement data, and other correspondence between the vendor and Georgia Power.

Q.	Did the total invoice amounts match the Excel invoice list amounts provided by Georgia Power?

A.	Yes, for the most part. We found that the total amounts of the sample invoices matched the amounts on the provided Excel lists for Hurricane Helene without exception.  However, we did find that the total amounts of five sample invoices did not match the invoice amounts on the Excel lists applicable to the non-Helene storms. Since the total amounts of those five invoices were different, we sought additional discovery to determine if there were any over-reported costs in the final analysis.  The five invoice amounts are portrayed in the table below.

The Company was asked in discovery to explain why each of these supporting document amounts were different than the amounts reflected in the storm cost regulatory asset invoice details. The Company answered in each instance that the difference relates to the amount of Georgia sales tax for taxable services or goods that was not reflected on the vendor invoice but that was instead accrued and paid directly to the state of Georgia.  In fact, the differences in the amounts listed above match the 8.9% Fulton County state and local tax rate applied to each invoice. Based on the Company’s further justification and provided support, Staff makes no recommendation to disallow the cost differences initially observed.

Q.	Did you find instances in which total invoice amounts or cost line items were duplicated?

A.	No.

Q.	Did you find instances in which hourly rates billed in contractor invoices did not comport with preauthorized contract rates?

A.	No. We found that contract billable rates for labor and equipment matched invoice amounts in all cases in which the appropriate detail invoice documentation and copies of contracts were provided. We address below the problem of missing contract data for certain vendors.

Q.	Did you find instances in which invoice costs appeared out of the ordinary and needed further explanation?

A.	Yes. We found two such instances in our review of the invoice copies that are detailed below. Additional discovery was required to ensure that reported costs were appropriate and reasonable.

The first instance involves a Hurricane Helene invoice that was paid but that should not have been included for recovery from ratepayers. Invoice number ….. associated with ............................ for ……….….. was originally included as a recoverable cost, even though the two descriptions of the services provided included “tree removal from requested houses of Georgia Power employees” and “install tarp on requested house of Georgia Power employees.” This invoice was for services that benefitted Georgia Power employees and not ratepayers. The Company provided proof in discovery that this amount was later reclassified via a journal entry in November 2024. The cost was removed from the storm cost regulatory asset and instead recorded to a below-the line account (account 426.5). This reclassification not only removed the invoice amount from the Hurricane Helene costs in this proceeding, but it also ensured that ratepayers would not be held responsible for it in any way in the determination of base rates. Thus, no disallowance is necessary.

The second instance involves the inclusion of invoice costs for restoration activities dating back to a storm that occurred years before the 2022 – 2025 review period. Invoice number ………….. for ………………. was included with the storm cost invoices provided in discovery related to the other unnamed storms. In fact, this mutual assistance invoice from ………….. related to storm restoration activities for Hurricane Michael that occurred in October 2018. The date of the invoice was …………….. The Company responded in discovery that this invoice was originally sent to a Georgia Power employee in 2019 that had retired, so it was never entered for processing. ………….... did not follow-up on the unpaid amount until Georgia Power engaged it to assist again in the aftermath of Hurricane Helene. The Company determined the costs to be legitimate Hurricane Michael storm restoration costs that had gone unrecorded and unpaid for a period of five years. Since the Company was obligated to pay the invoice, there is no reason to recommend a disallowance of these storm restoration costs.

Q.	Do you have an overall conclusion related to the Company’s invoice costs based on the invoice support and audit that your team performed?

A.	Yes. We conclude that the invoice costs associated with all contractors were appropriate for storm cost recognition by storm, that the line item cost rates matched contract pricing when applicable and available, that the total invoice levels match amounts on the Company-generated Excel invoice lists, and that there were no duplications of individual cost items or invoices included in the storm cost summaries.

Q.	Describe the contracts that you reviewed as part of the audit process.

A.	As noted above, we sought to obtain copies of all contracts applicable to the various time periods for the storms. Contract copies were provided in separate data responses for Hurricane Helene and for all the other non-Hurricane Helene storms combined. All contract copies were required in advance of the selection of sample invoices to streamline the review process.

The Company maintains contract Master Agreements (MAs) with many contractors that it anticipates utilizing. …………………………………………………… ………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………..

We found that contracts related to the various storms had differing levels of organization.  The contract copies provided for the non-Helene storms were organized in folders by vendor name, vendor type, and by contract time period. Each folder contained copies of the MAs and either the applicable ………….., making the search for contracts with applicable billing rates efficient. The contract copies for Hurricane Helene were provided as different files in one mass folder and were not organized in any manner. This made the review of all contract provisions and rates for each vendor needlessly cumbersome as it necessitated searching through hundreds of individual files, some with vendor names and some without, in order to find only the applicable contract information specific to each individual vendor.

We also found that there were no contract copies provided for a large number of line contractors associated with Hurricane Helene, presumably related to the unusually large emergency nature of the restoration process for this storm. Thus, there was no way to match invoice data pricing to pre-approved contract rates for these vendors. For instance, we could not locate the line contractor contracts applicable to 20 of the 122 Hurricane Helene vendor invoices over $1 million.  The invoice copies in such instances were stamped with the distinction of a “Non-PO Storm Invoice.” Company personnel also identified this as a concern in a recent audit report. The Company provided in discovery a copy of its December 30, 2025 internal audit report pertaining to the Company’s Hurricane Helene storm reserve costs. That report highlighted similar findings by stating the following:

Some third-party vendors utilized for storm recovery services did not have up to date contracts in place. There were instances where non-Purchase Order invoices were utilized even when contracts with third-party vendors were in place.

Q.	Do you recommend process improvements that would streamline the invoice verification and audit process?

A.	Yes. We recommend that the Commission direct the Company to ensure it obtains signed contracts and maintain copies of all contracts for all line and vegetation management contractors, as well as all other major storm response vendors, until all storm cost verification processes are complete. We further recommend that electronic versions of the contract documentation be maintained and organized in separate data folders by vendor name and major storm event or time period and that Georgia Power have this information readily available for internal invoice review and at the time it makes future storm cost recovery filings in order to avoid unnecessary delays for reviewers.  The separate folders for the contracts should include the MA for the vendor as well as copies of each applicable …………. that contains contract rates pertaining to each storm year.

VI. The Commission Should deny The Company’s PROPOSAL to Increase The Storm Cost Regulatory Asset INCLUDED IN RATE BASE FOR ESTIMATED STORM COSTS AFTER December 31, 2025

Q.	Describe the Company’s calculation of the storm cost regulatory asset and the related rate base, storm expense amortization, storm expense accrual for future storms, and estimated storm charges for future storms reflected in the storm cost revenue requirement.

A.	The Company included a return on the storm cost regulatory asset less accumulated amortization less related ADIT included in rate base in the first component of its request to increase base revenues to recover the storm cost regulatory asset. The Company started with the $911.591 million storm cost regulatory asset recorded at December 31, 2025. It then added another $8.438 million in estimated future storm costs based on its requested storm expense accrual for future storms for each month starting on January 1, 2026 and continuing through May 31, 2027. It subtracted $2.618 million for the storm expense accrual for future storm costs presently recovered in base revenues for each month starting January 1, 2026 and continuing through May 31, 2026, then subtracted $27.429 million for each month, calculated as the sum of its proposed annual $227.898 million in storm cost regulatory asset amortization expense and its proposed annual $101.254 million in storm expense accrual for future storms divided by 12.

The Company then calculated the return on the storm cost regulatory asset starting with the estimated $940.689 million storm cost regulatory asset at June 1, 2026 instead of the actual $911.591 million storm cost regulatory asset recorded at December 31, 2025.

The following table shows the Company’s calculation of the rate base for each month starting with the $940.689 million in June 2026 through May 2027 and the 13-month average used to calculate the return on rate base amount included in the base revenue requirement and requested increase.

Q.	Are the Company’s calculations of the return on component of the base revenue requirement correct?

A.	No. First, the calculations are not based on the storm cost regulatory asset at December 31, 2025. The calculations include additions for estimated storm costs after December 31, 2025 and subtractions for presently authorized recoveries for future storm costs through base revenues from January 2026 through May 2026 and then its requested recoveries for future storm costs from June 2026 through May 2027.

The Company’s calculations violate the requirements set forth in paragraph 3 of the Stipulation approved by the Commission in Docket 44280 in its Order dated July 31, 2025, which states:

The Company will be allowed to recover actual reasonable and prudent storm damage cost incurred through December 31, 2025, that exceeds the amount of the annual storm damage accrual approved in the Order Adopting Settlement Agreement as Modified.

None of the Company’s adjustments to the storm cost regulatory asset after December 31, 2025 are allowed pursuant to the Stipulation, except the reductions related to recoveries of the storm cost regulatory asset authorized in this present proceeding. We subsequently address this issue in more detail.

Second, the Company’s calculations include estimated storm costs greater than the storm expense accrual for future storm costs presently recovered in base revenues for January 2026 through May 2026. This error resulted in an increase of $29.098 million in the storm cost regulatory asset from the $911.591 million at December 31, 2025 to $940.689 million at May 31, 2026. Although this error did not affect the Company’s requested amortization expense included in the storm expense accrual, which was based on the storm cost regulatory asset at December 31, 2025, it overstated the rate base used to calculate the return on the storm cost regulatory asset included in the requested base revenue requirement.

Third, the Company’s methodology presumes that it is entitled to a rate of return, not only on the storm cost regulatory asset at December 31, 2025, but on any increases in the regulatory asset after December 31, 2025 for storm costs that exceed recoveries of the storm expense accruals for future storms. This would represent a significant change in policy for the Commission, one the Company did not expressly request in this proceeding, but appears to have implicitly requested by incorporating the change in methodology into its calculations. The Commission historically has not allowed a return on storm costs incurred and deferred to a storm cost regulatory asset in the interval between the effective dates when base rates are reset or on a deferred basis.

Q.	What are your recommendations?

A.	We recommend the Commission deny the Company’s request to recover a return on the estimated storm costs incurred after December 31, 2025 in this proceeding. The Commission’s Order and the Stipulation last year limited recovery in this proceeding to costs incurred through December 31, 2025.

In addition, we note that the Company’s request to recover the “return of” (amortization) of the storm cost regulatory asset is, in fact, correctly limited to the storm cost regulatory asset at December 31, 2025. The return on the storm cost regulatory asset should be based on the same date that is used to calculate the return of the storm cost regulatory asset, and more specifically, the December 31, 2025 date specified in the Commission Order.

Further, we note that, as a practical matter, the Commission cannot review estimated costs that have not yet been incurred for the five months after December 31, 2025. To the extent costs actually were and are incurred and correctly recorded to the storm cost regulatory asset after December 31, 2025, then the Company will be eligible to seek recovery of these additional costs in its next base rate proceeding to the extent that the recoveries for such costs in present base revenues are not sufficient to cover those actual costs.

Q.	What is the effect of your recommendation?

A.	The effect is an incremental reduction of $2.138 million in the requested base revenue increase based on a reduction $29.098 million in the storm cost regulatory asset after consideration of the prior adjustments that we recommend.

VII. The Commission Should deny The Company’s Request To Recover A Return On The Storm cost Regulatory Asset At Its grossed-up Weighted average Cost of Capital

Q.	Describe the Company’s request to recover a grossed-up rate of return on the storm cost regulatory asset.

A.	The Company proposes to recover a grossed-up WACC return on the storm cost regulatory asset net of the accumulated amortization and net of the related ADIT for the twelve months ending May 31, 2027. The Company used a 13-month average to calculate the rate base for this purpose. The Company calculated the WACC based on a long-term debt ratio of 44.0% and an average cost of 4.41% and a common equity ratio of 56.0% at a cost of 10.50%.

Q.	Is it reasonable to include a rate of return at the Company’s WACC on the storm cost regulatory asset in the revenue requirement?

A.	No. The Company does not presently recover or defer any rate of return on the storm cost regulatory asset. If the Commission includes a rate of return in the revenue increase, it will incrementally increase the Company’s earned return, all else equal.

The Company has provided no evidence in this proceeding that a rate of return on the storm cost regulatory asset is necessary for its financial integrity or to earn the lower end of the earnings deadband set in the Stipulation approved by the Commission last year.

In addition, the Company has presented no evidence in this proceeding that it financed the storm cost regulatory asset using long-term debt and common equity. Further, even if it had or could provide such evidence, it, nevertheless, could modify its actual financing to reflect only debt, either short-term debt or intermediate term debt, or a combination of both.

Further, even with the Staff recommendation to levelize (annuitize) the recovery of the storm cost regulatory asset to minimize the overrecovery of these deferred costs, the Company inherently will overrecover between base rate proceedings due to increases in the kWh sales, kW demand, and customers used to calculate rates with the storm cost recovery costs included resulting in actual revenues greater than the revenue requirement reflected in the rates using those billing determinants.

Q.	What are your recommendations?

A.	We recommend the Commission authorize a debt only rate of return on the storm cost regulatory asset. The debt only rate of return reflects the lack of any evidence from the Company that it financed the storm cost regulatory asset through equity and long-term debt financing. This is an approximate midpoint between the status quo with no return on the storm cost regulatory asset and the Company’s request to recover a grossed-up rate of return It also reflects the lower financial and regulatory risk from recovery of a financial asset compared to the recovery of the costs of operating assets and activities. The Company has the option of actually financing the asset with debt, either short-term or long-term. Finally, it recognizes the Company will overrecover the storm cost regulatory asset even with the Staff recommendations to levelized recovery due to growth in sales and other billing determinants between base rate proceedings when the actual rates using those billing determinants are developed.

We also recommend that the return on be applied only to the storm cost regulatory asset at December 31, 2025 less accumulated amortization and related ADIT as the regulatory asset is amortized and recovered from customers.

Q.	What are the effects of your recommendation?

A.	The effect of using the Company’s debt only return is a reduction of $20.037 million in the requested base revenue increase.

VIII. The Storm Cost Regulatory Asset Recovery PERIOD Should Be EXTENDED AND THE REVENUE RECOVERY SHOULD BE LEVELIZED

Q.	Will the rate base amounts for the storm cost regulatory asset continue to decline in the months after May 2027?

A.	Yes. The Company calculated the rate base amounts for the twelve months ending May 2027. The rate base amounts for the storm cost regulatory asset will continue to decline each month as the amount recorded at December 31, 2025 is amortized and recovered from customers starting on June 1, 2026. This will result in a reduction in the revenue requirement each month from June 2026 through May 2027, which the Company reflected in its requested increase. This also will result in a reduction in the revenue requirement each month after May 2027 until the storm cost regulatory asset at December 31, 2025 is fully amortized and recovered from customers.

Q.	Did the Company reflect these declines in the rate base and the reduction in the revenue requirement each month after May 2027 in its requested increase in base revenues?

A.	No. This is an error because the Company will continue to recover the return on rate base amounts at the amounts included in its requested increase in base revenues even as the underlying costs and revenue requirement continue to decline. The Company will retain these excess recoveries absent a form of recovery that expressly addresses these ongoing reductions in the underlying costs and revenue requirement.

We note that the return on the declining rate base is a concern only if the Commission authorizes a return on rate base. If there is no return on rate base, then the revenue requirement consists only of the return of, or amortization of, the storm cost regulatory asset and the revenue requirement will remain the same throughout the recovery period until the storm cost regulatory asset is fully amortized.

Q	What alternatives are available to the Commission to reflect these declines in the rate base and the return on if a return on is included in the revenue requirement as the rate base declines each month?

A.	Other than the use of a rider to recover these storm costs, there are two practical base revenue approaches that ensure the Company recovers and customers pay only the Company’s actual costs, no more and no less, except for the inherent overrecovery due to the growth in sales, demand, and customer billing determinants between base rate proceedings.

The first and best approach is to calculate the revenue requirement on a levelized (annuitized) basis over the recovery period in the same manner as a home mortgage payment is calculated. This first approach is designed to avoid excessive recoveries that either are retained by the utility or subject to true-up and refunded at a later date.

The second approach is to calculate the excess base revenue recoveries compared to the declining revenue requirement and defer these amounts and a return on the deferred amounts at the grossed-up WACC as a regulatory liability for refund in a future base rate proceeding. This second approach is inferior to the first approach because it unnecessarily requires customers to pay excessive amounts only to have them refunded at a later date.

Q.	What is your recommendation?

A.	We recommend the Commission calculate the revenue requirement on a levelized basis over the recovery period. This will occur without any further decision required by the Commission if it denies a return on rate base. However, it will require the Commission to authorize the recovery on a levelized basis if it includes a return on rate base, whether the Company’s request for a grossed-up WACC or our alternative recommendation for a debt-only return

Q.	What is the effect of your recommendation?

A.	The effect is an incremental reduction of $12.929 million in the requested base revenue increase after consideration of the prior adjustments that we recommend.

Q.	Describe the Company’s proposed amortization and recovery period.

A.	The Company proposes to amortize and recovery the storm cost regulatory asset over four years.

Q.	Is there any compelling reason to amortize and recover the storm cost regulatory asset over four years?

A.	No. The requested amortization and recovery period of four years is unduly short and does not align with the timing of the Company’s historic three-year alternative rate plans approved by the Commission in the last several base rate proceedings.

The amortization and recovery period is a matter of informed judgment for the Commission to decide. The shorter the amortization and recovery period, the greater the base revenue increase and the longer the amortization and recovery period, the lesser the base revenue increase.

Factors that should inform the judgment of the Commission are the magnitude of the storm cost regulatory asset, the timing of future rate proceedings, the form of recovery, and the financial integrity of the utility.

In this case, the storm cost regulatory asset is significant, caused in large part by the unprecedented damage and costs caused by Hurricane Helene. This argues for a longer amortization period to mitigate the effects on customer rates.

In this case, the Company’s base revenues were set through December 31, 2028 via the Stipulation approved by the Commission last year, subject to change only for recovery of the storm cost regulatory asset costs and refund of the PTC regulatory liabilities. This argues for a longer amortization period, properly timed so that it is consistent with the timing of the three-year alternative rate plans the Commission has approved in the last several base rate proceedings. If the three-year pattern is maintained, then the amortization period could be extended beyond May 31, 2030 (based on the 48 months requested by the Company) to coincide with that three-year pattern to December 31, 2031 (67 months), December 31, 2034 (103 months), or December 31, 2037 (139 months). The reason to set the amortization period to coincide with the three-year pattern is to ensure that the base revenue recovery does continue beyond the end of a three-year recovery period and result in excessive revenues to the Company and harm to customers.

In this case, the Company is financially healthy and does not require an unduly short amortization and recovery period to restore or maintain its financial integrity.

Q.	What is your recommendation?

A.	We recommend the Commission extend the amortization period through December 31, 2034 to 103 months from the requested 48 months and to coincide with the timing of the historic three-year rate case pattern ending on that date.

We also recommend the Commission adopt a condition that if the storm cost regulatory asset is fully amortized prior to the effective date of new base rates reset in base rate case proceeding, then the Company is required to defer the excess recoveries to a regulatory liability for future refund to customers.

Q.	What is the effect of your recommendation?

A.	The effect is an incremental reduction of $89.016 million in the requested base revenue increase after consideration of the prior adjustments that we recommend.

IX. The Company’s Definition of A Storm Event Reflects An Inordinately Low Threshold of $50,000

Q.	Describe the Company’s definition of storm event and how the dollar threshold affects the storm reserve and/or storm cost regulatory asset.

A.	The Company’s definition of a major storm event involves the repair/restoration of its system for incremental costs exceeding only $50,000 and even for other emergency situations. The full definition is found in the Company’s Storm Accounting Guidelines and replicated below:

The following procedure should be followed in the event of a major storm that damages Georgia Power’s Distribution, Transmission, or Generation systems, and other emergency situations described below.

A major storm is defined as a storm where the cost to repair / restore the systems to normal operating conditions will exceed $50,000 of incremental costs including labor, materials and other directly related incremental costs. These procedures will be followed by all Georgia Power Company personnel involved in accounting for major storm costs. Questions regarding Major Storm Declarations should be directed to the Storm Center Operations Manager.

Other emergency situations covered by this procedure include localized storms not meeting the requirements to be classified as a major storm; holding personnel over as a contingency for possible storm activity; load shed contingency actions in the event of major system problems; and other emergency situations determined by the Southern Company Security Council. For each of the situations described above, the costs associated with them should be charged to the applicable project (will be provided via storm declaration), as well as the business units organization code.

Once a major storm is declared by the Company, 100% of the incremental costs associated with the repair/restoration of the system for that storm are recorded directly to the storm reserve/storm cost regulatory asset. The net balance associated with all major storms is defined as a storm reserve if the net balance in the storm reserve is a liability, while it is defined as a storm cost regulatory asset if the net balance in the storm reserve is an asset. If the total costs for a storm event were $45,000, the storm would not be declared as a major storm event and none of those costs would be recorded to the storm reserve/storm cost regulatory asset. If the total costs for a storm event were $100,000, the storm would be declared as a major storm event and the entire $100,000 would be recorded to the storm reserve/storm cost regulatory asset.

Q.	Under the Company’s definition of a major storm event, does the storm have to be a named storm?

A.	No. In fact, there were numerous storms during the 2022-2025 review period declared as major storms that were unnamed. The Company’s application details the total costs for such storms during this period. Total costs recorded to the storm cost regulatory asset for these storms were $191.770 million at December 31, 2025. The Company did not identify or provide the costs for each declared, but unnamed, major storm event that comprise the amount deferred to the storm cost regulatory asset.

Q.	Is the $50,000 threshold for a storm event to be declared a major storm event inordinately low?

A.	Yes. The $50,000 threshold can be met very quickly and is extremely low for such a large utility. Assume four outside line contractor crews of four workers each from one vendor are involved with storm restoration for one full day. Assume also that the standard 16-hour storm event day is required at an average billing rate of $230 per hour (including labor and equipment rates). The incremental storm costs from this restoration event would be $58,880 (16 workers x 16 hours x $230 per hour). That amount is before the addition of material costs and Georgia Power labor costs needed to supervise the restoration event. Storm events such as these are both frequent and recurring and are more akin to routine expenses. They might only impact a few hundred customers in one small region of Georgia Power’s large service territory and involve a relatively small number of customer minutes of interruption.

Q.	How does the Company’s $50,000 threshold compare to other utilities?

A.	It is extremely low. The Company’s threshold is much lower than other utilities that are much smaller. The Company has approximately 2,700,000 customers and a $50,000 threshold. In contrast, Kentucky Power Company has only 163,000 customers and a $2 million threshold. New York State Electric & Gas Corporation (NYSEG) has approximately 894,000 customers and a $750,000 threshold. Rochester Gas and Electric Corporation (RG&E) has approximately 378,500 customers and a $500,000 threshold.

Q.	What do you conclude about the Company’s definition of a major storm event?

A.	The Company’s definition of a major storm event should reflect a higher threshold to reflect the fact that minor and unnamed storm events are frequent and recurring. These events should be considered and managed as routine expenses to streamline and limit the costs deferred to the storm reserve to more significant weather events that require enhanced response activities and incur higher costs. They definitely should not be considered extraordinary or nonrecurring costs and should be considered as part of the base rate planning process. In addition, only incremental costs above that threshold amount should be allowed to be deferred.

Q.	What is your recommendation?

A.	We recommend the Commission set the major storm declaration threshold to a minimum of $2 million per storm event before the Company is allowed to defer the costs over that threshold to the storm reserve/storm cost regulatory asset. The Company would record all costs below that threshold as operations and maintenance (O&M) expenses and recover those costs in base revenues. This is a prospective change and does not impact the storm cost regulatory asset recovery requested in this proceeding.

X. The Commission Should Deny The Company’s Request to Increase The Storm Expense Accrual For Future Storms By $69.835 Million In This Proceeding And Address ChangEs In FUTURE COMPREHENSIVE BASE RATE PROCEEDINGS

Q.	Describe the Company’s request to increase the storm expense accrual for future storms in this proceeding.

A.	As we noted previously, the Company seeks to expand the scope of this proceeding to increase the storm expense accrual for future storm costs from the present $31.419 million recovered in base revenues to $101.254 million, an increase of $69.835 million.

Q.	Did the Stipulation approved by the Commission last year include consideration of the storm expense accrual for future storm costs in this limited storm cost recovery proceeding?

A.	No. The Stipulation addressed only the recovery of the storm cost regulatory asset. In the Commission Order approving the Stipulation under Findings of Fact 2, the Commission described its understanding of the scope of this limited storm cost recovery proceeding as follows:

The Company agrees to no adjustment to base rates, with any under-recovered storm costs considered in a separate proceeding to be filed in 2026.

The Settlement Agreement states that base rates will not be adjusted in 2026, 2027, and 2028. The rate freeze ensures that customer rates are predictable and stable. The Company agrees to continue the amortization of liabilities and regulatory assets approved by the Commission in its 2022 Rate Case Settlement Agreement. Joint Petitioners agree to allow the Company to recover its reasonable and prudent under-recovered storm damage costs that result from major storms, such as from Hurricane Helen. The Settlement Agreement allows for consideration of the recovery to be considered through fully litigated and narrow proceedings, which are to take place in 2026.

The Stipulation (referred to as the “Settlement Agreement” in the Commission Order) itself approved by the Commission addressed only the recovery of the storm cost regulatory asset. The Stipulation does not address changes in the storm damage expense accrual for future storm costs. It addresses only the recovery of storm damage costs incurred through December 31, 2025 and the related changes in the storm damage accrual to recover those costs. The relevant portion of the Stipulation states:

The Company will be allowed to recover actual reasonable and prudent storm damage cost incurred through December 31, 2025, that exceeds the amount of the annual storm damage accrual approved in the Order Adopting Settlement Agreement as Modified. The Company will file for the recovery of under-recovered storm damage cost no sooner than February 1, 2026, and no later than July I, 2026, with new rates effective the 1st of the month following 90 days after the request for recovery. The Company's filing will include at a minimum pre-filed direct testimony and the documentation supporting the request for changes in the storm damage accrual as well as the proposed period over which to allow recovery of the under-recovered storm damage balance. The Commission shall determine the rates, the period over which underrecovered storm costs will be recovered, and any other issues the Commission deem necessary to address the limited issue of storm damage cost recovery.

Q.	What is your recommendation?

A. 	We recommend the Commission deny the request to increase the storm expense accrual for future storm costs in this proceeding. The Company’s request to increase the storm expense accrual for future storm costs is separate and apart from the Company’s request to recover the “actual reasonable and prudent storm damage cost through December 31, 2025” and is outside the express scope of this proceeding reflected in the Commission’s Order and the Stipulation itself.

The request to increase the storm damage expense accrual for future storm costs is properly addressed in the context of a base rate proceeding wherein all revenues and all costs are considered on a comprehensive basis rather than on a selective basis. The Company is not harmed or benefited as a result of this recommendation. If actual storm expenses are more or less than the storm expense accrual presently reflected in the base revenues, then the under or over recovery, respectively, will be captured in the storm reserve for Commission consideration recovery or refund in a future base rate proceeding.

Q.	What is the effect of your recommendation?

A.	The effect is an incremental reduction of $69.835 million in the requested base revenue increase after consideration of the prior adjustments that we recommend.

Q.	Does this conclude your testimony?

A.	Yes.

BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S 2022 RATE CASE: STORM DAMAGE RECOVERY APPLICATION | DOCKET NO. 44280 |
| --- | --- |

|  | EXHIBIT |  |
| --- | --- | --- |
|  | STF-NKF-1 |  |

Summary of Educational and Professional Experience of Tom J. Newsome

Mr. Newsome received a Bachelor of Chemical Engineering with certificates in Pulp & Paper and Polymers from the Georgia Institute of Technology in June 1986.  In 1994, Mr. Newsome passed both required examinations and received a professional engineering license (PE) from the State of North Carolina. Mr. Newsome received a Master of Science in Business Economics and a Master of Science in Finance from Georgia State University in August 1996 and June 1997, respectively. Mr. Newsome is the recipient of the George J. Malanos Graduate Award for Academic Excellence for completing the finance program with a 4.0 grade-point average. In 2003, Mr. Newsome received Chartered Financial Analyst (CFA) designation from the CFA Institute after successfully completing three six-hour examinations on security analysis and portfolio management.

After graduation from Georgia Tech, Mr. Newsome worked as plant/process engineer for Shaw Industries, a carpet manufacturer. In April 1988, Mr. Newsome joined Weatherly, Inc., engineering and construction firm specializing in fertilizer plants, as a process engineer. Mr. Newsome’s primary responsibilities were process design and plant start-ups, including start-ups in Korea and India. Mr. Newsome joined Midrex Direction Reduction Corp., an applied research, engineering and construction firm with proprietary iron ore processing plant technology in March 1993 as a process engineer. Mr. Newsome duties were similar to those at Weatherly, including assisting in the start-up of the world’s largest Direct Reduction Iron plant in India.

Following graduation from graduate school at Georgia State, Mr. Newsome joined Georgia Gulf Corporation in 1997 as a corporate development analyst. While at Georgia Gulf, Mr. Newsome performed financial analysis and modeling for natural gas purchasing/hedging program, developed a “make-or-buy” model for methanol business, performed financial modeling for an acquisition, and calculated and summarized the financial performance of prior capital investments. In 1999, Mr. Newsome joined FMV Opinions, Inc. as a business valuation analyst and valued private companies for gift and estate tax, transactional and management planning purposes.

Mr. Newsome joined the Georgia Public Service Commission (“Commission”) in January 2005 as a Financial Analyst/Economist. Mr. Newsome was promoted to Director of Utility Finance in 2008.

Mr. Newsome has testified in twenty six Georgia Power Company (“Company” or “Georgia Power”) proceedings before the Commission.  Mr. Newsome’s most recent testimony was in Dockets  56298 and 56310 relating to the Company’s 2029-20231 All Source RTP and Supplemental Capacity Resources.  Prior to that, Mr. Newsome testified in Dockets 56002 and 56003 related to the Company’s 2025 IRP. Prior to that, Mr. Newsome testified in Docket 55378 in 2023 IRP Update. Prior to that, Mr. Newsome testified in Docket 29849 in 28th Vogtle Construction Monitoring (“VCM”). Prior to that, Mr. Newsome’s testified in Docket 44902 Fuel Cost Recovery (FCR-26). Prior to that Mr. Newsome’s testified in Docket 29849 26th and 27th Vogtle Construction Monitoring (“VCM”). Prior to that Mr. Newsome testified in Docket 44160 2022 Integrated Resources Planning on supply side resources. Prior to that Mr. Newsome testified in Docket 29849 23rd Vogtle Construction Monitoring (“VCM”), 24th VCM and 25th VCM on Vogtle economics. Prior to that was testimony in 22nd VCM and in Docket 43011 Fuel Cost Recovery (FCR-25) on the Company’s hedging program and certain other issues. Prior to that Mr. Newsome’s testified in Docket 29849 20th / 21st Vogtle Construction Monitoring (“VCM”) on Vogtle economics. Prior to that Mr. Newsome’s testified in Docket 42310 Georgia Power Company’s 2019 Integrated Resource Plan on supply side and certain other issues. Prior to that testimony Mr. Newsome testified in Docket 29849 19th Vogtle Construction Monitoring (“VCM”), 18th VCM and 17th VCM on the economics of continuing Vogtle 3 and 4 construction and provided the Commission policy recommendations to protect ratepayers. Prior to testifying in the 17th VCM Mr. Newsome testified in the 2016 Integrated Resource Plan on the Company’s requested to capitalize cost for investigation of new nuclear units. Mr. Newsome’s testified in Docket No. 39638 Fuel Cost Recovery (FCR-24) on the Company’s natural gas hedging program. In Docket No. 22403, Mr. Newsome addressed Georgia Power Company’s natural gas hedging program and in Docket No. 24506 Mr. Newsome testified on the application of AFUDC accounting for calculating financing cost of capital projects. In Docket No. 27800, Certification of Plant Vogtle Expansion, Mr. Newsome addressed the sources, impact and mitigation of financial risk from the construction and operation of new nuclear units at Plant Vogtle.  Mr. Newsome testified in Docket No. 29849 concerning Georgia Power’s First Semi-annual Construction Monitoring Report on Plant Vogtle expansion.  Mr. Newsome evaluated the economic analysis performed by Georgia Power and developed Staff’s own independent economic and risk analysis of the Project. In the Second Vogtle Semi-annual hearing, Mr. Newsome testified on the Company’s proposal to change how escalation on certain project cost was calculated (Amendment 3).  In the Third Vogtle Semiannual hearing and in separate proceeding, Adoption of a Risk Sharing Mechanism, Mr. Newsome testified on Staff’s revised risk sharing mechanism for Vogtle 3 & 4.  In Docket No. 28945 Fuel Cost Recovery FCR–21, Mr. Newsome testified on seasonal rates.  Mr. Newsome also presented cost of equity testimony in Atmos Energy Corporation’s Rate Case in Docket No. 30442 and Generic Proceeding to Implement House Bill 168 (small telephone companies) in Docket No. 32235 in 2011 and 2018. Mr. Newsome provided testimony before the Commission in Georgia Power’s 2013 Base Rate Case in Docket No. 36989 on the Company’s projected cost of debt for 2014 – 2016. Mr. Newsome’s primarily responsibility, prior to presenting testimony in these dockets, has been performing analyses of the parties’ cost of equity capital positions in Docket Nos. 18638 (Atlanta Gas Light Company 2004/2005 Rate Case), 19758 (Savannah Electric and Power Company 2004 Rate Case), 20298 (Atmos Energy Corporation - Georgia Division 2005 Rate Case), 25060 (Georgia Power Co. 2007 Rate Case) and 27163 (Atmos Energy Corporation - Georgia Division 2008 Rate Case) and developing the Advisory PIA Staff’s cost of equity recommendation to the Commission.

BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S 2022 RATE CASE: STORM DAMAGE RECOVERY APPLICATION | DOCKET NO. 44280 |
| --- | --- |

|  | EXHIBIT |  |
| --- | --- | --- |
|  | STF-NKF-2 |  |

# EDUCATION

University of Toledo, BBA

Accounting

University of Toledo, MBA

Luther Rice University, MA

PROFESSIONAL CERTIFICATIONS

Certified Public Accountant (CPA)

Certified Management Accountant (CMA)

Chartered Global Management Accountant (CGMA)

PROFESSIONAL AFFILIATIONS

American Institute of Certified Public Accountants

Georgia Society of Certified Public Accountants

Institute of Management Accountants

Society of Depreciation Professionals

Mr. Kollen has more than forty years of utility industry experience in the financial, rate, tax, and planning areas.  He specializes in revenue requirements analyses, taxes, evaluation of rate and financial impacts of traditional and nontraditional ratemaking, utility mergers/acquisition and diversification.  Mr. Kollen has expertise in proprietary and nonproprietary software systems used by utilities for budgeting, rate case support and strategic and financial planning.

EXPERIENCE

1986 to

Present:	J. Kennedy and Associates, Inc.:  Vice President and Principal.  Responsible for utility stranded cost analysis, revenue requirements analysis, cash flow projections and solvency, financial and cash effects of traditional and nontraditional ratemaking, and research, speaking and writing on the effects of tax law changes.  Testimony before Connecticut, Florida, Georgia, Indiana, Louisiana, Kentucky, Maine, Maryland, Minnesota, New York, North Carolina, Ohio, Pennsylvania, Tennessee, Texas, West Virginia and Wisconsin state regulatory commissions and the Federal Energy Regulatory Commission.

1983 to

1986:		Energy Management Associates:  Lead Consultant.

Consulting in the areas of strategic and financial planning, traditional and nontraditional ratemaking, rate case support and testimony, diversification and generation expansion planning.  Directed consulting and software development projects utilizing PROSCREEN II and ACUMEN proprietary software products.  Utilized ACUMEN detailed corporate simulation system, PROSCREEN II strategic planning system and other custom developed software to support utility rate case filings including test year revenue requirements, rate base, operating income and pro-forma adjustments.  Also utilized these software products for revenue simulation, budget preparation and cost-of-service analyses.

1976 to

1983:		The Toledo Edison Company:  Planning Supervisor.

Responsible for financial planning activities including generation expansion planning, capital and expense budgeting, evaluation of tax law changes, rate case strategy and support and computerized financial modeling using proprietary and nonproprietary software products.  Directed the modeling and evaluation of planning alternatives including:

Rate phase-ins.

Construction project cancellations and write-offs.

Construction project delays.

Capacity swaps.

Financing alternatives.

Competitive pricing for off-system sales.

Sale/leasebacks.

CLIENTS SERVED

Industrial Companies and Groups

Air Products and Chemicals, Inc.

Airco Industrial Gases

Alcan Aluminum

Armco Advanced Materials Co.

Armco Steel

Bethlehem Steel

CF&I Steel, L.P.

Climax Molybdenum Company

Connecticut Industrial Energy Consumers

ELCON

Enron Gas Pipeline Company

Florida Industrial Power Users Group

Gallatin Steel

General Electric Company

GPU Industrial Intervenors

Indiana Industrial Group

Industrial Consumers for

Fair Utility Rates - Indiana

Industrial Energy Consumers - Ohio

Kentucky Industrial Utility Customers, Inc.

Kimberly-Clark Company

Lehigh Valley Power Committee

Maryland Industrial Group

Multiple Intervenors (New York)

National Southwire

North Carolina Industrial

Energy Consumers

Occidental Chemical Corporation

Ohio Energy Group

Ohio Industrial Energy Consumers

Ohio Manufacturers Association

Philadelphia Area Industrial Energy

Users Group

PSI Industrial Group

Smith Cogeneration

Taconite Intervenors (Minnesota)

West Penn Power Industrial Intervenors

West Virginia Energy Users Group

Westvaco Corporation

Regulatory Commissions and
Government Agencies

Cities in Texas-New Mexico Power Company’s Service Territory

Cities in AEP Texas Central Company’s Service Territory

Cities in AEP Texas North Company’s Service Territory

City of Austin

Georgia Public Service Commission Staff

Florida Office of Public Counsel

Indiana Office of Utility Consumer Counsel

Kentucky Office of Attorney General

Louisiana Public Service Commission

Louisiana Public Service Commission Staff

Maine Office of Public Advocate

New York City

New York State Energy Office

South Carolina Office of Regulatory Staff

Texas Office of Public Utility Counsel

Utah Office of Consumer Services

Utilities

Allegheny Power System

Atlantic City Electric Company

Carolina Power & Light Company

Cleveland Electric Illuminating Company

Delmarva Power & Light Company

Duquesne Light Company

General Public Utilities

Georgia Power Company

Middle South Services

Nevada Power Company

Niagara Mohawk Power Corporation

Otter Tail Power Company

Pacific Gas & Electric Company

Public Service Electric & Gas

Public Service of Oklahoma

Rochester Gas and Electric

Savannah Electric & Power Company

Seminole Electric Cooperative

Southern California Edison

Talquin Electric Cooperative

Tampa Electric

Texas Utilities

Toledo Edison Company

| Date | Case | Jurisdict. | Party | Utility | Subject |
| --- | --- | --- | --- | --- | --- |
| 10/86 | U-17282 Interim | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Cash revenue requirements financial solvency. |
| 11/86 | U-17282 Interim Rebuttal | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Cash revenue requirements financial solvency. |
| 12/86 | 9613 | KY | Attorney General Div. of Consumer Protection | Big Rivers Electric Corp. | Revenue requirements accounting adjustments financial workout plan. |
| 1/87 | U-17282 Interim | LA 19th Judicial District Ct. | Louisiana Public Service Commission Staff | Gulf States Utilities | Cash revenue requirements, financial solvency. |
| 3/87 | General Order 236 | WV | West Virginia Energy Users' Group | Monongahela Power Co. | Tax Reform Act of 1986. |
| 4/87 | U-17282 Prudence | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Prudence of River Bend 1, economic analyses, cancellation studies. |
| 4/87 | M-100 Sub 113 | NC | North Carolina Industrial Energy Consumers | Duke Power Co. | Tax Reform Act of 1986. |
| 5/87 | 86-524-E-SC | WV | West Virginia Energy Users' Group | Monongahela Power Co. | Revenue requirements, Tax Reform Act of 1986. |
| 5/87 | U-17282 Case In Chief | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, River Bend 1 phase-in plan, financial solvency. |
| 7/87 | U-17282 Case In Chief Surrebuttal | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, River Bend 1 phase-in plan, financial solvency. |
| 7/87 | U-17282 Prudence Surrebuttal | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Prudence of River Bend 1, economic analyses, cancellation studies. |
| 7/87 | 86-524 E-SC Surrebuttal | WV | West Virginia Energy Users' Group | Monongahela Power Co. | Revenue requirements, Tax Reform Act of 1986. |
| 8/87 | 9885 | KY | Attorney General Div. of Consumer Protection | Big Rivers Electric Corp. | Financial workout plan. |
| 8/87 | E-015/GR-87-223 | MN | Taconite Intervenors | Minnesota Power & Light Co. | Revenue requirements, O&M expense, Tax Reform Act of 1986. |
| 10/87 | 870220-EI | FL | Occidental Chemical Corp. | Florida Power Corp. | Revenue requirements, O&M expense, Tax Reform Act of 1986. |
| 11/87 | 87-07-01 | CT | Connecticut Industrial Energy Consumers | Connecticut Light & Power Co. | Tax Reform Act of 1986. |
| 1/88 | U-17282 | LA 19th Judicial District Ct. | Louisiana Public Service Commission | Gulf States Utilities | Revenue requirements, River Bend 1 phase-in plan, rate of return. |
| 2/88 | 9934 | KY | Kentucky Industrial Utility Customers | Louisville Gas & Electric Co. | Economics of Trimble County, completion. |
| 2/88 | 10064 | KY | Kentucky Industrial Utility Customers | Louisville Gas & Electric Co. | Revenue requirements, O&M expense, capital structure, excess deferred income taxes. |
| 5/88 | 10217 | KY | Alcan Aluminum National Southwire | Big Rivers Electric Corp. | Financial workout plan. |
| 5/88 | M-87017-1C001 | PA | GPU Industrial Intervenors | Metropolitan Edison Co. | Nonutility generator deferred cost recovery. |
| 5/88 | M-87017-2C005 | PA | GPU Industrial Intervenors | Pennsylvania Electric Co. | Nonutility generator deferred cost recovery. |
| 6/88 | U-17282 | LA 19th Judicial District Ct. | Louisiana Public Service Commission | Gulf States Utilities | Prudence of River Bend 1 economic analyses, cancellation studies, financial modeling. |
| 7/88 | M-87017-1C001 Rebuttal | PA | GPU Industrial Intervenors | Metropolitan Edison Co. | Nonutility generator deferred cost recovery, SFAS No. 92. |
| 7/88 | M-87017-2C005 Rebuttal | PA | GPU Industrial Intervenors | Pennsylvania Electric Co. | Nonutility generator deferred cost recovery, SFAS No. 92. |
| 9/88 | 88-05-25 | CT | Connecticut Industrial Energy Consumers | Connecticut Light & Power Co. | Excess deferred taxes, O&M expenses. |
| 9/88 | 10064 Rehearing | KY | Kentucky Industrial Utility Customers | Louisville Gas & Electric Co. | Premature retirements, interest expense. |
| 10/88 | 88-170-EL-AIR | OH | Ohio Industrial Energy Consumers | Cleveland Electric Illuminating Co. | Revenue requirements, phase-in, excess deferred taxes, O&M expenses, financial considerations, working capital. |
| 10/88 | 88-171-EL-AIR | OH | Ohio Industrial Energy Consumers | Toledo Edison Co. | Revenue requirements, phase-in, excess deferred taxes, O&M expenses, financial considerations, working capital. |
| 10/88 | 8800-355-EI | FL | Florida Industrial Power Users' Group | Florida Power & Light Co. | Tax Reform Act of 1986, tax expenses, O&M expenses, pension expense (SFAS No. 87). |
| 10/88 | 3780-U | GA | Georgia Public Service Commission Staff | Atlanta Gas Light Co. | Pension expense (SFAS No. 87). |
| 11/88 | U-17282 Remand | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Rate base exclusion plan (SFAS No. 71). |
| 12/88 | U-17970 | LA | Louisiana Public Service Commission Staff | AT&T Communications of South Central States | Pension expense (SFAS No. 87). |
| 12/88 | U-17949 Rebuttal | LA | Louisiana Public Service Commission Staff | South Central Bell | Compensated absences (SFAS No. 43), pension expense (SFAS No. 87), Part 32, income tax normalization. |
| 2/89 | U-17282 Phase II | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, phase-in of River Bend 1, recovery of canceled plant. |
| 6/89 | 881602-EU 890326-EU | FL | Talquin Electric Cooperative | Talquin/City of Tallahassee | Economic analyses, incremental cost-of-service, average customer rates. |
| 7/89 | U-17970 | LA | Louisiana Public Service Commission Staff | AT&T Communications of South Central States | Pension expense (SFAS No. 87), compensated absences (SFAS No. 43), Part 32. |
| 8/89 | 8555 | TX PUCT | Occidental Chemical Corp. | Houston Lighting & Power Co. | Cancellation cost recovery, tax expense, revenue requirements. |
| 8/89 | 3840-U | GA | Georgia Public Service Commission Staff | Georgia Power Co. | Promotional practices, advertising, economic development. |
| 9/89 | U-17282 Phase II Detailed | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, detailed investigation. |
| 10/89 | 8880 | TX PUCT | Enron Gas Pipeline | Texas-New Mexico Power Co. | Deferred accounting treatment, sale/leaseback. |
| 10/89 | 8928 | TX PUCT | Enron Gas Pipeline | Texas-New Mexico Power Co. | Revenue requirements, imputed capital structure, cash working capital. |
| 10/89 | R-891364 | PA | Philadelphia Area Industrial Energy Users Group | Philadelphia Electric Co. | Revenue requirements. |
| 11/89 12/89 | R-891364 Surrebuttal (2 Filings) | PA | Philadelphia Area Industrial Energy Users Group | Philadelphia Electric Co. | Revenue requirements, sale/leaseback. |
| 1/90 | U-17282 Phase II Detailed Rebuttal | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements, detailed investigation. |
| 1/90 | U-17282 Phase III | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Phase-in of River Bend 1, deregulated asset plan. |
| 3/90 | 890319-EI | FL | Florida Industrial Power Users Group | Florida Power & Light Co. | O&M expenses, Tax Reform Act of 1986. |
| 4/90 | 890319-EI Rebuttal | FL | Florida Industrial Power Users Group | Florida Power & Light Co. | O&M expenses, Tax Reform Act of 1986. |
| 4/90 | U-17282 | LA 19th Judicial District Ct. | Louisiana Public Service Commission | Gulf States Utilities | Fuel clause, gain on sale of utility assets. |
| 9/90 | 90-158 | KY | Kentucky Industrial Utility Customers | Louisville Gas & Electric Co. | Revenue requirements, post-test year additions, forecasted test year. |
| 12/90 | U-17282 Phase IV | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Revenue requirements. |
| 3/91 | 29327, et. al. | NY | Multiple Intervenors | Niagara Mohawk Power Corp. | Incentive regulation. |
| 5/91 | 9945 | TX PUCT | Office of Public Utility Counsel of Texas | El Paso Electric Co. | Financial modeling, economic analyses, prudence of Palo Verde 3. |
| 9/91 | P-910511 P-910512 | PA | Allegheny Ludlum Corp., Armco Advanced Materials Co., The West Penn Power Industrial Users' Group | West Penn Power Co. | Recovery of CAAA costs, least cost financing. |
| 9/91 | 91-231-E-NC | WV | West Virginia Energy Users Group | Monongahela Power Co. | Recovery of CAAA costs, least cost financing. |
| 11/91 | U-17282 | LA | Louisiana Public Service Commission Staff | Gulf States Utilities | Asset impairment, deregulated asset plan, revenue requirements. |
| 12/91 | 91-410-EL-AIR | OH | Air Products and Chemicals, Inc., Armco Steel Co., General Electric Co., Industrial Energy Consumers | Cincinnati Gas & Electric Co. | Revenue requirements, phase-in plan. |
| 12/91 | PUC Docket 10200 | TX PUCT | Office of Public Utility Counsel of Texas | Texas-New Mexico Power Co. | Financial integrity, strategic planning, declined business affiliations. |
| 5/92 | 910890-EI | FL | Occidental Chemical Corp. | Florida Power Corp. | Revenue requirements, O&M expense, pension expense, OPEB expense, fossil dismantling, nuclear decommissioning. |
| 8/92 | R-00922314 | PA | GPU Industrial Intervenors | Metropolitan Edison Co. | Incentive regulation, performance rewards, purchased power risk, OPEB expense. |
| 9/92 | 92-043 | KY | Kentucky Industrial Utility Consumers | Generic Proceeding | OPEB expense. |
| 9/92 | 920324-EI | FL | Florida Industrial Power Users' Group | Tampa Electric Co. | OPEB expense. |
| 9/92 | 39348 | IN | Indiana Industrial Group | Generic Proceeding | OPEB expense. |
| 9/92 | 910840-PU | FL | Florida Industrial Power Users' Group | Generic Proceeding | OPEB expense. |
| 9/92 | 39314 | IN | Industrial Consumers for Fair Utility Rates | Indiana Michigan Power Co. | OPEB expense. |
| 11/92 | U-19904 | LA | Louisiana Public Service Commission Staff | Gulf States Utilities /Entergy Corp. | Merger. |
| 11/92 | 8469 | MD | Westvaco Corp., Eastalco Aluminum Co. | Potomac Edison Co. | OPEB expense. |
| 11/92 | 92-1715-AU-COI | OH | Ohio Manufacturers Association | Generic Proceeding | OPEB expense. |
| 12/92 | R-00922378 | PA | Armco Advanced Materials Co., The WPP Industrial Intervenors | West Penn Power Co. | Incentive regulation, performance rewards, purchased power risk, OPEB expense. |
| 12/92 | U-19949 | LA | Louisiana Public Service Commission Staff | South Central Bell | Affiliate transactions, cost allocations, merger. |
| 12/92 | R-00922479 | PA | Philadelphia Area Industrial Energy Users' Group | Philadelphia Electric Co. | OPEB expense. |
| 1/93 | 8487 | MD | Maryland Industrial Group | Baltimore Gas & Electric Co., Bethlehem Steel Corp. | OPEB expense, deferred fuel, CWIP in rate base. |
| 1/93 | 39498 | IN | PSI Industrial Group | PSI Energy, Inc. | Refunds due to over-collection of taxes on Marble Hill cancellation. |
| 3/93 | 92-11-11 | CT | Connecticut Industrial Energy Consumers | Connecticut Light & Power Co | OPEB expense. |
| 3/93 | U-19904 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities /Entergy Corp. | Merger. |
| 3/93 | 93-01-EL-EFC | OH | Ohio Industrial Energy Consumers | Ohio Power Co. | Affiliate transactions, fuel. |
| 3/93 | EC92-21000 ER92-806-000 | FERC | Louisiana Public Service Commission Staff | Gulf States Utilities /Entergy Corp. | Merger. |
| 4/93 | 92-1464-EL-AIR | OH | Air Products Armco Steel Industrial Energy Consumers | Cincinnati Gas & Electric Co. | Revenue requirements, phase-in plan. |
| 4/93 | EC92-21000 ER92-806-000 (Rebuttal) | FERC | Louisiana Public Service Commission | Gulf States Utilities /Entergy Corp. | Merger. |
| 9/93 | 93-113 | KY | Kentucky Industrial Utility Customers | Kentucky Utilities | Fuel clause and coal contract refund. |
| 9/93 | 92-490, 92-490A, 90-360-C | KY | Kentucky Industrial Utility Customers and Kentucky Attorney General | Big Rivers Electric Corp. | Disallowances and restitution for excessive fuel costs, illegal and improper payments, recovery of mine closure costs. |
| 10/93 | U-17735 | LA | Louisiana Public Service Commission Staff | Cajun Electric Power Cooperative | Revenue requirements, debt restructuring agreement, River Bend cost recovery. |
| 1/94 | U-20647 | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Audit and investigation into fuel clause costs. |
| 4/94 | U-20647 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Nuclear and fossil unit performance, fuel costs, fuel clause principles and guidelines. |
| 4/94 | U-20647 (Supplemental Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Audit and investigation into fuel clause costs. |
| 5/94 | U-20178 | LA | Louisiana Public Service Commission Staff | Louisiana Power & Light Co. | Planning and quantification issues of least cost integrated resource plan. |
| 9/94 | U-19904 Initial Post-Merger Earnings Review | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | River Bend phase-in plan, deregulated asset plan, capital structure, other revenue requirement issues. |
| 9/94 | U-17735 | LA | Louisiana Public Service Commission Staff | Cajun Electric Power Cooperative | G&T cooperative ratemaking policies, exclusion of River Bend, other revenue requirement issues. |
| 10/94 | 3905-U | GA | Georgia Public Service Commission Staff | Southern Bell Telephone Co. | Incentive rate plan, earnings review. |
| 10/94 | 5258-U | GA | Georgia Public Service Commission Staff | Southern Bell Telephone Co. | Alternative regulation, cost allocation. |
| 11/94 | U-19904 Initial Post-Merger Earnings Review (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | River Bend phase-in plan, deregulated asset plan, capital structure, other revenue requirement issues. |
| 11/94 | U-17735 (Rebuttal) | LA | Louisiana Public Service Commission Staff | Cajun Electric Power Cooperative | G&T cooperative ratemaking policy, exclusion of River Bend, other revenue requirement issues. |
| 4/95 | R-00943271 | PA | PP&L Industrial Customer Alliance | Pennsylvania Power & Light Co. | Revenue requirements. Fossil dismantling, nuclear decommissioning. |
| 6/95 | 3905-U Rebuttal | GA | Georgia Public Service Commission | Southern Bell Telephone Co. | Incentive regulation, affiliate transactions, revenue requirements, rate refund. |
| 6/95 | U-19904 (Direct) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Gas, coal, nuclear fuel costs, contract prudence, base/fuel realignment. |
| 10/95 | 95-02614 | TN | Tennessee Office of the Attorney General Consumer Advocate | BellSouth Telecommunications, Inc. | Affiliate transactions. |
| 10/95 | U-21485 (Direct) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Nuclear O&M, River Bend phase-in plan, base/fuel realignment, NOL and AltMin asset deferred taxes, other revenue requirement issues. |
| 11/95 | U-19904 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. Division | Gas, coal, nuclear fuel costs, contract prudence, base/fuel realignment. |
| 11/95 12/95 | U-21485 (Supplemental Direct) U-21485 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Gulf States Utilities Co. | Nuclear O&M, River Bend phase-in plan, base/fuel realignment, NOL and AltMin asset deferred taxes, other revenue requirement issues. |
| 12/95 | 95-299-EL-AIR 95-300-EL-AIR | OH | Industrial Energy Consumers | The Toledo Edison Co., The Cleveland Electric Illuminating Co. | Competition, asset write-offs and revaluation, O&M expense, other revenue requirement issues. |
| 2/96 | PUC Docket 14965 | TX PUCT | Office of Public Utility Counsel | Central Power & Light | Nuclear decommissioning. |
| 5/96 | 95-485-LCS | NM | City of Las Cruces | El Paso Electric Co. | Stranded cost recovery, municipalization. |
| 7/96 | 8725 | MD | The Maryland Industrial Group and Redland Genstar, Inc. | Baltimore Gas & Electric Co., Potomac Electric Power Co., and Constellation Energy Corp. | Merger savings, tracking mechanism, earnings sharing plan, revenue requirement issues. |
| 9/96 11/96 | U-22092 U-22092 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | River Bend phase-in plan, base/fuel realignment, NOL and AltMin asset deferred taxes, other revenue requirement issues, allocation of regulated/nonregulated costs. |
| 10/96 | 96-327 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Environmental surcharge recoverable costs. |
| 2/97 | R-00973877 | PA | Philadelphia Area Industrial Energy Users Group | PECO Energy Co. | Stranded cost recovery, regulatory assets and liabilities, intangible transition charge, revenue requirements. |
| 3/97 | 96-489 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Co. | Environmental surcharge recoverable costs, system agreements, allowance inventory, jurisdictional allocation. |
| 6/97 | TO-97-397 | MO | MCI Telecommunications Corp., Inc., MCImetro Access Transmission Services, Inc. | Southwestern Bell Telephone Co. | Price cap regulation, revenue requirements, rate of return. |
| 6/97 | R-00973953 | PA | Philadelphia Area Industrial Energy Users Group | PECO Energy Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning. |
| 7/97 | R-00973954 | PA | PP&L Industrial Customer Alliance | Pennsylvania Power & Light Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning. |
| 7/97 | U-22092 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Depreciation rates and methodologies, River Bend phase-in plan. |
| 8/97 | 97-300 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas & Electric Co., Kentucky Utilities Co. | Merger policy, cost savings, surcredit sharing mechanism, revenue requirements, rate of return. |
| 8/97 | R-00973954 (Surrebuttal) | PA | PP&L Industrial Customer Alliance | Pennsylvania Power & Light Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning. |
| 10/97 | 97-204 | KY | Alcan Aluminum Corp. Southwire Co. | Big Rivers Electric Corp. | Restructuring, revenue requirements, reasonableness. |
| 10/97 | R-974008 | PA | Metropolitan Edison Industrial Users Group | Metropolitan Edison Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning, revenue requirements. |
| 10/97 | R-974009 | PA | Penelec Industrial Customer Alliance | Pennsylvania Electric Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning, revenue requirements. |
| 11/97 | 97-204 (Rebuttal) | KY | Alcan Aluminum Corp. Southwire Co. | Big Rivers Electric Corp. | Restructuring, revenue requirements, reasonableness of rates, cost allocation. |
| 11/97 | U-22491 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, other revenue requirement issues. |
| 11/97 | R-00973953 (Surrebuttal) | PA | Philadelphia Area Industrial Energy Users Group | PECO Energy Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning. |
| 11/97 | R-973981 | PA | West Penn Power Industrial Intervenors | West Penn Power Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, fossil decommissioning, revenue requirements, securitization. |
| 11/97 | R-974104 | PA | Duquesne Industrial Intervenors | Duquesne Light Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning, revenue requirements, securitization. |
| 12/97 | R-973981 (Surrebuttal) | PA | West Penn Power Industrial Intervenors | West Penn Power Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, fossil decommissioning, revenue requirements. |
| 12/97 | R-974104 (Surrebuttal) | PA | Duquesne Industrial Intervenors | Duquesne Light Co. | Restructuring, deregulation, stranded costs, regulatory assets, liabilities, nuclear and fossil decommissioning, revenue requirements, securitization. |
| 1/98 | U-22491 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, other revenue requirement issues. |
| 2/98 | 8774 | MD | Westvaco | Potomac Edison Co. | Merger of Duquesne, AE, customer safeguards, savings sharing. |
| 3/98 | U-22092 (Allocated Stranded Cost Issues) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Restructuring, stranded costs, regulatory assets, securitization, regulatory mitigation. |
| 3/98 | 8390-U | GA | Georgia Natural Gas Group, Georgia Textile Manufacturers Assoc. | Atlanta Gas Light Co. | Restructuring, unbundling, stranded costs, incentive regulation, revenue requirements. |
| 3/98 | U-22092 (Allocated Stranded Cost Issues) (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Restructuring, stranded costs, regulatory assets, securitization, regulatory mitigation. |
| 3/98 | U-22491 (Supplemental Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, other revenue requirement issues. |
| 10/98 | 97-596 | ME | Maine Office of the Public Advocate | Bangor Hydro- Electric Co. | Restructuring, unbundling, stranded costs, T&D revenue requirements. |
| 10/98 | 9355-U | GA | Georgia Public Service Commission Adversary Staff | Georgia Power Co. | Affiliate transactions. |
| 10/98 | U-17735 Rebuttal | LA | Louisiana Public Service Commission Staff | Cajun Electric Power Cooperative | G&T cooperative ratemaking policy, other revenue requirement issues. |
| 11/98 | U-23327 | LA | Louisiana Public Service Commission Staff | SWEPCO, CSW and AEP | Merger policy, savings sharing mechanism, affiliate transaction conditions. |
| 12/98 | U-23358 (Direct) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, tax issues, and other revenue requirement issues. |
| 12/98 | 98-577 | ME | Maine Office of Public Advocate | Maine Public Service Co. | Restructuring, unbundling, stranded cost, T&D revenue requirements. |
| 1/99 | 98-10-07 | CT | Connecticut Industrial Energy Consumers | United Illuminating Co. | Stranded costs, investment tax credits, accumulated deferred income taxes, excess deferred income taxes. |
| 3/99 | U-23358 (Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, tax issues, and other revenue requirement issues. |
| 3/99 | 98-474 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co. | Revenue requirements, alternative forms of regulation. |
| 3/99 | 98-426 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements, alternative forms of regulation. |
| 3/99 | 99-082 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co. | Revenue requirements. |
| 3/99 | 99-083 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements. |
| 4/99 | U-23358 (Supplemental Surrebuttal) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, tax issues, and other revenue requirement issues. |
| 4/99 | 99-03-04 | CT | Connecticut Industrial Energy Consumers | United Illuminating Co. | Regulatory assets and liabilities, stranded costs, recovery mechanisms. |
| 4/99 | 99-02-05 | CT | Connecticut Industrial Utility Customers | Connecticut Light and Power Co. | Regulatory assets and liabilities, stranded costs, recovery mechanisms. |
| 5/99 | 98-426 99-082 (Additional Direct) | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co. | Revenue requirements. |
| 5/99 | 98-474 99-083 (Additional Direct) | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements. |
| 5/99 | 98-426 98-474 (Response to Amended Applications) | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co., Kentucky Utilities Co. | Alternative regulation. |
| 6/99 | 97-596 | ME | Maine Office of Public Advocate | Bangor Hydro- Electric Co. | Request for accounting order regarding electric industry restructuring costs. |
| 7/99 | U-23358 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Affiliate transactions, cost allocations. |
| 7/99 | 99-03-35 | CT | Connecticut Industrial Energy Consumers | United Illuminating Co. | Stranded costs, regulatory assets, tax effects of asset divestiture. |
| 7/99 | U-23327 | LA | Louisiana Public Service Commission Staff | Southwestern Electric Power Co., Central and South West Corp, American Electric Power Co. | Merger Settlement and Stipulation. |
| 7/99 | 97-596 Surrebuttal | ME | Maine Office of Public Advocate | Bangor Hydro- Electric Co. | Restructuring, unbundling, stranded cost, T&D revenue requirements. |
| 7/99 | 98-0452-E-GI | WV | West Virginia Energy Users Group | Monongahela Power, Potomac Edison, Appalachian Power, Wheeling Power | Regulatory assets and liabilities. |
| 8/99 | 98-577 Surrebuttal | ME | Maine Office of Public Advocate | Maine Public Service Co. | Restructuring, unbundling, stranded costs, T&D revenue requirements. |
| 8/99 | 98-426 99-082 Rebuttal | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co. | Revenue requirements. |
| 8/99 | 98-474 98-083 Rebuttal | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements. |
| 8/99 | 98-0452-E-GI Rebuttal | WV | West Virginia Energy Users Group | Monongahela Power, Potomac Edison, Appalachian Power, Wheeling Power | Regulatory assets and liabilities. |
| 10/99 | U-24182 Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, affiliate transactions, tax issues, and other revenue requirement issues. |
| 11/99 | PUC Docket 21527 | TX PUCT | The Dallas-Fort Worth Hospital Council and Coalition of Independent Colleges and Universities | TXU Electric | Restructuring, stranded costs, taxes, securitization. |
| 11/99 | U-23358 Surrebuttal Affiliate Transactions Review | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Service company affiliate transaction costs. |
| 01/00 | U-24182 Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, affiliate transactions, tax issues, and other revenue requirement issues. |
| 04/00 | 99-1212-EL-ETP 99-1213-EL-ATA 99-1214-EL-AAM | OH | Greater Cleveland Growth Association | First Energy (Cleveland Electric Illuminating, Toledo Edison) | Historical review, stranded costs, regulatory assets, liabilities. |
| 05/00 | 2000-107 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Co. | ECR surcharge roll-in to base rates. |
| 05/00 | U-24182 Supplemental Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Affiliate expense proforma adjustments. |
| 05/00 | A-110550F0147 | PA | Philadelphia Area Industrial Energy Users Group | PECO Energy | Merger between PECO and Unicom. |
| 05/00 | 99-1658-EL-ETP | OH | AK Steel Corp. | Cincinnati Gas & Electric Co. | Regulatory transition costs, including regulatory assets and liabilities, SFAS 109, ADIT, EDIT, ITC. |
| 07/00 | PUC Docket 22344 | TX PUCT | The Dallas-Fort Worth Hospital Council and The Coalition of Independent Colleges and Universities | Statewide Generic Proceeding | Escalation of O&M expenses for unbundled T&D revenue requirements in projected test year. |
| 07/00 | U-21453 | LA | Louisiana Public Service Commission | SWEPCO | Stranded costs, regulatory assets and liabilities. |
| 08/00 | U-24064 | LA | Louisiana Public Service Commission Staff | CLECO | Affiliate transaction pricing ratemaking principles, subsidization of nonregulated affiliates, ratemaking adjustments. |
| 10/00 | SOAH Docket 473-00-1015 PUC Docket 22350 | TX PUCT | The Dallas-Fort Worth Hospital Council and The Coalition of Independent Colleges and Universities | TXU Electric Co. | Restructuring, T&D revenue requirements, mitigation, regulatory assets and liabilities. |
| 10/00 | R-00974104 Affidavit | PA | Duquesne Industrial Intervenors | Duquesne Light Co. | Final accounting for stranded costs, including treatment of auction proceeds, taxes, capital costs, switchback costs, and excess pension funding. |
| 11/00 | P-00001837 R-00974008 P-00001838 R-00974009 | PA | Metropolitan Edison Industrial Users Group Penelec Industrial Customer Alliance | Metropolitan Edison Co., Pennsylvania Electric Co. | Final accounting for stranded costs, including treatment of auction proceeds, taxes, regulatory assets and liabilities, transaction costs. |
| 12/00 | U-21453, U-20925, U-22092 (Subdocket C) Surrebuttal | LA | Louisiana Public Service Commission Staff | SWEPCO | Stranded costs, regulatory assets. |
| 01/01 | U-24993 Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Allocation of regulated and nonregulated costs, tax issues, and other revenue requirement issues. |
| 01/01 | U-21453, U-20925, U-22092 (Subdocket B) Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Industry restructuring, business separation plan, organization structure, hold harmless conditions, financing. |
| 01/01 | Case No. 2000-386 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas & Electric Co. | Recovery of environmental costs, surcharge mechanism. |
| 01/01 | Case No. 2000-439 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Recovery of environmental costs, surcharge mechanism. |
| 02/01 | A-110300F0095 A-110400F0040 | PA | Met-Ed Industrial Users Group, Penelec Industrial Customer Alliance | GPU, Inc. FirstEnergy Corp. | Merger, savings, reliability. |
| 03/01 | P-00001860 P-00001861 | PA | Met-Ed Industrial Users Group, Penelec Industrial Customer Alliance | Metropolitan Edison Co., Pennsylvania Electric Co. | Recovery of costs due to provider of last resort obligation. |
| 04/01 | U-21453, U-20925, U-22092 (Subdocket B) Settlement Term Sheet | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Business separation plan: settlement agreement on overall plan structure. |
| 04/01 | U-21453, U-20925, U-22092 (Subdocket B) Contested Issues | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Business separation plan: agreements, hold harmless conditions, separations methodology. |
| 05/01 | U-21453, U-20925, U-22092 (Subdocket B) Contested Issues Transmission and Distribution Rebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Business separation plan: agreements, hold harmless conditions, separations methodology. |
| 07/01 | U-21453, U-20925, U-22092 (Subdocket B) Transmission and Distribution Term Sheet | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Business separation plan: settlement agreement on T&D issues, agreements necessary to implement T&D separations, hold harmless conditions, separations methodology. |
| 10/01 | 14000-U | GA | Georgia Public Service Commission Adversary Staff | Georgia Power Company | Revenue requirements, Rate Plan, fuel clause recovery. |
| 11/01 | 14311-U Direct Panel with Bolin Killings | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co | Revenue requirements, revenue forecast, O&M expense, depreciation, plant additions, cash working capital. |
| 11/01 | U-25687 Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, capital structure, allocation of regulated and nonregulated costs, River Bend uprate. |
| 02/02 | PUC Docket 25230 | TX PUCT | The Dallas-Fort Worth Hospital Council and the Coalition of Independent Colleges and Universities | TXU Electric | Stipulation. Regulatory assets, securitization financing. |
| 02/02 | U-25687 Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, River Bend uprate. |
| 03/02 | 14311-U Rebuttal Panel with Bolin Killings | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Revenue requirements, earnings sharing plan, service quality standards. |
| 03/02 | 14311-U Rebuttal Panel with Michelle L. Thebert | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Revenue requirements, revenue forecast, O&M expense, depreciation, plant additions, cash working capital. |
| 03/02 | 001148-EI | FL | South Florida Hospital and Healthcare Assoc. | Florida Power & Light Co. | Revenue requirements. Nuclear life extension, storm damage accruals and reserve, capital structure, O&M expense. |
| 04/02 | U-25687 (Suppl. Surrebuttal) | LA | Louisiana Public Service Commission | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, River Bend uprate. |
| 04/02 | U-21453, U-20925 U-22092 (Subdocket C) | LA | Louisiana Public Service Commission | SWEPCO | Business separation plan, T&D Term Sheet, separations methodologies, hold harmless conditions. |
| 08/02 | EL01-88-000 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | System Agreement, production cost equalization, tariffs. |
| 08/02 | U-25888 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. and Entergy Louisiana, Inc. | System Agreement, production cost disparities, prudence. |
| 09/02 | 2002-00224 2002-00225 | KY | Kentucky Industrial Utilities Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Line losses and fuel clause recovery associated with off-system sales. |
| 11/02 | 2002-00146 2002-00147 | KY | Kentucky Industrial Utilities Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Environmental compliance costs and surcharge recovery. |
| 01/03 | 2002-00169 | KY | Kentucky Industrial Utilities Customers, Inc. | Kentucky Power Co. | Environmental compliance costs and surcharge recovery. |
| 04/03 | 2002-00429 2002-00430 | KY | Kentucky Industrial Utilities Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Extension of merger surcredit, flaws in Companies’ studies. |
| 04/03 | U-26527 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, capital structure, post-test year adjustments. |
| 06/03 | EL01-88-000 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | System Agreement, production cost equalization, tariffs. |
| 06/03 | 2003-00068 | KY | Kentucky Industrial Utility Customers | Kentucky Utilities Co. | Environmental cost recovery, correction of base rate error. |
| 11/03 | ER03-753-000 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Unit power purchases and sale cost-based tariff pursuant to System Agreement. |
| 11/03 | ER03-583-000, ER03-583-001, ER03-583-002 ER03-681-000, ER03-681-001 ER03-682-000, ER03-682-001, ER03-682-002 ER03-744-000, ER03-744-001 (Consolidated) | FERC | Louisiana Public Service Commission | Entergy Services, Inc., the Entergy Operating Companies, EWO Marketing, L.P, and Entergy Power, Inc. | Unit power purchases and sale agreements, contractual provisions, projected costs, levelized rates, and formula rates. |
| 12/03 | U-26527 Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, capital structure, post-test year adjustments. |
| 12/03 | 2003-0334 2003-0335 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Earnings Sharing Mechanism. |
| 12/03 | U-27136 | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, Inc. | Purchased power contracts between affiliates, terms and conditions. |
| 03/04 | U-26527 Supplemental Surrebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Revenue requirements, corporate franchise tax, conversion to LLC, capital structure, post-test year adjustments. |
| 03/04 | 2003-00433 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas & Electric Co. | Revenue requirements, depreciation rates, O&M expense, deferrals and amortization, earnings sharing mechanism, merger surcredit, VDT surcredit. |
| 03/04 | 2003-00434 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co. | Revenue requirements, depreciation rates, O&M expense, deferrals and amortization, earnings sharing mechanism, merger surcredit, VDT surcredit. |
| 03/04 | SOAH Docket 473-04-2459 PUC Docket 29206 | TX PUCT | Cities Served by Texas- New Mexico Power Co. | Texas-New Mexico Power Co. | Stranded costs true-up, including valuation issues, ITC, ADIT, excess earnings. |
| 05/04 | 04-169-EL-UNC | OH | Ohio Energy Group, Inc. | Columbus Southern Power Co. & Ohio Power Co. | Rate stabilization plan, deferrals, T&D rate increases, earnings. |
| 06/04 | SOAH Docket 473-04-4555 PUC Docket 29526 | TX PUCT | Houston Council for Health and Education | CenterPoint Energy Houston Electric | Stranded costs true-up, including valuation issues, ITC, EDIT, excess mitigation credits, capacity auction true-up revenues, interest. |
| 08/04 | SOAH Docket 473-04-4555 PUC Docket 29526 (Suppl Direct) | TX PUCT | Houston Council for Health and Education | CenterPoint Energy Houston Electric | Interest on stranded cost pursuant to Texas Supreme Court remand. |
| 09/04 | U-23327 Subdocket B | LA | Louisiana Public Service Commission Staff | SWEPCO | Fuel and purchased power expenses recoverable through fuel adjustment clause, trading activities, compliance with terms of various LPSC Orders. |
| 10/04 | U-23327 Subdocket A | LA | Louisiana Public Service Commission Staff | SWEPCO | Revenue requirements. |
| 12/04 | Case Nos. 2004-00321, 2004-00372 | KY | Gallatin Steel Co. | East Kentucky Power Cooperative, Inc., Big Sandy Recc, et al. | Environmental cost recovery, qualified costs, TIER requirements, cost allocation. |
| 01/05 | 30485 | TX PUCT | Houston Council for Health and Education | CenterPoint Energy Houston Electric, LLC | Stranded cost true-up including regulatory Central Co. assets and liabilities, ITC, EDIT, capacity auction, proceeds, excess mitigation credits, retrospective and prospective ADIT. |
| 02/05 | 18638-U | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Revenue requirements. |
| 02/05 | 18638-U Panel with Tony Wackerly | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Comprehensive rate plan, pipeline replacement program surcharge, performance based rate plan. |
| 02/05 | 18638-U Panel with Michelle Thebert | GA | Georgia Public Service Commission Adversary Staff | Atlanta Gas Light Co. | Energy conservation, economic development, and tariff issues. |
| 03/05 | Case Nos. 2004-00426, 2004-00421 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric | Environmental cost recovery, Jobs Creation Act of 2004 and §199 deduction, excess common equity ratio, deferral and amortization of nonrecurring O&M expense. |
| 06/05 | 2005-00068 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Co. | Environmental cost recovery, Jobs Creation Act of 2004 and §199 deduction, margins on allowances used for AEP system sales. |
| 06/05 | 050045-EI | FL | South Florida Hospital and Heallthcare Assoc. | Florida Power & Light Co. | Storm damage expense and reserve, RTO costs, O&M expense projections, return on equity performance incentive, capital structure, selective second phase post-test year rate increase. |
| 08/05 | 31056 | TX PUCT | Alliance for Valley Healthcare | AEP Texas Central Co. | Stranded cost true-up including regulatory assets and liabilities, ITC, EDIT, capacity auction, proceeds, excess mitigation credits, retrospective and prospective ADIT. |
| 09/05 | 20298-U | GA | Georgia Public Service Commission Adversary Staff | Atmos Energy Corp. | Revenue requirements, roll-in of surcharges, cost recovery through surcharge, reporting requirements. |
| 09/05 | 20298-U Panel with Victoria Taylor | GA | Georgia Public Service Commission Adversary Staff | Atmos Energy Corp. | Affiliate transactions, cost allocations, capitalization, cost of debt. |
| 10/05 | 04-42 | DE | Delaware Public Service Commission Staff | Artesian Water Co. | Allocation of tax net operating losses between regulated and unregulated. |
| 11/05 | 2005-00351 2005-00352 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric | Workforce Separation Program cost recovery and shared savings through VDT surcredit. |
| 01/06 | 2005-00341 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Co. | System Sales Clause Rider, Environmental Cost Recovery Rider. Net Congestion Rider, Storm damage, vegetation management program, depreciation, off-system sales, maintenance normalization, pension and OPEB. |
| 03/06 | PUC Docket 31994 | TX PUCT | Cities | Texas-New Mexico Power Co. | Stranded cost recovery through competition transition or change. |
| 05/06 | 31994 Supplemental | TX PUCT | Cities | Texas-New Mexico Power Co. | Retrospective ADFIT, prospective ADFIT. |
| 03/06 | U-21453, U-20925, U-22092 (Subdocket B) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Jurisdictional separation plan. |
| 03/06 | NOPR Reg 104385-OR | IRS | Alliance for Valley Health Care and Houston Council for Health Education | AEP Texas Central Company and CenterPoint Energy Houston Electric | Proposed Regulations affecting flow- through to ratepayers of excess deferred income taxes and investment tax credits on generation plant that is sold or deregulated. |
| 04/06 | U-25116 | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, Inc. | 2002-2004 Audit of Fuel Adjustment Clause Filings. Affiliate transactions. |
| 07/06 | R-00061366, Et. al. | PA | Met-Ed Ind. Users Group Pennsylvania Ind. Customer Alliance | Metropolitan Edison Co., Pennsylvania Electric Co. | Recovery of NUG-related stranded costs, government mandated program costs, storm damage costs. |
| 07/06 | U-23327 | LA | Louisiana Public Service Commission Staff | Southwestern Electric Power Co. | Revenue requirements, formula rate plan, banking proposal. |
| 08/06 | U-21453, U-20925, U-22092 (Subdocket J) | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc. | Jurisdictional separation plan. |
| 11/06 | 05CVH03-3375 Franklin County Court Affidavit | OH | Various Taxing Authorities (Non-Utility Proceeding) | State of Ohio Department of Revenue | Accounting for nuclear fuel assemblies as manufactured equipment and capitalized plant. |
| 12/06 | U-23327 Subdocket A Reply Testimony | LA | Louisiana Public Service Commission Staff | Southwestern Electric Power Co. | Revenue requirements, formula rate plan, banking proposal. |
| 03/07 | U-29764 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc., Entergy Louisiana, LLC | Jurisdictional allocation of Entergy System Agreement equalization remedy receipts. |
| 03/07 | PUC Docket 33309 | TX PUCT | Cities | AEP Texas Central Co. | Revenue requirements, including functionalization of transmission and distribution costs. |
| 03/07 | PUC Docket 33310 | TX PUCT | Cities | AEP Texas North Co. | Revenue requirements, including functionalization of transmission and distribution costs. |
| 03/07 | 2006-00472 | KY | Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative | Interim rate increase, RUS loan covenants, credit facility requirements, financial condition. |
| 03/07 | U-29157 | LA | Louisiana Public Service Commission Staff | Cleco Power, LLC | Permanent (Phase II) storm damage cost recovery. |
| 04/07 | U-29764 Supplemental and Rebuttal | LA | Louisiana Public Service Commission Staff | Entergy Gulf States, Inc., Entergy Louisiana, LLC | Jurisdictional allocation of Entergy System Agreement equalization remedy receipts. |
| 04/07 | ER07-682-000 Affidavit | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Allocation of intangible and general plant and A&G expenses to production and state income tax effects on equalization remedy receipts. |
| 04/07 | ER07-684-000 Affidavit | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Fuel hedging costs and compliance with FERC USOA. |
| 05/07 | ER07-682-000 Supplemental Affidavit | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Allocation of intangible and general plant and A&G expenses to production and account 924 effects on MSS-3 equalization remedy payments and receipts. |
| 06/07 | U-29764 | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, LLC, Entergy Gulf States, Inc. | Show cause for violating LPSC Order on fuel hedging costs. |
| 07/07 | 2006-00472 | KY | Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative | Revenue requirements, post-test year adjustments, TIER, surcharge revenues and costs, financial need. |
| 07/07 | ER07-956-000 Affidavit | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Storm damage costs related to Hurricanes Katrina and Rita and effects of MSS-3 equalization payments and receipts. |
| 10/07 | 05-UR-103 Direct | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company, Wisconsin Gas, LLC | Revenue requirements, carrying charges on CWIP, amortization and return on regulatory assets, working capital, incentive compensation, use of rate base in lieu of capitalization, quantification and use of Point Beach sale proceeds. |
| 10/07 | 05-UR-103 Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company, Wisconsin Gas, LLC | Revenue requirements, carrying charges on CWIP, amortization and return on regulatory assets, working capital, incentive compensation, use of rate base in lieu of capitalization, quantification and use of Point Beach sale proceeds. |
| 10/07 | 25060-U Direct | GA | Georgia Public Service Commission Public Interest Adversary Staff | Georgia Power Company | Affiliate costs, incentive compensation, consolidated income taxes, §199 deduction. |
| 11/07 | 06-0033-E-CN Direct | WV | West Virginia Energy Users Group | Appalachian Power Company | IGCC surcharge during construction period and post-in-service date. |
| 11/07 | ER07-682-000 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Functionalization and allocation of intangible and general plant and A&G expenses. |
| 01/08 | ER07-682-000 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Functionalization and allocation of intangible and general plant and A&G expenses. |
| 01/08 | 07-551-EL-AIR Direct | OH | Ohio Energy Group, Inc. | Ohio Edison Company, Cleveland Electric Illuminating Company, Toledo Edison Company | Revenue requirements. |
| 02/08 | ER07-956-000 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Functionalization of expenses, storm damage expense and reserves, tax NOL carrybacks in accounts, ADIT, nuclear service lives and effects on depreciation and decommissioning. |
| 03/08 | ER07-956-000 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and the Entergy Operating Companies | Functionalization of expenses, storm damage expense and reserves, tax NOL carrybacks in accounts, ADIT, nuclear service lives and effects on depreciation and decommissioning. |
| 04/08 | 2007-00562, 2007-00563 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas and Electric Co. | Merger surcredit. |
| 04/08 | 26837 Direct Bond, Johnson, Thebert, Kollen Panel | GA | Georgia Public Service Commission Staff | SCANA Energy Marketing, Inc. | Rule Nisi complaint. |
| 05/08 | 26837 Rebuttal Bond, Johnson, Thebert, Kollen Panel | GA | Georgia Public Service Commission Staff | SCANA Energy Marketing, Inc. | Rule Nisi complaint. |
| 05/08 | 26837 Suppl Rebuttal Bond, Johnson, Thebert, Kollen Panel | GA | Georgia Public Service Commission Staff | SCANA Energy Marketing, Inc. | Rule Nisi complaint. |
| 06/08 | 2008-00115 | KY | Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative, Inc. | Environmental surcharge recoveries, including costs recovered in existing rates, TIER. |
| 07/08 | 27163 Direct | GA | Georgia Public Service Commission Public Interest Advocacy Staff | Atmos Energy Corp. | Revenue requirements, including projected test year rate base and expenses. |
| 07/08 | 27163 Taylor, Kollen Panel | GA | Georgia Public Service Commission Public Interest Advocacy Staff | Atmos Energy Corp. | Affiliate transactions and division cost allocations, capital structure, cost of debt. |
| 08/08 | 6680-CE-170 Direct | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Power and Light Company | Nelson Dewey 3 or Colombia 3 fixed financial parameters. |
| 08/08 | 6680-UR-116 Direct | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Power and Light Company | CWIP in rate base, labor expenses, pension expense, financing, capital structure, decoupling. |
| 08/08 | 6680-UR-116 Rebuttal | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Power and Light Company | Capital structure. |
| 08/08 | 6690-UR-119 Direct | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Public Service Corp. | Prudence of Weston 3 outage, incentive compensation, Crane Creek Wind Farm incremental revenue requirement, capital structure. |
| 09/08 | 6690-UR-119 Surrebuttal | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Public Service Corp. | Prudence of Weston 3 outage, Section 199 deduction. |
| 09/08 | 08-935-EL-SSO, 08-918-EL-SSO | OH | Ohio Energy Group, Inc. | First Energy | Standard service offer rates pursuant to electric security plan, significantly excessive earnings test. |
| 10/08 | 08-917-EL-SSO | OH | Ohio Energy Group, Inc. | AEP | Standard service offer rates pursuant to electric security plan, significantly excessive earnings test. |
| 10/08 | 2007-00564, 2007-00565, 2008-00251 2008-00252 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Co., Kentucky Utilities Company | Revenue forecast, affiliate costs, ELG v ASL depreciation procedures, depreciation expenses, federal and state income tax expense, capitalization, cost of debt. |
| 11/08 | EL08-51 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Spindletop gas storage facilities, regulatory asset and bandwidth remedy. |
| 11/08 | 35717 | TX PUCT | Cities Served by Oncor Delivery Company | Oncor Delivery Company | Recovery of old meter costs, asset ADFIT, cash working capital, recovery of prior year restructuring costs, levelized recovery of storm damage costs, prospective storm damage accrual, consolidated tax savings adjustment. |
| 12/08 | 27800 | GA | Georgia Public Service Commission | Georgia Power Company | AFUDC versus CWIP in rate base, mirror CWIP, certification cost, use of short term debt and trust preferred financing, CWIP recovery, regulatory incentive. |
| 01/09 | ER08-1056 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Entergy System Agreement bandwidth remedy calculations, including depreciation expense, ADIT, capital structure. |
| 01/09 | ER08-1056 Supplemental Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Blytheville leased turbines; accumulated depreciation. |
| 02/09 | EL08-51 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Spindletop gas storage facilities regulatory asset and bandwidth remedy. |
| 02/09 | 2008-00409 Direct | KY | Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative, Inc. | Revenue requirements. |
| 03/09 | ER08-1056 Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Entergy System Agreement bandwidth remedy calculations, including depreciation expense, ADIT, capital structure. |
| 03/09 | U-21453, U-20925 U-22092 (Sub J) Direct | LA | Louisiana Public Service Commission Staff | Entergy Gulf States Louisiana, LLC | Violation of EGSI separation order, ETI and EGSL separation accounting, Spindletop regulatory asset. |
| 04/09 | Rebuttal |  |  |  |  |
| 04/09 | 2009-00040 Direct-Interim (Oral) | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Emergency interim rate increase; cash requirements. |
| 04/09 | PUC Docket 36530 | TX PUCT | State Office of Administrative Hearings | Oncor Electric Delivery Company, LLC | Rate case expenses. |
| 05/09 | ER08-1056 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Entergy System Agreement bandwidth remedy calculations, including depreciation expense, ADIT, capital structure. |
| 06/09 | 2009-00040 Direct- Permanent | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Revenue requirements, TIER, cash flow. |
| 07/09 | 080677-EI | FL | South Florida Hospital and Healthcare Association | Florida Power & Light Company | Multiple test years, GBRA rider, forecast assumptions, revenue requirement, O&M expense, depreciation expense, Economic Stimulus Bill, capital structure. |
| 08/09 | U-21453, U-20925, U-22092 (Subdocket J) Supplemental Rebuttal | LA | Louisiana Public Service Commission | Entergy Gulf States Louisiana, LLC | Violation of EGSI separation order, ETI and EGSL separation accounting, Spindletop regulatory asset. |
| 08/09 | 8516 and 29950 | GA | Georgia Public Service Commission Staff | Atlanta Gas Light Company | Modification of PRP surcharge to include infrastructure costs. |
| 09/09 | 05-UR-104 Direct and Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company | Revenue requirements, incentive compensation, depreciation, deferral mitigation, capital structure, cost of debt. |
| 09/09 | 09AL-299E Answer | CO | CF&I Steel, Rocky Mountain Steel Mills LP, Climax Molybdenum Company | Public Service Company of Colorado | Forecasted test year, historic test year, proforma adjustments for major plant additions, tax depreciation. |
| 09/09 | 6680-UR-117 Direct and Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Power and Light Company | Revenue requirements, CWIP in rate base, deferral mitigation, payroll, capacity shutdowns, regulatory assets, rate of return. |
| 10/09 | 09A-415E Answer | CO | Cripple Creek & Victor Gold Mining Company, et al. | Black Hills/CO Electric Utility Company | Cost prudence, cost sharing mechanism. |
| 10/09 | EL09-50 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Waterford 3 sale/leaseback accumulated deferred income taxes, Entergy System Agreement bandwidth remedy calculations. |
| 10/09 | 2009-00329 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Company, Kentucky Utilities Company | Trimble County 2 depreciation rates. |
| 12/09 | PUE-2009-00030 | VA | Old Dominion Committee for Fair Utility Rates | Appalachian Power Company | Return on equity incentive. |
| 12/09 | ER09-1224 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Hypothetical versus actual costs, out of period costs, Spindletop deferred capital costs, Waterford 3 sale/leaseback ADIT. |
| 01/10 | ER09-1224 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Hypothetical versus actual costs, out of period costs, Spindletop deferred capital costs, Waterford 3 sale/leaseback ADIT. |
| 01/10 | EL09-50 Rebuttal Supplemental Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Waterford 3 sale/leaseback accumulated deferred income taxes, Entergy System Agreement bandwidth remedy calculations. |
| 02/10 | ER09-1224 Final | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Hypothetical versus actual costs, out of period costs, Spindletop deferred capital costs, Waterford 3 sale/leaseback ADIT. |
| 02/10 | 30442 Wackerly-Kollen Panel | GA | Georgia Public Service Commission Staff | Atmos Energy Corporation | Revenue requirement issues. |
| 02/10 | 30442 McBride-Kollen Panel | GA | Georgia Public Service Commission Staff | Atmos Energy Corporation | Affiliate/division transactions, cost allocation, capital structure. |
| 02/10 | 2009-00353 | KY | Kentucky Industrial Utility Customers, Inc., Attorney General | Louisville Gas and Electric Company, Kentucky Utilities Company | Ratemaking recovery of wind power purchased power agreements. |
| 03/10 | 2009-00545 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Ratemaking recovery of wind power purchased power agreement. |
| 03/10 | E015/GR-09-1151 | MN | Large Power Interveners | Minnesota Power | Revenue requirement issues, cost overruns on environmental retrofit project. |
| 04/10 | 2009-00459 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Revenue requirement issues. |
| 04/10 | 2009-00548, 2009-00549 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company, Louisville Gas and Electric Company | Revenue requirement issues. |
| 08/10 | 31647 | GA | Georgia Public Service Commission Staff | Atlanta Gas Light Company | Revenue requirement and synergy savings issues. |
| 08/10 | 31647 Wackerly-Kollen Panel | GA | Georgia Public Service Commission Staff | Atlanta Gas Light Company | Affiliate transaction and Customer First program issues. |
| 08/10 | 2010-00204 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Company, Kentucky Utilities Company | PPL acquisition of E.ON U.S. (LG&E and KU) conditions, acquisition savings, sharing deferral mechanism. |
| 09/10 | 38339 Direct and Cross-Rebuttal | TX PUCT | Gulf Coast Coalition of Cities | CenterPoint Energy Houston Electric | Revenue requirement issues, including consolidated tax savings adjustment, incentive compensation FIN 48; AMS surcharge including roll-in to base rates; rate case expenses. |
| 09/10 | EL10-55 | FERC | Louisiana Public Service Commission | Entergy Services, Inc., Entergy Operating Cos | Depreciation rates and expense input effects on System Agreement tariffs. |
| 09/10 | 2010-00167 | KY | Gallatin Steel | East Kentucky Power Cooperative, Inc. | Revenue requirements. |
| 09/10 | U-23327 Subdocket E Direct | LA | Louisiana Public Service Commission | SWEPCO | Fuel audit: S02 allowance expense, variable O&M expense, off-system sales margin sharing. |
| 11/10 | U-23327 Rebuttal | LA | Louisiana Public Service Commission | SWEPCO | Fuel audit: S02 allowance expense, variable O&M expense, off-system sales margin sharing. |
| 09/10 | U-31351 | LA | Louisiana Public Service Commission Staff | SWEPCO and Valley Electric Membership Cooperative | Sale of Valley assets to SWEPCO and dissolution of Valley. |
| 10/10 | 10-1261-EL-UNC | OH | Ohio OCC, Ohio Manufacturers Association, Ohio Energy Group, Ohio Hospital Association, Appalachian Peace and Justice Network | Columbus Southern Power Company | Significantly excessive earnings test. |
| 10/10 | 10-0713-E-PC | WV | West Virginia Energy Users Group | Monongahela Power Company, Potomac Edison Power Company | Merger of First Energy and Allegheny Energy. |
| 10/10 | U-23327 Subdocket Direct | LA | Louisiana Public Service Commission Staff | SWEPCO | AFUDC adjustments in Formula Rate Plan. |
| 11/10 | EL10-55 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc., Entergy Operating Cos | Depreciation rates and expense input effects on System Agreement tariffs. |
| 12/10 | ER10-1350 Direct | FERC | Louisiana Public Service Commission | Entergy Services, Inc. Entergy Operating Cos | Waterford 3 lease amortization, ADIT, and fuel inventory effects on System Agreement tariffs. |
| 01/11 | ER10-1350 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc., Entergy Operating Cos | Waterford 3 lease amortization, ADIT, and fuel inventory effects on System Agreement tariffs. |
| 03/11 04/11 | ER10-2001 Direct Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc., Entergy Arkansas, Inc. | EAI depreciation rates. |
| 04/11 | U-23327 Subdocket E | LA | Louisiana Public Service Commission Staff | SWEPCO | Settlement, incl resolution of S02 allowance expense, var O&M expense, sharing of OSS margins. |
| 04/11 05/11 | 38306 Direct Suppl Direct | TX PUCT | Cities Served by Texas-New Mexico Power Company | Texas-New Mexico Power Company | AMS deployment plan, AMS Surcharge, rate case expenses. |
| 05/11 | 11-0274-E-GI | WV | West Virginia Energy Users Group | Appalachian Power Company, Wheeling Power Company | Deferral recovery phase-in, construction surcharge. |
| 05/11 | 2011-00036 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Revenue requirements. |
| 06/11 | 29849 | GA | Georgia Public Service Commission Staff | Georgia Power Company | Accounting issues related to Vogtle risk-sharing mechanism. |
| 07/11 | ER11-2161 Direct and Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and Entergy Texas, Inc. | ETI depreciation rates; accounting issues. |
| 07/11 | PUE-2011-00027 | VA | Virginia Committee for Fair Utility Rates | Virginia Electric and Power Company | Return on equity performance incentive. |
| 07/11 | 11-346-EL-SSO 11-348-EL-SSO 11-349-EL-AAM 11-350-EL-AAM | OH | Ohio Energy Group | AEP-OH | Equity Stabilization Incentive Plan; actual earned returns; ADIT offsets in riders. |
| 08/11 | U-23327 Subdocket Rebuttal | LA | Louisiana Public Service Commission Staff | SWEPCO | Depreciation rates and service lives; AFUDC adjustments. |
| 08/11 | 05-UR-105 | WI | Wisconsin Industrial Energy Group | WE Energies, Inc. | Suspended amortization expenses; revenue requirements. |
| 08/11 | ER11-2161 Cross-Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. and Entergy Texas, Inc. | ETI depreciation rates; accounting issues. |
| 09/11 | PUC Docket 39504 | TX PUCT | Gulf Coast Coalition of Cities | CenterPoint Energy Houston Electric | Investment tax credit, excess deferred income taxes; normalization. |
| 09/11 | 2011-00161 2011-00162 | KY | Kentucky Industrial Utility Consumers, Inc. | Louisville Gas & Electric Company, Kentucky Utilities Company | Environmental requirements and financing. |
| 10/11 | 11-4571-EL-UNC 11-4572-EL-UNC | OH | Ohio Energy Group | Columbus Southern Power Company, Ohio Power Company | Significantly excessive earnings. |
| 10/11 | 4220-UR-117 Direct | WI | Wisconsin Industrial Energy Group | Northern States Power-Wisconsin | Nuclear O&M, depreciation. |
| 11/11 | 4220-UR-117 Surrebuttal | WI | Wisconsin Industrial Energy Group | Northern States Power-Wisconsin | Nuclear O&M, depreciation. |
| 11/11 | PUC Docket 39722 | TX PUCT | Cities Served by AEP Texas Central Company | AEP Texas Central Company | Investment tax credit, excess deferred income taxes; normalization. |
| 02/12 | PUC Docket 40020 | TX PUCT | Cities Served by Oncor | Lone Star Transmission, LLC | Temporary rates. |
| 03/12 | 11AL-947E Answer | CO | Climax Molybdenum Company and CF&I Steel, L.P. d/b/a Evraz Rocky Mountain Steel | Public Service Company of Colorado | Revenue requirements, including historic test year, future test year, CACJA CWIP, contra-AFUDC. |
| 03/12 | 2011-00401 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Big Sandy 2 environmental retrofits and environmental surcharge recovery. |
| 4/12 | 2011-00036 Direct Rehearing Supplemental Rebuttal Rehearing | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Rate case expenses, depreciation rates and expense. |
| 04/12 | 10-2929-EL-UNC | OH | Ohio Energy Group | AEP Ohio Power | State compensation mechanism, CRES capacity charges, Equity Stabilization Mechanism |
| 05/12 | 11-346-EL-SSO 11-348-EL-SSO | OH | Ohio Energy Group | AEP Ohio Power | State compensation mechanism, Equity Stabilization Mechanism, Retail Stability Rider. |
| 05/12 | 11-4393-EL-RDR | OH | Ohio Energy Group | Duke Energy Ohio, Inc. | Incentives for over-compliance on EE/PDR mandates. |
| 06/12 | 40020 | TX PUCT | Cities Served by Oncor | Lone Star Transmission, LLC | Revenue requirements, including ADIT, bonus depreciation and NOL, working capital, self insurance, depreciation rates, federal income tax expense. |
| 07/12 | 120015-EI | FL | South Florida Hospital and Healthcare Association | Florida Power & Light Company | Revenue requirements, including vegetation management, nuclear outage expense, cash working capital, CWIP in rate base. |
| 07/12 | 2012-00063 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corp. | Environmental retrofits, including environmental surcharge recovery. |
| 09/12 | 05-UR-106 | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Electric Power Company | Section 1603 grants, new solar facility, payroll expenses, cost of debt. |
| 10/12 | 2012-00221 2012-00222 | KY | Kentucky Industrial Utility Customers, Inc. | Louisville Gas and Electric Company, Kentucky Utilities Company | Revenue requirements, including off-system sales, outage maintenance, storm damage, injuries and damages, depreciation rates and expense. |
| 10/12 | 120015-EI Direct | FL | South Florida Hospital and Healthcare Association | Florida Power & Light Company | Settlement issues. |
| 11/12 | 120015-EI Rebuttal | FL | South Florida Hospital and Healthcare Association | Florida Power & Light Company | Settlement issues. |
| 10/12 | 40604 | TX PUCT | Steering Committee of Cities Served by Oncor | Cross Texas Transmission, LLC | Policy and procedural issues, revenue requirements, including AFUDC, ADIT – bonus depreciation & NOL, incentive compensation, staffing, self-insurance, net salvage, depreciation rates and expense, income tax expense. |
| 11/12 | 40627 Direct | TX PUCT | City of Austin d/b/a Austin Energy | City of Austin d/b/a Austin Energy | Rate case expenses. |
| 12/12 | 40443 | TX PUCT | Cities Served by SWEPCO | Southwestern Electric Power Company | Revenue requirements, including depreciation rates and service lives, O&M expenses, consolidated tax savings, CWIP in rate base, Turk plant costs. |
| 12/12 | U-29764 | LA | Louisiana Public Service Commission Staff | Entergy Gulf States Louisiana, LLC and Entergy Louisiana, LLC | Termination of purchased power contracts between EGSL and ETI, Spindletop regulatory asset. |
| 01/13 | ER12-1384 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Gulf States Louisiana, LLC and Entergy Louisiana, LLC | Little Gypsy 3 cancellation costs. |
| 02/13 | 40627 Rebuttal | TX PUCT | City of Austin d/b/a Austin Energy | City of Austin d/b/a Austin Energy | Rate case expenses. |
| 03/13 | 12-426-EL-SSO | OH | The Ohio Energy Group | The Dayton Power and Light Company | Capacity charges under state compensation mechanism, Service Stability Rider, Switching Tracker. |
| 04/13 | 12-2400-EL-UNC | OH | The Ohio Energy Group | Duke Energy Ohio, Inc. | Capacity charges under state compensation mechanism, deferrals, rider to recover deferrals. |
| 04/13 | 2012-00578 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Resource plan, including acquisition of interest in Mitchell plant. |
| 05/13 | 2012-00535 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Revenue requirements, excess capacity, restructuring. |
| 06/13 | 12-3254-EL-UNC | OH | The Ohio Energy Group, Inc., Office of the Ohio Consumers’ Counsel | Ohio Power Company | Energy auctions under CBP, including reserve prices. |
| 07/13 | 2013-00144 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Biomass renewable energy purchase agreement. |
| 07/13 | 2013-00221 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Agreements to provide Century Hawesville Smelter market access. |
| 10/13 | 2013-00199 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Revenue requirements, excess capacity, restructuring. |
| 12/13 | 2013-00413 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Agreements to provide Century Sebree Smelter market access. |
| 01/14 | ER10-1350 Direct and Answering | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Waterford 3 lease accounting and treatment in annual bandwidth filings. |
| 02/14 | U-32981 | LA | Louisiana Public Service Commission | Entergy Louisiana, LLC | Montauk renewable energy PPA. |
| 04/14 | ER13-432 Direct | FERC | Louisiana Public Service Commission | Entergy Gulf States Louisiana, LLC and Entergy Louisiana, LLC | Union Pacific Settlement benefits and damages. |
| 05/14 | PUE-2013-00132 | VA | HP Hood LLC | Shenandoah Valley Electric Cooperative | Market based rate; load control tariffs. |
| 07/14 | PUE-2014-00033 | VA | Virginia Committee for Fair Utility Rates | Virginia Electric and Power Company | Fuel and purchased power hedge accounting, change in FAC Definitional Framework. |
| 08/14 | ER13-432 Rebuttal | FERC | Louisiana Public Service Commission | Entergy Gulf States Louisiana, LLC and Entergy Louisiana, LLC | Union Pacific Settlement benefits and damages. |
| 08/14 | 2014-00134 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Requirements power sales agreements with Nebraska entities. |
| 09/14 | E-015/CN-12-1163 Direct | MN | Large Power Intervenors | Minnesota Power | Great Northern Transmission Line; cost cap; AFUDC v. current recovery; rider v. base recovery; class cost allocation. |
| 10/14 | 2014-00225 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Allocation of fuel costs to off-system sales. |
| 10/14 | ER13-1508 | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Entergy service agreements and tariffs for affiliate power purchases and sales; return on equity. |
| 10/14 | 14-0702-E-42T 14-0701-E-D | WV | West Virginia Energy Users Group | First Energy-Monongahela Power, Potomac Edison | Consolidated tax savings; payroll; pension, OPEB, amortization; depreciation; environmental surcharge. |
| 11/14 | E-015/CN-12-1163 Surrebuttal | MN | Large Power Intervenors | Minnesota Power | Great Northern Transmission Line; cost cap; AFUDC v. current recovery; rider v. base recovery; class allocation. |
| 11/14 | 05-376-EL-UNC | OH | Ohio Energy Group | Ohio Power Company | Refund of IGCC CWIP financing cost recoveries. |
| 11/14 | 14AL-0660E | CO | Climax, CF&I Steel | Public Service Company of Colorado | Historic test year v. future test year; AFUDC v. current return; CACJA rider, transmission rider; equivalent availability rider; ADIT; depreciation; royalty income; amortization. |
| 12/14 | EL14-026 | SD | Black Hills Industrial Intervenors | Black Hills Power Company | Revenue requirement issues, including depreciation expense and affiliate charges. |
| 12/14 | 14-1152-E-42T | WV | West Virginia Energy Users Group | AEP-Appalachian Power Company | Income taxes, payroll, pension, OPEB, deferred costs and write offs, depreciation rates, environmental projects surcharge. |
| 01/15 | 9400-YO-100 Direct | WI | Wisconsin Industrial Energy Group | Wisconsin Energy Corporation | WEC acquisition of Integrys Energy Group, Inc. |
| 01/15 | 14F-0336EG 14F-0404EG | CO | Development Recovery Company LLC | Public Service Company of Colorado | Line extension policies and refunds. |
| 02/15 | 9400-YO-100 Rebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Energy Corporation | WEC acquisition of Integrys Energy Group, Inc. |
| 03/15 | 2014-00396 | KY | Kentucky Industrial Utility Customers, Inc. | AEP-Kentucky Power Company | Base, Big Sandy 2 retirement rider, environmental surcharge, and Big Sandy 1 operation rider revenue requirements, depreciation rates, financing, deferrals. |
| 03/15 | 2014-00371 2014-00372 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company and Louisville Gas and Electric Company | Revenue requirements, staffing and payroll, depreciation rates. |
| 04/15 | 2014-00450 | KY | Kentucky Industrial Utility Customers, Inc. and the Attorney General of the Commonwealth of Kentucky | AEP-Kentucky Power Company | Allocation of fuel costs between native load and off-system sales. |
| 04/15 | 2014-00455 | KY | Kentucky Industrial Utility Customers, Inc. and the Attorney General of the Commonwealth of Kentucky | Big Rivers Electric Corporation | Allocation of fuel costs between native load and off-system sales. |
| 04/15 | ER2014-0370 | MO | Midwest Energy Consumers’ Group | Kansas City Power & Light Company | Affiliate transactions, operation and maintenance expense, management audit. |
| 05/15 | PUE-2015-00022 | VA | Virginia Committee for Fair Utility Rates | Virginia Electric and Power Company | Fuel and purchased power hedge accounting; change in FAC Definitional Framework. |
| 05/15 09/15 | EL10-65 Direct, Rebuttal Complaint | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Accounting for AFUDC Debt, related ADIT. |
| 07/15 | EL10-65 Direct and Answering Consolidated Bandwidth Dockets | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Waterford 3 sale/leaseback ADIT, Bandwidth Formula. |
| 09/15 | 14-1693-EL-RDR | OH | Public Utilities Commission of Ohio | Ohio Energy Group | PPA rider for charges or credits for physical hedges against market. |
| 12/15 | 45188 | TX PUCT | Cities Served by Oncor Electric Delivery Company | Oncor Electric Delivery Company | Hunt family acquisition of Oncor; transaction structure; income tax savings from real estate investment trust (REIT) structure; conditions. |
| 12/15 01/16 | 6680-CE-176 Direct, Surrebuttal, Supplemental Rebuttal | WI | Wisconsin Industrial Energy Group, Inc. | Wisconsin Power and Light Company | Need for capacity and economics of proposed Riverside Energy Center Expansion project; ratemaking conditions. |
| 03/16 03/16 04/16 05/16 06/16 | EL01-88 Remand Direct Answering Cross-Answering Rebuttal | FERC | Louisiana Public Service Commission | Entergy Services, Inc. | Bandwidth Formula: Capital structure, fuel inventory, Waterford 3 sale/leaseback, Vidalia purchased power, ADIT, Blythesville, Spindletop, River Bend AFUDC, property insurance reserve, nuclear depreciation expense. |
| 03/16 | 15-1673-E-T | WV | West Virginia Energy Users Group | Appalachian Power Company | Terms and conditions of utility service for commercial and industrial customers, including security deposits. |
| 04/16 | 39971 Panel Direct | GA | Georgia Public Service Commission Staff | Southern Company, AGL Resources, Georgia Power Company, Atlanta Gas Light Company | Southern Company acquisition of AGL Resources, risks, opportunities, quantification of savings, ratemaking implications, conditions, settlement. |
| 04/16 | 2015-00343 | KY | Office of the Attorney General | Atmos Energy Corporation | Revenue requirements, including NOL ADIT, affiliate transactions. |
| 04/16 | 2016-00070 | KY | Office of the Attorney General | Atmos Energy Corporation | R & D Rider. |
| 05/16 | 2016-00026 2016-00027 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Co., Louisville Gas & Electric Co. | Need for environmental projects, calculation of environmental surcharge rider. |
| 05/16 | 16-G-0058 16-G-0059 | NY | New York City | Keyspan Gas East Corp., Brooklyn Union Gas Company | Depreciation, including excess reserves, leak prone pipe. |
| 06/16 | 160088-EI | FL | South Florida Hospital and Healthcare Association | Florida Power and Light Company | Fuel Adjustment Clause Incentive Mechanism re: economy sales and purchases, asset optimization. |
| 07/16 | 160021-EI | FL | South Florida Hospital and Healthcare Association | Florida Power and Light Company | Revenue requirements, including capital recovery, depreciation, ADIT. |
| 07/16 | 16-057-01 | UT | Office of Consumer Services | Dominion Resources, Inc. / Questar Corporation | Merger, risks, harms, benefits, accounting. |
| 08/16 | 15-1022-EL-UNC 16-1105-EL-UNC | OH | Ohio Energy Group | AEP Ohio Power Company | SEET earnings, effects of other pending proceedings. |
| 9/16 | 2016-00162 | KY | Office of the Attorney General | Columbia Gas Kentucky | Revenue requirements, O&M expense, depreciation, affiliate transactions. |
| 09/16 | E-22 Sub 519, 532, 533 | NC | Nucor Steel | Dominion North Carolina Power Company | Revenue requirements, deferrals and amortizations. |
| 09/16 10/16 | 15-1256-G-390P (Reopened) 16-0922-G-390P 10-2929-EL-UNC 11-346-EL-SSO 11-348-EL-SSO 11-349-EL-SSO 11-350-EL-SSO 14-1186-EL-RDR | WV OH | West Virginia Energy Users Group Ohio Energy Group | Mountaineer Gas Company AEP Ohio Power Company | Infrastructure rider, including NOL ADIT and other income tax normalization and calculation issues. State compensation mechanism, capacity cost, Retail Stability Rider deferrals, refunds, SEET. |
| 11/16 | 16-0395-EL-SSO Direct | OH | Ohio Energy Group | Dayton Power & Light Company | Credit support and other riders; financial stability of Utility, holding company. |
| 12/16 | Formal Case 1139 | DC | Healthcare Council of the National Capital Area | Potomac Electric Power Company | Post test year adjust, merger costs, NOL ADIT, incentive compensation, rent. |
| 01/17 | 46238 | TX PUCT | Steering Committee of Cities Served by Oncor | Oncor Electric Delivery Company | Next Era acquisition of Oncor; goodwill, transaction costs, transition costs, cost deferrals, ratemaking issues. |
| 02/17 | 16-0395-EL-SSO Direct (Stipulation) | OH | Ohio Energy Group | Dayton Power & Light Company | Non-unanimous stipulation re: credit support and other riders; financial stability of utility, holding company. |
| 02/17 | 45414 | TX PUCT | Cities of Midland, McAllen, and Colorado City | Sharyland Utilities, LP, Sharyland Distribution & Transmission Services, LLC | Income taxes, depreciation, deferred costs, affiliate expenses. |
| 03/17 | 2016-00370 2016-00371 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company, Louisville Gas and Electric Company | AMS, capital expenditures, maintenance expense, amortization expense, depreciation rates and expense. |
| 06/17 | 29849 (Panel with Philip Hayet) | GA | Georgia Public Service Commission Staff | Georgia Power Company | Vogtle 3 and 4 economics. |
| 08/17 10/17 | 17-0296-E-PC 2017-00179 | WV KY | West Virginia Energy Users Group Kentucky Industrial Utility Customers, Inc. | Monongahela Power Company, The Potomac Edison Power Company Kentucky Power Company | ADIT, OPEB. Weather normalization, Rockport lease, O&M, incentive compensation, depreciation, income taxes. |
| 10/17 | 2017-00287 | KY | Kentucky Industrial Utility Customers, Inc. | Big Rivers Electric Corporation | Fuel cost allocation to native load customers. |
| 12/17 | 2017-00321 | KY | Attorney General | Duke Energy Kentucky (Electric) | Revenues, depreciation, income taxes, O&M, regulatory assets, environmental surcharge rider, FERC transmission cost reconciliation rider. |
| 12/17 | 29849 (Panel with Philip Hayet, Tom Newsome) | GA | Georgia Public Service Commission Staff | Georgia Power Company | Vogtle 3 and 4 economics, tax abandonment loss. |
| 01/18 | 2017-00349 | KY | Kentucky Attorney General | Atmos Energy Kentucky | O&M expense, depreciation, regulatory assets and amortization, Annual Review Mechanism, Pipeline Replacement Program and Rider, affiliate expenses. |
| 06/18 | 18-0047 | OH | Ohio Energy Group | Ohio Electric Utilities | Tax Cuts and Jobs Act. Reduction in income tax expense; amortization of excess ADIT. |
| 07/18 | T-34695 | LA | LPSC Staff | Crimson Gulf, LLC | Revenues, depreciation, income taxes, O&M, ADIT. |
| 08/18 | 48325 | TX PUCT | Cities Served by Oncor | Oncor Electric Delivery Company | Tax Cuts and Jobs Act; amortization of excess ADIT. |
| 08/18 | 48401 | TX PUCT | Cities Served by TNMP | Texas-New Mexico Power Company | Revenues, payroll, income taxes, amortization of excess ADIT, capital structure. |
| 08/18 | 2018-00146 | KY | KIUC | Big Rivers Electric Corporation | Station Two contracts termination, regulatory asset, regulatory liability for savings |
| 09/18 10/18 | 20170235-EI 20170236-EU Direct Supplemental Direct | FL | Office of Public Counsel | Florida Power & Light Company | FP&L acquisition of City of Vero Beach municipal electric utility systems. |
| 09/18 10/18 | 2017-370-E Direct 2017-207, 305, 370-E Surrebuttal Supplemental Surrebuttal | SC | Office of Regulatory Staff | South Carolina Electric & Gas Company and Dominion Energy, Inc. | Recovery of Summer 2 and 3 new nuclear development costs, related regulatory liabilities, securitization, NOL carryforward and ADIT, TCJA savings, merger conditions and savings. |
| 12/18 | 2018-00261 | KY | Attorney General | Duke Energy Kentucky (Gas) | Revenues, O&M, regulatory assets, payroll, integrity management, incentive compensation, cash working capital. |
| 01/19 | 2018-00294 2018-00295 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company, Louisville Gas & Electric Company | AFUDC v. CWIP in rate base, transmission and distribution plant additions, capitalization, revenues generation outage expense, depreciation rates and expenses, cost of debt. |
| 01/19 | 2018-00281 | KY | Attorney General | Atmos Energy Corp. | AFUDC v. CWIP in rate base, ALG v. ELG depreciation rates, cash working capital, PRP Rider, forecast plant additions, forecast expenses, cost of debt, corporate cost allocation. |
| 02/19 04/19 | UD-18-07 Direct Surrebuttal and Cross-Answering | New Orleans | Crescent City Power Users Group | Entergy New Orleans, LLC | Post-test year adjustments, storm reserve fund, NOL ADIT, FIN48 ADIT, cash working capital, depreciation, amortization, capital structure, formula rate plans, purchased power rider. |
| 03/19 | 2018-00358 | KY | Attorney General | Kentucky American Water Company | Capital expenditures, cash working capital, payroll expense, incentive compensation, chemicals expense, electricity expense, water losses, rate case expense, excess deferred income taxes. |
| 03/19 | 48929 | TX PUCT | Steering Committee of Cities Served by Oncor | Oncor Electric Delivery Company LLC, Sempra Energy, Sharyland Distribution & Transmission Services, L.L.C.., Sharyland Utilities, L.P. | Sale, transfer, merger transactions, hold harmless and other regulatory conditions. |
| 06/19 | 49421 | TX PUCT | Gulf Coast Coalition of Cities | CenterPoint Energy Houston Electric | Prepaid pension asset, accrued OPEB liability, regulatory assets and liabilities, merger savings, storm damage expense, excess deferred income taxes. |
| 07/19 | 49494 | TX PUCT | Cities Served by AEP Texas | AEP Texas, Inc. | Plant in service, prepaid pension asset, O&M, ROW costs, incentive compensation, self-insurance expense, excess deferred income taxes. |
| 08/19 | 19-G-0309 19-G-0310 | NY | New York City | National Grid | Depreciation rates, net negative salvage. |
| 10/19 | 42315 | GA | Atlanta Gas Light Company | Public Interest Advocacy Staff | Capital expenditures, O&M expense, prepaid pension asset, incentive compensation, merger savings, affiliate expenses, excess deferred income taxes. |
| 10/19 | 45253 | IN | Duke Energy Indiana | Office of Utility Consumer Counselor | Prepaid pension asset, inventories, regulatory assets and labilities, unbilled revenues, incentive compensation, income tax expense, affiliate charges, ADIT, riders. |
| 12/19 | 2019-00271 | KY | Attorney General | Duke Energy Kentucky | ADIT, EDIT, CWC, payroll expense, incentive compensation expense, depreciation rates, pilot programs |
| 05/20 | 202000067-EI | FL | Office of Public Counsel | Tampa Electric Company | Storm Protection Plan. |
| 06/20 | 20190038-EI | FL | Office of Public Counsel | Gulf Power Company | Hurricane Michael costs. |
| 07/20 09/20 | PUR-2020-00015 Direct Surrebuttal | VA | Old Dominion Committee for Fair Utility Rates | Appalachian Power Company | Coal Amortization Rider, storm damage, prepaid pension and OPEB assets, return on joint-use assets. |
| 07/20 09/20 | 2019-226-E Direct Surrebbutal | SC | Office of Regulatory Staff | Dominion Energy South Carolina | Integrated Resource Plan. |
| 10/20 | 2020-00160 | KY | Attorney General | Water Service Corporation of Kentucky | Return on rate base v. operating ratio. |
| 10/20 | 2020-00174 | KY | Attorney General and Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Rate base v. capitalization, Rockport UPA, prepaid pension and OPEB, cash working capital, incentive compensation, Rockport 2 depreciation expense, EDIT, AMI, grid modernization rider. |
| 11/20 12/20 | 2020-125-E Direct Surrebuttal | SC | Office of Regulatory Staff | Dominion Energy South Carolina | Summer 2 and 3 cancelled plant and transmission cost recovery; TCJA; regulatory assets. |
| 12/20 | 2020172-EI | FL | Office of Public Counsel | Florida Power & Light Company | Hurricane Dorian costs. |
| 12/20 | 29849 (Panel with Philip Hayet, Tom Newsome) | GA | Georgia Public Service Commission Staff | Georgia Power Company | VCM23, Vogtle 3 and 4 rate impact analyses. |
| 02/21 04/21 | 2019-224-E 2019-225-E Direct Surrebuttal | SC | Office of Regulatory Staff | Duke Energy Carolinas, LLC, Duke Energy Progress, LLC | Integrated Resource Plans. |
| 03/21 | 51611 | TX PUCT | Steering Committee of Cities Served by Oncor | Sharyland Utilities, L.L.C. | ADIT, capital structure, return on equity. |
| 03/21 | 2020-00349 2020-00350 | KY | Attorney General and Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company and Louisville Gas and Electric Company | Rate base v. capitalization, retired plant costs, depreciation, securitization, staffing + payroll, pension + OPEB, AMI, off-system sales margins. |
| 04/21 Direct 07/21 | 18-857-EL-UNC 19-1338-EL-UNC 20-1034-EL-UNC 20-1476-EL-UNC Supplemental Direct | OH | The Ohio Energy Group | First Energy Ohio Companies | Significantly Excessive Earnings Test; legacy nuclear plant costs. |
| 05/21 06/21 | 2021-00004 Direct Supplemental Direct | KY | Attorney General and Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | CPCN for CCR/ELG Projects at Mitchell Plant. |
| 06/21 | 29849 (Panel with Philip Hayet, Tom Newsome) | GA | Georgia Public Service Commission Staff | Georgia Power Company | VCM24, Vogtle 3 and 4 rate impact analyses. |
| 06/21 | 2021-00103 | KY | Attorney General and Nucor Steel Gallatin | East Kentucky Power Cooperative, Inc. | Revenues, depreciation, interest, TIER, O&M, regulatory asset. |
| 07/21 08/21 10/21 | U-35441 Direct Cross-Answering Surrebuttal | LA | Louisiana Public Service Commission Staff | Southwestern Electric Power Company | Revenues, O&M expense, depreciation, retirement rider. |
| 09/21 | 05-21-00007061 | TX RRCT | Texas Cities Alliance | CenterPoint, CoServe, Corix, EPCOR, SiEnergy, TGS, UniGas | Securitization; regulatory asset; rates. |
| 09/21 | 2021-00190 | KY | Attorney General | Duke Energy Kentucky | Revenues, O&M expense, depreciation, capital structure, cost of long-term debt, government mandate rider. |
| 09/21 | 43838 | GA | Public Interest Advocacy Staff | Georgia Power Company | Vogtle 3 base rates, NCCR rates; deferrals. |
| 09/21 | 2021-00214 | KY | Attorney General | Atmos Energy Corp. | NOL ADIT, working capital, affiliate expenses, amortization EDIT, capital structure, cost of debt, accelerated replacement Aldyl-A pipe, PRP Rider, Tax Act Adjustment Rider. |
| 12/21 | 29849 (Panel with Philip Hayet, Tom Newsome) | GA | Georgia Public Service Commission Staff | Georgia Power Company | VCM25, Vogtle 3 and 4 rate impact analyses. |
| 01/22 | 2021-00358 | KY | Attorney General | Jackson Purchase Energy Corporation | Revenues, nonrecurring expenses, normalized expenses, interest expense, TIER. |
| 01/22 | 2021-00421 | KY | Attorney General and Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Proposed Mitchell Plant Operations and Maintenance and Ownership Agreements; sale of Mitchell Plant interest. |
| 02/22 | 2021-00481 | KY | Attorney General and Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Proposed Liberty Utilities, Inc. acquisition of Kentucky Power Company; harm to customers; conditions to mitigate harm. |
| 03/22 | 2021-00407 | KY | Attorney General | South Kentucky Rural Electric Cooperative Corporation | Revenues, interest income, interest expense, TIER, payroll. |
| 03/22 04/22 | U-36190 Direct Cross-Answering | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, LLC | Certification of solar resources. |
| 05/22 | 20200241-EI 20210078-EI 20210079-EI | FL | Office of Public Counsel | Florida Power & Light Company, Gulf Power Company | Hurricanes Sally, Zeta, Isaias; Tropical Storm Eta, pre-planning, restoration and repair, costs, ratemaking recovery. |
| 05/22 | U-36268 | LA | Louisiana Public Service Commission Staff | 1803 Electric Cooperative, Inc. | Wholesale power contracts, wholesale rate tariffs, wholesale rates. |
| 06/22 | 20220048-EI 20220049-EI 20220050-EI 20220051-EI | FL | Office of Public Counsel | Tampa Electric Company, Florida Public Utilities Company, Duke Energy Florida, LLC, Florida Power & Light Company | Storm Protection Plans. prudence, reasonableness, cost recovery, including deferred return on CWIP. |
| 06/22 | 29849 (Panel with Philip Hayet, Tom Newsome) | GA | Georgia Public Service Commission Staff | Georgia Power Company | VCM26, Vogtle 3 and 4 rate impact analyses. |
| 07/22 | S-36267 | LA | Louisiana Public Service Commission Staff | 1803 Electric Cooperative, Inc. | Non-opposition to establish revolving LOC and supporting guarantees by member cooperatives. |
| 08/22 | 53601 | TX PUCT | Steering Committee of Cities Served by Oncor | Oncor Electric Delivery Company, LLC | Vendor financing, customer advances, cash working capital, ADFIT and temporary differences, depreciation expense, amortization expense. |
| 09/22 | 20220010-EI | FL | Office of Public Counsel | Tampa Electric Company, Florida Public Utilities Company, Duke Energy Florida, LLC, Florida Power & Light Company | Storm Protection Plan, Cost Recovery Clause, prudence, reasonableness, deferred return on CWIP. |
| 10/22 | 5-UR-110 | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company | Levelized recovery of retired plan costs, securitization financing. |
| 10/22 | 2022-00283 | KY | Attorney General and Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Rockport deferrals and recoveries. |
| 12/22 | 2022-00263 | KY | Attorney General and Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Fuel adjustment clause methodology and disallowances. |
| 01/23 | 29849 (Panel with Philip Hayet, Tom Newsome) | GA | Georgia Public Service Commission Staff | Georgia Power Company | VCM27, Vogtle 3 and 4 rate impact analyses. |
| 1/23 02/23 | 2022-256-E Direct Surrebuttal | SC | Office of Regulatory Staff | Duke Energy Progress, LLC | Storm response process, costs, deferrals, deferred carrying costs. |
| 03/23 | 2022-00372 | KY | Attorney General | Duke Energy Kentucky, Inc. | Cash working capital, depreciation, decommissioning, regulatory asset amortization, retired generation asset recovery, modifications to existing tariffs, proposed new tariffs. |
| 06/23 | 20230023-GU | FL | Office of Public Counsel | Peoples Gas System, Inc. | Restructuring, staffing, O&M expenses, storm expense, depreciation expense, amortization of theoretical depreciation surplus. |
| 07/23 | 2022-00402 | KY | Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company and Louisville Gas and Electric Company | CPCNs for combined cycle and owned solar resources, acquisition of PPA solar resources, retirement of coal resources. |
| 07/23 08/23 | 2023-89-E Direct Surrebuttal | SC | Office of Regulatory Staff | Duke Energy Progress, LLC | Securitization financing, quantifiable net benefits, regulatory liability for return on ADIT, financing order and tariff language for calculation of storm recovery charges. |
| 08/23 | U-36685 | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, LLC | Certification of solar PPAs and related ratemaking. |
| 09/23 | 6680-UR-124 Direct Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Power and Light Company | Ratemaking alternatives for recovery of retired plant costs, including securitization financing. |
| 09/23 | 05-UR-110 (Reopener) Direct | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company | Ratemaking alternatives for recovery of retired plant costs, including securitization financing. |
| 10/23 | 29849 | GA | Georgia Public Service Commission Staff | Georgia Power Company | Vogtle 3 and 4 prudence. |
| 10/23 | 2023-00159 | KY | Attorney General Kentucky Industrial Utility Customer, Inc. | Kentucky Power Company | NOL, COR, and other ADIT, incentive comp, regulatory assets, transmission and distribution cost riders, CAMT and other IRA, tax costs rider, securitization. |
| 12/23 02/24 | 2021-00370 Direct Rebuttal | KY | Attorney General Kentucky Industrial Utility Customer, Inc. | Kentucky Power Company | Investigation into adequacy of service and reasonableness of rates. |
| 02/24 | 2023-00008 | KY | Attorney General, Kentucky Industrial Utility Customesr, Inc. | Kentucky Power Company | Fuel adjustment clause; fuel and purchased power expense; peaking unit equivalent methodology. |
| 03/24 | 05-23-0015513 | TX RRCT | Cities Served by CenterPoint Gas | CenterPoint Energy Resources Corp. | Capital structure, Tax Rider, NOL ADIT, CAMT ADIT, annualize revenues, incentive compensation, vendor financing, customer financing, working capital. |
| 05/24 | 56165 | TX PUCT | Cities Served by AEP Texas | AEP Texas, Inc. | Tax Rider, NOL ADIT, CAMT ADIT, annualize revenues, incentive compensation, vendor financing, customer financing, working capital. |
| 05/24 06/24 | U-37071 Direct Direct in Support of Settlement | LA | Louisiana Public Service Commission Staff | Entergy Louisiana, LLC | RFP for solar resources; certification of Mondu PPA. |
| 06/24 | 2024-34-E | SC | Office of Regulatory Staff | Dominion Energy South Carolina, Inc. | Working capital, cash working capital. |
| 06/24 | 20240026-EI | FL | Office of Public Counsel | Tampa Electric Company | O&M expense, A&G expense, incentive compensation, depreciation rates and expenses, dismantlement expense, tax credits, subsequent year adjustments, tax rider. |
| 06/24 | 56211 | TX PUCT | Gulf Coast Coalition of Cities | Centerpoint Energy Houston Electric, LLC | Tax Rider, CAMT ADIT, vendor financing, customer financing, working capital, prepaid pension, regulatory assets, annualize revenues, Texas margin tax. |
| 08/24 09/24 09/24 | 5-UR-111 Direct Rebuttal Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Electric Power Company | Recovery of retired plant costs; securitization. |
| 08/24 09/24 09/24 | 6690-UR-128 Direct Rebuttal Surrebuttal | WI | Wisconsin Industrial Energy Group | Wisconsin Public Service Corporation | Recovery of retired plant costs; securitization. |
| 11/24 | 2024-00243 | KY | Attorney General, Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Bright Mountain Solar renewable energy purchase agreement. |
| 12/24 | 2024-00285 | KY | Attorney General | Duke Energy Kentucky, Inc. | Transition from PJM FRR entity to RPM entity; modifications to Rider Profit Sharing Mechanism. |
| 01/25 | 2024-00276 | KY | Attorney General | Atmos Energy Corporation | NOLC DTA, working capital, cash working capital, riders. |
| 02/25 | 05-24-00018879 | TX (RRCT) | Cities Served by Atmos West Texas | Atmos Energy Corporation | NOLC DTA, other DTAs, DTLs, working capital, riders. |
| 03/25 | 2024-00354 | KY | Attorney General | Duke Energy Kentucky, Inc. (electric) | CAMT, working capital, CWC, unbilled revenues, depreciation, decommissioning, credit card fees, capacity performance insurance, new programs and riders. |
| 05/25 06/25 | 2025-65-E Direct Surrebuttal | SC | Office of Regulatory Staff | Duke Energy Carolinas | Storm recovery costs, securitization, net benefits, regulatory assets and liabilities. |
| 06/25 | 57568 | TX | Freeport-McMoRan, Inc. | El Paso Electric Company | Revenue annualization, nuclear decommissioning, depreciation rates, long term debt interest payable. |
| 06/25 | 2025-00045 | KY | Attorney General, Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company, Louisville Gas and Electric Company | CPCN, AFUDC, post in-service deferrals, generation cost recover rider, extremely high factor tariff. |
| 08/25 | 2025-00113 2025-00114 | KY | Attorney General, Kentucky Industrial Utility Customers, Inc. | Kentucky Utilities Company, Louisville Gas and Electric Company | Capitalization vs. rate base, CWIP in rate base, storm damage, vegetation management, pension, OPEB, depreciation, sharing OSS margins, extremely high load factor tariff, renewable purchased power agreement, tariff, Mill Creek 2 tariff, Mill Creek 6 tariff. |
| 09/25 10/25 | 2025-154-E Direct Surrebuttal | SC | Office of Regulatory Staff | Duke Energy Progress, LLC | Working capital, cash working capital. |
| 09/25 | 2025-00125 | KY | Attorney General | Duke Energy Kentucky, Inc. (gas) | Cash working capital, CAMT, unbilled revenues, credit card fees, accelerated replacement of Aldyl-A. |
| 10/25 | 57932 | TX (PUCT) | Steering Committee of Cities Served by Oncor | Oncor Electric Delivery Company, LLC | Deferral of increases in insurance expense, self- insurance expense. |
| 10/25 11/25 | 2025-172-E Direct Surrebuttal | SC | Office of Regulatory Staff | Duke Energy Carolinas, LLC | Working capital, cash working capital. |
| 10/25 | 58306 | TX (PUCT) | Steering Committee of Cities Served by Oncor | Oncor Electric Delivery Company, LLC | Securitization of storm costs, self-insurance, cost-free vendor and customer financing, revenue annualization, deferral of tax rate changes. |
| 10/25 | 2025-00208 | KY | Attorney General, Kentucky Industrial Utility Customers, Inc. | East Kentucky Power Cooperative, Inc. | Annualization and normalization of revenues, terminal net salvage, interim retirements, interim net salvage, life spans, earnings mechanism, deferral mechanism for revenues, RTEP expenses. |
| 10/25 | 2025-00175 | KY | Attorney General, Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Mitchell ELG CPCN, securitization, environmental surcharges, deferral of costs. |
| 11/25 | 2025-00257 | KY | Attorney General, Kentucky Industrial Utility Customers, Inc. | Kentucky Power Company | Revenue requirements, cost-free vendor financing, NOLC DTAs, terminal net salvage, interim retirements, interim net salvage, Generation Rider. |
| 02/26 | 2025-230-E | SC | Office of Regulatory Staff | Duke Energy Carolinas, LLC, Duke Energy Progress, LLC | Merger, cost/benefit analyses, legacy utility rate convergence, regulatory assets and liabilities, conditions. |
| 02/26 | 58964 | TX (PUCT) | Cities Served by Texas-New Mexico Power Company | Texas-New Mexico Power Company | Service company plant costs, cost-free customer and vendor financing, revenue annualization, self-insurance, vegetation management, ad valorem tax, hurricane cost recovery rider. |

BEFORE THE

GEORGIA PUBLIC SERVICE COMMISSION

| IN THE MATTER OF: GEORGIA POWER COMPANY’S 2022 RATE CASE: STORM DAMAGE RECOVERY APPLICATION | DOCKET NO. 44280 |
| --- | --- |

|  | EXHIBIT |  |
| --- | --- | --- |
|  | STF-NKF-3 |  |

# EDUCATION

Mississippi State University, BBS in Business Administration

Accounting

# EXPERIENCE

J. Kennedy and Associates, Inc.				2003 - Present

Director of Consulting

Responsible for utility revenue requirements analysis, affiliate transaction auditing and analysis, fuel adjustment clause auditing and research involving tax and public reporting matters.  Clients served include the Georgia Public Service Commission (“GPSC”) Staff, the Louisiana Public Service Commission (“LPSC”) and its Staff, the Florida Office of Public Counsel (“OPC”), the Office of the Attorney General of the Commonwealth of Kentucky (“KY AG”), the South Carolina Office of Regulatory Staff (“ORS”), the Houston Council for Health and Education, the Gulf Coast Coalition of Cities, Cities Served by Texas Gas Service Company, the Alliance for Valley Healthcare, the Ohio Energy Group, Inc. (“OEG”), the Kentucky Industrial Utility Customers (“KIUC”), Nucor Gallatin Steel (“Nucor”), the Municipalities of Alda, Grand Island, Kearney and North Platte, Nebraska, the City of Clinton, and the Wisconsin Industrial Energy Group, Inc.

Direct and Responsive Testimonies filed on behalf of Louisiana Public Service Commission or its Staff:

LPSC Docket No. U-23327    Southwestern Electric Power Company, Revenue Requirement Review, October 2004.

LPSC Docket No. U-21453, U-20925, U-22092   Entergy Gulf States, Inc., Jurisdictional Separation Plan, March 2006.

LPSC Docket No. U-25116    Entergy Louisiana, Inc., 2002-2004 Audit of Fuel Adjustment Clause, April 2006.

LPSC Docket No. U-23327    Southwestern Electric Power Company, Revenue Requirement Review, July 2006.

LPSC Docket No. U-21453, U-20925, U-22092   Entergy Gulf States, Inc., Jurisdictional Separation Plan, August 2006.

FERC Docket No. ER07-682        Entergy Services, Inc., Company’s Section 205 Changes to Rough Production Cost Equalization Computation, November 2007.

FERC Docket No. ER07-956        Entergy Services, Inc., Company’s 2007 Filing to be in Compliance with FERC Opinions’ 480and 480-A, March 2008.

FERC Docket No. ER08-51        Entergy Services, Inc., LPSC Section 206 Filing Related to Spindletop Regulatory Asset in Rough Production Cost Equalization Computation, November 2008.

FERC Docket No. ER08-1056        Entergy Services, Inc., Company’s 2008 Filing to be in Compliance with FERC Opinions’ 480and 480-A, January 2009.

LPSC Docket No. U-31066    Dixie Electric Membership Corporation, Company’s Application to Implement a Storm Recovery Rate Rider, September 2009.

LPSC Docket No. U-30893    Dixie Electric Membership Corporation, Company’s Application to Implement a Formula Rate Plan, September 2009.

FERC Docket No. EL09-61 (Phase I)    Entergy Services, Inc., LPSC Complaint Regarding Single Operating Company Opportunity Sales, April 2010.

LPSC Docket No. U-31066    Dixie Electric Membership Corporation, Company’s Application to Implement a Storm Recovery Rate Rider, May 2010.

FERC Docket No. EL10-55        Entergy Services, Inc.

LPSC Complaint Regarding Depreciation Rates, September 2010.

LPSC Docket No. U-23327, Subdocket E    Southwestern Electric Power Company, 2003-2004 Fuel Audit, September 2010.

LPSC Docket No. U-23327, Subdocket F    Southwestern Electric Power Company, 2009 Test Year Formula Rate Plan Filing, October  2010.

LPSC Docket No. U-23327, Subdocket C    Southwestern Electric Power Company, 2007 Test Year Formula Rate Plan Filing, February 2011.

LPSC Docket No. U-23327, Subdocket D    Southwestern Electric Power Company, 2008 Test Year Formula Rate Plan Filing, February 2011.

FERC Docket No. ER10-2001        Entergy Arkansas, Inc., Company’s 2010 Filing to Request Approval of Changed Depreciation Rates, March  2011.

FERC Docket No. ER11-2161        Entergy Texas, Inc., Company’s 2010 Filing to Request Approval of Changed Depreciation Rates, July  2011.

LPSC Docket No. U-31835   South Louisiana Electric Cooperative Association, Company’s Application to Implement a Formula Rate Plan and Initial Revenue Adjustment, August 2011.

FERC Docket No. ER12-1384        Entergy Services, Inc., Company’s Section 205 Fling Related to Little Gypsy 3 Cancellation Costs, September 2012.

LPSC Docket No. U-32315   Claiborne Electric Cooperative, Inc.’s Application to Implement a Formula Rate Plan and Initial Revenue Adjustment, September 2012.

FERC Docket No. ER10-1350        Entergy Services, Inc., Company’s 2010 Filing to be in Compliance with FERC Opinions’ 480 and 480-A, January 2014.

FERC Docket No. EL-01-88-015        Entergy Services, Inc., Company’s 2005 Remand Filing to be in Compliance with FERC Opinions’ 480 and 480-A, March 2016.

LPSC Docket No. U-33984 Claiborne Electric Cooperative, Inc., Formula Rate Plan Extension, October  2016.

FERC Docket No. EL09-61(Phase III) Entergy Services, Inc., LPSC Complaint Regarding Single Operating Company Opportunity Sales, November 2016.

LPSC Docket No. U-33323    Entergy Louisiana LLC, 2010-2013 Fuel Audit, July 2019.

LPSC Docket No. U-33324    Entergy Gulf States Louisiana LLC, 2010-2013 Fuel Audit, July 2019.

LPSC Docket No. U-35441  Southwestern Electric Power Company, Rate Case, July 2021 Direct, October 2021 Surrebuttal.

Direct Testimony filed on behalf of the Florida OPC:

FPSC Docket Nos. 20200241-EI, 202100178-EI, and 202100179-EI  Florida Power and Light Company and Gulf Power Company, Storm Cost Audit, May 2022.

Direct Testimony filed on behalf of the KY AG:

KPSC Case No. 2022-00372 Duke Energy Kentucky, Inc. (Electric Division), Rate Case, March 2023.

KPSC Case No. 2023-00276 Kenergy Corp., Rate Case, January 2024.

KPSC Case No. 2024-00211 Licking Valley Rural Electric Cooperative Corporation, Rate Case, October 2024.

KPSC Case No. 2024-00276 Atmos Energy Corporation, Rate Case, January 2025.

KPSC Case No. 2024-00354 Duke Energy Kentucky, Inc. (Electric Division), Rate Case, March 2025.

KPSC Case No. 2024-00402 South Kentucky Rural Electric Cooperative Corporation, Rate Case, May 2025.

KPSC Case No. 2025-00125 Duke Energy Kentucky, Inc. (Gas Division), Rate Case, September 2025.

Direct Testimony filed on behalf of the KY AG and the City of Clinton:

KPSC Case No. 2022-00147 Water Service Corporation of Kentucky, Rate Case, October 2022.

Direct Testimony filed on behalf of the KY AG and KIUC:

KPSC Case No. 2022-00263 Kentucky Power Company, Fuel Adjustment Clause – Six-Month Review, December 2022.

KPSC Case No. 2023-00318 Kentucky Power Company, Tariff PPA Modification, November 2023.

KPSC Case No. 2023-00008 Kentucky Power Company, Fuel Adjustment Clause – Two-Year Review, December 2023.

KPSC Case Nos. 2025-00113 and 2025-00114 Kentucky Utilities Company and Louisville Gas and Electric Company, Rate Cases, August 2025.

Direct Testimony filed on behalf of the KY AG and Nucor:

KPSC Case No. 2025-00208 East Kentucky Power Cooperative, Inc., Rate Case, October 2025.

Direct Testimony filed on behalf of the South Carolina ORS:

SCPSC Docket No. 2022-256-E Duke Energy Progress, LLC, Cost Recovery for 8 Named Storms Since 2014, January 2023.

Direct Testimony filed on behalf of the OEG in Ohio:

PUCO Case No. 23-301-EL-SSO FirstEnergy Utilities, Standard Service Offer in the Form of an Electric Security Plan, October 2023.

Direct Testimony filed on behalf of Georgia Public Service Commission Staff:

GPSC Docket No. U-43830    Atlanta Gas Light Company, Affiliate Audit, May 2024.

Direct Testimony filed on behalf of Cities Served by Texas Gas Service Company:

Texas Railroad Commission Case No. OS-24-00017471  Texas Gas Service Company, Rate Case, August 2024.

Telscape International, Inc.				             1997 - 2003

Corporate Controller				             1999 - 2003

Assistant Controller					             1997 - 1999

Complete responsibility and accountability for the accounting and financial functions of a $160 million newly public company providing telecommunication and high-end internet access services.  Telscape served as a telephony carrier of services domestically and to Latin and Central America targeting other service carriers as well as individuals.  Reported directly to CFO and managed a staff of eleven.

- Managed the day to day processes required to produce timely and accurate financial statements, including general ledger, account reconciliations, AP, AR, fixed assets, payroll, treasury, tax, internal and external reporting.

- Worked with attorneys and auditors on mergers and acquisitions including due diligence, audits, tax and integrating the accounting functions of eleven acquisitions.

- Grew the accounting department from four to eleven employees while developing and implementing company policies and procedures.

- Instituted capital investment policy and accounts payable management for twenty-one separate entities and twenty-four bank accounts to facilitate effective use of cash flow.

- Created capital and operating budgeting and variance analysis package for five separate business lines.

- Developed the consolidations and inter-company billings process across all entities including six in Latin and Central America.

- Worked with CFO to develop financial models and business plans in raising over $240 million over a three-year period through private preferred placements, debenture offerings and asset based credit facilities.

- Responsible for relationship management with external auditors, attorneys, and the banking community while reviewing and approving all SEC filings, including quarterly and annual reports, proxies and informational filings.

- Developed line cost accounting for revenues and carrier invoices saving thousands monthly and providing the justification for invoice reductions.

## Comcast Communications, Inc.				1988 - 1997

## Regional Controller						1993 - 1997

Regional Assistant Controller				1991 - 1992

Regional Senior Financial Analyst				1988 - 1991

Complete responsibility and accountability for the accounting functions of a $2.1 billion regional division of the world’s third largest cable television provider serving approximately 490,000 subscribers.  Reported to the Regional VP of Finance and managed a staff of twelve.

- Managed the day to day processes required to produce timely and accurate financial statements, including general ledger, account reconciliations, AP, AR, fixed assets and internal reporting.

- Controlled extensive budgeting, forecasting, and variance reporting for eighteen separate entities covering eight states, training employees and management throughout the region.

- Performed due diligence related to the acquisition of seven cable system entities and coordinated the integration of all accounting functions with the corporate office.

- Instituted all FCC informational and rate increase filings throughout the region based on the Cable Act of 1992.

- Responsible for the coordination of all subscriber reporting, sales and property tax filings, franchise fee and copyright filings.

- Grew the accounting department from seven to thirteen before its move to Atlanta, restaffing ninety percent of the department after the move.

- Directed all efforts throughout the region to implement Oracle as the new financial package and a new Access database for the budgeting and forecasting processes.

Storer Cable Communications, Inc				1987 - 1988

Senior Accountant for Operations

Responsibility for the accounting, budgeting, and forecasting activities of this 82,000 subscriber area for this cable television concern that was acquired by Comcast listed above.  Reported to the Area VP and General Manager and managed three employees.

- Implemented new Lotus based model for budgeting and forecasting, training all management on its use.

- Transitioned financial statement preparation from the regional office level to this area office.

- Managed the day to day processes required to produce timely and accurate financial statements for six separate entities including general ledger, AP, AR, fixed assets, subscriber reporting and other internal reporting.

- Developed and maintained tracking mechanism to track progress of cable plant rebuild and the associated competitor overbuild in the area’s largest cable system.

Tracey-Luckey Pecan & Storage, Inc.			1986 - 1987

Senior Accountant

Responsibility for the accounting, budgeting, and office management for a divisional office of this pecan production, processing, and storage entity annually grossing approximately $22 million.  Financial statements were produced for three entities.  Reported directly to the president of the division and managed three employees.

Tarpley & Underwood, CPA’s		   	       	 1984 - 1986

Staff Accountant

Responsibility for the completion of monthly and quarterly client write-up for twenty-three small businesses for this regional CPA firm that is now one of the top twenty-five firms in Atlanta.  Performed all payroll tax, sales tax, property tax, and income tax filings for these and other clients as well as approximately eighty individual returns per year.  Reported directly to both partners with dotted line responsibility to all managers.

The Company requests a return of (amortization) and a return on the costs incurred to respond to Winter Storm Izzy (January 2022), Hurricane Ian (September 2022), Hurricane Nicole (November 2022), Winter Storm Elliot (December 2022), Hurricane Idalia (August 2023), Winter Storm Finn (January 2024), Hurricane Debby (August 2024), Hurricane Helene (September 2024), Winter Storm Cora (January 2025), Winter Storm Enzo (January 2025), numerous other unnamed storms from January 2022 through December 2025, and a return on estimated costs to respond to unknown storm events after December 31, 2025 through May 31, 2026.

Regulatory liabilities represent amounts that are due to ratepayers and reduce the revenue requirement during the refund period. The PTC regulatory liabilities and the proposed refunds are the result of terms unrelated to storm costs in the Stipulation to Extend the Alternate Rate Plan in Docket 44280 approved by the Commission in its Order dated July 31, 2025.

This table is based on the Company’s Exhibit___(CLF JJS MSB), but disaggregates the calculations provided by the Company in the Excel workbook underlying this Exhibit into the Company’s three separate requests that we described.

We provide a more expanded version of this table as Exhibit STF-NKF-4.

At a minimum, the Company’s revenue requirement should have been calculated for the 31 months through December 31, 2028 when rates would be reset in the next base rate proceeding.

The amortization and recovery period is a matter of informed judgment by the Commission and can be extended and shaped to minimize the effects on customer rates.

The Staff recommendation will result in the complete amortization and full recovery of the storm cost regulatory asset on December 31, 2034, or eight years and seven months compared to the Company’s request for amortization and recovery over four years.

Refer to the Company’s response to STF-PIA-29-1.

Refer to the Company’s responses to STF-PIA-29-2, STF-PIA-29-3 and STF-PIA-29-4.

Direct Testimony of Company witnesses Cleve Flann, Josh Stallings, and Matthew Berrigan at 12-14.

Id.

Id.

Refer to the Company’s response to STF-PIA-29-4.

Refer to the Company’s response to STF-PIA-29-3.

Refer to the Company’s response to STF-PIA-29-5.

Id.

Refer to the Company’s response to STF-PIA-29-6.

Id.

Refer to the Company’s response to STF-PIA-29-7.

Id.

Refer to the Company’s response to STF-PIA-29-9.

Id.

Refer to the Company’s response to STF-PIA-29-4.

This statement is based on Witness Kollen’s and Witness Futral’s experience in their reviews of storm responses, including resourcing, management, technology used, and storm costs incurred by utilities in other jurisdictions, including multiple utilities in Florida and South Carolina.

Refer to the Company’s response to STF-PIA-29-3.

In the absence of technology tools and detailed documentation of resourcing decisions and management, it is not possible to recreate the circumstances at the time the decisions were made or to quantify the effects of different decisions that would have been made.

Refer to the Company’s response to STF-PIA-33-1.

Refer to the Company’s response to STF-PIA-29-8.

Id.

Refer to the Company’s response to STF-PIA-29-10.

Refer to the Company’s response to STF-SCR-1-13 and Attachments G and H.

Refer to the Company’s response to STF-PIA-29-10.

Refer to the Company’s response to STF-PIA-29-28.

Id.

Refer to the Company’s response to STF-PIA-33-7(c), (d), and (e).

Email from Regulatory Affairs (Georgia Power Company) to Rob Trokey (Staff) and Tom Newsome (Staff) dated December 18, 2025 with two Excel file attachments. The Excel file “Consolidated MFRs – Staff Edits 11.20.25 w Notes-1” explaining why the Company could not provide the information in its MFRs as requested by the Staff in response to draft MFRs provided to Staff for comment.

Refer to the Company’s informal April 3, 2026 response to a March 26, 2026 Teams meeting set of generated questions.  Refer further to the attachment file named PSC Staff Follow Up – 4.3.26 at tab JETS External Charges (table showing external contractor costs by category, consistent with those listed in the Company’s response to STF-SCR-1-13 Attachments G).

This answer is based on Witness Kollen’s and Witness Futral’s experience in their reviews of storm responses, including resourcing, management, technology used, and storm costs incurred by utilities in other jurisdictions, including multiple utilities Florida and South Carolina.

Refer to the Company’s response to STF-SCR-1-13 and Attachments G and H. These assets are referred to as “units of property.”

Id.

Refer to the Company’s response to STF-PIA-29-10.

Refer to the Company’s response to STF-SCR-1-13 Attachment G.

Refer to the Company’s MFR 3 Schedules for each named storm and for the “other” un-named storms.

Refer to the Direct Testimony of Melissa Culbreath at Culbreath Exhibit 1 in Duke Energy Carolinas, LLC. Docket No. 2025-65-E filed with the South Carolina Public Service Commission on March 21, 2025. We have attached a copy of the testimony cover page and this exhibit as Exhibit STF-NKF-5. Total estimated South Carolina jurisdictional incremental storm restoration costs were depicted as $505.028 million and the capitalized portion of those costs were depicted as $212.487 million, approximately 42% of the total.

Id.

Refer to the Company’s response to STF-SCR-1-17.

Refer to the Company’s follow-up responses on April 3, 2026 to the March 26, 2026 Teams meeting Staff inquiries.

Refer to MFR-4 submitted with the Company’s application, which summarizes costs for all 2022-2025 storms combined. Total outside services costs summed to $1.117 billion for all the storms and total costs originally included in the storm cost regulatory assets before capitalization and other adjustments summed to $1.191 billion for all the storms.

Refer to the TRADE SECRET response to STF-PIA-1-33, Attachment A, for the list of invoices associated with Hurricane Helene processed through March 2025 and to the TRADE SECRET response to STF-PIA-4-3, Attachment at tab Additional Invoices, for the list of invoices posted after March 2025 associated with Hurricane Helene. Refer also to the TRADE SECRET response to STF-SCR-1-23, Attachment A, for the list of invoices by storm associated with all the other storms in the 2022-2025 review period.

Id.

Id.

Refer to the Company’s TRADE SECRET responses to STF-SCR-7-1 through 7-5.

Refer to the Company’s TRADE SECRET response to STF-SCR-4-1.

Refer to the Company’s TRADE SECRET response to STF-SCR-4-2.

Refer to the Company’s TRADE SECRET response to STF-SCR-1-14 for the contract copies associated with Hurricane Helene, the Company’s TRADE SECRET response to STF-SCR-1-15 for the contract copies associated with all the other storms in the 2022-2025 review period, and the Company’s TRADE SECRET response to STF-SCR-1-16 for the contract copies associated with all embedded or native contractors.

Refer to the Company’s Supplemental Attachment response to STF-PIA-29-16.

Id. at 3.

Refer to the Company’s MFR 7.2 for the annual amounts and to MFR 6.1 for the monthly amounts.

Refer to Company’s MFR 6.1. We provide a copy of this MFR 6.1 as Exhibit STF-NKF-7 for ease of reference.

Refer to Company’s MFR 8.

Refer to the Company’s response to STF-PIA-29-10 and Attachment at 1.

Refer to the Company’s MFR 3 - Other at line 13.

See the Kentucky Public Service Commission’s February 28, 2026 Order in Case No. 2025-00257 at 12, 87-89, and 92-94.

See the New York State Public Service Commission’s June 15,2016 Order in Cases 15-E-0283 et al adopting the February 19, 2016 Joint Proposal containing these terms at Appendix I at 1.