Pro Forma Power Purchase Agreement for

Firm Capacity, Energy Storage Services, and Ancillary Services from a

Battery Energy Storage System

[Paired with a Renewable Resource]

for 2026 All-Source Capacity Request for Proposals for

Need Years 2032-2033

at #FacilityName#

between

Georgia Power Company

and

#SellerLegalName#

# This agreement contains confidential information for use by Georgia Power Company, Seller, or their Affiliates only; do not disclose, copy, or scan for any other purpose, except to the extent required by law or allowed by contract.

Table of Contents

Schedule of Defined Terms	8

Part 1	Term of Agreement	24

1.1	Term.	24

1.2	Survival.	24

1.3	Conditions Subsequent.	24

Part 2	Representations, Warranties, and Covenants	27

2.1	Seller Representations, Warranties, and Covenants.	27

2.2	GPC Representations, Warranties, and Covenants.	30

Part 3	Preservation of Terms; Consents; Taxes	30

3.1	Preservation of Terms.	30

3.2	Other Approvals.	31

3.3	Taxes.	31

Part 4	Sale and Delivery of Capacity	31

4.1	Agreement to Sell and Purchase.	31

4.2	Calculation of Monthly Capacity Payments.	33

4.3	Paired Renewable Resource.	33

Part 5	Billing and Collections	33

5.1	Capacity Billing and Payment.	33

5.2	Billing Disputes and Final Accounting.	34

5.3	Interest.	35

5.4	Billing and Payment Records.	35

Part 6	Performance Security	35

6.1	Performance Security.	35

6.2	Replacement Collateral; Substituted Collateral; Release of Collateral.	36

6.3	Draws; Replenishment.	36

6.4	Reporting.	36

6.5	Pre-Approval of Non-Cash Eligible Collateral.	36

6.6	Delivery of Eligible Collateral for Performance Security.	37

Part 7	Facility Design and Construction; Achieving Commercial Operation	37

7.1	Design and Construction of the Facility.	37

7.2	Key Milestones and Milestone Schedule.	39

7.3	Failure to Achieve Commercial Operation by RCOD.	40

Part 8	Interconnection and Metering	41

8.1	Interconnection.	41

8.2	Metering and Telemetry.	42

Part 9	BESS Capacity and Performance Tests	43

9.1	Tested Storage Capacity and Contracted Capacity.	43

9.2	Disputes Concerning Capacity Tests.	43

Part 10	Operation and Maintenance	43

10.1	Operation and Maintenance.	43

10.2	Maintenance Scheduling.	44

10.3	Reserved.	45

10.4	Access to the Site and the Facility.	45

10.5	Availability of Records.	46

10.6	Effect of GPC Action.	46

10.7	Operating Committee.	46

10.8	AGC.	47

10.9	AGC Performance Requirements.	47

10.10	Reserved.	48

10.11	Performance Metrics.	48

10.12	Reactive Power.	48

10.13	Cyber Security.	48

Part 11	BESS; Grid Charging; Renewable Resource Charging	49

11.1	Use of BESS.	49

11.2	Reserved.	49

11.3	Grid Charging; Renewable Resource Charging.	49

Part 12	Energy Dispatch	49

12.1	Energy Dispatch.	49

12.2	Coordination and Dispatch.	49

12.3	Effect of Grid Emergencies.	49

12.4	Effect of Insufficient Capability in the Transmission System.	50

Part 13	Insurance	50

13.1	Insurance Required of Seller.	50

13.2	Proof of Insurance.	50

13.3	General Terms.	50

13.4	Required Insurance.	50

13.5	Notice of Change or Cancellation.	51

13.6	Payment of Premiums.	51

13.7	No Waiver of Liability.	51

Part 14	Risk and Claims	52

14.1	Liability for Facility.	52

14.2	No Liability.	52

14.3	Scope of Indemnity.	52

14.4	Survival.	52

Part 15	Force Majeure	52

15.1	Definition of Force Majeure Event.	52

15.2	Force Majeure Exclusions.	53

15.3	No Breach or Liability.	53

15.4	Monthly Capacity Payments.	54

15.5	Notice of FME; Updates.	54

15.6	Requirements for Relief.	54

15.7	Extended FME.	55

Part 16	Default and Remedies	55

16.1	Default by Seller.	55

16.2	Default by GPC.	59

16.3	Remedies.	61

16.4	Rights of Specific Performance.	62

16.5	Limitation of Remedies, Liability, and Damages.	62

16.6	Waiver of Consequential Damages.	62

16.7	Disclaimer of Warranties.	63

16.8	No Interruption.	63

16.9	Duty to Mitigate.	63

Part 17	Compliance with Laws	63

17.1	Change of Law.	63

17.2	No Dedication.	70

17.3	Compliance.	70

17.4	Environmental Compliance.	70

17.5	Wildlife.	72

17.6	Notices of Violations and Potential Violations; NOV Remediation Plan.	72

Part 18	Assignment, Transfers, and Changes of Control	72

18.1	Assignment, Transfers, and Changes of Control.	72

18.2	Financing Assignment; Estoppels.	73

18.3	Reimbursement of GPC’s Costs.	73

18.4	General Requirements.	74

Part 19	Dispute Resolution	74

19.1	Notice of Dispute; Dispute Resolution Process.	74

19.2	Expert Arbitration.	75

19.3	JAMS Arbitration.	75

19.4	Location of Arbitration.	77

19.5	Mandatory Arbitration.	77

19.6	Injunctive Relief.	77

19.7	Continued Performance.	78

Part 20	Miscellaneous Provisions	78

20.1	Amendments.	78

20.2	Binding Effect.	78

20.3	Counterparts.	78

20.4	Notice.	78

20.5	Entire Agreement.	78

20.6	Governing Law.	78

20.7	Liability.	78

20.8	GPC’s Agent.	78

20.9	No GPC Affiliate Liability.	78

20.10	Time of Essence; No Waiver.	79

20.11	Headings.	79

20.12	Third Parties.	79

20.13	Agency.	79

20.14	Severability.	79

20.15	Negotiated Agreement.	79

20.16	Confidentiality.	79

20.17	Contract Interpretation.	80

20.18	Replacement Index.	81

20.19	Recording.	81

20.20	Further Assurances.	81

20.21	Transfer of Information Acknowledgement.	81

20.22	Service Contract.	81

Exhibit A – Facility Description and Additional Details	82

Exhibit A-1 – Key Milestones and Required Key Milestone Dates	85

Exhibit A-2 – Performance Security and Liquidated Damages	88

Exhibit B – Capacity; Capacity Payments and Payment Reductions; Buydown	89

Exhibit C – Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance METRICS AND Requirements	93

Exhibit D – Reserved	102

Exhibit E – Performance Testing Procedures	103

Exhibit G – AGC and Facility Minimum Data Requirements	105

Exhibit H – Facility One-Line Diagram	112

Exhibit I – Requirements for PPA Facility	113

Exhibit J – Form of Commercial Operation Completion Certificate	116

Exhibit K – Form of Standby Letter of Credit	118

Exhibit L – Form of Guaranty	123

Exhibit M – VIE Certification	133

136

Exhibit N  – Transfer of Information Acknowledgement	137

Exhibit O – Environmental Compliance Certification	138

Exhibit P – Notices	140

Schedule of Defined Terms

## This PPA uses the defined terms identified in this Schedule of Defined Terms or in the body of this PPA and the rules of construction identified in Section 20.17 (Contract Interpretation).

Abandonment: Any Seller: (i) cessation of Facility development, construction, or installation activities for a continuous period of not less than 90 consecutive Days, other than: (a) as mutually agreed by the Parties in writing; (b) a suspension resulting from an FME; or (c) planned periods of inactivity reflected in the level 3 critical path method EPC Contract Schedule provided by Seller for the corresponding Key Milestone Date; or (ii) written statement or action evidencing Seller’s intent to permanently discontinue development or construction of the Facility or otherwise not to achieve Commercial Operation.

ACP: See Annual Capacity Price.

ACP Adjustment: As defined in Section 17.1.3 (GPC Review; ACP Adjustment).

Adjustment Period: As defined in Section 8.2.3 (Adjustments).

### Affiliate: For any specific Person, any other Person directly or indirectly controlling or controlled by or under common control with that Person. For purposes of this definition, “control” when used regarding any entity means the power to direct the management and policies of the entity, directly or indirectly, whether through the ownership of voting securities, by contract, or otherwise. For purposes of this PPA, it is assumed that a Person directly or indirectly owning 50% or more of the outstanding stock or other equity interest of another Person has “control” of that Person. The terms “controlling” and “controlled” have meanings correlative to “control.”

After-Tax Basis: With respect to a given payment required to be made to any Person, the amount of such payment (“Base Payment”) supplemented by a further payment (“Additional Payment”) to that Person so that the sum of the Base Payment plus the Additional Payment will, after deduction of the amount of all income taxes required to be paid by such Person in respect of the receipt or accrual of the Base Payment and the Additional Payment (taking into account the net present value of any reduction in such income taxes resulting from tax benefits realized by the recipient as a result of the payment or the event giving rise to the payment), be equal to the amount required to be received. Such calculations will be made on the basis of the highest generally applicable federal, state, and local income tax rates applicable to the Person for whom the calculation is being made for all relevant periods and will take into account the deductibility of state and local income taxes for federal income tax purposes.

### AGC: See Automatic Generation Control.

### AGC Performance Requirements: The AGC Status Performance Requirement and the AGC Setpoint Response Performance Requirement.

### AGC Plan: As defined in Section 10.9 (AGC Performance Requirements).

### AGC Setpoint: A value (MW) that will range from the Operating Low Limit to the Operating High Limit.

### AGC Setpoint Response Performance Metric: As defined in Section 3.2.2 (AGC Setpoint Response Performance Requirement) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### AGC Setpoint Response Performance Requirement: As defined in Section 3.2.2 (AGC Setpoint Response Performance Requirement) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### AGC Status: As defined in Section 3.2.1 (AGC Status Performance Requirement) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### AGC Status Performance Metric: As defined in Section 3.2.1 (AGC Status Performance Requirement) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### AGC Status Performance Requirement: As defined in Section 3.2.1 (AGC Status Performance Requirement) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### AIER: As determined for each Hour, the variable dispatch cost of the incremental resources that serve the collective obligations of the Southern Companies.

Amended Commission Certificate: As defined in Section 1.3.4 (Revocation, Qualifications, or Conditions).

### Ancillary Services: All commercial products other than electrical output that are produced by or related to the Facility, including Electrical Products, Environmental Attributes, any other environmental or regulatory credits or allowances resulting from operation of the Facility, and any other benefit GPC otherwise would have realized from or related to the Facility if GPC rather than Seller had constructed, owned, or operated the Facility, it being the Parties’ intent that all the benefits and entitlements in addition to electrical output that flow to the owner or operator of the Facility, whether existing as of the Effective Date or at any time during the Term, belong to GPC at no additional cost to GPC. However, if a commercial product is not produced by the Facility, Seller will not be required to acquire the commercial product in the market to comply with this PPA. Ancillary Services do not include: (i) any federal, state, or local tax attributes arising from the ownership of the Facility, including investment tax credit (ITC), production tax credit (PTC), and depreciation deductions; (ii) grants in lieu of investment tax credits or any similar financial payment or grant regarding the Facility; or (iii) the metered electric energy produced by the Facility.

### Annual Capacity Price (ACP): The annual price to be paid by GPC to Seller for GPC’s purchase of the Facility’s capacity, as set forth in Table C-1 (Annual Capacity Price) in Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements), subject to adjustment as set forth in  Part 17 (Compliance with Laws). .

### Annual Period: Each consecutive 12-Month period during the Term, with the first Annual Period beginning on the Delivery Commencement Date.

### Annual RTE: As defined in Section 2.4.1 (Annual RTE Performance Test) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Annual RTE Test: As defined in Section 2.4.1 (Annual RTE Performance Test) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

Arbitration Panel: As defined in Section 19.3.2(i) (Initiation of Arbitration; Selection of Party-Appointed Arbitrators).

### ASC: The FASB Accounting Standards Codification.

### Automatic Generation Control (AGC): The equipment and capability of a facility to automatically adjust energy output within the applicable balancing authority for purposes of interchange balancing, and specifically, the Facility’s capability to accept a set point electronically and the automatic adjustment and regulation of the Facility’s energy output to meet that set point.

### Auxiliary Operational Load: Load that is required for thermal management of the BESS (e.g. HVAC) and essential Facility operation (e.g. control system building) that must be metered separately from Charging Energy or, if the BESS is not capable of separately metering Auxiliary Operational Load, determined based on aggregated telemetry from the BESS controller or other measurement mutually agreed by the Operating Committee. Auxiliary Operational Load is distinct from and must be measured or calculated separately from Charging Energy and paid for by Seller.

### Available: All times following the Delivery Commencement Date when the BESS, as applicable, is not Unavailable.

### Banking Day: Any Day on which banking institutions in Atlanta, Georgia are open.

### Battery Energy Storage System (BESS): The battery energy storage system at the Site, as further described in Exhibit A (Facility Description and Additional Details), that is interconnected to the Southern Company Transmission System at the POI.

Battery Management System (BMS): As defined in Section 10.13.1 (Sourcing Restrictions).

### BESS: See Battery Energy Storage System.

### BESS Controller: As defined in Section 10.13.1 (Sourcing Restrictions).

Billing Dispute: As defined in Section 19.3 (JAMS Arbitration).

### BMS: See Battery Management System.

### Business Day: Any Day excluding Saturday, Sunday, and NERC-defined holidays.

### Central Prevailing Time (CPT): The time in the central time zone of the United States, considering daylight savings time if it is in effect (i.e., Central Standard Time (CST) or Central Daylight Time (CDT), as applicable).

Change in Accounting Standards: As defined in Section 2.1.8(iv) (VIE Certification).

### Change of Control Transaction: Any transaction or series of related transactions that, if consummated, would result in a Party being an Affiliate of a different Ultimate Parent Entity immediately after the transaction.

Change of Law: An applicable law or a change to or repeal of an existing applicable law, including changes in legally binding interpretations of applicable law, in each case, enacted after the Effective Date.

Change of Law Expenditures: (i) reasonable and documented capital expenditures (determined in accordance with GAAP) and incremental operating costs (including new Taxes imposed directly on the ownership, operation, or maintenance of the Facility solely to the extent properly treated as operating expenses in accordance with GAAP), including: (a) capital expenditures or operating costs incurred to modify, operate, or maintain the Facility in compliance with the Change of Law during the Term; and (b) additional or different Facility equipment, engineering, procurement, construction, or other Facility modifications required to comply with the Change of Law; and (ii) any actual and realized loss or reduction of applicable tax incentives, tariffs, credits, rebates, or other governmental benefits applicable to the Facility, in each case, incurred by Seller as a direct result of a Change of Law, reasonable in amount, consistent with Prudent Industry Practice, and net of any costs saving, insurance proceeds, tax benefit, and third-party recovery. Capital expenditures or operating costs will not constitute Change of Law Expenditures unless GPC, using Prudent Industry Practices, would incur the same capital expenditures or operating costs regarding its own facilities of the same type as the Facility because of the requirements of the Change of Law (taking into account differences in facility generating capacity, location, and the frequency and duration of facility dispatch).

Change of Law Notice: Written notice from Seller to GPC of a Change of Law that will cause, or is reasonably expected to cause, Seller to incur Change of Law Expenditures.

### Charge/Discharge Rate Performance Metric: As defined in Section 2.3.2 (Charge/Discharge Rate Performance Metric) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Charging Energy: Energy provided from Grid Charging or, if applicable, the Renewable Resource, for the purpose of charging the BESS in accordance with GPC’s AGC Setpoint signals or direction.

### Claim: Any loss, damage, cost, expense, or liability (on an After-Tax Basis) for any damage or claim (including any demand, suit, settlement, judgment, penalty, fine, proceeding, or action of any kind) for: (i) personal or bodily injury (including death); (ii) property damage (including loss of use);; (iii) infringement; (iv) monetary damage or expense; or (v) equitable relief, including all Claim expenses (e.g., actual attorneys’ fees reasonably incurred; investigation, defense, litigation, court, arbitration, or mediation costs; and expert, consultant, arbitrator, or mediator fees or expenses and bond expense).

### Commercial Operation: The Facility’s ability to meet the requirements of Section 7.1.5 (Commercial Operation).

Commercial Operation Completion Certificate: The certificate in the form of Exhibit J (Form of Commercial Operation Completion Certificate) that Seller submits to GPC pursuant to Section 7.1.6 (Commercial Operation Completion Certificate).

### Commercial Operation Date (COD): The date the Facility achieves Commercial Operation.

### Commission: The Georgia Public Service Commission, or any Governmental Authority succeeding to the powers and functions of the Commission.

### Commission Certificate: A certificate of public convenience and necessity as required by OCGA § 46-3A-1, et seq.

### Commission Certificate Target Date: The date that is 250 Days after the date GPC requests a Commission Certificate for this PPA.

### Confidential Information: Business or technical information rightfully in the possession of either Party that derives actual or potential commercial value from not being generally known or readily ascertainable through independent development or reverse engineering by Person(s) who can obtain economic value from its disclosure or use, including information furnished or disclosed by the disclosing Party or another Person on behalf of the disclosing Party to the other Party in connection with discussions leading up to execution of this PPA, including this PPA. Seller must designate Confidential Information as confidential in writing on each page of a document contemporaneously with Seller’s supply of the information. Confidential Information does not include information that: (i) is or becomes publicly available other than because of a violation of this PPA; (ii) was, at the time of the disclosure, already in the receiving Party’s possession; (iii) is disclosed to the receiving Party by a third party who, to the receiving Party’s knowledge, is not prohibited from disclosing the information under any agreement with the disclosing Party; (iv) the receiving Party develops or derives without the aid, application or use of the privileged or proprietary information; or (v) the receiving Party is required to disclose in accordance with applicable law.

### Consent: Any approval, consent, authorization, or other applicable requirement that is required regarding the Project or Facility from any Governmental Authority, including all applicable environmental certificates, licenses, permits, and approvals, and any federal or state compliance program that GPC is or becomes subject to at any time during the Term.

### Contracted Capacity: The Storage Device Design Capacity established at the Effective Date and as stated in Table A-3 (Additional Facility and Operating Information) of Exhibit A (Facility Description and Additional Details).

Costs: As defined in Section 16.3.3 (Determining Gains, Losses, and Costs).

### CPT: See Central Prevailing Time.

### Creditworthy or Creditworthiness: With respect to a Person, the Person has (i) a senior unsecured debt rating, or if the Person has no senior unsecured debt rating, an issuer rating from two of the Rating Agencies above: (a) BBB+ by S&P, if rated by S&P; (b) Baa1 by Moody’s, if rated by Moody’s; and (c) BBB+ by Fitch, if rated by Fitch, respectively; or (ii) (1) a senior unsecured debt rating or, if the Person has no senior unsecured debt rating, an issuer rating from two of the Rating Agencies of at least: (x) BBB- by S&P, if rated by S&P; (y) Baa3 by Moody’s, if rated by Moody’s; and (z) BBB- by Fitch, if rated by Fitch, respectively; and (2) satisfactory and verifiable creditworthiness determined in GPC’s reasonable discretion.

Cure Certification: As defined in Section 16.1.8(iii) (Storage Performance Metric Achieved Below .60).

### Cure Period: The reasonable period within which Seller must: (i) cure an Event of Default arising from inadequate Storage Performance Metric Achieved in accordance with Section 16.1.8 (Storage Performance Metric Achieved Below .60), which must not exceed 180 Days from when the default first occurred unless extended in accordance with Section 16.1.8(ii); or (ii) cure an inadequate Tested Storage Capacity in accordance with Section 16.1.9 (Tested Storage Capacity Below 70% Contracted Capacity; Cure; Remedies) or Section 1.3.1 (Cure Plan and Cure Period) of Exhibit B (Capacity; Capacity Payments and Payment Reductions; Buydown), as applicable, which must not exceed 180 Days from the completion of the Performance Test unless extended in accordance with PPA Section 16.1.9(i) (Cure Period Extension) or Exhibit B, Section 1.3.1.A (Cure Period Extension).

Cyber Security Incident: As defined in Section 10.13 (Cyber Security).

### Cycle or Cycled: The equivalent charge of Storage Device Operating Energy (in MWhs) from 0% to 100% and subsequent discharge from 100% to 0%, regardless of whether the complete charge or complete discharge occurs during one or more charges or discharges. For Daily Cycle determinations, the Day in which the relevant discharging occurs will include the discharge in the Cycle determination for that Day, regardless of when the charging occurs.

### Cycle Limit: For each Annual Period, the maximum number of times that the BESS may be Cycled.

### Daily Cycle Limit: The maximum number of Cycles per Day, which is [two]. [Note to Bidders: Bidder may propose a value for the Daily Cycle Limit, but GPC requires a minimum of one Cycle per Day].

### Day: Any calendar day, including Saturday, Sunday, or a holiday.

Defaulting Party: As defined in Section 16.3.1 (Remedies for Event of Default).

### Delivery Commencement Date: The Commercial Operation Date, except that the Delivery Commencement Date may not be more than nine Months before the RCOD. If Commercial Operation occurs more than nine Months before the RCOD, the Delivery Commencement Date will be the date that is nine months before RCOD. [Note to Bidders: For any Month before the Delivery Commencement Date, Exhibit B provides that Monthly Capacity Payments are not owed to Seller as set forth in Exhibit B.]

### Discharging Energy: Energy discharged from the BESS in accordance with GPC’s AGC Setpoint signals or direction.

### Dispatch Center: The control center designated by GPC in writing as being the primary control point for dispatch instructions and other notifications provided in accordance with Part 12 (Energy Dispatch) and Exhibit F (Facility Operating and Dispatching Requirements), Part 2 (Dispatch), as may be modified during the Term. There may only be one Dispatch Center designated at any one time.

Dispute Response: As defined in Section 19.1 (Notice of Dispute; Dispute Resolution Process).

Disputing Party: As defined in Section 19.1 (Notice of Dispute; Dispute Resolution Process).

Early Termination Date: As defined in Section 16.3.1 (Remedies for Event of Default).

### Eastern Time (ET): The time in the easternmost time zone of the United States, considering daylight savings time if it is in effect (i.e., Eastern Standard Time (EST) or Eastern Daylight Time (EDT), as applicable).

### Effective Date: The date of full execution of this PPA, which will be the date on which GPC signs this PPA, as shown on the signature page.

Effective Date Accounting Standards: As defined in Section 2.1.8(i) (VIE Certification).

### Electric System: The network of electric generation, transmission, or distribution facilities owned or operated by GPC or other electric utilities.

### Electrical Products: All electrical products produced by or related to the Facility, including spinning reserves, operating reserves, black start capability, balancing energy, regulation service, ramping capability, reactive power and voltage control, frequency control, and other ancillary or essential reliability service products. Electrical Products also include any benefit GPC otherwise would have realized from or related to the Facility if GPC, rather than Seller, had constructed, owned, or operated the Facility, it being the Parties’ intent that all those benefits and entitlements, in addition to electrical output, that flow from construction, ownership, or operation of the Facility, whether existing as of the Effective Date or at any time during the Term, will belong to GPC, at no additional cost to GPC. Electrical Products do not include: (i) any federal, state, or local tax attribute arising from ownership of the Facility, including investment tax credit (ITC), production tax credit (PTC), or depreciation deductions; (ii) any grant in lieu of investment tax credit or any similar financial payment or grant regarding the Facility; or (iii) the metered electric energy produced by the Facility.

### Eligible Collateral: Either: (i) a Letter of Credit; (ii) cash deposited into a GPC Security Account by Seller; or (iii) a Seller Guaranty. However, at least 50% of any Eligible Collateral required under any provision of this PPA must be in the form of either a Letter of Credit or cash deposited into a GPC Security Account whenever a Seller Guarantor supplying a Seller Guaranty under this PPA has an investment grade rating such that its senior unsecured debt (or issuer rating if such Person has no senior unsecured debt rating) is not rated at least: (a) BBB by S&P, if rated by S&P; (b) Baa2 by Moody’s, if rated by Moody’s; and (c) BBB by Fitch, if rated by Fitch, respectively. For the purposes of the immediately preceding sentence, a Person is not required to have a senior unsecured debt rating (or issuer rating if such Person has no senior unsecured debt rating) from each of S&P, Moody’s, and Fitch, but must have the requisite senior unsecured debt rating (or issuer rating if such Person has no senior unsecured debt rating) as set forth above from at least two of the three Rating Agencies.

### Emergency Condition: Defined in the IA.

### Energy Storage Performance Metric: As defined in Section 2.3.1 (Energy Storage Performance Metric) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Environmental Attributes: Either: (i) any fuel-related, emissions-related, air quality-related, energy source related, or other environmental-related aspect, claim, characteristic, benefit, certificate, credit, reduction, offset, saving, allowance, efficiency, tag, attribute, demand reduction, or similar product or right (including any right relating to greenhouse gases and any green certificate, green tag, renewable certificate, REC, CO2 credit, emission reduction credit, and any that otherwise arise or result from the use  or existence of the Facility): (a) howsoever titled and whether known or unknown; (b) whether existing as of the Effective Date or at any time during the Term; and (c) any attribute  that could qualify or does qualify for application toward compliance with any local, state, federal, international, or private sector energy portfolio standard, green pricing or green certification program, energy program, carbon reduction or greenhouse gas reduction initiative, carbon or greenhouse gas offset program, carbon or greenhouse trading program, carbon or greenhouse gas cap and trade program, carbon or greenhouse taxation, electricity savings program, or other environmental program, incentive, mandate, or objective, in each case whether voluntary or mandatory; or (ii) any environmental benefit GPC otherwise would have realized from or related to the Facility if GPC, rather than Seller, had constructed, owned, or operated the Facility, as applicable. Environmental Attributes do not include: (I) any federal, state, or local tax attribute arising from ownership of the Facility, including any investment tax credit (ITC), production tax credit (PTC), or depreciation deduction; (II) any grant in lieu of ITC or any similar financial payment or grant regarding the Facility; or (III) the metered electric energy produced by the Facility.

### Environmental Law: Any applicable law that relates to pollution, occupational safety, protection of occupational health, or the protection of the environment, including, (a) the Comprehensive Environmental Response, Compensation and Liability Act, 42 U.S.C. § 9601 et seq., (b) the Resource Conservation and Recovery Act, 42 U.S.C. § 6901 et seq., (c) the Federal Water Pollution Control Act, 33 U.S.C. § 1251 et seq., (d) the Clean Air Act, 42 U.S.C. § 7401 et seq., (e) the Hazardous Materials Transportation Authorization Act of 1994, 49 U.S.C. § 5101 et seq., (f) the Toxic Substances Control Act, 15 U.S.C. §§ 2601 through 2629, (g) the Oil Pollution Act, 33 U.S.C. § 2701 et seq., (h) the Emergency Planning and Community Right-to-Know Act, 42 U.S.C. § 11001 et seq., (i) the Safe Drinking Water Act, 42 U.S.C. §§ 300f through 300j, (j) the Federal Insecticide, Fungicide, & Rodenticide Act, 7 U.S.C. § 136 et seq., (k) the Endangered Species Act, 16 U.S.C. § 1531 et seq., (l) the Clean Water Act, 33 U.S.C. § 1251 et seq., (m) National Environmental Policy Act, 42 U.S.C. § 55 et seq., (n) the Migratory Bird Treaty Act, 16 U.S.C. § 703 et seq., (o) the Bald and Golden Eagle Protection Act, (p) Archeological Resources Protection Act, 16 U.S.C. § 470aa et seq., (q) National Historic Preservation Act, 54 U.S.C. § 300101 et seq., and (r) state or local equivalents to items (a) through (q). However, the term “Environmental Law” does not include any law relating to worker health or safety matters to the extent not related to human exposure to hazardous or toxic materials, wastes, or substances.

Environmental Recommendations: As defined in Section 17.4.2 (Environmental Recommendations).

### EPA: The U.S. Environmental Protection Agency.

### ET: See Eastern Time.

### Event of Default: A Party’s failure to perform or comply with a material PPA term or condition, as further described in Section 16.1 (Default by Seller) for Seller and in Section 16.2 (Default by GPC) for GPC.

Excess Expenditures: The portion of Change of Law Expenditures that exceeds the Threshold Amount, as calculated by subtracting the Threshold Amount (expressed in dollars) from the total Change of Law Expenditures for an applicable Change of Law.

Excess Expenditures Notice: Written notice from Seller to GPC requesting recovery of Excess Expenditures or approval of an Operational Alternative.

### Extended FME: As defined in Section 15.7.1 (Notice and Remedy Plan for Extended FME).

### Facility: The complete facility comprised of the BESS and ancillary facilities and equipment located at the Site but excluding any Renewable Resource. The Facility will include all auxiliary equipment and facilities necessary or used for the control, storage, delivery, or monitoring of electricity stored on the Site. All equipment and facilities installed on Seller’s side of the POI at the Site will be part of the Facility, except for those that constitute Interconnection Facilities or, if applicable, any Renewable Resource.

### FASB: Financial Accounting Standards Board.

### Federal Power Act:  The Federal Power Act, 16 U.S.C. § § 791a et seq. (1994), as amended from time to time, and any successor statute of similar import.

### FERC: The Federal Energy Regulatory Commission, or any Governmental Authority succeeding to the powers or functions of FERC.

Financing Assignment: An assignment of this PPA or interest in the Facility for collateral security purposes in connection with any financing or refinancing relating to the Facility.

### Fitch: Fitch Ratings Ltd. or its successor. If Fitch ceases to exist or publish ratings, Fitch will mean a nationally recognized rating agency mutually agreed upon by the Parties.

FME Remedy Plan: As defined in Section 15.7.1 (Notice and Remedy Plan for Extended FME).

Force Majeure Event (FME): As defined in Section 15.1 (Definition of Force Majeure Event).

### Forced Derate: A time during which the operational capability of the BESS is reduced to a level below the Storage Device Design Capacity, SDOE, or Maximum Rate of Charge for reasons other than a Force Majeure Event and that is not a Scheduled Outage, Maintenance Outage, or a Forced Outage.

### Forced Outage: A time during which the BESS is wholly Unavailable for reasons other than a Force Majeure Event and that is not a Scheduled Outage or a Maintenance Outage.

### GAAP: Generally accepted accounting principles issued by the Financial Accounting Standards Board (FASB), as may be modified.

Gains: As defined in Section 16.3.3 (Determining Gains, Losses, and Costs).

### Georgia Integrated Transmission System (Georgia ITS):  The Georgia Integrated Transmission System, which is owned individually by GPC, Georgia Transmission Corporation, Municipal Electric Authority of Georgia, or Dalton Utilities, and operated as an integrated transmission system for transmitting, receiving, or distributing electric energy or capacity.

Governmental Approvals: As defined in Section 7.1.5(viii) (Commercial Operation).

### Governmental Authority:  As applicable to the specific Party, facility, or event, any federal, state, or local governmental or regulatory authority, administrative agency, commission, department, board, or court that has jurisdiction over that Party, the Facility, or the subject matter of this PPA, but excluding any federal, state, or local governmental or regulatory authority, administrative agency, commission, department, board, or other such entity acting in a capacity as lender, guarantor, or mortgagee.

GPC: Georgia Power Company, a Georgia corporation, as specified in the preamble.

### GPC-Related Party: Each of GPC, Southern Company, and their Affiliates, and the officers, directors, employees, representatives, and agents of each of them.

GPC Consolidation: As defined in Section 2.1.8(i) (VIE Certification).

GPC Election Deadline: (i) with respect to an Excess Expenditures Notice concerning capital expenditures, Taxes, or operating costs, the date that is 180 Days after GPC’s receipt of the Excess Expenditures Notice; and (ii) with respect to an Initial Tariff Notice, the date that is 90 Days after GPC’s receipt of the Initial Tariff Notice.

GPC Election Notice: Written notice from GPC to Seller of GPC’s election to pay an ACP Adjustment, implement Operational Alternatives, or terminate the PPA.

### GPC Security Account:  An account designated by GPC for the benefit of GPC, under the exclusive control of GPC and free of any liens (including the lien of any lender) of any Person or entity other than GPC. Any GPC Security Account will be established and maintained at the expense of Seller and held by a depositary bank acceptable to GPC under a control agreement in form and substance acceptable to GPC.

### Grid Charging: Charging the BESS from the Electric System.

### Grid Charging Energy: Charging Energy supplied via Grid Charging.

### Guaranteed RTE: The guaranteed Round-Trip Efficiency rate of the BESS stated in Table A-3 (Additional Facility and Operating Information) in Exhibit A (Facility Description and Additional Details).

### Hour: One of the 24 clock-hours of a Day. “Hourly” has a meaning correlative to that of Hour.

Impasse Notice: As defined in Section 19.1 (Notice of Dispute; Dispute Resolution Process).

### Indebtedness: For any Person, each of the following without duplication: (i) obligations of the Person for borrowed money evidenced by bonds, debentures, notes, loan agreements, or other similar instruments; (ii) purchase money indebtedness of the Person constituting an obligation to pay the deferred purchase price of property or services, other than trade payables incurred in the ordinary course of business; (iii) lease obligations of the Person that are capitalized on the balance sheet of the Person in accordance with GAAP; (iv) liabilities of the second Person secured by any lien on any property of the first Person, whether or not the liabilities have been assumed by the first Person; (v) liabilities of the Person regarding letters of credit, applications, or reimbursement agreements for the liabilities; (vi) net obligations of the Person under any swap or hedging agreement; or (vii) indebtedness of the Person owing under direct or indirect guarantees of indebtedness of any other Person or constituting obligations to purchase, acquire, or otherwise protect or insure a creditor against loss regarding indebtedness of any other Person, excluding endorsements of negotiable instruments for deposit or collection in the ordinary course of business.

Initial Capital Expenditures Notice: A preliminary Excess Expenditures Notice solely concerning additional capital costs that Seller must incur because of a Change of Law.

### Initial Synchronization Date: The date that includes the first instant in time when energy discharged by the BESS is delivered to the POI in accordance with the IA.

Initial Tariff Notice: A preliminary Excess Expenditures Notice solely concerning Tariffs.

### Interconnection Agreement (IA): The agreement, entered into, or to be entered into, between Seller and Interconnection Provider, in accordance with Section 8.1 (Interconnection), that provides for the construction and operation of the Interconnection Facilities and governs the interconnection and parallel operation of the Facility with the Electric System.

### Interconnection Facilities: The facilities described in the IA that: (i) must be installed or modified to enable the Facility to deliver the Contracted Capacity and associated energy; (ii) are owned by the Interconnection Provider; and (iii) are necessary to provide the physical electrical connection between the Facility and the Electric System.

### Interconnection Limit: The maximum output amount of power allowed by the IA.

### Interconnection Provider: The owner or operator of the Electric System responsible for providing transmission interconnection service to the Facility (i.e., GPC).

### Interconnection Study: A study by the Interconnection Provider in which the provider studies the Facility’s potential impact on the Electric System to determine necessary Interconnection Facilities and Electric System improvements or affected system upgrades, the estimated related costs, and the schedule of construction, for purposes of entering into an IA or amending an existing IA.

### Interconnection Study Agreement: An agreement between Seller and the Interconnection Provider under which the Interconnection Provider performs the Interconnection Study.

### Interest Rate: Interest per annum equal to the prime rate as published in The Wall Street Journal, or comparable successor publication, under “Money Rates,” as applied daily and compounded quarterly.

ITS Participant: Any of Dalton Utilities, Georgia Transmission Corporation, or the Municipal Electric Authority of Georgia. As used in this PPA, ITS Participant excludes GPC.

JAMS: As defined in Section 19.3.1 (JAMS).

### Key Milestones: Each of the milestones identified in Exhibit A-1 (Key Milestones and Required Key Milestone Dates).

### Key Milestone Date: Each of the dates identified in Exhibit A-1 (Key Milestones and Required Key Milestone Dates) as the date by which Seller guarantees the corresponding Key Milestone will be achieved.

### kV: Kilovolt(s).

### kW: Kilowatt(s).

### kWh: Kilowatt-hours (AC).

### Letter of Credit: An irrevocable standby letter of credit that is: (i) substantially in the form set forth in Exhibit K (Form of Standby Letter of Credit); (ii) issued by a U.S. commercial bank or a U.S. branch of a foreign bank: (a) with total assets of at least 10 billion dollars ($10,000,000,000); and (b) having a general long-term senior unsecured debt rating of: (I) A minus or higher as rated by S&P; (II) A3 or higher as rated by Moody’s; or (III) A minus or higher as rated by Fitch; and (iii) acceptable to GPC in GPC’s sole, but reasonable, discretion.

Losses: As defined in Section 16.3.3 (Determining Gains, Losses, and Costs).

### Maintenance Outage: A planned interruption of a portion or all of the Facility’s operational capability or the charging or discharging capability of the BESS that: (i) has been coordinated in advance with GPC with a mutually agreed start date, time, and duration or to which GPC has consented in accordance with Section 10.2.2 (Maintenance Outages); and (ii) is for the purpose of performing work on specific components of the Facility that would limit the operational capability of the Facility or the charging or discharging capability of the BESS but should not, in the reasonable judgment of Seller, be postponed until the next Scheduled Outage.

### Maintenance Schedule: Seller’s maintenance schedule, including the scope of the maintenance, and outage plans for the Facility that conform to Prudent Industry Practices for similar equipment, including in terms of frequency and duration. Upon GPC approval, the Maintenance Schedule establishes Scheduled Outages.

### Material Adverse Change: Seller or, if Seller is providing Eligible Collateral in the form of a Seller Guaranty, Seller Guarantor experiences any of the following conditions: (i) Seller or Seller Guarantor is no longer Creditworthy; or (ii) the maturity of any Indebtedness of Seller or Seller Guarantor that in the aggregate exceeds fifty million dollars ($50,000,000.00) or 3% of equity, whichever is less, is accelerated by the holder or holders of the Indebtedness because of a Seller or Seller Guarantor default regarding the Indebtedness.

### Maximum Rate of Charge (ROC): The guaranteed maximum rate of charge of the BESS, as further defined in Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### MCF: See Monthly Capacity Fee.

### MCP: See Monthly Capacity Payment.

### Metering System: All meters, metering devices, and related instruments used to measure and record electric energy and to determine the amount of energy that is being made available or delivered to GPC at the POI and for the other purposes set forth in Section 8.2 (Metering and Telemetry).

### Milestone Schedule: A schedule containing, at a minimum, Key Milestones and other significant milestones related to Facility design, engineering, procurement,  construction, Initial Synchronization Date, testing, startup, RCOD, and any other milestone GPC may reasonably request.

### Month: A calendar month, commencing at the beginning of the first Day of such calendar month. “Monthly” has a meaning correlative to that of Month.

### Monthly Capacity Fee (MCF): As defined and determined in accordance with Section 1.2 (Monthly Capacity Payment) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Monthly Capacity Payment (MCP): The amount to be paid by GPC to Seller for GPC’s purchase of the Storage Device Design Capacity for a particular Month, which will equal the Monthly Capacity Fee as adjusted, if applicable, by Monthly Capacity Reduction in accordance with Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements), Part 2 (Monthly Capacity Reductions; Performance Metrics):

### MCP = MCF – MCR

### Monthly Capacity Reduction (MCR): As defined and determined in accordance with Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements), Part 2 (Monthly Capacity Reductions; Performance Metrics).

### Monthly Invoice: As defined in Section 5.1.1 (Seller Invoices).

### Monthly RTE True-Up: As defined in Section 2.1 (Monthly Capacity Reduction) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Monthly Value Factor (MVF): For a given Month, the value factor stated in Table C-2 (Monthly Value Factor (MVF)) in Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Moody’s: Moody’s Investors Service, Inc. or its successor. If Moody’s ceases to exist or publish ratings, Moody’s will mean a nationally recognized rating agency mutually agreed upon by the Parties.

### MVF: See Monthly Value Factor.

### MW: Megawatt alternating current (AC).

### MWh: Megawatt-hour (AC).

### NERC: The North American Electric Reliability Corporation, including any successor, and subdivisions.

Non-Defaulting Party: As defined in Section 16.3.1 (Remedies for Event of Default).

Notice of Dispute: As defined in Section 19.1 (Notice of Dispute; Dispute Resolution Process).

NOV: As defined in Section 17.6.1 (Notices of Violations).

NOV Remedy Plan: As defined in Section 17.6.2 (NOV Remedy Plan).

### Off Peak Season: The Months of March, April, May, September, October, and November.

### On Peak Season: The Months of January, February, June, July, August, and December.

### Operating Committee: The committee established in accordance with Section 10.7 (Operating Committee).

### Operating High Limit: For AGC purposes, the current maximum discharging capability of the BESS, adjusted for any equipment limitation or outage that could limit the maximum output, as further described in Exhibit G (AGC and Facility Minimum Data Requirements).

### Operating Low Limit: For AGC purposes, the current maximum charging capability of the BESS, adjusted for any equipment limitation or outage that could limit charging capability, as further described in Exhibit G (AGC and Facility Minimum Data Requirements).

### Operating Procedures: Procedures developed by the Parties in accordance with Section 10.1.2 (Written Operating Procedures).

### Operating Representatives: Those individuals appointed by each of the Parties to the Operating Committee in accordance with Section 10.7 (Operating Committee).

Operational Alternatives: Proposed changes to the operation of the Facility that avoid or reduce Change of Law Expenditures.

### Party or Parties: Either GPC or Seller or both, as applicable.

Party-Appointed Arbitrators: As defined in Section 19.3.2(i) (Initiation of Arbitration; Selection of Party-Appointed Arbitrators).

### Performance Guarantees: Each of the BESS performance guarantees identified as items A through E in Table A-3 (Additional Facility and Operating Information) of Exhibit A (Facility Description and Additional Details).

### Performance Metrics: Each of the performance metrics described in Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Performance Security: Security in the form of Eligible Collateral that Seller must deliver to GPC to secure Seller’s due performance of Seller’s PPA obligations, as required under Section 6.1 (Performance Security) and Part 1 (Performance Security) of Exhibit A-2 (Performance Security and Liquidated Damages).

### Performance Test: A performance test conducted in accordance with the procedures set forth in Exhibit E (Performance Testing Procedures). Performance Testing has a meaning correlative to that of Performance Test.

### Person: Any natural person, corporation, limited liability company, general partnership, limited partnership, proprietorship, other business organization, trust, union, association, or Governmental Authority.

### Point of Interconnection (POI): The point of connection between the Southern Company Transmission System and the Facility and, if applicable, the Renewable Resource, as identified in Table A-1 of Exhibit A (Facility Description and Additional Details) and further described in the IA.

Potential High Limit (PHL): The estimated value of the potential instantaneous power output (MW) of the Facility as if the Facility is not in a period of curtailment, as further described in Exhibit G (AGC and Facility Minimum Data Requirements).

### PPA: This Power Purchase Agreement for Firm Capacity, Energy Storage Services, and Ancillary Services from a Battery Energy Storage System [Paired with a Renewable Resource] for 2026 All-Source Capacity Request for Proposals for Need Years 2032- 2033 at #FacilityName# between GPC and Seller.

### Primary Beneficiary: As defined in FASB ASC Topic 810 (Consolidation), as issued and modified from time to time by FASB.

### Project: The design, engineering, construction, testing, and commissioning of the Facility and, as applicable, the ownership, operation, management, and maintenance of the Facility, all of which being reasonably expected to enable Seller to fulfill its obligations under this PPA.

### Proposed Resolutions: As defined in Section 19.3.3 (Discovery; Hearing).

### Prudent Industry Practices: Any of the practices, methods, standards, or acts engaged in or approved by a significant portion of the electric power industry in the United States that, at a particular time, in the exercise of reasonable judgment in light of the facts known or that should reasonably have been known when a decision was made, could have been expected to accomplish the desired result, consistent with good business practices, reliability, economy, safety, and expedition. Prudent Industry Practices are not intended to be limited to the optimum practices, methods, or acts to the exclusion of all others, but rather to be acceptable practices, methods, or acts generally accepted in the United States electric power industry having due regard for, among other things, manufacturers’ warranties, applicable law, and, as applicable, requirements of this PPA.

### Rating Agency: The rating entities of S&P, Moody’s, or Fitch. If any Rating Agency ceases to exist or publish ratings, the Rating Agency will be replaced under this PPA with a nationally recognized rating agency mutually agreed upon by the Parties.

### RCOD: See Required Commercial Operation Date.

### Renewable Resource:  If applicable and as may be further described in Exhibit A (Facility Description and Additional Details), a renewable energy generating facility that: (i) connects or will connect to the Southern Company Transmission System at the POI; (ii) will have achieved commercial operation, as defined by the Renewable Resource PPA, on or before the RCOD; (iii) is subject to a Renewable Resource PPA; and (iv) is or will be paired with the Facility.

### Renewable Resource Charging: Charging the BESS from the Renewable Resource, if applicable and as may be further described in Exhibit A (Facility Description and Additional Details).

### Renewable Resource Charging Energy: Charging Energy delivered to the BESS from the Renewable Resource, if applicable.

### Renewable Resource Seller: The counterparty identified in the Renewable Resource PPA responsible for providing to GPC energy from the Renewable Resource, if applicable and as may be further described in Table A-4 (Renewable Resource and Site Information) of Exhibit A (Facility Description and Additional Details).

### Renewable Resource PPA: Either: (i) an existing power purchase agreement (a) under which GPC purchases energy generated by the Renewable Resource; and (b) that was awarded by GPC through a prior GPC RFP; or (ii) a new power purchase agreement in the form of Power Purchase Agreement for Firm Capacity, Associated Energy, and Ancillary Services from a Battery Energy Storage System with Renewable Resource for ESS 500, in either case, if applicable and as may be further described in Table A-1 (Facility and Site Information) of Exhibit A (Facility Description and Additional Details).

Renewable Resource PPA Amendment: If applicable, an amendment to the Renewable Resource PPA executed by GPC and Renewable Resource Seller for the purpose of allowing the paired operation of the Renewable Resource and the BESS.

Reorganization Transaction: A transaction or series of transactions that, if consummated, would result in a change to the interest, or the addition, of a parent of Seller, but that does not change Seller nor its Ultimate Parent Entity.

### Representative: When used regarding a Person, collectively or individually (as the context indicates), the Person, its Affiliates, and any permitted successor or assign, and the directors, officers, employees, representatives, consultants, attorneys, agents, bankers, insurers, financiers, accountants, contractors, or subcontractors of each of them.

Required BMPs: As defined in Section 17.4.1 (Required BMPs).

### Required Commercial Operation Date (RCOD): The date by which the Facility must obtain Commercial Operation, as stated in Table A-2 (Term, RCOD) of Exhibit A (Facility Description and Additional Details), subject to any extension of this date in accordance with Section 7.3.6 (Commercial Operation Delay Caused by Southern Company Transmission System Capability) or Section 15.3.2 (Extension of RCOD).

Responding Party: As defined in Section 19.1 (Notice of Dispute; Dispute Resolution Process).

### ROC: See Maximum Rate of Charge.

### Round-Trip Efficiency (RTE): The amount of energy discharged from the BESS at the low voltage AC side of the main power transformer(s) (exclusive of the Auxiliary Operational Load) divided by the original amount of energy that was used to charge the BESS at the low voltage AC side of the main power transformer(s) (exclusive of the Auxiliary Operational Load).

Rules: As defined in Section 19.3.1 (JAMS).

### S&P: S&P Global Ratings, a division of S&P Global Inc., or its successor. If S&P ceases to exist or publish ratings, S&P will mean a nationally recognized rating agency mutually agreed upon by the Parties.

### Scheduled Outage: Any Facility outage (whole or partial) scheduled in the final, approved Maintenance Schedule.

### SCS: See Southern Company Services.

### SDDC: See Storage Device Design Capacity.

### SDDD: See Storage Device Discharge Duration.

### SDOE: See Storage Device Operating Energy.

### Seller: The counterparty to GPC in this PPA, as specified in the preamble.

### Seller Entity: Each of Seller or any Affiliate, contractor, supplier, contractual party, or customer, or an officer, director, employee, representative, or agent of one of them.

### Seller Guarantor: A Person who, at the time of execution and delivery of its Seller Guaranty: (i) is either: (a) an Affiliate of Seller; or (b) otherwise an entity acceptable to GPC; and (ii) is Creditworthy.

### Seller Guaranty: A guaranty provided by the Seller Guarantor that is substantially in the form of the guaranty attached as Exhibit L (Form of Guaranty).

### Seller Response Notice: As defined in Section 17.1.4 (Seller Response Notice; GPC Response).

### Seller Response Deadline: As defined in Section 17.1.4 (Seller Response Notice; GPC Response).

### SERC: The Southeastern Electric Reliability Corporation, including any successor.

### Site: The physical location (i.e., real property) where the Facility is or will be located, as described in Exhibit A (Facility Description and Additional Details).

### Site Controller: As defined in Section 10.13.1 (Sourcing Restrictions).

### Southern Balancing Authority Area (SBAA): The NERC- and SERC- recognized balancing authority area that includes the Southern Company Transmission System.

### Southern Companies: Collectively, the regulated electric operating companies of The Southern Company (i.e., Alabama Power Company, GPC, and Mississippi Power Company).

### Southern Company: The Southern Company, a Delaware corporation, the parent of GPC.

Southern Company Services (SCS): Southern Company Services, Inc., an Affiliate of GPC that performs services as agent for GPC.

### Southern OATT: Southern Company’s Open Access Transmission Tariff.

### Southern Company Transmission System: The transmission system consisting of transmission facilities (>40 kV) owned by the Southern Companies, as the system may be modified or expanded from time to time, as well as any successor transmission system. For the avoidance of doubt, the Southern Company Transmission System does not include the Georgia ITS facilities owned by the ITS Participants.

### State of Charge (SOC): The amount of stored energy in the BESS in real time, which may be expressed either as: (i) a percentage of the SDOE (e.g., a 95% SOC); or (ii) a quantity of energy (e.g., 400 MWh SOC). SOC is considered usable and dispatchable energy at the POI, and the BESS must be able to operate at the: (a) Maximum Rate of Charge from 0% to 100% of the SDOE; and (b) Storage Device Design Capacity from 100% to 0% of the SDOE.

### Station Service: Energy that is used to serve the electrical requirements of the Facility, excluding any Charging Energy not consumed as Auxiliary Operational Load and Discharging Energy. For a BESS, Station Service includes all energy required to operate and maintain the BESS (e.g., Auxiliary Operational Load, power conversion stations).

### Storage Device Design Capacity (SDDC): The guaranteed amount of BESS storage capacity (in MW) allocated to GPC under this PPA and that represents the guaranteed continuous discharge capability of the BESS for the Storage Device Discharge Duration.

### Storage Device Discharge Duration (SDDD): The guaranteed number of Hours that the BESS must be capable of continuously discharging to the POI at the Storage Device Design Capacity.

### Storage Performance Metric Achieved: As defined in Section 2.3 (Storage Performance Metric Achieved) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Storage Performance Reduction (SPR): The applicable amount stated in Table C-3 (Storage Performance Reduction) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

### Storage Device Operating Energy (SDOE): The guaranteed number of MWh that the BESS must be capable of discharging to the POI and is equal to the product of the Storage Device Design Capacity multiplied by Storage Device Discharge Duration.

### System Emergency: When the Dispatch Center has determined in accordance with its prevailing practices that conditions are expected to occur or have occurred that could jeopardize the ability to meet projected loads in the SBAA.

Tariff: Any import tariff, customs duty, trade measure, surcharge, or similar governmental charge imposed on the importation of equipment, components, materials, or supplies used for the construction, repair, operation, or maintenance of the Facility.

### Tax or Taxes: Any income, gross receipts, license, employment, excise, recording, stamp, customs, capital stock, franchise, profits, withholding, social security, unemployment, disability, property (real or personal), sales, use, transfer, value added, net worth, capital gains, payroll, alternative minimum or other tax, or any other charge, fee, levy, tariff, duty, liability, imposition or other assessment in the nature of a tax, imposed by any Governmental Authority, including any interest, penalties and additions to tax imposed with respect thereto, and any liability for any of the foregoing of any Person under any applicable law, including as a transferee or successor, by contract or otherwise.

### Technical Limits: The operational limits and constraints described in Exhibit F (Facility Operating and Dispatching Requirements).

### Term: The term of this PPA, which becomes effective on the Effective Date and continues for the number of Annual Periods specified in Table A-2 (Term, RCOD) of Exhibit A (Facility Description and Additional Details), unless terminated earlier as provided in this PPA.

### Termination Payment: As defined in Section 16.3.2 (Termination Payment).

### Test Charge Energy: Any: (i) before COD, Grid Charging Energy or Renewable Resource Charging Energy used to charge the BESS; or (ii) after COD, any Grid Charging Energy or Renewable Resource Charging Energy used to charge the BESS not at the direction of GPC or by an AGC Setpoint signal.

### Test Charge Energy Price: Equals AIER.

### Test Discharge Energy: Any energy delivered to the POI from the BESS before the earlier of RCOD or COD.

### Test Discharge Energy Price: Equals AIER.

### Tested Storage Capacity: The actual BESS capability (MW) demonstrated during a Performance Test.

Third Arbitrator: As defined in Section 19.3.2(i) (Initiation of Arbitration; Selection of Party-Appointed Arbitrators).

### Threshold Amount: $8.00/kW of Contracted Capacity, expressed in dollars by multiplying $8.00 by the Contracted Capacity (kW).

### Triggering Failure: As defined in Section 10.9 (AGC Performance Requirements).

Ultimate Parent Entity: With respect to a Party, the Person who (i) directly or indirectly controls 50% or more of the outstanding capital stock or other equity interests in such Party; (ii) has ordinary voting power; and (iii) does not itself have an Ultimate Parent Entity.

### Unavailable: The extent to which, after the Delivery Commencement Date, the Facility is unable (in whole or in part) to store or deliver energy due to a Scheduled Outage, Maintenance Outage, Forced Outage, Forced Derate, or a Force Majeure Event.

### Unavailability Period: Any single, continuous period during which the BESS is Unavailable to respond to GPC’s AGC Setpoint signals or other dispatch instructions, in whole or in part.

### Variable Interest (VI): Defined in ASC Topic 810 (Consolidation), as issued and modified from time to time by FASB.

### Variable Interest Entity (VIE): Defined in ASC Topic 810 (Consolidation), as issued and modified from time to time by FASB.

Power Purchase Agreement for

Firm Capacity, Energy Storage Services, and Ancillary Services

from a Battery Energy Storage System

[Paired with a Renewable Resource]

for 2026 All-Source Capacity Request for Proposals for Need Years 2032- 2033

at #FacilityName#

between Georgia Power Company

and #SellerLegalName#

Georgia Power Company (“GPC”), a Georgia corporation, and #SellerLegalName# (“Seller”) enter into this Power Purchase Agreement for Firm Capacity, Energy Storage Services, and Ancillary Services from a Battery Energy Storage System [Paired with a Renewable Resource] for 2026 All-Source Capacity Request for Proposals for Need Years 2032- 2033 at #FacilityName# as of the Effective Date. GPC and Seller acknowledge:

- Seller desires to sell, and GPC desires to purchase capacity, energy storage services, and Ancillary Services from the Facility consistent with the Commission’s Orders in Docket Nos. 56002 and 56368;

- If specified in Exhibit A (Facility Description and Additional Details), the Facility is paired with the Renewable Resource described in Exhibit A (Facility Description and Additional Details);

- If specified in Exhibit A (Facility Description and Additional Details), GPC and Renewable Resource Seller executed the Renewable Resource PPA Amendment; and

- The Parties desire to set forth the terms and conditions upon which the sale and purchase of capacity, energy storage services, and Ancillary Services may be conducted between the Parties.

In consideration of the mutual promises described in this PPA, and other good and valuable consideration, the receipt, adequacy, and sufficiency of which each Party acknowledges, and intending to be legally bound, the Parties agree:

Term of Agreement

Term.

Subject to applicable law and any earlier termination as permitted in this PPA, this PPA becomes effective on the Effective Date and continues for the Term.

Survival.

PPA provisions that by their nature or context should apply beyond PPA expiration, suspension, cancelation, completion, or termination, or after transfer, assignment, novation, merger, or other entity change, will survive per applicable law or PPA terms, including all provisions of this PPA that must survive to give effect to the rights and obligations of the Parties. Expiration or termination of this PPA will not relieve either Party of its liabilities or obligations that accrue before or at termination, and those liabilities and obligations will survive PPA termination.

Conditions Subsequent.

This PPA is subject to termination for failure of any of the following conditions:

FERC Delay or Rejection.

If FERC acceptance of this PPA is required by applicable law, and if: (a) FERC issues a valid order rejecting this PPA; or (b) FERC fails to take action or takes action that, in either case, has the effect of delaying the date when FERC will issue an order accepting this PPA to a date beyond 285 Days after the Commission Certificate, then in the case of (a) or (b) the Parties will meet no later than 10 Business Days after the date of the order or the date that is 285 Days after the Commission Certificate, as applicable, to negotiate amendments to this PPA, an extension of time for FERC to accept this PPA beyond 285 Days from the granting of a Commission Certificate, or other appropriate measure, so that this PPA, as amended or taking into account the appropriate measure, is legal and fully enforceable without materially increasing the risks for either Party or adversely affecting the value of the economic bargain to either Party contemplated by this PPA in its original form.

If the Parties are unable to negotiate any acceptable amendment, or other appropriate measure, then either Party may terminate this PPA upon notice to the other Party, so long as such notice is delivered to the non-terminating Party no later than 30 Days after 285 Days from the granting of a Commission Certificate. In no event will this termination right be available to the Parties, and a Party will be deemed to have waived its termination right, absent receipt of notice by the non-terminating Party before the expiration of the 30-Day period. Upon termination in accordance with this Section 1.3.1, neither Party will have any liability to the other Party under this PPA, and GPC will return to Seller the Eligible Collateral then held by GPC.

FERC Acceptance with Modification.

Despite the preceding provisions, if, before 285 Days after the granting of a Commission Certificate, FERC issues a valid order accepting this PPA subject to material modification or condition(s), including acceptance subject to refund following an administrative proceeding, then the adversely affected Party or Parties (as applicable) will have the right to terminate this PPA if the material modification or condition(s) are not acceptable. By no later than 15 Days after the issuance date of a FERC order, Seller must provide GPC with a copy of the FERC order along with notice of whether the FERC order is subject to material modification or condition(s) that adversely affect Seller and, if so, whether the material modification or condition(s) are acceptable to Seller. If Seller fails to provide the notice before the 15th Day, then Seller will be deemed to have accepted any FERC order accepting this PPA subject to material modification or condition(s).

      - By no later than 15 Days after the receipt date of a copy of the FERC order from Seller, GPC will provide Seller with notice of whether the FERC order is subject to material modification or condition(s) that adversely affect GPC and, if so, whether such material modification or condition(s) are acceptable to GPC. If GPC does not provide the notice before the 15th Day, then GPC will be deemed to have accepted the FERC order accepting this PPA subject to material modification or condition(s).

      - If either Party provides notice that such material modification or condition(s) are not acceptable, then the Parties will meet no later than 10 Business Days following the date of the notice to negotiate an amendment to this PPA, or other appropriate measure, so that this PPA, as amended or taking into account any other appropriate measure, is legal and fully enforceable without materially increasing the risks for either Party or adversely affecting the value of the economic bargain to either Party contemplated by this PPA in its original form. If the Parties are unable to negotiate any acceptable amendment, or other appropriate measure, then the Party who delivers the notice will have the right to terminate this PPA upon notice to the other Party so long as the notice is delivered no later than 30 Days after the 285 Days from the granting of a Commission Certificate. Upon termination in accordance with this Section 1.3.2, neither Party will have any liability to the other Party under this PPA, and GPC will return to Seller the Eligible Collateral then held by GPC.

Commission Certificate Target Date Conditions.

      - Initial Termination Rights for Commission Certificate Target Conditions. If: (a) after the Commission Certificate Target Date the Commission has not approved this PPA or, if applicable, the Renewable Resource PPA Amendment through a Commission Certificate, or (b) the Commission has issued a Commission Certificate that is subject to material qualification or condition(s) that adversely affect GPC or Seller, then (x) in the case of clause (a), either Party may terminate this PPA upon notice to the other Party, so long as the notice is delivered to the other Party by no later than 30 Days after the Commission Certificate Target Date, or (y) in the case of clause (b), the Party or Parties (as applicable) that is or are adversely affected by the Commission Certificate may terminate this PPA upon notice to the other Party, so long as the notice is delivered by no later than 30 Days after the date the Commission issued the Commission Certificate that is subject to material qualification or condition that adversely affects such Party or Parties (as applicable). If Commission certification is delayed for reasons not attributable to Seller and GPC does not elect to terminate this PPA, Seller will be entitled to an RCOD extension.

      - Motion to Reconsider or Appeal; Extended PPA Termination Rights for Commission Certificate Target Conditions. If, within 30 Days after the issuance of the Commission Certificate or an order denying a Commission Certificate, any Person files a motion to reconsider with the Commission or an appeal with Fulton County Superior Court regarding the issuance or denial of the Commission Certificate, then either Party may terminate this PPA upon notice to the other Party, so long as the notice is delivered to the other Party no later than 80 Days after the Commission Certificate Target Date; however, Seller will not have a termination right under this Section 1.3.3(ii) (Motion to Reconsider or Appeal; Extended PPA Termination Rights for Commission Certificate Target Conditions) so long as the Commission Certificate remains in effect with respect to this PPA or this PPA otherwise remains certified.

      - Waiver of PPA Termination Right. If, within the applicable notice period, a Party does not exercise its termination right in accordance with this Section 1.3.3, then the Party will be deemed to have waived the termination right.

      - Obligations following PPA Termination. Upon PPA termination in accordance with this Section 1.3.3: (a) neither Party will have any further liability to the other Party under this PPA; and (b) GPC will promptly return to Seller any unused portion of Performance Security, if applicable.

Revocation, Qualifications, or Conditions.

Despite Section 1.3.3 (Commission Certificate Target Date Conditions), if, at any time during the Term the Commission issues an amendment to the Commission Certificate regarding this PPA (“Amended Commission Certificate”) that revokes the Commission Certificate or imposes a material qualification or condition that adversely affects either Party and that is not acceptable to the affected Party, the affected Party will have the right to terminate this PPA, unless GPC and Seller agree to amend this PPA in accordance with Section 1.3.6 (PPA Amendment). Within 15 Days after the issuance of the Amended Commission Certificate, each Party must provide the other Party with notice of whether the Amended Commission Certificate is subject to material qualification or condition and, if so, whether the material qualification or condition is acceptable. If a Party does not provide notice within the 15-Day period, the Amended Commission Certificate will be deemed to be acceptable to that Party. Upon a termination in accordance with this Section 1.3.4: (i) neither Party will have any further liability to the other Party under this PPA; and (ii) GPC will promptly return to Seller any unused portion of Performance Security, if applicable.

Change in Economic Circumstances or Market Conditions.

Despite any other provision in this PPA, and so long as it is not required by Commission Rule 515-3-4.08, neither Party will seek to have the Commission revoke the Commission Certificate of its own initiative for reasons solely related to changed economic circumstances or market conditions affecting this PPA.

PPA Amendment.

If the Commission issues an Order approving this PPA with any modification or condition, or issues an Amended Commission Certificate, as applicable, this PPA will not be amended to include the modification or condition unless the Parties execute a written amendment agreeing to the modification or condition. If GPC requests, within 30 Days after issuance of the Order, that Seller execute a written amendment agreeing to the modification or condition, and Seller does not execute the written amendment by no later than 30 Days after the date of GPC’s request, GPC may terminate this PPA. Upon termination of this PPA in accordance with this Section 1.3.6: (i) GPC will promptly return to Seller any unused portion of the Performance Security, if applicable; and (ii) neither Party will have any further obligation to the other Party under this PPA.

Payment of Winner’s Fee. After the Commission approves this PPA through a Commission Certificate, GPC will calculate the winner’s fee owed by Seller per the terms of GPC’s 2026 All-Source Capacity Request for Proposals for Need Years 2032 - 2033 and notify Seller of the amount. Seller must pay the winner’s fee to GPC: (i) within 10 Days after receipt of GPC’s notice; and (ii) following the instructions in the notice. Seller’s failure to timely pay the winner’s fee as required by this Section 1.3.7 (Payment of Winner’s Fee) will be a Seller Event of Default.

Representations, Warranties, and Covenants

Seller Representations, Warranties, and Covenants.

Seller makes to GPC the following additional representations, warranties, and covenants as the basis for the benefits and obligations contained in this PPA:

Organization; Facility Ownership; Legal Power and Authority.

Seller is duly organized and validly existing in accordance with the Seller information provided in Exhibit A (Facility Description and Additional Details), in good standing under the laws of the state of Georgia, qualified to do business in the state of Georgia, the sole owner and operator of the Facility, and has the legal power and authority to: (i) own its properties; (ii) carry on its business as now being conducted; (iii) enter into this PPA; (iv) to otherwise carry out the transactions contemplated by this PPA; and (v) perform and fulfill all covenants and obligations on Seller’s part to be performed under this PPA.

Authorization.

The execution, delivery, and performance by Seller of this PPA have been duly authorized by all necessary action and do not and will not require any consent or approval of any Person other than those already properly obtained.

No Conflict or Breach.

The execution and delivery of this PPA, the consummation of the transactions contemplated by this PPA, and the fulfillment of and compliance with this PPA, do not and will not conflict with or constitute a breach of or a default under, any of the terms, conditions, or provisions of any applicable law, charter, bylaw, operating agreement or other formation or organizational document of Seller, or any deed of trust, mortgage, loan agreement, other evidence of Indebtedness, or any other agreement or instrument to which Seller is a party or by which Seller or any of its property is bound.

Legal, Valid, and Binding Obligations.

This PPA contains the legal, valid, and binding obligations of Seller that are enforceable in accordance with their terms, except as the enforceability may be limited by bankruptcy, insolvency, reorganization, or similar laws relating to or affecting the enforcement of creditors’ rights generally or by general equitable principles, regardless of whether the enforceability is considered in a proceeding in equity or at law.

No Proceedings Impacting Legality, Validity, or Enforceability of this PPA.

As of the Effective Date, there is no pending, or to the knowledge of Seller, threatened action or proceeding affecting Seller before any Governmental Authority that purports to affect the legality, validity, or enforceability of this PPA or that could reasonably be expected to have a material adverse effect on Seller.

No Bankruptcy Proceeding.

There is no bankruptcy proceeding pending or being contemplated by Seller or, to Seller’s knowledge, threatened against Seller.

No Federal Debarment.

Seller is not debarred, suspended, or proposed for debarment as a contractor or subcontractor to any department, agency, or other division of the United States Government.

VIE Certification.

      - As of the Effective Date, Seller has determined that Seller does not constitute a VIE for which GPC is the Primary Beneficiary and therefore that GPC is not required to consolidate Seller or any of its Affiliates in GPC’s financial statements under ASC Topic 810 (Consolidation) and related applicable accounting standards (“GPC Consolidation”) as in effect on the Effective Date (“Effective Date Accounting Standards”).

Seller must not take any action that would reasonably cause, and must take any commercially reasonable action necessary to avoid, GPC Consolidation.

Seller must promptly notify GPC of any determination made by Seller or Seller’s independent auditor that: (a) Seller’s VIE status has changed; or (b) Seller constitutes a VIE for which GPC is the Primary Beneficiary, considering this PPA individually or together with any other power purchase agreement between Seller and GPC.

If during the Term (x) existing accounting standards are modified or new standards are adopted and implemented by FASB that supersede the Effective Date Accounting Standards (“Change in Accounting Standards”) and GPC or its independent auditor determines in good faith that GPC Consolidation is required, Seller and GPC must, as soon as practicable, cooperate in good faith to implement contractual or operational modifications to avoid such determination. If, despite the Parties’ best efforts, the Parties are unable to avoid the GPC Consolidation determination before the fifth Business Day before the end of the first reporting period during which such GPC Consolidation is required, GPC may terminate this PPA upon notice to Seller under this Section 2.1.8 and the Parties will have no further liability or obligation except for any liability or obligation arising before the termination.

Seller must provide to GPC a VIE certification substantially in the form of Exhibit M (VIE Certification) signed by the chief financial officer of Seller: (a) at the time of execution of this PPA; (b) before each Delivery Commencement Date anniversary during the Term; (c) at any time this PPA is amended by the Parties; and (d) with any Change of Control Transaction.

If existing accounting standards are modified or new standards are adopted that supersede the Effective Date Accounting Standards, Seller must provide GPC with a then current certification in the form of Exhibit M, modified accordingly to account for and comply with any modification to existing accounting standards or adoption of new accounting standards.

Facility Modifications Resulting in Material Adverse Effect.

No modification to, or expansion of, the Facility that would have a material adverse effect on GPC’s rights or obligations under this PPA will occur without GPC’s prior written consent, which consent will not be unreasonably withheld, conditioned, or delayed.

Sale, Lease, Transfer, or Other Disposal of Business or Assets Resulting in Material Adverse Effect.

Seller must not sell, lease, transfer, or otherwise dispose of all or substantially all of its business or assets, whether now owned or later acquired, to the extent that the sale, lease, transfer, or other disposition would have a material adverse effect on GPC’s rights or obligations under this PPA or, if applicable, the Renewable Resource PPA without GPC’s prior written consent, which consent will not be unreasonably withheld, conditioned, or delayed, subject to Seller’s compliance with all requirements in Part 18 (Assignment, Transfers, and Changes of Control).

Legal Right to Possess and Operate Facility and Deliver Capacity, Energy Storage Services, and Ancillary Services.

Except as may be allowed under Sections 2.1.10 (Sale, Lease, Transfer, or Other Disposal of Business or Assets Resulting in Material Adverse Effect), 18.2 (Financing Assignment; Estoppels), or any other provision of this PPA, Seller must maintain the legal right to and will possess and operate the Facility and deliver the capacity, energy storage services, and Ancillary Services of the Facility to GPC in accordance with this PPA, including maintaining the right for GPC to direct Charging Energy and Discharging Energy.

GPC’s Exclusive Right to Environmental Attributes.

GPC will have exclusive rights to all Environmental Attributes associated with the Facility, which include the exclusive right to: (i) report to any Governmental Authority, or other Person for compliance with any applicable law or other purpose, that it owns the Environmental Attributes; and (ii) claim the Environmental Attributes to customers or potential customers for purposes of marketing and advertising. However, Seller and Seller’s Affiliates may issue marketing materials and other statements regarding their respective operations and business activities so long as the issuance of the materials and statements does not: (a) reduce the economic value to GPC of the Environmental Attributes; (b) reduce GPC’s claims to the Environmental Attributes; or (c) result in the double counting of the Environmental Attributes.

Information Regarding Environmental Attributes.

To the extent applicable during the Term, Seller must maintain and provide to GPC (or, if directed by GPC, other applicable Persons) the information as necessary to substantiate, account for, or track the quantity of Environmental Attributes, if any, delivered to GPC under this PPA, including all information necessary for GPC to comply with the requirements of any Governmental Authority or other certifying or standard-setting body relating to the Environmental Attributes. Seller must provide GPC with attestations regarding the accuracy of the information as reasonably requested by GPC. Upon GPC’s request, Seller, at Seller’s expense, must cooperate with GPC to obtain compliance with any required documentation or reporting obligation under any federal or state renewable energy plan to certify the Facility or the Environmental Attributes. Additionally, upon GPC’s request, Seller, at Seller’s expense, must use reasonable efforts to obtain verification from a certification authority mutually agreed upon by the Parties that the Environmental Attributes sold to GPC in accordance with this PPA comply with the standards set by the certification authority. Seller is responsible for the costs associated with registering, qualifying, or recording any Environmental Attributes with any applicable Governmental Authority or other certifying or standard-setting body at GPC’s request.  GPC will have the right to disclose the information publicly or to any third party, without Seller’s prior consent, as reasonably required in connection with the operation of GPC’s business, including disclosures: (i) to any Person that purchases the Environmental Attributes from GPC; (ii) to any Governmental Authority; (iii) to any auditor or any Person that certifies or sets standards with respect to Environmental Attributes; or (iv) as necessary for GPC to defend, verify, or substantiate its ownership of the Environmental Attributes.

If during the Term a Governmental Authority or certification body establishes an Environmental Attribute applicable to the BESS and the cost for Seller to track, attest to, register, or verify that Environmental Attribute materially exceeds costs typically incurred to perform those same activities for RECs, the Parties will negotiate in good faith a mutually agreeable cost-sharing arrangement for BESS-specific tracking, attestation, registration, or verification costs.

Environmental Compliance Certification.

On each anniversary of the Commercial Operation Date through the end of the Term, Seller must provide to GPC an Environmental Compliance certificate in the form of Exhibit O (Environmental Compliance Certification) signed by a duly authorized officer of Seller.

Extreme Weather Technical Requirements.

Throughout the Term, the Facility will comply with NERC EOP-12-1 (Extreme Cold Weather Preparedness and Operations) or successor reliability standard, to the extent applicable, as further described in Section 7.1.1 (Facility Design).

Legal Right to Use Renewable Resource Interconnection Facilities and POI. If the Facility is paired with a Renewable Resource, as may be described in Exhibit A (Facility Description and Additional Details), Seller has, and will maintain throughout the Term, the legal right and entitlement to share the POI with the Renewable Resource and to use all Renewable Resource interconnection facilities, infrastructure, and control systems necessary to deliver BESS output to the POI.

GPC Representations, Warranties, and Covenants.

GPC makes the following representations, warranties, and covenants to Seller as of the Effective Date as the basis for the benefits and obligations contained in this PPA:

Organization; Facility Ownership; Legal Power and Authority.

GPC is a corporation, duly organized, validly existing, and in good standing under the laws of the state of Georgia, that is qualified to do business in the state of Georgia and has the legal power and authority to own its properties, to carry on its business as now being conducted and to enter into this PPA and carry out the transactions contemplated by this PPA, and perform and fulfill all covenants and obligations on its part to be performed under this PPA.

Authorization.

The execution, delivery, and performance by GPC of this PPA have been duly authorized by all necessary corporate action and does not and will not require any consent or approval of GPC’s board of directors or shareholders other than that already obtained.

No Conflict or Breach.

Subject to Section 1.3 (Conditions Subsequent), the execution and delivery of this PPA, the consummation of the transactions contemplated by this PPA, and the fulfillment of and compliance with this PPA do not and will not conflict with any of the terms, conditions, or provisions of any applicable laws applicable to GPC, or of any partnership agreement, deed of trust, mortgage, loan agreement, other evidence of Indebtedness, or any other agreement or instrument to which GPC is a party or by which GPC or any of its property is bound, or result in a breach of or a default under any of the foregoing.

Legal, Valid, and Binding Obligations.

This PPA constitutes the legal, valid, and binding obligation of GPC that is enforceable in accordance with its terms, except as such enforceability may be limited by bankruptcy, insolvency, reorganization, or similar laws relating to or affecting the enforcement of creditors’ rights generally or by general equitable principles, regardless of whether such enforceability is considered in a proceeding in equity or at law.

No Proceeding Impacting Legality, Validity, or Enforceability of this PPA.

There is no pending or, to the knowledge of GPC, threatened action or proceeding affecting GPC before any Governmental Authority that purports to materially adversely affect the legality, validity, or enforceability of this PPA or that reasonably could be expected to have a material adverse effect on GPC’s ability to perform its obligations under this PPA.

Creditworthiness and No Bankruptcy Proceedings.

GPC is Creditworthy (determined solely by clause (i) of the definition of Creditworthy) and there are no bankruptcy proceedings pending or being contemplated by it or, to its knowledge, threatened against it.

Preservation of Terms; Consents; Taxes

Preservation of Terms.

Each Party agrees that, subject to Section 3.2 (Other Approvals), except with the prior written consent of the other Party, the Party will not institute or voluntarily cooperate in the institution or conduct of any claim, action, or proceeding before FERC under Section 205, Section 206, or any other portion of the Federal Power Act, or before any other Governmental Authority under any applicable law that is intended to, or could reasonably be expected to, change PPA terms then in effect. Without limiting the preceding sentence, but subject to the terms of this PPA, the Parties agree that the rates for service specified in this PPA will remain in effect for the Term and will not be subject to change through application to FERC in accordance with Section 205 or 206 of the Federal Power Act, or to any other Governmental Authority under any provision of federal law, Georgia state or local law, or any other applicable law, absent written agreement of the Parties.

FERC Filings Waiver; Standard of Review.

Each Party waives all rights to submit filings to FERC seeking modification or rescission of this PPA under Section 205 or 206 of the Federal Power Act.

      - FERC Standard of Review. In any proceeding before FERC involving this PPA, the Parties will request that FERC review all aspects of this PPA under the “public interest” application of the “just and reasonable” standard of review in United Gas Pipe Line Co. v. Mobile Gas Service Corp., 350 U.S. 332 (1956) and Federal Power Commission v. Sierra Pacific Power Co., 350 U.S. 348 (1956), each clarified by NRG Power Marketing LLC v. Maine Public Utility Commission, 130 S. Ct. 693 (2010).

Other Approvals.

Throughout the Term, each Party will diligently seek to obtain, achieve, maintain, pursue, or cause to be pursued, comply with, and, as necessary, renew or modify all other Consents required to be possessed by the Party in a manner that is reasonably expected to enable the Party to perform its PPA obligations. Each Party agrees to assist and support the other Party, in a timely manner and to the extent reasonably requested by either Party, in obtaining the Consents. Upon request, a Party will provide a copy of Consents to the requesting Party.

Taxes.

Payment by Seller.

Subject to Section 17.1 (Change of Law), Seller will be responsible for, and must pay, or cause to be paid, all Taxes on or regarding: (i) the Facility, including its development, permitting, design, engineering, procurement, construction, testing, startup, ownership, leasing, financing, operation, and maintenance; and (ii) the production, storage, and delivery of energy and Ancillary Services to be provided to GPC arising, in the case of energy, before the time of Seller’s delivery of energy to GPC at the POI, or, in the case of Ancillary Services, before the time the Ancillary Services are made available to GPC.

Payment by GPC.

GPC will pay or cause to be paid all Taxes on or regarding: (i) energy received by GPC arising at and after the time the energy is delivered by Seller to the POI; and (ii) Ancillary Services received by GPC arising at and after the time the Ancillary Services are made available to GPC. The Taxes will include sales, use, excise, or other similar Taxes on the sale to GPC and purchase from Seller of capacity, energy, and Ancillary Services in accordance with this PPA.

Efforts to Implement PPA Provisions to Minimize Taxes.

Each Party will use reasonable efforts to implement and administer the PPA provisions to minimize Taxes on the other Party so long as neither Party is materially adversely affected by such efforts.

GPC Reimbursement or Deduction for Taxes.

If Seller is required by law or regulation to remit or pay Taxes that are GPC’s responsibility under this PPA, Seller may include the Taxes in the next Monthly Invoice and GPC will remit payment for the applicable Taxes on an After-Tax Basis in accordance with Part 5 (Billing and Collections). Conversely, if GPC is required by law or regulation to remit or pay Taxes that are Seller’s responsibility under this PPA, GPC may deduct those Taxes from the sums otherwise due to Seller under this PPA on an After-Tax Basis. Any refund associated with the Taxes will be handled in the same manner. Nothing in this PPA will obligate or cause a Party to pay or be liable to pay any Taxes from which the Party is exempt under applicable law.

Sale and Delivery of Capacity

Agreement to Sell and Purchase.

Sale and Purchase Obligations During the Term.

From the Delivery Commencement Date through the end of the Term, but subject to the terms of this PPA, Seller must sell to GPC: (i) the entire electrical capability of the Facility, net of any Station Service; and (ii) all associated energy storage services and Ancillary Services. The receipt and delivery of energy to the POI includes the transfer to GPC of all Ancillary Services associated with the energy. Seller must make available and provide to GPC all Ancillary Services as instructed by GPC at all power output levels and during periods that the Facility is not actively delivering energy. The Monthly Capacity Payment (subject to the Monthly Capacity Reduction in accordance with Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements)) is the exclusive compensation owed to Seller for capacity, energy storage services, and Ancillary Services under this PPA. GPC will have full discretion to dispatch the BESS to cause energy to be stored in the BESS or sent to the POI, and Seller must maintain throughout the Term GPC’s right to direct Charging Energy and Discharging Energy.

Dispatch and Energy Delivery.

GPC may dispatch the BESS by sending AGC Setpoint signals every six seconds or instructions from the Dispatch Center, in each case in accordance with the dispatch procedures set forth in Exhibit F (Facility Operating and Dispatching Requirements) and subject to the Technical Limits and the Interconnection Limit. GPC retains full control of energy delivery, whether through AGC or specific directives from GPC, from the BESS.

Station Service.

Seller is responsible for all Station Service at Seller’s expense. If the Facility is located within the state of Georgia, Seller must arrange Station Service for the Facility in accordance with the Georgia Territorial Electric Service Act (O.C.G.A. §§ 46-3-1 through 46-3-15). Seller must separately meter Auxiliary Operational Load at all times, and Auxiliary Operational Load will not be netted as part of Charging Energy or Discharging Energy. Seller will be responsible for all costs associated with Station Service, including Station Service used for the operation of equipment (e.g. power conversion stations) during periods when the BESS is not charging or discharging (e.g. idle).

Delivery of Energy; Risk of Loss; Balancing Services.

Seller must (i) ensure the Facility is Available in accordance with this PPA and (ii) subject to GPC’s provision of Charging Energy, deliver energy from the Facility to GPC at the POI in accordance with GPC’s AGC Setpoint signals or instructions from the Dispatch Center. GPC’s provision of Charging Energy is subject at all times to GPC’s discretion. The risk of loss of: (i) Grid Charging Energy will pass from GPC to Seller at the POI; (ii) Discharging Energy will pass from Seller to GPC at the POI; and (iii) if applicable per Exhibit A (Facility Description and Additional Details), Renewable Resource Charging Energy will pass from Renewable Resource Seller to Seller at the low side of the Renewable Resource meter or other point of delivery identified in the Renewable Resource PPA. The Facility must interconnect to the Southern Company Transmission System at the POI and must be situated such that GPC can provide balancing services and direct Grid Charging under the Southern OATT or Renewable Resource Charging, if applicable per Exhibit A (Facility Description and Additional Details). GPC will be responsible for providing generator balancing services regarding the SBAA and Southern OATT necessary for the receipt of energy in accordance with GPC’s dispatch instructions and for any associated costs.

Unavailability.

      - Seller must promptly and accurately communicate to GPC any Facility outage, derate, or other operational limitation via GPC’s data systems and email as specified in the Operating Procedures.

GPC’s Dispatch Right for Storage Device Design Capacity and Ancillary Services.

GPC will be entitled to dispatch and receive, and if dispatched by GPC in accordance with Section 4.1.2 (Dispatch and Energy Delivery), Seller must: (i)  discharge the BESS in accordance with GPC’s AGC Setpoint signals or other direction, up to the SDDC; and (ii) deliver all capacity, energy storage services, and Ancillary Services, in each of subsections (i) and (ii) in accordance with Seller’s delivery obligations under this PPA, including Section 4.1.4 (Delivery of Energy; Risk of Loss; Balancing Services) and Part 12 (Energy Dispatch).

Reserved.

No Sale of Capacity, Energy, or Ancillary Services to a Third Party.

During the Term, Seller must not sell any of the capacity, energy, energy storage services, or Ancillary Services associated with the BESS to any Person other than GPC, including the sale of any energy not dispatched by GPC.

Calculation of Monthly Capacity Payments.

Subject to the terms of this PPA, GPC will pay Seller a Monthly Capacity Payment calculated in accordance with Section 1.2 (Monthly Capacity Payment) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements), subject to the Monthly Capacity Reduction in accordance with Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements). Other than the Monthly Capacity Payments, GPC will not owe Seller any payment or other compensation for the Facility’s capacity, energy storage services, or Ancillary Services.

No Seller Entitlement to Payment or Other Compensation.

GPC will not owe Seller any payment or other compensation for energy losses associated with Round-Trip Efficiency of the BESS. GPC will not owe Seller any payment or other compensation under this PPA for energy generated by the Renewable Resource, if applicable, and delivered directly to the POI or the BESS. GPC retains sole title to energy delivered to the Point of Delivery under the Renewable Resource PPA and the Charging Energy delivered to the BESS.

Paired Renewable Resource.

This Section 4.3 is applicable if the Facility is paired with a Renewable Resource.

    - BESS with Renewable Resource.

Seller has elected to pair the BESS with the Renewable Resource and represents Renewable Resource Seller has agreed to: (i) allow Seller to use the POI and Renewable Resource interconnection facilities, equipment, and other infrastructure necessary for GPC to dispatch energy from the Renewable Resource to or from the POI; and (ii) allow GPC to dispatch Renewable Resource Charging Energy to the BESS. Seller must diligently coordinate with Renewable Resource Seller all activities necessary for delivery of Renewable Resource Charging Energy to the BESS in accordance with GPC’s dispatch instructions under the Renewable Resource PPA and this PPA.

    - Effect of Amended PPA Between GPC and Renewable Resource Seller.

Despite any term of the Renewable Resource PPA, as between GPC and Seller: (i) the Renewable Resource PPA does not alter Seller’s obligations to GPC or GPC’s rights against Seller; and (ii) Seller remains primarily liable to GPC for all Seller’s PPA obligations to the fullest extent allowed by applicable law. [Note to Bidders: Additional requirements may be added based on the applicable Renewable Resource PPA amendment between GPC and Renewable Resource Seller, if applicable because Bidder proposed to pair the BESS with an existing Renewable Resource.]

Billing and Collections

Capacity Billing and Payment.

Seller Invoices.

Subject to Section 5.2 (Billing Disputes and Final Accounting), by no later than the 10th Day of each Month (commencing with the first Month after the Delivery Commencement Date), Seller must send to GPC an invoice stating the Monthly Capacity Payment for the immediately preceding Month (“Monthly Invoice”), including any Monthly Capacity Reduction under Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements). If the 10th Day is not a Business Day, Seller must send to GPC the applicable Monthly Invoice by no later than the Business Day succeeding the 10th Day. The invoice must also specify any other payment required to be made by either Party in accordance with this PPA.

Notice of Invoice Adjustment.

By no later than the 10th Business Day of each Month (commencing with the first Month after the Delivery Commencement Date), GPC will provide Seller notice of any amount that must be deducted from amounts owed by GPC to Seller, including, if applicable, any Monthly Capacity Reduction for the immediately preceding Month or annual true-up. If the 10th Day is not a Business Day, GPC will send Seller the applicable notice by no later than the Business Day after the 10th Day. After receipt of GPC’s notice, Seller must provide an appropriately adjusted Monthly Invoice.

GPC Invoice Payments.

GPC will pay all Monthly Invoices on or before the 20th Day after GPC’s receipt of the Monthly Invoice. If the 20th Day is not a Business Day, then GPC may pay the Monthly Invoice by the Business Day succeeding the 20th Day. Subject to Sections 5.1.4 (Net Payment or Net Bill) and 5.2 (Billing Disputes and Final Accounting), GPC will pay Seller in accordance with the Monthly Invoice by the due date in immediately available funds through wire transfer of funds to an account designated by Seller, or other means acceptable to Seller. Interest on unpaid amounts will accrue from the date the payment was due at a rate equal to the Interest Rate. Each Monthly Invoice will contain a statement explaining in reasonable detail how the invoice was calculated in accordance with Section 4.2 (Calculation of Monthly Capacity Payments).

Net Payment or Net Bill.

GPC may provide a net payment or net bill, whichever is applicable, that consolidates amounts owing to Seller with amounts owing to GPC under this PPA.

Billing Disputes and Final Accounting.

Payment of Undisputed Amounts.

If GPC questions or disputes the amount or propriety of any payment Seller claims to be due under this PPA, GPC will pay Seller any amount not in dispute but may withhold any amount disputed in good faith until after the settlement of the question or contest in accordance with this Section 5.2.

Billing Dispute Notice.

If GPC questions or disputes the correctness of any invoice charge or credit, GPC must provide notice to Seller containing the amount and basis for GPC’s question or dispute within the time provided in Section 5.2.3 (Time for Permitted Disputes). Upon receipt of notice from GPC, Seller must promptly review the questioned charge or credit and by no later than 30 Days after the date Seller receives GPC’s notice: (i) respond to GPC in writing confirming or denying any error in Seller’s previous determination of amounts owed by GPC; and (ii) if applicable, issue an amended invoice for any payment that GPC is required to make regarding the re-determination. If Seller disagrees with GPC’s question or dispute, Seller’s response must include a reasonably detailed explanation of the basis for Seller’s position, including supporting calculations and documentation. If GPC in good faith disputes Seller’s response or amended invoice, the matter will be a Billing Dispute and resolved in accordance with Part 19 (Dispute Resolution).

Time for Permitted Disputes.

Seller will have until 90 Days after the date of a Monthly Invoice to: (i) correct the Monthly Invoice for payment due for the Monthly Capacity Payment; and (ii) deliver a corrected Monthly Invoice to GPC. GPC will have until the end of one year after its receipt of any Monthly Invoice or adjusted Monthly Invoice to dispute the correctness of any charge or credit made to GPC on the invoice. If within the one-year period, GPC has made payment under a Monthly Invoice and later disputes the correctness of the invoice, Seller will not be required to refund any payment received from GPC until the time as it is finally determined that Seller’s Monthly Invoice was in error.

Interest.

If either Party does not make a payment required by this PPA when due, then interest at the Interest Rate from the date the overdue payment was due until the overdue payment, together with interest, is paid, will be added to the due payment. If either Party makes a payment in accordance with an invoice that is later determined to have been incorrect, then interest at the Interest Rate from the date the overpayment was made will be added to the overpayment until the overpayment, together with interest, is refunded to the Party. Remittance received by mail, if mail is a means of payment acceptable to a Party owed payment, will be accepted without interest charges if the payment is postmarked on or before the due date. If the due date of any payment falls on a Day other than a Business Day, the next succeeding Business Day will be the last Day on which payment can be postmarked without interest charges being assessed. Despite this Section 5.3, no interest will be paid regarding any Monthly Capacity Reduction except to the extent the applicable reduction or true-up was not correctly calculated or invoiced in accordance with this PPA.

Billing and Payment Records.

Each Party will, until the end of one year after its receipt of any invoice, make available to the other Party, and each Party may audit, the books and records of the other Party as are necessary for the Party to verify the calculation of the Monthly Capacity Payments, any Monthly Capacity Reduction, and any true-up of the Monthly Capacity Payment for the final Month of an Annual Period under Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements), and any other invoice, charge, or payment demand made concerning this PPA.

Performance Security

Performance Security.

Simultaneous with the execution of this PPA, if Seller is not Creditworthy, Seller must deliver to GPC Eligible Collateral in an amount equal to the initial Performance Security required by Part 1 (Performance Security) of Exhibit A-2 (Performance Security and Liquidated Damages). If Seller is not Creditworthy or later suffers a Material Adverse Change, Seller must maintain Performance Security throughout the Term or remaining Term, as applicable, in the applicable amount required by Part 1 of Exhibit A-2 (which amount, if the Term is longer than five Annual Periods, is adjusted every five Annual Periods as shown in Part 1 of Exhibit A-2) and adjust its Eligible Collateral as and when required to comply with this Part 6 (Performance Security), including, if the Term is longer than five Annual Periods, to comply with adjustments to the required Performance Security amount in accordance with Part 1 of Exhibit A-2. If during the Term Seller suffers a Material Adverse Change, Seller must deliver to GPC the required Eligible Collateral within five Banking Days after the Material Adverse Change occurs, subject to extension in accordance with Section 6.5 (Pre-Approval of Non-Cash Eligible Collateral). If: (i) any portion of the Eligible Collateral that GPC is then holding is in the form of a Seller Guaranty, and (ii) a Material Adverse Change occurs regarding Seller Guarantor, then by no later than five Banking Days after the Material Adverse Change occurs, subject to extension in accordance with Section 6.5, Seller must deliver to GPC replacement Eligible Collateral to replace the Seller Guaranty: (a) in a form other than a Seller Guaranty; or (b) in the form of a Seller Guaranty from a different Seller Guarantor that is Creditworthy.

Requirements if Seller Becomes Creditworthy. If, during the Term, Seller has provided Performance Security to GPC in accordance with the requirements of this Part 6 (Performance Security) and either: (i) Seller becomes Creditworthy; or (ii) Seller assigns this PPA in accordance with Section 18.1.1 (Assignment by Seller) to a Person (other than a Financing Assignment) that is Creditworthy, then in either case: (a) Seller or such Person, as applicable, will not be required to maintain Performance Security for so long as it is Creditworthy; and (b) GPC will return Seller’s Eligible Collateral within five Business Days after Seller becomes Creditworthy or the effective date of the assignment, as applicable.

Replacement Collateral; Substituted Collateral; Release of Collateral.

Replacement Collateral.

To the extent that any Performance Security supplement or replacement is required to maintain compliance with Section 6.1 (Performance Security) (including any adjustment to the required Performance Security amount in accordance with Part 1 (Performance Security) of Exhibit A-2 (Performance Security and Liquidated Damages)), Seller must deliver to GPC the supplemental or replacement Performance Security by no later than 45 Days before the earlier to occur of: (i) the date when an increase or decrease in Eligible Collateral is required in accordance with Part 1 of Exhibit A-2; or (ii) the date when the existing Eligible Collateral will expire. However, the increase or decrease, as applicable, in Eligible Collateral will not become effective until the applicable date indicated in Part 1 of Exhibit A-2. If the U.S. commercial bank or a U.S. branch of a foreign bank that issued the Letter of Credit fails to maintain: (a) total assets of at least ten billion dollars ($10,000,000,000); or (b) a general long-term senior unsecured debt rating required for a Letter of Credit under this PPA, Seller must deliver to GPC a replacement Letter of Credit by no later than 10 Banking Days after the disqualifying event of (a) or (b). If Seller does not comply with the previous sentence, GPC has the right, without limitation to its other remedies under this PPA or at law, to: (I) draw the full amount on the existing Eligible Collateral before the expiration of the existing Eligible Collateral; and (II) take further action to protect its interests under this PPA.

Release of Collateral; Substituted Collateral.

Upon replacement of the Performance Security in accordance with Section 6.2.1 (Replacement Collateral), GPC will promptly release back to Seller the Eligible Collateral that Seller replaced. During the Term, Seller may substitute the Eligible Collateral by providing GPC with notice and the substitute Eligible Collateral. If GPC accepts the substitute Eligible Collateral, GPC will promptly release the Eligible Collateral for which substitution is being made in an amount equal to the substitution amount. Following any expiration or termination of this PPA, the Parties will mutually agree to a final settlement of all obligations under this PPA, which period will not exceed six Months after the expiration or termination date. After the settlement, GPC will return to Seller any remaining Eligible Collateral that Seller posted and upon which GPC has not drawn in accordance with GPC’s rights under this PPA. Any dispute between the Parties regarding a final settlement will be resolved according to Part 19 (Dispute Resolution), and GPC will not return to Seller any remaining Eligible Collateral that Seller posted until the resolution of the dispute.

Draws; Replenishment.

In addition to the draws permitted by Section 6.2.1 (Replacement Collateral), GPC may draw upon the Eligible Collateral provided by Seller to recover any damages to which GPC is entitled under this PPA (including damages following the occurrence of a Seller Event of Default) or any other unpaid amount owed by Seller under this PPA, including to recover delay liquidated damages under Section 7.3 (Failure to Achieve Commercial Operation by RCOD), damages arising from a Seller Event of Default, or termination damages arising from GPC’s termination of this PPA for a Seller Event of Default, in each case if not paid by Seller in accordance with this PPA. If GPC draws upon the Eligible Collateral, then, except in the circumstance when GPC establishes an Early Termination Date under Section 16.3.1 (Remedies for Event of Default) or this PPA otherwise terminates, Seller, within five Business Days, must replenish the Eligible Collateral to the full amount required by Section 6.1 (Performance Security).

Reporting.

Seller must promptly notify GPC of any circumstance that results in Seller’s failure to comply with the Performance Security requirements of this Part 6 (Performance Security). From time to time, at GPC’s written request, Seller must provide GPC with evidence as GPC reasonably requests to demonstrate that Seller and any Seller Guarantor, Seller Guaranty, Letter of Credit, or GPC Security Account is in full compliance with this PPA.

Pre-Approval of Non-Cash Eligible Collateral.

If Seller intends to provide Eligible Collateral in any form other than cash, including any replacement or supplemental Eligible Collateral, or any amendment to Eligible Collateral, Seller, at least 10 Business Days before the applicable due date, must submit a draft (unissued) Letter of Credit or Seller Guaranty for GPC’s review and approval. If Seller lacked sufficient advance notice of a Material Adverse Change to deliver the draft (unissued) Letter of Credit or Seller Guaranty to GPC for review within the time stated in the preceding sentence, Seller must notify GPC of the Material Adverse Change by no later than three Banking Days after Seller knew or should have known of the Material Adverse Change and promptly submit the draft (unissued) Letter of Credit or Seller Guaranty for GPC’s review and approval and, upon approval, promptly deliver the Eligible Collateral to GPC by no later than two Banking Days after receipt of GPC’s approval.

Delivery of Eligible Collateral for Performance Security.

Seller must provide to GPC Eligible Collateral to meet any of the Performance Security requirements under this PPA by delivering, as applicable: (i) cash wired to a GPC Security Account; or (ii) Letter of Credit or Seller Guaranty to the address indicated in Exhibit P (Notices).

Facility Design and Construction; Achieving Commercial Operation

Design and Construction of the Facility.

Facility Design.

Seller must design and construct the BESS in accordance with the applicable specifications set forth in Exhibit F (Facility Operating and Dispatching Requirements) and Exhibit I (Requirements for PPA Facility). The BESS must meet the requirements in Exhibit I by the deadlines specified in Exhibit I; if no deadline is specified, the BESS must meet the requirements by the Commercial Operation Date. The Facility must be designed to allow for Grid Charging and, if applicable per Exhibit A (Facility Description and Additional Details), Renewable Resource Charging. Seller must design the Facility and otherwise complete the Project in accordance with Prudent Industry Practices and applicable law. The Facility must comply with applicable EOP-012-1 (Extreme Cold Weather Preparedness and Operations) requirements, including Requirements R1 (applicable to New Facilities), R2 (applicable to Existing Facilities), R3, R4, R5, R6, and R7, and any successor reliability standard. EOP-012-1 is published by NERC and available at: https://www.nerc.com/pa/Stand/Reliability%20Standards/EOP-012-1.pdf.

BESS Design and Specifications.

The BESS must be designed to deliver the Contracted Capacity (MW) over the Storage Device Discharge Duration (SDDD), delivering the entire Storage Device Operating Energy (SDOE) (MWh), as measured at the POI. The BESS must also be capable of charging at the Maximum Rate of Charge throughout the Term. Seller must maintain these energy storage capabilities throughout the Term. Seller must design, build, and maintain the BESS with adequate margins, including any future augmentation, to demonstrate and perform to these specifications, accounting for any RTE losses, conversion losses, storage losses, efficiency degradation, or any other possible decrease in performance so that the Performance Guarantees are met over the Term. Each Month, GPC will assess the applicable Performance Metrics detailed in Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements) and calculate any Monthly Capacity Reduction. Seller must coordinate its control system design details with GPC, as GPC Representatives may request, throughout Project scoping, design, procurement, and construction and will reasonably consider GPC’s requests, provided that Seller’s obligation will be limited to ensuring that the PPA requirements are met.

Facility Control System Design and Capabilities.

Seller must design the control and data systems of the BESS to provide: (i) all real-time AGC Setpoint signals and data detailed in Exhibit G (AGC and Facility Minimum Data Requirements); (ii) any additional information that GPC requires to manage GPC’s dispatch of the Facility’s energy and capacity and to track and measure BESS performance. The BESS Operating High Limit will be updated in real time based on the Interconnection Limit (i.e. available discharge from BESS) to limit BESS operation, if applicable. The Facility control system will receive and send, every six seconds, AGC Setpoint signals to allow GPC to direct the energy input/output of the BESS. Seller must coordinate its control system design details with GPC, as GPC Representatives may request, throughout Project scoping, design, procurement, and construction to ensure that PPA requirements are met.

RCOD and Facility Construction Key Milestones.

Seller must progress Facility construction in accordance with applicable Key Milestone Dates, including achievement of Commercial Operation by the RCOD.

Commercial Operation.

The Facility will be deemed to have achieved Commercial Operation under this PPA when Seller demonstrates, to GPC’s reasonable satisfaction, that the following listed criteria are fulfilled. GPC is entitled, but not required, to verify achievement of these criteria before GPC’s acceptance of Commercial Operation.

      - Reserved.

      - The BESS is capable of receiving Grid Charging Energy and delivering Discharging Energy on a reliable basis.

      - The Facility’s AGC system, as approved by GPC: (a) is completely installed and fully operational, is connected to GPC’s AGC RTU, and is capable of supplying all needed data, control system access, interconnection, and AGC Setpoint signals to allow GPC to dispatch the BESS; and (b) otherwise satisfies Section 10.8 (AGC) and Exhibit G (AGC and Storage Device Minimum Data Requirements);

      - If the BESS is paired with a Renewable Resource per Exhibit A (Facility Description and Additional Details): (a) the BESS is capable of receiving Renewable Resource Charging Energy on a reliable basis; and (b) the Renewable Resource achieved and has maintained commercial operation, as defined by the Renewable Resource PPA;

      - (a) Seller has satisfied all IA requirements that are conditions to commercial operation (as defined in the IA); (b) the Facility otherwise is in compliance with the IA; and (c) the Facility has demonstrated the reliability of its communication systems with the Dispatch Center;

      - Seller has successfully completed Performance Testing of the Facility and achieved the Performance Guarantees in accordance with Exhibit B (Capacity; Capacity Payments and Payment Reductions; Buydown), Part 1 (Testing Requirements), including a Tested Storage Capacity higher than 70% of the Contracted Capacity under Exhibit B;

      - Seller must have provided GPC with a certificate from a responsible officer of Seller reasonably acceptable to GPC stating that the Facility has been designed, engineered, constructed, and tested in accordance with Prudent Industry Practices and is capable of performing in accordance with the terms of this PPA;

      - Seller must have delivered to GPC a certificate from a responsible officer of Seller certifying that Seller has obtained all licenses, permits, franchises, agreements, approvals, authorizations, Consents, waivers, rights, exemptions, releases, variances, exceptions, or orders of or issued by, or filing with, or notice to, any Governmental Authority required under applicable law (“Governmental Approvals”) for the construction, ownership, operation, and maintenance of the Facility in accordance with this PPA; and

      - Any additional criteria set forth in the Commercial Operation Completion Certificate.

- For the avoidance of doubt, the Facility may achieve commercial operation in accordance with the Interconnection Agreement, and may be considered operational for all other purposes, including tax purposes, but the Facility will not be deemed to have achieved Commercial Operation for purposes of this PPA until (a) subsections (i) through (ix) are satisfied, and (b) GPC has reasonably determined Commercial Operation has been achieved in accordance with Section 7.1.6 (Commercial Operation Completion Certificate).

Commercial Operation Completion Certificate.

When Seller believes the Facility achieved the Commercial Operation requirements set forth in Section 7.1.5 (Commercial Operation), Seller must complete and submit to GPC the Commercial Operation Completion Certificate. Upon receipt of the Commercial Operation Completion Certificate, GPC will have the right, but not the obligation, to inspect the Facility or review inspection-related information before acceptance, as such inspection-related information may be reasonably requested by GPC. Within 20 Days after receipt, GPC will review the Commercial Operation Completion Certificate and notify Seller whether GPC agrees in its reasonable discretion that Commercial Operation was achieved. If GPC agrees in its reasonable discretion that Commercial Operation was achieved, the date that Seller submitted the Commercial Operation Completion Certificate will be the Commercial Operation Date. However, if GPC determines in its reasonable discretion that the Facility has not actually achieved Commercial Operation, GPC will notify Seller of any issue and deficiency, and Seller must: promptly (i) resolve any issue or deficiency and then resubmit the Commercial Operation Completion Certificate; or (ii) demonstrate to GPC’s reasonable satisfaction why the Facility has actually achieved Commercial Operation. This process will repeat until Commercial Operation (as determined by GPC in its reasonable discretion) is achieved. Seller will be liable for delay liquidated damages under Section 7.3 (Failure to Achieve Commercial Operation by RCOD) if GPC determines in its reasonable discretion that Seller did not timely achieve Commercial Operation. Subject to Section 7.3.4 (RCOD Exceptions), if applicable, Seller will be entitled to an RCOD extension if the Interconnection Provider is solely responsible for a delay in the construction of Interconnection Facilities.

Key Milestones and Milestone Schedule.

By no later than 10 Business Days after the date of the Commission Certificate, Seller must provide a Milestone Schedule. At a minimum, the Milestone Schedule must include the Key Milestones stated in Exhibit A-1 (Key Milestones and Required Key Milestone Dates) and supported by documentation, as applicable.

Milestone Schedule Updates; Monthly Reports.

Until COD, Seller must  submit to GPC a Monthly written status report that: (i) covers the previous Month; (ii) is prepared in a manner and format (hard copy and electronic) reasonably acceptable to GPC; and (iii) includes a detailed summary of (a) Seller’s progress toward each of the Key Milestones and the Facility’s development and construction, (b) Seller’s adherence to the Milestone Schedule, (c) any significant event that is scheduled or expected to occur during the following 30 Days, and (d) any other information reasonably requested by GPC. Seller must promptly notify GPC of any significant change in the Milestone Schedule that may delay Commercial Operation or the status of construction as may occur from time to time (including the reason for the change).

Recovery Plan.

Promptly, but no later than 10 Business Days, after becoming aware of any event or circumstance that is reasonably expected to cause a delay in achieving any Key Milestone by its Key Milestone Date, Seller must provide to GPC for GPC’s review and approval a recovery plan setting forth in detail and with supporting documentation: (i) the cause(s) of the event or circumstance and the expected length of delay; and (ii) Seller’s plan to recover the lost time and regain compliance with the Milestone Schedule to achieve Commercial Operation by the RCOD, or if not by the RCOD, then by no later than nine Months after the RCOD. GPC’s right to approve Seller’s recovery plan is limited solely to determining if the recovery plan demonstrates with sufficient particularity that Seller will regain compliance with the Milestone Schedule and achieve Commercial Operation by the RCOD or, if not by the RCOD, then by no later than nine Months after the RCOD, and these approval rights do not extend to the general mode, manner, or cost of Seller’s performance of the recovery plan. If GPC does not approve Seller’s recovery plan, GPC will notify Seller of the specific deficiencies in the recovery plan by no later than 10 Days after GPC’s receipt of the recovery plan. By no later than 10 Days after receipt of GPC’s rejection, Seller must revise the recovery plan to address the deficiencies stated in GPC’s notice and resubmit the recovery plan to GPC. Nothing in this Section 7.2.2 will be construed to relieve Seller of any of its PPA obligations. The delivery of a recovery plan meeting GPC’s approval as outlined in this Section 7.2.2 (Recovery Plan) will satisfy Seller’s obligation with respect to any delay in achieving a Key Milestone, except for a delay in achieving Commercial Operation as set forth in Section 7.3 (Failure to Achieve Commercial Operation by RCOD) or any delay caused by an FME as set forth in Part 15 (Force Majeure).

Requested Information and Physical Inspections.

GPC may reasonably request information regarding the status of the Facility and inspect the Facility’s construction, startup, and testing. Seller must provide, or cause to be provided, to GPC the requested information. Additionally, Seller must coordinate physical inspection of the Facility as GPC may reasonably request during or after completion of construction. GPC will provide Seller reasonable prior notice regarding an inspection. All GPC or GPC-Representative activities at the Site will be subject to Seller’s reasonable rules and procedures (including those related to health and safety).

Failure to Achieve Commercial Operation by RCOD.

Delay Liquidated Damages.

If Seller fails to achieve Commercial Operation by the RCOD, Seller must pay to GPC delay liquidated damages calculated in accordance with Part 2 (Liquidated Damages) of Exhibit A-2 (Performance Security and Liquidated Damages), prorated daily, until the earlier of: (i) COD; (ii) the Day GPC receives notice from Seller that Commercial Operation will not be achieved; or (iii) termination of this PPA for an Event of Default by Seller.

No Payment to Seller during Delay.

GPC will not owe any Monthly Capacity Payment to Seller during any period of delay in achieving Commercial Operation.

Seller Payment of Delay Liquidated Damages; Pre-COD Termination Damages.

Seller must pay GPC, on a Monthly basis by no later than 10 Days after the end of the applicable Month, delay liquidated damages that accrued under this Section 7.3 (Failure to Achieve Commercial Operation by RCOD) during the preceding Month. In accordance with Section 6.3 (Draws; Replenishment): (i) GPC may draw upon the Performance Security to recover delay liquidated damages owed under this Section 7.3 to the extent not paid when due; and (ii) Seller must replenish the Performance Security. The Parties will resolve any dispute regarding delay liquidated damages under this Section 7.3 in accordance with Section 5.2 (Billing Disputes and Final Accounting). If Seller notifies GPC that Seller has reasonably determined that Seller will not achieve Commercial Operation and GPC does not terminate this PPA within 30 Days after GPC’s receipt of Seller’s notice, Seller will have the right to terminate this PPA on notice to GPC. A Seller termination in accordance with the preceding sentence will constitute a Seller Event of Default under Section 16.1.12 (Abandonment or Failure to Achieve RCOD). If GPC terminates this PPA for a Seller Event of Default under Section 16.1.12, or if Seller terminates the PPA in accordance with the preceding sentences, then, in addition to Seller’s payment of the delay liquidated damages that accrue under Section 7.3, Seller must pay to GPC, as the Termination Payment, termination liquidated damages in an amount equal to the applicable Performance Security amount shown in Part 1 (Performance Security) of Exhibit A-2 (Performance Security and Liquidated Damages). Seller must also reimburse GPC for the total costs GPC incurred for modifications to the Electric System associated with the Facility and the operational capability to deliver energy from the Facility to GPC’s customers, subject to any applicable requirement of the Southern OATT. Following termination, as described in the preceding sentences, and Seller’s payment to GPC of all required damages in accordance with this Section 7.3 and Section 16.3.2, neither Party will have any other liability to the other Party under this PPA.

RCOD Exceptions.

If Seller’s failure to achieve Commercial Operation by the RCOD is solely caused by: (i) an FME under Section 15.3 (No Breach or Liability); (ii) a delay in the construction by Interconnection Provider of the Interconnection Facilities; or (iii) a delay in GPC’s review and coordination of Seller’s AGC system design for the Facility, so long as Seller has complied with Section 8.1.3 (Interconnection Projected Completion Date) and the delay is not caused by any action or inaction on the part of Seller, the RCOD will be extended, in each case, by the number of days supported by a critical path analysis. In the case of (ii), if Seller has not met all IA obligations in a timely manner, Seller’s failure to achieve Commercial Operation by the RCOD will not be excused, the RCOD will not be extended, and, while the Interconnection Provider completes construction of the Interconnection Facilities, Seller will owe delay liquidated damages for each Day of delay after RCOD as set forth in Section 7.3.1 (Delay Liquidated Damages).

Liability Following Termination.

If GPC terminates this PPA in accordance with Section 16.3 (Remedies) for a Seller Event of Default under Section 16.1.12 (Abandonment or Failure to Achieve RCOD), Seller will owe the Termination Payment under Section 16.3 in addition to the delay liquidated damages that accrue before termination. After the termination, other than the requirement for Seller to pay the damages that accrue under this Section 7.3 (Failure to Achieve Commercial Operation by RCOD) and Section 16.3.2 (Termination Payment), neither Party will have any further liability to the other Party under this PPA.

Commercial Operation Delay Caused by Southern Company Transmission System Capability.

RCOD Extension to Accommodate Start-Up and Testing.

Subject to all conditions in this Section 7.3.6(i), the RCOD will be extended if: (a) as a sole and direct result of Interconnection Facilities construction delay, Facility start-up and testing activities are delayed and Seller is prevented from achieving Commercial Operation by the RCOD; (b) the Interconnection Provider is solely responsible under the IA for the Interconnection Facilities construction delay; and (c) Seller undertakes all commercially reasonable action to avoid, overcome, or otherwise mitigate the impact of the delay. Any RCOD extension under this Section 7.3.6(i) will be based on the demonstrable impact to the critical path of the Milestone Schedule. The RCOD will not be extended if: (I) Seller has not timely complied with Section 8.1 (Interconnection); or (II) the delay was caused, in whole or in part, by any action or inaction on the part of Seller or a Seller Representative.

Exclusive Remedy.

Seller understands and acknowledges that extension of RCOD in accordance with Section 7.3.6(i) (RCOD Extension to Accommodate Start-Up and Testing) will be Seller’s exclusive remedy for any delay described in Section 7.3.6(i).

No PPA Term Extension.

Despite any other provision in this PPA, an extension of RCOD under Section 7.3.6(i) (RCOD Extension to Accommodate Start-Up and Testing) will not cause an extension of the Term, and no delay described in this Section 7.3.6 will otherwise extend this PPA beyond its stated Term.

Interconnection and Metering

Interconnection.

Interconnection Study and Entry into IA.

Seller must (a) have entered into an IA with the Interconnection Provider on or before the Effective Date, or (b) enter into an IA with the Interconnection Provider by no later than 30 Days after the Interconnection Provider presents Seller with the IA for execution, unless GPC agrees otherwise in writing. Seller must timely comply with all obligations under the Interconnection Study Agreement and IA, including timely submission of required data, documentation, and payment, as applicable. Contracted Capacity must not exceed the Interconnection Limit. The IA must be maintained in effect throughout the Term (or, if entered into after the Effective Date, throughout the remainder of the Term). Seller must promptly provide notice to GPC of  the execution of the IA or any amendment to the IA, including a copy of the executed IA or amendment.

Interconnection Costs and Expenses.

GPC will not be responsible under this PPA for any cost or expense (including overheads and administrative costs) or risk incurred concerning: (i) the Interconnection Study; or (ii) the design, construction, installation, modification, or maintenance of the Interconnection Facilities. Seller is responsible for determining all transmission- and interconnection-related rules, practices, and policies with which Seller must comply. Seller also is responsible for satisfying the payment or security requirements of any Interconnection Provider.

Interconnection Projected Completion Date.

The IA must reflect a projected completion date for construction or modification of the Interconnection Facilities, including a reasonable schedule between initial synchronization and the RCOD to allow for operations verification and testing consistent with the Interconnection Provider’s current practices. Seller must, in a timely manner, execute and perform under the IA, including providing timely notice to proceed, timely submission of required data and documentation, and timely payment or security. Seller acknowledges that before entering an IA with Interconnection Provider, as described in Section 8.1.1 (Interconnection Study and Entry into IA), Seller may need to enter an engineering, procurement, and construction agreement to provide timely notice to proceed.

Interconnection to Southern Company Transmission System.

The IA will be read in conjunction with this Part 8 (Interconnection and Metering) and any contradictory provision related to Facility interconnection will be resolved in favor of the IA.

Metering and Telemetry.

Metering System.

Seller must ensure the Metering System is designed, located, constructed, installed, owned, operated, and maintained in accordance with the IA and Prudent Industry Practices to measure and record the energy delivered to the POI from the Facility, and to the Facility from the POI and, if applicable, from  the Renewable Resource, to determine: (i) BESS capacity; and (ii) the measured availability of the BESS in meeting GPC’s AGC Setpoint signals. The Metering System must: (a) continuously measure BESS input/output and report the values at all times; and (b) if the BESS is paired with a Renewable Resource, continuously and separately measure the BESS input/output and Renewable Resource output and report both values at all times. If applicable, the Renewable Resource output must be measured at the low side of the GSU and at the POI. The low side meter output will be reported unadjusted and will also be reported adjusted to the POI to account for all losses, at GPC’s discretion. The Metering System will be of a mutually acceptable accuracy range and type, including audit capabilities. Seller and Seller’s Representatives must not adjust the Metering System without GPC’s written consent. GPC, at its own cost, may install additional meters or other such facilities, equipment, or devices as GPC deems necessary or appropriate to monitor the measurements of the Metering System. Seller must install, at its own expense, all needed metering support equipment on its side of the POI to facilitate GPC’s dispatch of the BESS via AGC Setpoint signals. Seller must also, at Seller’s expense, install or upgrade the Facility control systems to allow GPC’s AGC dispatch of the BESS. GPC will reasonably establish the telemetering equipment and systems that are necessary to dispatch the BESS from the Dispatch Center, and Seller, at Seller’s expense, must install or cause the installation of such telemetering equipment. Seller must deliver to GPC all the telemetered data and any other data GPC requests.

Inspection.

Seller must inspect and test all meters at such times as will conform to Prudent Industry Practices, but not less often than once biennially. Seller will be responsible for all costs and expenses incurred in connection with such inspections or tests.

Adjustments.

If the Metering System, including any meter or measuring component of the Metering System, fails to register, has a broken seal, or upon testing, provides a measurement that varies by more than the lesser of: (i) 0.5% relative to the measurement made by the standard meter used in the test, or (ii) 1.0% relative to the manufacturer’s accuracy specification for the standard meter used in the test, then Seller must, at its sole cost and expense, repair or replace the affected portion(s) of the Metering System within a reasonable period after the test. Further, if the Metering System or component provides a measurement that varies by more than 1.0% relative to the measurement made by the standard meter used in the test, then all measurements of energy made by the Metering System during the Adjustment Period will be adjusted to correct any inaccuracies, and all amounts previously invoiced or paid for that energy will be reconciled. “Adjustment Period” means either: (a) the actual period when inaccurate measurements were made by the Metering System, if that period can be determined to the mutual satisfaction of the Parties; or (b) if the actual period cannot be determined to the mutual satisfaction of the Parties, the second half of the period from the date of the last test of the Metering System to the date the failure is discovered or the test is made. If the Parties are unable to agree on the adjustment to be applied to the Adjustment Period, the adjustment will be determined: (I) by correcting the error if the percentage of error is ascertainable by calibration, test, or mathematical calculation; or (II) if not so ascertainable, by estimating based on deliveries made under similar conditions during the period since the last test. Within 30 Days after the determination of any adjustment, GPC will pay Seller any additional amount then due or GPC will be entitled to a credit against any subsequent Monthly Capacity Payment.

Notice of Testing.

GPC and its Representatives may be present at any test, inspection, maintenance, adjustment, or replacement of any part of the Metering System relating to obligations under this PPA. Seller must provide GPC with reasonable prior notice regarding an activity described in the preceding sentence.

Loss Factor Adjustment.

If, and to the extent, the Metering System is not measuring deliveries of energy physically at the POI, the metered energy quantity will be adjusted for losses to or from the POI by a loss factor determined by GPC, in accordance with Prudent Industry Practices.

BESS Capacity and Performance Tests

Tested Storage Capacity and Contracted Capacity.

Before Commercial Operation, Seller must conduct, at its expense, Performance Testing as detailed in Section 1.2 (Tested Storage Capacity; Performance Testing) of Exhibit B (Capacity; Capacity Payments and Payment Reductions; Buydown). Seller must notify GPC Representatives in advance of Seller’s Performance Testing and allow GPC to witness and participate in the Performance Testing as GPC desires. Subject to Seller’s compliance with the previous sentence, Seller will not be required to delay or reschedule Performance Testing solely due to GPC’s unavailability. Upon Seller’s completion of any Performance Test, Seller must promptly provide to GPC a complete written report, in accordance with Exhibit E (Performance Testing Procedures), of the Performance Test, certified by a responsible officer of Seller, for GPC’s review and verification. Following the Delivery Commencement Date, Seller must cooperate with GPC’s request for information concerning Facility performance that GPC may reasonably request from time to time.

Disputes Concerning Capacity Tests.

If the Parties disagree regarding the Performance Test results, the Parties will resolve the dispute in accordance with Section 19.2 (Expert Arbitration). If the dispute is not resolved by the first Day of any Annual Period, the relevant Tested Storage Capacity from the most recent undisputed Performance Test will be used by GPC for the Monthly Capacity Fee calculation until the dispute is resolved. After the dispute is resolved, an adjustment may be made to Monthly Capacity Payments made regarding the Annual Period to account for any difference between the SDDC and the preceding Tested Storage Capacity from the most recent Performance Test.

Operation and Maintenance

Operation and Maintenance.

General Standards.

Seller must manage, control, operate, and maintain all parts of the Facility in a manner consistent with Prudent Industry Practices, considering GPC’s right to dispatch the BESS and, if applicable, the Renewable Resource, in accordance with applicable planning standards and operating policies of SERC and NERC, and in accordance with the Operating Procedures to be developed by the Operating Committee. The requirements of this Section 10.1.1 will not be interpreted to limit GPC’s dispatch rights as provided for elsewhere in this PPA.

Written Operating Procedures.

Seller and GPC will mutually develop and agree upon written Operating Procedures no later than six Months before the Delivery Commencement Date. Topics covered will include: (i) Performance Tests procedures, deliveries of energy during start-up, and testing of the Facility; (ii) the method of Day-to-Day communications; (iii) clearance and switching practices; (iv) daily capacity availability and energy reports; (v) Facility operations log; (vi) reactive power output; (vii) Technical Limits regarding Facility operation (including maximum ramp rates and other limits specified in Exhibit F (Facility Operating and Dispatching Requirements)); (viii) ramp rates for the delivery of power to the POI; (ix) coordination of maintenance scheduling; (x) designation of Confidential Information; and (xi) any other matters as the Operating Representatives agree are appropriate. The Operating Representatives will be responsible for modifying, from time to time, these Operating Procedures in writing to reflect agreed changes. In the event of inconsistency or conflict between the Operating Procedures and specific terms of this PPA, the specific terms of this PPA will take precedence. If the Facility is paired with a Renewable Resource, the Operating Procedures must align with and be complementary to the operating procedures for the Renewable Resource developed under the Renewable Resource PPA.

Safety Devices, Safety Practices, and Records. Seller must employ at the Facility all safety devices and safety practices required by Prudent Industry Practices. Seller must keep accurate records of any accident or other occurrence at the Site that results in injury to persons or damage to property. Seller must provide to GPC reasonable access to these records upon at least seven Days’ notice during normal business Hours, but Seller will not be required to provide access to employment records regarding Facility personnel.

Facility Personnel.

During the Term, Seller must employ qualified and trained personnel for management, operation, and maintenance of the Facility.

Maintenance Scheduling.

Maintenance Schedule Reporting and Approvals.

Commencing in the year before the year of the Delivery Commencement Date, and continuing throughout the Term, Seller must submit to GPC before September 1 Maintenance Schedules covering the next four Annual Periods or the number of Annual Periods remaining in the Term, whichever is less. Seller must not schedule any maintenance of the Facility during any On Peak Season of any Annual Period that would decrease the BESS: (i) capacity output below the SDDC; (ii) energy storage capability below the SDOE; or (iii) rate of charge capability below the ROC, without the prior written consent of GPC. The proposed Maintenance Schedules are subject to the approval of GPC, which approval GPC will not unreasonably withhold or delay. GPC will have 30 Days to review the proposed Maintenance Schedules and may approve or reject (in whole or in part) the Maintenance Schedules. If any portion of a Maintenance Schedule is rejected by GPC, Seller must resubmit a revised Maintenance Schedule to GPC within 30 Days of GPC’s rejection and GPC and Seller agree to use best efforts to promptly develop Maintenance Schedules that are mutually acceptable, considering the burdens that GPC’s changes impose on Seller compared to the burdens avoided by GPC because of such changes. Any dispute concerning this Section 10.2.1 will be resolved in accordance with the provisions of Part 19 (Dispute Resolution) applicable to Maintenance Schedule disputes. The outages included in the final, approved Maintenance Schedule for the current Annual Period will be the Scheduled Outages for that Annual Period. GPC will exclude Scheduled Outages from its calculation of Performance Metrics under Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements).

Maintenance Outages.

In addition to Scheduled Outages, Seller may request Maintenance Outages during any Annual Period. Seller must notify GPC (in writing, electronically, or orally) of each Maintenance Outage no less than 24 Hours in advance and at least one Business Day in advance of Seller’s proposed commencement of the Maintenance Outage. In Seller’s request, Seller must identify the equipment and the percentage of SDDC and SDOE that will not be available for delivery at the POI and the proposed start time and duration of the Maintenance Outage. GPC will respond to Seller’s request as soon as reasonably practicable. Seller must not take a Maintenance Outage that would impair the Facility’s ability to meet the SDDC or SDOE without GPC’s prior written or telephonic consent, and GPC’ will not unreasonably withhold, condition, or delay its consent. Despite the preceding sentence, each Party acknowledges that it will be reasonable for GPC to deny any request for a Maintenance Outage if GPC reasonably believes that it may need the BESS during the requested time period. GPC will have the right to revoke its consent to a Maintenance Outage if any changed condition requires the availability of the BESS. If GPC requests Seller to return to full Availability status all or part of that portion of the BESS that is affected by the Maintenance Outage, Seller must comply as soon as reasonably practical. GPC will not dispatch the BESS to the extent that the BESS is not capable of receiving or delivering energy as a direct result of a Scheduled Outage or a Maintenance Outage approved by GPC. GPC’s calculation of Performance Metrics under Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements) will exclude approved Maintenance Outages. For avoidance of doubt, GPC’s advanced consent is not required for Seller to take any action that Seller reasonably believes is necessary to prevent damage to person or property, but (i) any resulting outage or derate will not be considered a Maintenance Outage or Scheduled Outage; and (ii) Seller must notify GPC of any resulting outage or derate as soon as practicable.

Reporting of Forced Outages and Derates.

Through the method required by the Operating Procedures, Seller must notify GPC promptly upon the occurrence of any Forced Outage or Forced Derate, except that Seller will not be required to notify GPC of any Forced Derate that: (i) is less than 0.5 MW; (ii) falls within the rounding requirements specified in the Operating Procedures; or (iii) does not reduce the Facility’s ability to meet the SDDC or SDOE. As soon as practicable, but in any event not later than one Business Day after the beginning of the period of the Forced Outage or Forced Derate, Seller must notify GPC of: (i) the cause of the outage or derate; (ii) the amount of SDDC and SDOE affected by the outage or derate; (iii) the proposed corrective action to address the outage or derate; and (iv) Seller’s reasonable estimate of the expected duration of the Forced Outage or Forced Derate and expected return to full operation.

System Emergencies.

If Seller has a Scheduled Outage or Maintenance Outage, and the Scheduled Outage or Maintenance Outage occurs or would occur coincident with a System Emergency, GPC will notify Seller of the System Emergency. GPC may, because of the System Emergency, request Seller to reschedule the Scheduled Outage or Maintenance Outage or, if the Scheduled Outage or Maintenance Outage has begun, to expedite its completion, and Seller must comply with GPC’s request as soon as reasonably practical subject to Prudent Industry Practices and any limitation or coordination requirement outlined in the Operating Procedures as necessary for Seller to preserve its equipment warranties.

Reserved.

Access to the Site and the Facility.

Seller grants to GPC or GPC’s designated Representatives, with reasonable prior notice to Seller, the right to enter the Site at reasonable times (including nights and weekends) to: (i) inspect, maintain, or test meters and other GPC equipment; (ii) monitor or measure energy received or discharged by the BESS in accordance with this PPA and Prudent Industry Practices; (iii) monitor Performance Tests; or (iv) inspect the Facility. Seller must cooperate in the physical inspection of the Facility as GPC may reasonably require, so long as: (a) the inspection will not materially interfere with the Facility’s testing or operations; and (b) GPC complies with rules and regulations of Governmental Authorities having jurisdiction regarding the Facility and with Seller’s reasonable policies and procedures applicable to the Facility, including those regarding safety and any requirement that Seller Representatives accompany GPC Representatives during Site visits. GPC’s technical review or inspection of the Facility will not be construed as endorsing Facility design or construction or as any warranty of the safety, durability, or reliability of the Facility. Seller must cooperate, and must cause its Representatives to cooperate, in: (I) providing the information GPC reasonably requests; and (II) the physical inspection of the Facility as GPC may reasonably request during and after completion of construction.

Availability of Records.

Seller must keep complete and accurate records and all other data necessary for the purpose of proper PPA administration in accordance with the following guidelines:

Holding Period.

Seller must maintain all records related to the Facility and Seller’s performance under this PPA for a minimum of five years after the creation of the record or data and for any additional time period required by applicable law or a Governmental Authority. However, the records must be kept for as long as is necessary to complete any audit that began or was announced during the five-year period. Despite any other PPA provision, during the Term and for six years after the Term, , Seller must provide GPC with 30 Days’ prior notice before disposing of or destroying any record or data related to the Facility or Seller’s performance under this PPA.

Operating Logs.

Seller must maintain at the Facility an accurate and up-to-date operating log with records of: (i) real and reactive power production for each Hour; (ii) changes in operating status and scheduled maintenance; (iii) Scheduled Outages, Maintenance Outages, Forced Outages, Forced Derates, and Force Majeure Events; (iv) any unusual condition found during an inspection; and (v) any significant event related to the operation of the Facility.

GPC’s Access to Facility and PPA Records.

Upon reasonable advance notice and during normal business Hours, GPC will have the right from time to time to examine at the Facility, or at a location mutually agreed to by the Parties, the records and data relating to the Facility and this PPA, including all historical test records relating to the Facility.

GPC’s Access to Financial and Business Information.

At GPC’s request, throughout the Term, Seller must provide to GPC public and non-public financial and business information reasonably necessary for GPC to make accounting determinations. Without limiting the preceding sentence, upon reasonable notice to Seller, GPC and GPC’s independent auditor will have the right to inspect, from time to time, Seller’s books and records as are reasonably necessary for GPC to determine whether Seller constitutes a VIE or this PPA represents a VI. To the extent the inspection requires access to Seller’s Confidential Information, the information will constitute Confidential Information subject to Section 20.16 (Confidentiality).

GADS Data. Seller must provide to GPC, by no later than the 10th Day of each Month, all data for the preceding Month relating to the Facility that is required by applicable law to be reported to the NERC Generation Availability Data System (GADS) (or any successor system or other applicable system). Without limiting the previous sentence, Seller must use commercially reasonable efforts to obtain and provide to GPC any data not in Seller’s possession or control.

Effect of GPC Action.

Seller understands and agrees that GPC’s receipt and review of any material related to the Project or any physical inspection of the Facility GPC conducts under any PPA provision is solely for GPC’s own information. By conducting the review or inspection, GPC makes no endorsement of the design or representation or warranty of the safety, durability, or reliability of the Facility, all of which are the sole responsibility of Seller in accordance with the terms of this PPA, and GPC will not be deemed to have accepted any condition of the Facility that is not in full compliance with the terms of this PPA. Seller must not represent to any third party that, because of GPC’s receipt or review of any material or any inspection, GPC is in any way responsible for the engineering or construction soundness or operational practice of the Facility.

Operating Committee.

Appointments.

The Parties will establish an Operating Committee comprised of two Operating Representatives, one appointed by each of Seller and GPC. Each Party will provide notice of the appointment to the other Party. Each Party may change its Operating Representative appointment at any time by notice to the other Party. The Operating Representatives will meet as necessary, but not less often than once each calendar year, at a mutually agreeable time and place upon prior notice. The Operating Representatives will represent the Parties in all matters arising under this PPA that are delegated to them by mutual agreement of the Parties, but the Operating Representatives will not have any authority to modify or amend the terms of this PPA. The Parties, by mutual consent, may combine one or more Operating Committee meetings with the operating committee meetings (or functional equivalent) held under the Renewable Resource PPA, if applicable per Exhibit A (Facility Description and Additional Details).

Cooperation.

- Each Party will cooperate in providing the Operating Representatives all information required in the performance of their duties. If the Operating Representatives are unable to agree on any matter falling under their jurisdiction, the Operating Representatives will submit the matter to senior officers for discussion and resolution. All decisions and agreements made by the Operating Representatives or their principals must be evidenced in writing.

AGC.

Reserved.

Operation on AGC.

Seller must operate the BESS and charge or discharge in compliance with GPC‘s AGC Setpoint signals as further described in Section 10.8.3 (AGC Setpoint Signals). During periods when the AGC Setpoint is zero MW, the BESS must be controlled so that the BESS does not discharge (e.g., is in idle state). At any time during the Term, if the Facility cannot operate on AGC, in whole or in part, GPC can dispatch the BESS using scheduling instructions from the Dispatch Center, as further described in the Operating Procedures. Seller must comply with any scheduling instruction given by the Dispatch Center, subject to the Technical Limits and scheduling procedures stated in the Operating Procedures.

AGC Setpoint Signals.

At Seller’s sole expense, Seller will install, operate, and maintain AGC equipment and systems at the Facility as necessary to enable the Facility to respond to and follow GPC’s AGC Setpoint signals in compliance with this PPA but subject to any IA limitation, including the interconnection service limit. The Facility must be capable of remaining on AGC at all times while Available. The Facility’s AGC system will include all necessary connections to GPC’s AGC equipment (to GPC ’s satisfaction) to enable GPC to send AGC Setpoint signals to the Facility and to measure, record, and control energy input/output from the Facility at all times. The Facility’s AGC system must conform to Prudent Industry Practices and be configured to interface with GPC’s AGC RTU(s) to send and receive data for AGC that satisfies the minimum data requirements in Exhibit G (AGC and Facility Minimum Data Requirements).

AGC Performance Requirements.

Part 3 (AGC Performance Metrics and Requirements) of Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements) establishes the AGC Performance Requirements. Seller must comply with the AGC Status Performance Requirement and the AGC Setpoint Response Performance Requirement for each Month of each Annual Period. If, at any time during the Term, the Facility’s performance deviates from the AGC Status Performance Requirement or the AGC Setpoint Response Performance Requirement, Seller must promptly: (i) communicate to GPC the cause of the deviation; and (ii) take action to correct any deficiency and regain compliance with the AGC Performance Requirements, if applicable. If Seller fails to achieve the AGC Status Performance Requirement or the AGC Setpoint Response Performance Requirement for any three consecutive Months or for six non-consecutive Months in any 12-Month period (each, a “Triggering Failure”), Seller must perform an analysis of the reasons for the failure within five Business Days after notice of a Triggering Failure from GPC. Within 15 Business Days after receipt of a Triggering Failure notice, Seller must provide GPC with its analysis and a reasonable plan that explains the steps Seller will take to remedy the reason(s) for the failure and to regain compliance with the AGC Status Performance Requirement and the AGC Setpoint Response Performance Requirement (“AGC Plan”). If GPC has comments or recommendations to Seller’s AGC Plan, Seller must address GPC’s comments, incorporate GPC’s commercially reasonable recommendations, and resubmit the AGC Plan to GPC within 15 Business Days after receiving GPC’s comments. After GPC approves the AGC Plan, which approval will not be unreasonably withheld, Seller must diligently implement the AGC Plan. If Seller: (a) does not timely perform an analysis of a failure; (b) does not timely present the AGC Plan to GPC or respond to any comments or recommendations of GPC to Seller’s AGC Plan; or (c) fails to diligently implement the AGC Plan approved by GPC, GPC may declare an Event of Default by Seller pursuant to Section 16.1.10 (Failure to Meet AGC Performance Requirements).

AGC Plan Dispute. If the Parties cannot reach agreement on the proposed AGC Plan, either Party may submit the proposed AGC Plan to the Operating Committee for review. Within 15 Business Days after receipt of the AGC Plan, the Operating Committee must issue a report and recommendation regarding Seller’s proposed AGC Plan as last presented to GPC and any recommended modification. The Parties must consider the Operating Committee’s report and recommendation. If the AGC Plan is not resolved after considering the Operating Committee’s report, the dispute must be resolved in accordance with Part 19 (Dispute Resolution).

Reserved.

Performance Metrics.

Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements) details the Performance Metrics that Seller must achieve each Month of each Annual Period during the Term. If Seller fails to achieve certain required Performance Metrics in a given Month, Seller’s Monthly Capacity Payment will be reduced as described in Exhibit C.

Reactive Power.

During the Term, the Facility must be capable of providing, and upon GPC’s request Seller must cause the Facility to provide, reactive power support (i.e., to produce and absorb reactive power) to meet the Interconnection Provider’s voltage schedule requirements outlined in Southern Company Bulk Power Operation’s BPO-01 – Attachment A, as well as meeting the operational requirements  as specified in The Southern Company Bulk Power Operations Procedure BPO-01 at all real power levels (pushing and pulling), including zero real power. In the case of a BESS comprised of technology other than inverter-based technology, such requirements will apply only when the BESS is charging or discharging. For any BESS comprised of inverter-based technology, such requirements will apply at all times when the Facility is Available, regardless of whether the Facility is delivering real power.

Cyber Security.

The Facility must comply with the requirements for Bulk Electric System generation facilities in North America set forth in the NERC reliability standards (Cyber Security Standards) created pursuant to FERC Order 706 (Mandatory Reliability Standards for Critical Infrastructure Protection), other applicable law, or Prudent Industry Practices. With respect to any actual or suspected cyber security incident that compromises, disrupts, or constitutes an attempt to compromise or disrupt: (i) Seller’s cyber security or physical security at the Facility; (ii) the performance of Seller’s obligations regarding the operation of the Facility; or (iii) products, software, hardware, or systems provided or to be provided by Seller under this PPA (a “Cyber Security Incident”), Seller must report any Cyber Security Incident to GPC within 24 Hours after discovery. Seller must take immediate steps to address any Cyber Security Incident and to mitigate any impact to the Facility and GPC as a result of a Cyber Security Incident, up to and including the replacement of any affected equipment, if applicable.

Sourcing Restrictions. Programmable electronic components of the: (i) Battery Management System (BMS); (ii) BESS Controller; and (iii) Site Controller (including controls, hardware and software) must not be sourced from or manufactured by Foreign Entities of Concern (“FEOC”) as defined in 42 U.S.C. § 18741(5) and subsequently interpreted in “Interpretation of Foreign Entity of Concern,” 89 Fed. Reg. 37085 (May 6, 2024) or sourced from or manufactured in one of the following countries: China, Russia, North Korea, Saudi Arabia, Serbia, Algeria, Venezuela, Iran, Iraq, Belarus, Kazakhstan, Kyrgyzstan, Uzbekistan, Syria, Lebanon, South Sudan, Pakistan, or Cuba. For purposes of this provision, the terms Battery Management System, BESS Controller, and Site Controller are defined as follows:

Battery Management System (BMS): A control system used to protect the battery and to provide key parameters, such as state of charge, battery health, and temperature.

BESS Controller: A controller used to manage multiple stacks or arrays of batteries. This controller manages the balancing of the batteries.

Site Controller: A control system used to manage one or more sources (Photovoltaic solar, batteries, etc.) to achieve facility level control.

BESS; Grid Charging; Renewable Resource Charging

Use of BESS.

Seller acknowledges and agrees that the exclusive purpose and use of the BESS during the Term is to satisfy Seller’s capacity obligations under this PPA and to satisfy Seller’s obligations under this PPA to charge the BESS or discharge energy to the POI in accordance with GPC’s dispatch instructions.

Reserved.

Grid Charging; Renewable Resource Charging.

At GPC’s discretion, GPC may direct Grid Charging or, if a Renewable Resource is identified in Exhibit A (Facility Description and Additional Details), Renewable Resource Charging at any time after COD and in any amount within BESS operating limits. Any Charging Energy will be counted against the Cycle Limits when discharged.

Energy Dispatch

Energy Dispatch.

GPC will issue dispatch instructions via six-second AGC Setpoint signals for the BESS electrical input and output committed under this PPA. If the AGC capability of the BESS is unavailable, GPC may utilize non-AGC dispatching and Seller, at Seller’s expense, must use commercially reasonable efforts to re-establish AGC capability.

Coordination and Dispatch.

Electrical Input and Output; Dispatch Instructions; IA Compliance.

The electrical input and output of the BESS committed under this PPA will be subject to AGC Setpoint signals issued by GPC. Seller must comply with these signals when received, subject to the Interconnection Limit, Technical Limits, and dispatch procedures set forth in Exhibit F (Facility Operating and Dispatching Requirements).

Records and Energy Dispatch.

GPC and Seller will maintain electronic records of the quantities of energy delivered or received each six-second period and Hour during the Term.

System Emergency.

      - General System Emergency Procedure. The Parties recognize that GPC is a FERC jurisdictional entity subject to the reliability authority of NERC and that, to ensure continuous and reliable electric service, GPC operates its system in accordance with the operating criteria and guidelines of NERC. If a System Emergency is declared and AGC dispatch is not available, GPC may require Seller’s personnel to operate the Facility manually, including potential start-up or shutdown situations, to maintain safe and reliable load levels and voltages on the Electric System. To the extent Seller is required, under this Section 12.2.3 (System Emergency), to take any action, or GPC takes any action, which will adversely affect Seller’s ability to meet the Performance Metrics, including dispatch modified in accordance with Section 12.2.3(ii) (Cooperation During System Emergency), Seller may be excused from meeting GPC’s AGC Setpoint signals for purposes of the Performance Metrics calculations.

      - Cooperation During System Emergency. Seller must cooperate with GPC in establishing System Emergency plans, including recovery from a local or widespread electrical blackout, voltage reduction to effect load curtailment, or other plans that may be necessary or appropriate under the circumstances.

Effect of Grid Emergencies.

The Parties recognize that, in accordance with the IA, Seller may be required to reduce the Facility’s operational capability or take other actions during a grid emergency, including disconnection of the Facility from the Southern Company Transmission System, to allow mitigation of system problems and repair or maintenance of the Interconnection Facilities or the Southern Company Transmission System. To the extent Seller is required under the IA to take any action, other than instances where Seller’s acts or omissions are the cause for the required actions, which will adversely affect Seller’s ability to meet GPC’s AGC Setpoint signals, Seller will be excused from meeting GPC’s AGC Setpoint signals and, for the purposes of Performance Metrics calculations, such AGC intervals will be removed as appropriate.

Effect of Insufficient Capability in the Transmission System.

If the Southern Company Transmission System is unable to receive Discharging Energy from the Facility, Seller will be excused from meeting GPC’s AGC Setpoint signals. For purposes of Performance Metrics calculations, the AGC intervals during which the Southern Company Transmission System was unable to receive Discharging Energy will be removed.

Insurance

Insurance Required of Seller.

Throughout the Term, Seller must acquire and maintain in effect without interruption, at its sole cost and expense, the types and amounts of insurance coverage as are consistent with Prudent Industry Practices, but in no event less than the types and amounts described in this Part 13 (Insurance). All insurance must be with insurers: (i) holding an AM Best rating of at least A- VII or equivalent; (ii) whose financial condition and policy forms are acceptable to GPC (Seller must not unreasonably withhold requested documents); and (iii) authorized to transact insurance in the state where the Facility is located.

Proof of Insurance.

Before the Effective Date and annually after the Effective Date on the COD anniversary, Seller must provide to GPC a certificate of insurance certifying Seller’s coverage under insurance policy(ies) issued by an insurance company or insurance companies meeting the requirements of Section 13.1 (Insurance Required of Seller). GPC’s receipt or acceptance, without objection, of a certificate of insurance that does not comply with this Part 13 (Insurance) does not operate as GPC’s waiver of Seller’s obligations under the requirements of this Part 13.

General Terms.

Upon commencement of operation of the Facility, the required insurance coverage must contain a broad form contractual endorsement specifically covering liabilities arising out of or caused by the operation of the Facility or by Seller’s failure to maintain the Facility in satisfactory and safe operating condition. Seller’s insurance must be primary for any activity arising out of this PPA. Insurance or self-insurance maintained by GPC or other additional insureds is in excess of Seller’s insurance, contingent and non-contributory. To the extent allowed by applicable law, the GPC-Related Parties must be additional insureds under the commercial general liability policy, auto liability policy and, if applicable, excess/umbrella policy. To the extent allowed by applicable law, Seller waives, and must require its insurers to waive, a right of subrogation against the GPC-Related Parties for the commercial general liability policy, auto liability policy, umbrella policy, if applicable, and the workers’ compensation policy.

Required Insurance.

Seller must acquire and maintain throughout the Term, the following types of insurance:

Commercial General Liability Insurance.

      - Commercial General Liability insurance providing the following coverage, which can be exceeded by Seller and may be met through a combination of primary insurance and following form excess or umbrella insurance, so long as the combined limits meet requirements of this PPA:General Requirements. Commercial general liability insurance in an “occurrence” form with bodily injury and property damage combined liability limits of not less than twenty million dollars ($20,000,000.00) per occurrence and in the aggregate, except that: (i) Seller may use any combination of primary or excess policies to satisfy the overall limit requirements; and (ii) if Seller uses a “claims-made” policy, it must maintain continuous coverage in effect for at least five years beyond termination of this PPA, through continuous renewal of the original policy or by purchasing extended discovery period or retroactive insurance dated back to the Effective Date of this PPA.

      - Additional Requirements. Specific coverage for broad form contractual liability and a separation of insureds provision.

    - Additional Insurance.

In addition to the other requirements in Sections 13.1 (Insurance Required of Seller) through 13.4 (Required Insurance), Seller must acquire and maintain throughout the Term, the following additional types of insurance:

      - Workers’ Compensation.

Workers’ compensation insurance in accordance with statutory requirements, including employer’s liability insurance, with limits not less than one million dollars ($1,000,000.00) per occurrence and in the aggregate, and endorsement providing insurance for obligations under the U.S. Longshoremen’s and Harbor Worker’s Compensation Act and the Jones Act, where applicable.

      - Auto Liability.

Automobile liability insurance including owned, non-owned, and hired automobiles with combined bodily injury and property damage limits of at least two million dollars ($2,000,000.00).

      - Pollution Liability.

Coverage for bodily injury, property damage, including clean-up costs and defense costs resulting from sudden, accidental, or gradual pollution conditions, including the discharge, dispersal, release or escape of smoke, vapors, soot, fumes, acids, alkalis, toxic chemicals, hydrocarbons, liquids or gases, waste materials or other irritants, contaminants or pollutants into or upon land, the atmosphere or any water course or body of water will be maintained, with limits not less than five million dollars ($5,000,000.00) per occurrence or claim, except that, if Seller uses a “claims-made” policy, the policy must maintain continuous coverage in effect for at least five years beyond termination of this PPA through continuous renewal of the original policy or by purchasing extended discovery period retroactive insurance dated back to the Effective Date of this PPA. Seller may meet the requirements under this Section 13.4.2(iii) (Pollution Liability) through sudden or accidental pollution coverage as part of the insurance required under Section 13.4.1 (Commercial General Liability Insurance).

      - All Risk Property.

Replacement cost of the Facility. A deductible may be carried, which will be the absolute responsibility of Seller.

      - Umbrella/Excess.

Umbrella/Excess Liability Insurance on an occurrence basis in excess of the underlying insurance identified in this Section 13.4 (Required Insurance), except for workers’ compensation, and which is at least as broad as each and every one of the underlying policies. The umbrella/excess liability policy must be written on a “drop-down-following form” basis. The amounts of insurance required may be satisfied by Seller purchasing coverage for the limits specified or by any combination of underlying and umbrella limits, so long as the total amount of insurance is not less than twenty million dollars ($20,000,000) any one occurrence and annually reinstating general aggregate.

Notice of Change or Cancellation.

The required insurance policies will be endorsed with a provision requiring the insurance company to notify GPC at least 30 Days prior to the effective date of any cancellation, except for a 10 Days’ notice for nonpayment of premium. If notice of cancellation is only commercially available to Seller’s attention, then Seller will forward the 30-Day (or, for non-payment of premium, 10 Days’) advance notice to GPC immediately upon receipt. Furthermore, Seller agrees to notify GPC at least 30 Days before the effective date of any known material change in a required policy.

Payment of Premiums.

Seller must pay all premiums and other charges due on each insurance policy and will keep all coverage in force throughout the Term of this PPA. If Seller fails to pay any premium, GPC may (but will not have any obligation), in GPC’s sole discretion, elect to pay the premiums on Seller’s behalf and withhold any amount paid from any amount due to Seller under this PPA.

No Waiver of Liability.

The provisions requiring Seller to acquire and maintain insurance under this PPA will not be construed as a waiver, restriction, or limitation of any liability imposed on Seller under this PPA, whether the liability is covered by insurance. It is the intent of the Parties, however, that to the extent there is insurance coverage available to cover the legal or contractually assumed liability of Seller, any payments due because of such liability will be made first from the proceeds of such policies.

Risk and Claims

Liability for Facility.

As between the Parties, Seller retains all liability and risk regarding the Facility and the Site. As between GPC and Renewable Resource Seller, Renewable Resource Seller retains all liability and risk regarding the Renewable Resource, if applicable per Exhibit A (Facility Description and Additional Details). GPC: (i) assumes no duty, responsibility, obligation, or liability regarding Facility, Site, or Renewable Resource, if applicable per Exhibit A (Facility Description and Additional Details), condition or operation; (ii) is not liable for injury or damage associated with the Site, the Facility (including its operation, maintenance, repair, or replacement), or Renewable Resource, if applicable per Exhibit A (Facility Description and Additional Details); and (iii) is not responsible for transmission, distribution, or control of electric energy within the Site or at the Facility. The limitations in this Section 14.1 (Liability for Facility) do not apply to the extent injury or damage is caused by GPC’s sole negligence, gross negligence, or intentional misconduct.

No Liability.

Neither Party is responsible for the other Party’s equipment, including its condition or operation. Neither Party is responsible for the distribution or control of electric energy on the other Party’s side of the Point of Interconnection. GPC is not responsible for physical damage to, or destruction or degradation of, Seller’s property, nor will Seller seek recovery from GPC for property damage (including loss of use or electric service outage), except in the case of sole negligence or intentional wrongdoing by GPC or Persons acting on behalf of GPC and for whom GPC is otherwise responsible. Without limiting the generality of the previous sentence, neither Party is liable to the other for damage arising from the simple failure (i.e., failure not caused by breach of contract, negligence, or intentional wrongful act) of a protective device or scheme. The limitations in this Section 14.2 (No Liability) do not apply to the extent injury or damage is caused by the sole negligence, gross negligence, or intentional misconduct of a Party or any Persons acting on behalf of such Party for whom such Party is responsible.

Scope of Indemnity.

To the fullest extent allowed by applicable law, Seller must indemnify, release, hold harmless, and, at GPC’s request, defend GPC and any GPC-Related Party from or against a Claim caused by, arising out of, or related to an act or omission associated with the Facility or this PPA by any Seller Entity, including, for the avoidance of doubt, any Cyber Security Incident. If the Claim arises out of the joint, concurrent, or contributory acts of both Parties, Seller’s liability under this Section 14.3 (Scope of Indemnity) is proportional to the extent the Claim is attributable to a Seller Entity; provided however, if the Claim is for personal or bodily injury (including death) to Seller Entity personnel or for damage to Seller Entity or Facility property, Seller is fully responsible to GPC-Related Parties under this Section 14.3, unless such Claim arose out of the gross negligence or intentional misconduct of a GPC-Related Party, in which case Seller’s liability is limited to its proportionate share as described above. If the Claim results from the sole negligence of a GPC-Related Party, Seller will not be liable under this Section 14.3. Seller’s indemnity obligations are independent of its insurance obligations. The indemnity obligation expressly includes any Claim from any GPC customer or any third party arising from Seller’s operation of the Facility.

Survival.

Despite the expiration or termination of this PPA, Seller’s indemnification obligations under this Part 14 (Risk and Claims) will survive and continue in full force and effect after such expiration or termination, by default or otherwise, regardless of whether such obligations accrue prior to or after PPA expiration or termination.

Force Majeure

Definition of Force Majeure Event.

For purposes of this PPA, a “Force Majeure Event (FME)” is an occurrence, nonoccurrence, or set of circumstances that: (i) first occurs after the Effective Date; (ii) prevents a Party, in whole or in part, from performing any PPA obligation or satisfying any PPA condition; (iii) is beyond the reasonable control of the Party claiming FME; (iv) is not reasonably foreseeable (or, if foreseeable, cannot reasonably be avoided); and (v) is not caused by the Party’s negligence, inaction, lack of due diligence, PPA breach, or failure to follow Prudent Industry Practices.

Force Majeure Exclusions.

FME excludes: (i) the inability to comply with an applicable law for any reason other than the inability to comply with a change in an applicable law for non-economic reasons; (ii) the inability to comply with a change in an applicable law for purely economic reasons; (iii) a Site-specific strike, walkout, lockout, or other labor dispute at the Facility; (iv) ambient temperature or humidity at the Site; (v) failure or inability to obtain or retain sufficient funds for any reason, including funds from a Governmental Authority, or Seller’s loss of or inability to obtain or retain any tax credit or other incentive regarding any portion of the Facility; (vi) any event, including a change in any applicable law or accounting standard, that requires GPC to consolidate Seller or any Seller Affiliate or permitted assign as a VIE in GPC’s financial statements; (vii) any inability to obtain or maintain, or delay in obtaining, any permit, approval, or other Consent required from a Governmental Authority; (viii) equipment failure or damage; (ix) a change in any market condition that affects the cost or availability of equipment, materials, supplies, or services, including the cost of power from resources other than the Facility; (x) any act or inaction of a Party’s contractor, supplier, or vendor; (xi) Seller’s inability to arrange or maintain interconnection service for deliveries to the POI; (xii) the interruption, curtailment, or unavailability of service for the transmission of Discharging Energy from the Facility for any reason; or (xiii) any directive from the Interconnection Provider to curtail deliveries of Discharging Energy from the Facility or disconnect the Facility from the Electric System. Despite the preceding sentence, a Party claiming FME may be excused from PPA performance if: (a) a separate event that otherwise constitutes an FME directly and independently causes a circumstance described in subparts (viii) through (xiii); and (b) the Party satisfies all other requirements of this Part 15 (Force Majeure). For avoidance of doubt, a Change of Law may constitute an FME to the extent it meets the requirements of Section 15.1 (Definition of Force Majeure Event) and this Section 15.2.

  - No Breach or Liability.

If an FME occurs, subject to compliance with all provisions of this Part 15 (Force Majeure), the affected Party will be excused from performance of its obligations impacted by the FME, other than payment obligations that accrued before the declaration of the FME, and will not be construed to be in default regarding the obligations, to the extent that, and only for so long as, the failure to perform is due to an FME. However, the suspension of performance due to an FME will be of no greater scope and of no longer duration than is required by the FME. Despite any other provision in this PPA, no FME will extend this PPA beyond the Term.

Burden of Proof and Supporting Documentation.

The burden of proof as to whether an FME has occurred and as to the impact of an FME will be upon the affected Party. If the affected Party requests that its performance be excused because of an FME, then the affected Party must support its request with documentation demonstrating: (i) the existence of the FME; (ii) efforts by the affected Party to overcome or mitigate the effect of the FME; and (iii) following the conclusion of the FME, an analysis of the number of Days the FME delayed or otherwise prevented the performance of the affected Party’s obligations or satisfaction of any condition of this PPA and, if the FME occurred after COD, information reasonably required to determine the period of time the Facility, in whole or in part, is expected to be or was Unavailable because of FME for purposes of adjusting GPC’s calculation of the Performance Metrics. The affected Party must provide the required documentation by no later than 10 Business Days after the date the FME concludes.

Extension of RCOD.

If an FME directly and substantially impacts a critical path item on the Milestone Schedule and, as a result, prevents Seller from achieving Commercial Operation by the RCOD, then the RCOD will be extended by the number of Days of the delay caused by the impact to the critical path item on the Milestone Schedule, so long as, as a condition to any such extension of the RCOD, Seller must comply with the requirements of this Part 15 (Force Majeure), including Seller undertaking all commercially reasonable efforts to avoid, overcome, or otherwise mitigate the delay by revising, rearranging, expediting, or accelerating the Milestone Schedule.

Monthly Capacity Payments.

In the case of an Unavailability Period caused by an FME declared by Seller in accordance with this Part 15 (Force Majeure), GPC’s obligation to make a Monthly Capacity Payment for any Month will be excused pro rata, based on the number of the Days in the Month and the extent to which Seller is prevented on those Days from satisfying dispatch instructions from GPC because of the FME.

Notice of FME; Updates.

Following the occurrence of an FME, and as a condition to relief under Section 15.6 (Requirements for Relief), the affected Party will give the other Party notice of the FME  as promptly as possible after the affected Party becomes aware of the FME, but in no event later than 10 Business Days after the affected Party knew or should have known of the occurrence of the FME. The notice must describe the particulars of the FME, including an estimate of the anticipated duration and effect of the FME (if reasonably estimable) upon the performance of the Party’s obligations or satisfaction of any conditions under this PPA (including, if Seller is the affected Party, Seller must provide GPC with information reasonably required to determine the reduction of the BESS operational capability), and discussing any actions being taken to avoid or minimize the effect of the FME. The affected Party will have a continuing obligation to deliver to the other Party regular updated reports and any additional documentation and analysis supporting its claim regarding an FME.

Despite the preceding sentences, if the affected Party fails to provide initial notice within the 10 Business Day period or, following the affected Party’s initial notice, the affected Party fails to provide reasonable reports and substantiation of the claimed FME as required by this Part 15 (Force Majeure), the event or condition will be deemed not to be an FME and the affected Party’s performance will not be excused as a result of the FME.

Requirements for Relief.

Following the occurrence of an FME, as a condition to relief under Section 15.3 (No Breach or Liability):

Timely Notice.

The affected Party must comply with the notice requirements of Section 15.5 (Notice of FME; Updates).

Continued Performance of Obligations.

- The affected Party will continue to perform its obligations under this PPA to the extent not affected by the FME.

Reasonable Efforts to Mitigate.

- The affected Party will remedy its inability to perform as soon as reasonably practicable, but this Section 15.6 (Requirements for Relief) will not require the settlement of any non-Site-specific strike, walkout, lockout, or other general labor dispute on terms which, in the sole judgment of the affected Party, are contrary to its interest.

Resume Performance.

When the affected Party can resume performance of its obligations under this PPA, the affected Party will promptly provide notice to the other Party, promptly resume such performance, and provide the other Party with a written certification from an independent, registered engineer that the FME has been cured.

Extended FME.

Notice and Remedy Plan for Extended FME.

If the affected Party has reason to believe that a suspension of performance due to an FME will continue for a period of six Months or longer following the initial suspension of performance resulting from the Force Majeure Event (an “Extended FME”), the affected Party must notify the other Party promptly and will submit an “FME Remedy Plan” to the other Party no later than 30 Days after the affected Party’s initial notice to the other Party. In addition, if the other Party has reason to believe that an FME will be an Extended FME, the other Party may request that the affected Party submit an FME Remedy Plan to the other Party, which the affected Party will submit to the requesting Party no later than 30 Days after the other Party’s request. The FME Remedy Plan must set forth a plan and schedule for remedial measures (including a description of necessary repairs, improvements, changes to operations, or other actions) to cure the effects of the FME and to enable the affected Party to perform its obligations and resume full performance of the suspended obligations under this PPA as soon as reasonably practicable. The affected Party must diligently pursue the performance of the FME Remedy Plan to completion.

Monthly Status Reports and Updates to FME Remedy Plan.

While an FME Remedy Plan is in effect, the affected Party must provide the other Party with Monthly status reports regarding the implementation of the FME Remedy Plan, any other measures to remedy the FME, any changes to the FME Remedy Plan, and the expected remaining duration of the Party’s inability to perform its obligations, and any additional relevant information as may be reasonably requested by the other Party. The affected Party must modify the FME Remedy Plan if and as needed to achieve the objective of resuming full performance of the suspended obligations under this PPA as soon as reasonably practicable.

Early Termination Resulting from an Extended FME.

The Party not prevented from performing its obligations due to the FME may at any time terminate this PPA effective upon 10 Days prior notice to the affected Party if: (i) the affected Party does not or cannot provide an FME Remedy Plan as required by this Section 15.7 (Extended FME); (ii) the affected Party does not or cannot carry out the FME Remedy Plan in a method reasonably designed to achieve the objective of resuming full performance of the suspended obligations under this PPA as soon as reasonably practicable; or (iii) the affected Party remains unable to perform the suspended PPA obligations for 12 Months following the date of initial suspension of performance resulting from the FME. For purposes of subsection (iii) of this Section 15.7.3, the 12-Month period need not be continuous only if each period of suspension of performance comprising the 12-Month period is the result of a common cause such that, if the cause had been cured following the first suspension of performance, the additional suspensions of performance would not have occurred.

Liability following Termination.

Upon any termination of this PPA as provided in Section 15.7.3 (Early Termination Resulting from an Extended FME), the Parties will have no further liability or obligation to each other except for any obligation arising prior to the date of the termination or as provided in Section 1.2 (Survival).

Default and Remedies

Default by Seller.

The occurrence of any of the following events will constitute a Seller Event of Default:

Incorrect Representation or Warranty.

Any Seller representation or warranty in this PPA or in any certificate or other document delivered to GPC in accordance with this PPA proves to be incorrect in any material respect when made, unless Seller promptly commences and diligently pursues action to cause the representation or warranty to become true in all material respects and does so within 30 Days after GPC provides Seller notice of the incorrect representation or warranty (unless the cure is not capable of being accomplished within the 30 Days, in which case Seller will have an additional 30 Days to perform the cure) and the cure removes any material adverse effect on GPC of the incorrect representation or warranty. However, no Event of Default by Seller will occur under this Section 16.1.1 regarding: (i) any certificate provided under Section 2.1.8 (VIE Certification) if Seller cooperates with GPC during the cure period and Seller takes commercially reasonable actions (without causing a material adverse effect on GPC) necessary to bring about a determination by GPC and its independent auditor that Seller does not constitute a VIE for which GPC is the Primary Beneficiary as a result of this PPA; or (ii) Section 2.1.14 (Environmental Compliance Certification) if GPC determines in its sole discretion, that the incorrect representation, warranty, or covenant is not material, Seller cooperates with GPC during the cure period, and Seller takes commercially reasonable actions (without causing a material adverse effect on GPC) necessary to correct the immaterial representation, warranty, or covenant to GPC’s satisfaction.

Involuntary Bankruptcy, Insolvency, or Reorganization.

A court having jurisdiction enters: (i) a decree or order for relief in respect of Seller in an involuntary case or proceeding under any applicable Federal or state bankruptcy, insolvency, reorganization, or other similar law; or (ii) a decree or order, the entry of which was sought by an entity other than Seller, adjudicating Seller bankrupt or insolvent, or approving as properly filed a petition seeking reorganization, arrangement, adjustment, or composition of or in respect of Seller under any applicable Federal or state law, or appointing a custodian, receiver, liquidator, assignee, trustee, sequestrator, or other similar official of Seller or of any substantial part of its affairs and the proceeding is not stayed or dismissed within 60 Days.

Voluntary Bankruptcy, Insolvency or Reorganization.

Seller: (i) commences a voluntary case or proceeding under any applicable federal or state bankruptcy, insolvency, reorganization, or other similar law or any other case or proceeding to be adjudicated bankrupt or insolvent; (ii) consents to the entry of a decree or order for relief in respect of Seller in any involuntary case or proceeding under any applicable federal or state bankruptcy, insolvency, reorganization, or other similar law or to the commencement of any bankruptcy or insolvency case or proceeding against Seller; (iii) files any petition, answer, or consent seeking reorganization or similar relief under any applicable federal or state law, which, if granted would have the effect of relieving Seller of any of its obligations; (iv) consents to the filing of any petition or to the appointment of or taking possession by a custodian, receiver, liquidator, assignee, trustee, sequestrator, or similar official of Seller or of any substantial part of its property; (v) makes an assignment for the benefit of creditors; (vi) admits in writing its inability to generally pay its debts as they become due; or (vii) takes any action in furtherance of any of the preceding.

Failure to Comply with Performance Security Requirements.

(i) Seller fails to comply or cause compliance with Performance Security requirements of Section 6.1 (Performance Security); or (ii) Seller Guarantor breaches any of its obligations under the Seller Guaranty or if any representation or warranty Seller Guarantor made in the Seller Guaranty is incorrect in any material respect when made, unless Seller cures any of the preceding by the end of the fifth Business Day following Seller’s receipt of GPC’s notice of a failure under this Section 16.1.4.

Failure to Comply with Other Material PPA Terms.

Seller fails to perform or observe any material PPA obligation of Seller, other than those obligations specifically addressed in this Section 16.1 (Default By Seller), which failure continues for a period of 30 Days after notice of the failure from GPC, unless the cure is not capable of being effected within a 30-Day period, in which case Seller will have an additional 60-Day period in which to perform the cure, so long as the cure is diligently pursued.

Failure To Comply with PPA Assignment Requirements.

Seller violates the requirements of Part 18 (Assignment, Transfers, and Changes of Control) through an unpermitted assignment or transfer of this PPA or an ownership interest in the Facility or through a Change of Control Transaction.

Failure to Pay Amounts Due to GPC.

Seller fails, by the due date, to pay GPC any undisputed amount payable by Seller to GPC in accordance with this PPA and fails to cure the failure to pay within 15 Days after receipt of written demand from GPC.

Storage Performance Metric Achieved Below .60

. The Storage Performance Metric Achieved, as calculated by GPC in accordance with Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements), is below .6 for any three consecutive Months period or six Months in any 12 Month period, with either event being a separate cause for a Seller Event of Default, and Seller fails to cure the applicable default as described in this Section 16.1.8.

      - Seller must: (a) by no later than 10 Days after the applicable default first occurs, submit to GPC a written cure plan identifying the cause of the deficiency and the plan to be implemented by Seller to cure the deficient Storage Performance Metric Achieved; and (b) cure the default within the Cure Period after the applicable default first occurs. The Cure Period is subject to Seller diligently seeking to cure the applicable default beginning with the instance that the Storage Performance Metric Achieved was below .6 (for clarity, even if the applicable default has not yet occurred).

      - If Seller establishes a cure plan as described in 16.1.8(i) but requires a Cure Period of more than 180 Days, GPC will agree to extend the Cure Period up to an additional 180 Days for a total Cure Period not to exceed 360 Days so long as Seller: (a) provides a written certification to GPC before the expiration of the initial Cure Period demonstrating that Seller requires additional time to cure the default despite Seller’s diligent efforts; (b) provides reasonable substantiation supporting Seller’s certification, including any documentation explaining the cause of the deficiency and the plan to cure the default, including manufacturer reports, failure analyses, other relevant third-party documentation, and other documentation reasonably requested by GPC, in each case subject to Seller’s confidentiality obligations; (c) the default is capable of cure within the extended Cure Period; and (d) Seller has exercised diligent efforts to cure the default throughout the Cure Period and continues to exercise diligent efforts to cure the default throughout the extended Cure Period.

      - For the default to be cured, Seller must provide a written certification to GPC before the expiration of the applicable Cure Period that all causes of the default have been sufficiently cured such that the Facility is capable of achieving a Storage Performance Metric Achieved of 0.6 or greater (“Cure Certification”) along with reasonable documentation substantiating Seller’s certification that the default was cured. Seller must provide to GPC any documentation reasonably requested by GPC concerning such certification. If the Facility achieves a Storage Performance Metric Achieved of 0.6 or greater in each of the three consecutive Months immediately following Seller’s written certification that it has cured all causes of the default, then the default will be deemed to have been cured during the Cure Period, and any Month before Seller’s written certification for which the Storage Performance Metric was below 0.6 will no longer be considered for purposes of this Section 16.1.8 (Storage Performance Metric Achieved Below .6). If, after Seller delivers a Cure Certification but before the expiration of applicable Cure Period, the Facility fails to achieve a Storage Performance Metric Achieved of at least 0.6, then Seller will have until the end of the Cure Period, which may be extended as appropriate, subject to the original limitations in Section 16.1.8(ii), to fully cure the underlying causes of the default and provide another Cure Certification.

Tested Storage Capacity Below 70% Contracted Capacity; Cure; Remedies.

      - Despite any other PPA provision, the Tested Storage Capacity, determined in accordance with a Performance Test at any time after the Delivery Commencement Date, is below 70% of the  Contracted Capacity and Seller fails to: (i) submit to GPC, within 10 Days after determination by the Performance Test of the inadequate Tested Storage Capacity, a written cure plan reasonably acceptable to GPC for the inadequate Tested Storage Capacity; and (ii) cure the inadequate Tested Capacity within the Cure Period, except that the Cure Period may be extended in accordance with Section 16.1.9(i) (Cure Period Extension). GPC will have the right to declare an Event of Default if Seller fails to: (a) establish the cure plan within the required 10-Day period or, if applicable, establish the revised cure plan within the required 15-Day period under Section 16.1.9(i), or (b) diligently implement the cure plan (including implementation of such actions as GPC may reasonably request), or (c) cure the inadequate Tested Storage Capacity within the Cure Period (as the Cure Period may be extended under Section 16.1.9(i)) as set forth in Section 16.1.9(ii) (Requirements to Cure Inadequate Tested Storage Capacity).

      - Cure Period Extension. If Seller establishes a cure plan in accordance with this Section 16.1.9 (Tested Storage Capacity Below 70% Contracted Capacity; Cure; Remedies) but requires a Cure Period of more than 180 Days to cure the inadequate Tested Storage Capacity, then the Cure Period will be extended for a reasonable additional period of time, which extension will not in any case exceed 180 Days, so long as, by no later than 15 Days before the expiration of the 180-Day Cure Period, Seller provides to GPC: (a) a revised cure plan setting forth a reasonable extension of the Cure Period, such extension not to exceed 180 Days, which revised cure plan and extension must be reasonably acceptable to GPC, and (b) a written certification reasonably acceptable to GPC confirming that in order for Seller to cure the inadequate Tested Storage Capacity Seller must be afforded the requested additional period of time. The total duration of the Cure Period, as extended, must not exceed 360 Days.

      - Requirements to Cure Inadequate Tested Storage Capacity. An inadequate Tested Storage Capacity below 70% of the Contracted Capacity will be cured under this Section 16.1.9 only if: (i) Seller provides GPC with a written certification reasonably acceptable to GPC confirming that the inadequate Tested Storage Capacity has been cured; and (ii) the inadequate Tested Storage Capacity is increased to a value equal to or greater than 70% of the Contracted Capacity.

      - GPC Election.

- Despite the foregoing provisions of this Section 16.1.9, whenever a Performance Test demonstrates a Tested Storage Capacity below 70% of the Contracted Capacity and Seller fails to cure the inadequate Tested Storage Capacity as required by Section 16.1.9(ii) (Requirements to Cure Inadequate Tested Storage Capacity), GPC will have the unilateral right to elect to require and receive buydown liquidated damages as specified in Section 1.3.4 (Failure to Cure Inadequate Tested Storage Capacity Above 70% Contracted Capacity; Buydown Liquidated Damages) of Exhibit B (Capacity; Capacity Payments and Payment Reductions; Buydown) in lieu of terminating the PPA. To elect this remedy, GPC must notify Seller in writing of this election and must waive its right to declare a Seller Event of Default under this Section 16.1.9 with respect to the specific event of inadequate Tested Storage Capacity. GPC’s waiver is limited to the specific event of inadequate Tested Storage Capacity and does not waive any additional event.

Failure to Meet AGC Performance Requirements.

The Facility fails to achieve the AGC Status Performance Requirement or the AGC Setpoint Response Performance Requirement such that a Triggering Failure occurs, and Seller fails to comply with the applicable cure requirements in Section 10.9 (AGC Performance Requirements).

Breach of Energy Delivery Obligation.

Seller breaches its obligation to deliver energy in accordance with GPC’s AGC Setpoint signals or instructions from the Dispatch Center, as applicable to the extent that the Facility is Available, and the breach continues for more than two Hours after GPC provides written (by email) and verbal (by telephone call) notice of the breach to the Seller Representative designated in the Operating Procedures as the Person to whom GPC will provide notice of operational issues.

Abandonment or Failure to Achieve RCOD.

(i) Abandonment; or (ii) Seller (a) fails to achieve Commercial Operation by no later than nine Months after the RCOD;  (b) notifies GPC that Seller has reasonably determined that Seller will not achieve Commercial Operation or that Commercial Operation will not be achieved by no later than nine Months after the RCOD; or (c) terminates this PPA in accordance with Section 7.3.3 (Seller Payment of Delay Liquidated Damages; Pre-COD Termination Damages).

Ongoing Default under the Renewable Resource PPA. Failure by Renewable Resource Seller to cure an event of default (as defined in the Renewable Resource PPA) under the Renewable Resource PPA, if the Facility is paired with a Renewable Resource, as may be indicated by Exhibit A (Facility Description and Additional Details).

Adjusting Meter or Interconnection Facilities without GPC’s Consent.

Seller or any Seller Representative willfully adjusts the Metering System or the Interconnection Facilities without GPC’s written consent and which adjustment has the effect of falsely increasing any amount owed by GPC under this PPA.

Breach of Covenant.

Any failure of any covenant made by Seller in Section 2.1 (Seller Representations, Warranties, and Covenants), unless Seller promptly commences and diligently pursues action and cures the failure by no later than 30 Days after notice of the failure has been given to Seller by GPC (unless the cure is not capable of being effected within the 30-Day period in which case Seller must submit a cure plan before the end of the 30-Day period outlining steps to assure GPC that the failure will be cured, which cure plan will be subject to GPC’s approval, the approval not to be unreasonably withheld by GPC, but in no event will the total cure period exceed 180 Days) and the cure removes any adverse effect on GPC of the failure of such covenant. However, no Event of Default by Seller will occur in accordance with this Section 16.1.15  unless GPC cooperates with Seller during the cure period and, if applicable, takes commercially reasonable actions (without causing a material adverse effect on GPC) necessary to bring about a determination by GPC and its independent auditor that Seller does not constitute a VIE as because of this PPA.

Applicable Law Violation.

Seller violates any applicable law and the violation would have a material adverse effect on Seller’s ability to perform under this PPA and such violation is not cured within 30 Days after notice from GPC unless the cure is not capable of being effected within the 30-Day period, in which case Seller will have an additional 60-Day period in which to commence the cure so long as Seller diligently pursues the cure and completes the cure within 90 Days and the cure removes any material adverse effect on Seller’s ability to perform under this PPA. Seller will be deemed not to have committed an Event of Default under this Section 16.1.6 (Applicable Law Violation) if Seller has validly contested the alleged violation, the matter remains pending before the applicable Governmental Authorities, and any cease and desist order or other enforcement action due to an alleged violation of the applicable laws has been stayed.

IA Termination. (i) Failure of the Renewable Resource Seller to cure an event of default under the interconnection agreement for the Renewable Resource, to the extent the Facility is paired with a Renewable Resource, as may be indicated by Exhibit A (Facility Description and Additional Details); or (ii) termination of the IA due to a Seller event of default under the IA.

Default by GPC.

The occurrence of any of the following events will constitute a GPC Event of Default:

GPC Payment Default.

GPC fails, by the due date, to pay Seller any undisputed amount payable by GPC to Seller in accordance with this PPA and fails to cure the failure to pay within 15 Days after receipt of written demand from Seller.

Failure to Comply with Other Material PPA Terms.

GPC fails to perform or observe any material obligation of GPC under this PPA, other than those obligations included in this Section 16.2 (Default by GPC), which failure materially and adversely affects the ability of Seller or GPC to perform their respective obligations under this PPA and continues for a period of 30 Days after notice of the failure from Seller (unless the cure is not capable of being effected within the 30-Day period, in which case GPC will have an additional 30-Day period in which to perform the cure).

Incorrect Representation or Warranty.

Any representation or warranty made by GPC in this PPA or in any certificate or other document delivered to Seller in accordance with this PPA proves to be incorrect in any material respect when made, unless GPC promptly commences and diligently pursues action to cause the representation or warranty to become true in all material respects and does so within 30 Days after Seller has given GPC notice (unless the cure is not capable of being effected within such 30-Day period, in which case GPC will have an additional 30-Day period in which to perform the cure) and the cure removes any material adverse effect on Seller because of the representation or warranty having been incorrect.

Involuntary Bankruptcy, Insolvency, or Reorganization.

A court having jurisdiction enters: (i) a decree or order for relief in respect of GPC in an involuntary case or proceeding under any applicable Federal or state bankruptcy, insolvency, reorganization or other similar law; or (ii) a decree or order adjudicating GPC bankrupt or insolvent, or approving as properly filed a petition seeking reorganization, arrangement, adjustment or composition of or regarding GPC under any applicable Federal or state law, or appointing a custodian, receiver, liquidator, assignee, trustee, sequestrator, or other similar official of GPC or of any substantial part of its affairs.

Voluntary Bankruptcy, Insolvency, or Reorganization.

GPC: (i) commences a voluntary case or proceeding under any applicable Federal or state bankruptcy, insolvency, reorganization, or other similar law or any other case or proceeding to be adjudicated bankrupt or insolvent; (ii) consents to the entry of a decree or order for relief in respect of GPC in any involuntary case or proceeding under any applicable Federal or state bankruptcy, insolvency, reorganization, or other similar law, or to the commencement of any bankruptcy or insolvency case or proceeding against it; (iii) files any petition, answer, or consent seeking reorganization or similar relief under any applicable Federal or state law, which, if granted would have the effect of relieving GPC of any of its obligations; (iv) consents to the filing of any petition or to the appointment of or taking possession by a custodian, receiver, liquidator, assignee, trustee, sequestrator, or similar official of GPC or of any substantial part of its property; (v) makes an assignment for the benefit of creditors; (vi) admits in writing its inability to generally pay its debts as they become due; or (vii) takes any action in furtherance of any of the foregoing.

Failure to Comply with PPA Assignment Requirements.

GPC violates the requirements of Part 18 (Assignment, Transfers, and Changes of Control) through an unpermitted assignment or transfer of this PPA.

Material Violation of Applicable Law.

GPC violates an applicable law and the violation would have a material adverse effect on GPC’s ability to perform under this PPA and the violation is not cured within 30 Days after GPC receives Seller’s notice. If the cure is not capable of being effected within the 30-Day period, GPC will have an additional 30-Day period in which to commence the cure and after commencing the cure GPC will diligently pursue the cure and complete the cure within 60 Days. The cure must remove the material adverse effect(s) on GPC’s ability to perform under this PPA. GPC will be deemed not to have committed an Event of Default under this PPA if GPC has validly contested the alleged violation, the matter remains pending before the applicable Governmental Authorities, and the cease and desist order or other enforcement action due to an alleged violation of the applicable laws has been stayed.

Remedies.

Remedies for Event of Default.

If an Event of Default occurs at any time during the Term, the Party not in default under this PPA (“Non-Defaulting Party”) may, for so long as the Event of Default is continuing, subject to Part 19 (Dispute Resolution), take one or more of the following actions: (i) establish a date, no later than 10 Business Days after the Non-Defaulting Party delivers to the Party in default under this PPA (“Defaulting Party”) notice of the date, on which this PPA will terminate (“Early Termination Date”); (ii) proceed by appropriate proceedings in accordance with this PPA at law, in equity, or otherwise, to protect and enforce: (a) Non-Defaulting Party’s right to recover actual or liquidated damages; or (b) where the Event of Default is one other than the failure to pay money, equitable relief, including specific performance; and (iii) immediately stop performance or withhold any payments, or both, due under this PPA.

Termination Payment.

If an Early Termination Date has been established and Non-Defaulting Party has not successfully pursued an action for specific performance, Non-Defaulting Party will in good faith calculate its Gains, Losses, or Costs resulting from the PPA termination, aggregate into a single net amount Gains, Losses, or Costs, and then notify Defaulting Party. If Non-Defaulting Party’s aggregate Losses and Costs exceed Non-Defaulting Party’s aggregate Gains, Defaulting Party will, unless Defaulting Party disagrees with the calculation, within 15 Business Days after receipt of such notice, pay to Non-Defaulting Party the net amount (“Termination Payment”). The Termination Payment will bear interest at the Interest Rate from the Early Termination Date until paid to Non-Defaulting Party. If Non-Defaulting Party’s aggregate Gains exceed aggregate Losses and Costs, if any, resulting from the PPA termination, Non-Defaulting Party may retain the Gains. If Defaulting Party disagrees with the calculation of the Termination Payment, the issue will be resolved in accordance with Part 19 (Dispute Resolution) provisions applicable to Termination Payment disputes, and the resulting Termination Payment will be due by no later than three Business Days after the award. Despite any provision in this PPA, for any GPC PPA termination for a Seller Event of Default that occurs before the Facility achieves Commercial Operation, rather than the application of a calculation of Gains, Losses, or Costs resulting from the PPA termination, the Termination Payment will be liquidated damages in an amount equal to the full amount of the then-required Performance Security amount shown in Part 1 (Performance Security) of Exhibit A-2 (Performance Security and Liquidated Damages). In each case, Seller must also pay to GPC all other damages owed to GPC under this PPA, including any applicable amount specified in Section 7.3 (Failure to Achieve Commercial Operation by RCOD).

Determining Gains, Losses, and Costs.

Gains, Losses, or Costs will be determined by comparing the cost of the capacity that would be available for the remainder of the Term had this PPA not been terminated to the market price of capacity of equivalent reliability and dispatch flexibility for the remaining Term (had this PPA not been terminated). Nothing in Part 6 (Performance Security) is intended to limit liability under this Section 16.3 (Remedies). To ascertain the market price, Non-Defaulting Party may consider, among other evidence, the settlement prices of NYMEX energy futures contracts, quotations from leading dealers in energy and gas swap contracts, offers for replacement capacity and energy, or bids to purchase the remaining capacity that was to be sold in accordance with this PPA, in either case made by bona fide third-parties (including offers Non-Defaulting Party received in response to any request for proposals for capacity contracts), all adjusted for the length of the remaining Term (as of the PPA termination date) and differences in locational basis (including costs of transmission investments and transmission service), reliability, dispatch flexibility, and any other considerations affecting value. Neither Party will be required to enter into replacement transactions to determine the Termination Payment. As used in this Section 16.3 (Remedies): (i) “Costs” means: Brokerage fees, commissions, and other similar transaction costs and expenses reasonably incurred by a Party either in terminating any agreement it has entered into to fulfill its obligations under this PPA or entering into new agreements which replace this PPA, and attorneys’ fees, if any, incurred enforcing its rights under this PPA; (ii) “Gains” means: An amount equal to the economic benefit determined on a mark to market basis (exclusive of Costs), if any, to the Non-Defaulting Party resulting from the termination of this PPA; and (iii) “Losses” means: An amount equal to the economic loss determined on a mark to market basis (exclusive of Costs), if any, to the Non-Defaulting Party resulting from the termination of this PPA.

Rights of Specific Performance.

For an Event of Default, the Parties recognize that a remedy at law may be inadequate because this PPA is unique or because the actual damages of the Non-Defaulting Party may exceed any guaranty or other collateral available to the Non-Defaulting Party. The Parties agree that in an Event of Default for which this PPA has not prescribed a specific remedy, Non-Defaulting Party will be entitled to pursue an action for specific performance, and Defaulting Party waives Defaulting Party’s rights to assert as a defense to a specific performance action that the Non-Defaulting Party’s remedy at law is adequate. The Non-Defaulting Party will not be entitled to receive both specific performance and a Termination Payment from the Defaulting Party.

Limitation of Remedies, Liability, and Damages.

Each Party confirms that the express remedies and measures of damages provided in this PPA satisfy the essential purpose of this PPA for breach of any provision for which an express remedy or measure of damages is provided, in which event the express remedy or measure of damages will be the exclusive remedy, subject to Section 19.6 (Injunctive Relief) regarding injunctive relief. Except to the extent expressly provided in Section 7.3 (Failure to Achieve Commercial Operation by RCOD), where an express remedy or measure of damage is provided, the Party’s liability will be limited as set forth in the provision and all other remedies or damages at law or in equity are waived. However, if no remedy or measure of damages is expressly provided in this PPA, and subject to Section 19.6, a Party’s liability will be limited to direct, actual damages only. The direct, actual damages will be the exclusive remedy and all other remedies or damages at law or in equity are waived. The Parties explicitly agree and intend that Section 7.3.1 (Delay Liquidated Damages), Section 16.3.2 (Termination Payment), Exhibit B (Capacity; Capacity Payments and Payment Reductions; Buydown), and Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements) will be fully enforceable by any court exercising jurisdiction over any dispute between the Parties arising under this PPA. Each Party irrevocably waives any defense available to it under applicable law or equity relating to the enforceability of the liquidated damages provisions set forth in Section 7.3.1, Exhibit B, and Exhibit C.

Waiver of Consequential Damages.

Unless expressly provided in this PPA, neither Party nor its Affiliates will be liable for: (i) consequential, incidental, special, punitive, exemplary, treble, or indirect damages (including lost profits; loss of use, income tax benefit, data, business opportunity or anticipated savings; idled equipment costs; or increased overhead, financing, or operating costs); or (ii) other business interruption damages arising out of this PPA, any damage or delay in connection with this PPA, a Party’s act or failure to act, or a Party’s performance or non-performance under this PPA, whether or not reasonable, foreseeable, contemplated, or avoidable and whether by statute, in tort or contract, under any indemnity provision, or otherwise. The preceding sentence will not apply: (a) for amounts owed to a third party for which this PPA requires indemnification; (b) to limit the liability of Seller for liquidated damages specified in this PPA; (c) to limit the liability of a Person whose actions giving rise to the liability constitute gross negligence or willful misconduct; or (d) to limit or reduce the amounts owed by a defaulting Party under Section 16.3 (Remedies), it being expressly agreed that no portion of any amount owed under Section 16.3 will be considered consequential damages and  it being expressly agreed that the lost value of any investment tax credit (ITC), production tax credit (PTC), or any other similar Tax credit or benefit will be considered consequential damages. To the extent any damages required to be paid under this PPA are liquidated, the Parties acknowledge that: (I) the actual damages likely to be incurred are difficult or impossible to determine; (II) otherwise obtaining an adequate remedy is inconvenient; and (III) the liquidated damages do not constitute a penalty and are a reasonable approximation of the actual harm or loss. Despite any other provision in this PPA, in no event will GPC’s liability to Seller for a termination payment under this PPA exceed an amount equal to the sum of any amounts then owed by GPC under this PPA plus the total of all remaining monthly capacity payments following termination that would have been payable to Seller under this PPA had the PPA remained in effect through the end of the Term. The limitations in Section 16.5 (Limitation of Remedies, Liability, and Damages) and this Section 16.6 apply regardless of fault and will survive PPA termination, cancellation, suspension, completion, or expiration.

Disclaimer of Warranties.

There are no warranties under this PPA except to the extent specifically set forth in this PPA. The Parties specifically disclaim and exclude all implied warranties, including the implied warranties of merchantability and of fitness for a particular purpose.

No Interruption.

Except as otherwise provided in this PPA, unless this PPA has been terminated, neither Party will, because of any breach or alleged breach by the other Party: (i) refuse to deliver, or suspend or delay any delivery of, capacity or associated energy to be provided under this PPA; (ii) refuse to take energy to the extent required under this PPA; or (iii) suspend, delay, or refuse to make any of the payments required under this PPA.

Duty to Mitigate.

Despite any other provision of this PPA, each Party must: (i) mitigate damages; and (ii) use commercially reasonable efforts to minimize any damages it may incur because of the other Party’s performance or non-performance.

Compliance with Laws

Change of Law.

If a Change of Law occurs, Seller may request to recover Excess Expenditures as described in this Section 17.1 (Change of Law). Except as described in this Section 17.1 (Change of Law), Seller is not entitled to any PPA modification due to any Change of Law. For the avoidance of doubt, no Change of Law relieves Seller of its obligations to comply with this PPA and applicable law, and Seller’s sole relief, if any, is limited to the remedies expressly set forth in this Section 17.1.

Notice and Periodic Updates. If Seller expects, or should reasonably expect, to incur any Change of Law Expenditures (including amounts less than the Threshold Amount), Seller must notify GPC through a Change of Law Notice by no later than 45 Days after the enactment of the applicable Change of Law. The Change of Law Notice must include: (i) a description of Change of Law; (ii) Seller’s preliminary plan to comply with the Change of Law (including any additional or different Facility equipment or other modification of the Facility required to comply with the Change of Law); (iii) identification of the categories of costs or losses Seller will incur because of the Change of Law; and (iv) a good faith preliminary estimate of Change of Law Expenditures with supporting documentation. Seller must provide GPC with periodic updates regarding Seller’s compliance plan and Change of Law Expenditures and any other information GPC reasonably requests.

Threshold Amount; Excess Expenditures Notice. The Threshold Amount applies to each Change of Law and will not be aggregated if one of more Changes of Law occur during the Term. Seller is not entitled to any PPA modification unless Seller will incur Excess Expenditures for the applicable Change of Law, which must be substantiated in accordance with this Section 17.1 (Change of Law). If a Change of Law will cause Seller to incur Excess Expenditures, and Seller provided a Change of Law Notice in accordance with Section 17.1.1 (Notice and Periodic Updates), Seller may request recovery of Excess Expenditures by delivering an Excess Expenditures Notice to GPC by no later than 90 Days after the enactment of the Change of Law. If Seller reasonably determines that additional time is required to prepare an Excess Expenditures Notice, Seller may request an extension by notice to GPC delivered before expiration of the deadline. The extension request must describe in reasonable detail the basis for the request and the additional time reasonably needed. If GPC approves the request, the deadline will be extended for the period approved by GPC. Seller may also propose Operational Alternatives in its Excess Expenditures Notice. The Excess Expenditures Notice must include all information and documentation necessary for GPC to validate Change of Law Expenditures or Operational Alternatives, including: (i) evidence that the Change of Law applies to the Facility and will cause Seller to incur Change of Law Expenditures that Seller would not have incurred but for the Change of Law; (ii) Seller’s final plan to comply with the Change of Law (including any additional or different Facility equipment or other modification of the Facility required to comply with the Change of Law); (ii) identification of the categories of costs or losses Seller will incur because of the Change of Law; (iv) a reasonable and good faith estimate of Change of Law Expenditures with detail and supporting documentation; and (v) Seller’s proposed adjustment to the Annual Capacity Price, with supporting calculations. Seller’s Excess Expenditures Notice must also include the following information, as applicable:

Any Initial Capital Expenditures Notice must include: (A) a detailed description of the addition, modification, or other capital work required to comply with the Change of Law, including the scope of work and the key technical and operational assumptions; (B) an itemized list of the capital expenditures and the expected in-service date(s), including supporting documentation (e.g., vendor quotes, invoices, purchase orders, construction contracts, and change orders); (C) identification and substantiation of Seller’s baseline assumptions and costs before the Change of Law and a calculation of the incremental capital expenditures attributable to the Change of Law; and (D) a schedule for engineering, procurement, and construction (including any material milestones) and identification of any material project risks that could affect cost or timing.

Any Initial Tariff Notice must: (A) identify the applicable Tariff; (B) provide evidence that the Tariff applies to the Facility; (C) identify the incremental cost to Seller, including identification and substantiation of Seller’s baseline cost before the Change of Law; and (D) include applicable vendor and governmental authority documentation.

For any Excess Expenditures resulting from changes in applicable Taxes, the Excess Expenditures Notice must: (A) identify the applicable Tax; (B) evidence that the change in Taxes apply directly to the Facility; (C) identify the incremental increase in Taxes, including identification and substantiation of Seller’s baseline Taxes assumptions before the Change of Law; and (D) include a written certification from an independent accounting firm certifying that the claimed loss is accurate.

For any Excess Expenditures comprised of additional Facility operating costs, the Excess Expenditures Notice must: (A) include a detailed explanation of the Change of Law’s impact on Facility operations and operating assumptions; (B) identify the incremental operating costs Seller will incur; (D) include any applicable contracts, invoices, and other documentation; and (E) include supporting calculations.

The Excess Expenditures Notice must demonstrate that: (a) Seller’s proposed plan for complying with the Change of Law is reasonable and conforms with Prudent Industry Practices; and (b) all Excess Expenditures are reasonable, consistent with Prudent Industry Practices, required for compliance with the Change of Law, and otherwise comply with this Section 17.1 (Change of Law). In response to any Excess Expenditures Notice, GPC may request, and Seller must provide, any additional information or documentation reasonably necessary for GPC to evaluate and validate Excess Expenditures. If Seller fails to timely deliver any required notice, supporting information, certification, or other substantiation required under this Section 17.1, Seller will be deemed to have waived and released any claim to recover the applicable Excess Expenditures and any related right or entitlement arising from the applicable Change of Law. GPC will have no obligation to consider, approve, or pay any untimely or unsupported claim.

GPC Review; ACP Adjustment. After receiving a timely and fully substantiated Excess Expenditures Notice, GPC will review the notice and evaluate Seller’s proposed ACP Adjustment. If Seller is entitled to recover Excess Expenditures, the Annual Capacity Price will be increased by a fixed amount ($/kW-year) to recover the approved Excess Expenditures (“ACP Adjustment”). The ACP Adjustment will begin in the Annual Period in which Seller first incurs Excess Expenditures and will be prorated for the remainder of the Term, subject to any applicable not-to-exceed amount and reconciliation. If the Parties are unable to agree on the ACP Adjustment (including the methodology or inputs) by a date that allows GPC to timely deliver the Election Notice in accordance with Section 17.1.5 (GPC Election; Objection Period), then GPC may, for purposes of meeting the GPC Election Deadline, deliver an Election Notice that (a) accepts Seller’s request subject to the Parties’ subsequent agreement on the ACP Adjustment, or (b) rejects Seller’s request, in each case without waiver of either Party’s rights under this Part 17 (Compliance with Laws). Subject to Section 17.1.5, the ACP Adjustment will be calculated as follows:

For Excess Expenditures comprised of capital expenditures, the ACP Adjustment will be based on substantiated capital expenditures required to comply with the Change of Law. Substantiated Excess Expenditures will be converted into a per-kW amount by dividing the amount by the Contracted Capacity (kW) and then annualized over the remaining Term using a fixed charge rate consistent with generally accepted project finance methodologies and otherwise reasonably acceptable to GPC. GPC will include in its Election Notice a fixed not-to-exceed ACP Adjustment, which will be final and may not be rescinded except to the extent (a) Seller fails to fully substantiate its Initial Capital Expenditures Notice as described in Section 17.1.3(iii) (GPC Review; ACP Adjustment); or (b) Commission approval is withheld or denied, if required by Section 17.1.7 (Exclusive Relief; Commission Approval). The not-to-exceed ACP Adjustment will represent the maximum and exclusive amount recoverable by Seller with respect to the Change of Law described in Seller’s Initial Capital Expenditures Notice, and Seller will not be entitled to recover any additional amount regardless of Seller’s actual incurred costs. By no later than 30 Days after the capital project described in the Initial Capital Expenditures Notice is complete, Seller must deliver to GPC a Final Capital Expenditures Notice substantiating the actual Excess Expenditures incurred by Seller. By no later than 60 Days after receipt of the Final Capital Expenditures Notice, GPC will deliver a final notice to Seller either: (a) confirming the not-to-exceed ACP Adjustment; or (b) proposing a reduced ACP Adjustment if GPC reasonably determines, based on its review of Seller’s Final Capital Expenditures Notice, that a lower adjustment is appropriate. If GPC provides notice that a reduced adjustment is appropriate, GPC and Seller will confer in good faith to mutually agree to an ACP Adjustment that is less than the not-to-exceed ACP Adjustment.

For Excess Expenditures comprised of Tariffs, the ACP Adjustment will be based on substantiated incremental Tariff costs caused by the Change of Law. Substantiated Excess Expenditures will be converted into a per-kW amount by dividing the amount by the Contracted Capacity (kW) and then prorating it over the remaining Term. GPC will include in its Election Notice a fixed not-to-exceed ACP Adjustment, which will be final and may not be rescinded except to the extent (a) Seller fails to fully substantiate its Initial Tariff Notice as described in Section 17.1.3(iii) (GPC Review; ACP Adjustment); or (b) Commission approval is withheld or denied, if required by Section 17.1.7 (Exclusive Relief; Commission Approval). The not-to-exceed ACP Adjustment will represent the maximum and exclusive amount recoverable by Seller with respect to the Change of Law described in Seller’s Initial Tariff Notice, and Seller will not be entitled to recover any additional amount regardless of Seller’s actual incurred costs. By no later than 30 Days after delivery at the Site of all equipment or other goods described in the Initial Tariff Notice, Seller must deliver to GPC a Final Tariff Notice substantiating the actual Excess Expenditures incurred by Seller. By no later than 60 Days after receipt of the Final Tariff Notice, GPC will deliver a final notice to Seller either: (a) confirming the not-to-exceed ACP Adjustment; or (b) proposing a reduced ACP Adjustment if GPC reasonably determines, based on its review of Seller’s Final Tariff Notice, that a lower adjustment is appropriate. If GPC provides notice that a reduced ACP Adjustment is appropriate, GPC and Seller will confer in good faith to mutually agree to an ACP Adjustment that is less than the not-to-exceed ACP Adjustment.

For Excess Expenditures comprised of Taxes arising from any loss, reduction, or elimination of tax credits, incentives, or other governmental benefits, the ACP Adjustment will be based on the actual loss, reduction, or elimination caused by the Change of Law. The amount will be determined by comparing the tax credits, incentives, or benefits that would have been available to and claimed by Seller in the absence of the Change of Law to those available to Seller after the Change of Law. The value of the loss, reduction, or elimination must be reasonably supported by the substantiation provided in the Excess Expenditures Notice and must be certified by an independent accounting professional as accurately reflecting the value of the loss, reduction, or elimination incurred by Seller. The resulting amount will be converted into an ACP Adjustment without markup or return..

For Excess Expenditure comprised of operating costs, the ACP Adjustment will be based on the additional operating costs substantiated by the Excess Expenditures Notice and using assumptions consistent with Prudent Industry Practice and reasonably acceptable to GPC. Substantiated Excess Expenditures will be converted into an ACP Adjustment without markup or return.

Mitigation; Operational Alternatives. Seller must use commercially reasonable efforts, consistent with Prudent Industry Practices, to avoid, minimize, and mitigate any Excess Expenditure arising from a Change of Law. Seller must take reasonable steps to evaluate and propose available Operational Alternatives, seek available exemptions, credits, rebates, or other relief, and avoid incurring unnecessary or avoidable costs. Excess Expenditures will exclude any amount to the extent resulting from Seller’s failure to comply with this Section 17.1.4 (Mitigation; Operational Alternatives), and GPC will have no obligation to pay or include those amounts in any ACP Adjustment or termination payment. Despite any other provision of this Section 17.1 (Change of Law), if Seller submits an Excess Expenditures Notice or otherwise seeks recovery of Excess Expenditures, GPC may, in lieu of approving all or any portion of the requested ACP Adjustment or other recovery, require Seller to implement one or more reasonable Operational Alternatives designed to comply with the applicable Change of Law while avoiding or reducing such Excess Expenditures. Operational Alternatives may include changes to operating procedures, dispatch practices, maintenance scheduling, charging or discharging profiles, cycling limits, monitoring or reporting processes, or other non-capital operational measures that do not require material modification of the Facility. Seller must implement any Operational Alternative directed by GPC within a commercially reasonable period, provided that such Operational Alternative: (i) permits continued compliance with applicable law, (ii) does not materially impair the safe and prudent operation of the Facility, and (iii) does not require Seller to violate any Permit, interconnection requirement, or reliability standard. If GPC requires an Operational Alternative under this Section, GPC will be responsible only for the incremental direct, out-of-pocket operating costs reasonably incurred by Seller solely as a result of implementing the Operational Alternative, to the extent approved by GPC. Seller will not be entitled to recover any avoided capital expenditures, avoided Taxes, avoided tariffs, lost profits, financing costs, or any other Excess Expenditures that would have been incurred absent the Operational Alternative. If any Operational Alternative is accepted by GPC or otherwise requested by GPC that impacts Seller’s ability to achieve required availability or other Facility performance requirements, the Parties will confer in good faith to agree to corresponding adjustments to those performance requirements.

GPC Election; Objection Period. In response to an Excess Expenditures Notice, GPC may elect to either: (i) agree to accept an ACP Adjustment and/or Operational Alternatives; or (ii) terminate this PPA. After receipt of an Excess Expenditures Notice submitted and substantiated in accordance with this Section 17.1 (Change of Law), and by no later than the applicable GPC Election Deadline, GPC will provide its GPC Election Notice to Seller. If GPC elects, in its sole discretion, to terminate this PPA, GPC will state in its GPC Election Notice any termination payment to be paid to Seller, as determined in accordance with Section 17.1.6 (Change of Law Termination). Any election made by GPC is conditioned on GPC’s receipt of Commission approval, as contemplated by Section 17.1.7 (Exclusive Relief; Commission Approval), and GPC will have no liability to Seller for GPC’s election until Commission approval is received. By no later than 15 Days after receipt of the GPC Election Notice, Seller may object to any ACP Adjustment stated in the GPC Election Notice by notice delivered to GPC describing in reasonable detail the basis for Seller’s objection. If Seller does not deliver a timely objection, Seller will be deemed to have accepted the ACP Adjustment. After the expiration of any applicable objection period, GPC will seek Commission approval of GPC’s election as contemplated by Section 17.1.7.

Change of Law Termination. Subject to Section 17.1.7 (Exclusive Relief; Commission Approval), if the Facility has achieved Commercial Operation and GPC elects to terminate this PPA in lieu of accepting an ACP Adjustment, GPC will pay to Seller a termination payment calculated per the formula set forth in Section 17.1.6(i). The termination payment will be Seller’s sole and exclusive remedy arising from or relating to GPC’s termination of this PPA, and, upon GPC’s payment of the termination payment, Seller will have no further right to payment, damages, or other recovery under this PPA arising from or relating to the termination or any Change of Law. If the Facility has not achieved Commercial Operation by the effective date of termination, GPC will not owe any termination payment and may terminate this PPA in accordance with Section 17.1.6 (GPC Election; Objection Period) without any liability to Seller. Upon termination under this Section 17.1 (Change of Law) and payment of the termination payment, if required and approved by the Commission, neither Party will have any further liability under this PPA except for obligations that expressly survive termination.

Termination Payment = 0.25 x NPV (Remaining Capacity Payments) x Performance Adjustment

- Where:

- NPV = the net present value, calculated as of the effective date of termination, of the Remaining Capacity Payments using a discount rate based on GPC’s Commission approved return on equity.

- Remaining Capacity Payments = the sum of Monthly Capacity Payments that would have become payable during the remainder of the Term if this PPA had not been terminated.

- Performance Adjustment = the average Storage Performance Metric Achieved for the 36 Month period ending the last day of the Month immediately preceding the effective date of termination, expressed as a decimal and capped at 1.00. Any availability of, and any delivery from, an Alternate Resource will be excluded from the calculation of each Monthly Availability Percentage and the resulting average.

Exclusive Relief; Commission Approval. The Parties acknowledge that, except as provided in this Section 17.1 (Change of Law), the PPA will not be amended or terminated because of any Change of Law. If GPC accepts an ACP Adjustment, Seller may not seek any additional adjustment to Annual Capacity Prices for the same Change of Law(s) addressed in the GPC Election Notice (including for any additional or different Change of Law Expenditures arising from such Change of Law(s)). Any election by GPC under Section 17.1.5 (GPC Election; Objection Period) to allow Seller to recover Excess Expenditures will apply only to the Change of Law and Excess Expenditures addressed in GPC’s Election Notice. Further, for the avoidance of doubt: (i) any agreement by GPC to adjust the Annual Capacity Price because of a Change of Law is conditioned on approval of the Commission, where required by applicable law; and (ii) if the Commission denies approval of any such agreement and corresponding amendment, Seller may elect to terminate this PPA without any liability to GPC and GPC will have no liability to Seller for the termination.

Disputes. Any dispute arising out of or relating to any Change of Law, including any dispute concerning the adequacy of substantiation, an ACP Adjustment, or the termination payment, will be resolved in accordance with this Section 17.1.8 (Disputes). Pending resolution of a Change of Law dispute, the Parties must continue to perform their undisputed obligations under this PPA.

The Party initiating a Change of Law dispute must provide notice to the other Party describing the dispute in reasonable detail and the relief requested. The dispute will be promptly referred to. Within 15 Days after receipt of the dispute notice, GPC’s Director of Resource Planning and Seller’s #IdentifiyRepresentative must meet and attempt in good faith to resolve the dispute.

If the Change of Law dispute is not resolved 15 Days after the meeting described in Section 17.1.8(i) (Disputes), either Party may escalate the dispute by providing notice to the other Party. Within 10 Days after receipt of the escalation notice, one executive of each Party with authority to resolve the dispute must meet and attempt in good faith to resolve the dispute.

If the Change of Law dispute is not resolved by 15 Days after the meeting described in Section 17.1.8(ii) (Disputes), either Party may initiate mediation by providing notice to the other Party, which mediation must then be conducted within 30 Days after the mediation notice is received.

New or Different Changes in Applicable Law; Payments; Repeal. Seller acknowledges and agrees that except as provided in this Part 17 (Compliance with Laws): (i) GPC will not be responsible for any cost, expense, or loss incurred by Seller that results from any Change of Law; and (ii) in no event will the payments required to be made by GPC under this PPA be increased because of any cost or expense that Seller incurs because of any Change of Law. If any Change of Law that forms the basis for an ACP Adjustment or Operational Alternative repealed, rescinded, invalidated, overturned, or otherwise ceases to be legally effective or applicable to the Facility (in whole or in part), then, effective as of the date the Change of Law no longer has legal effect: (a) the ACP Adjustment will be reduced or eliminated, as applicable, to reflect the remaining legally effective portion of the Change of Law; (b) Seller will no longer be entitled to recover any further Excess Expenditures attributable to the Change of Law (or portion thereof); and (c) if Seller is no longer required to comply with the Change of Law (or portion thereof), Seller will use commercially reasonable efforts to discontinue or unwind any related capital expenditure or operational measure to the extent practicable and consistent with Prudent Industry Practice. Notwithstanding the foregoing, Seller will not be required to refund or credit amounts attributable to irreversible capital expenditures reasonably incurred before the date the Change of Law ceased to be effective, provided the expenditures were prudently incurred in compliance with this Section 17.1 (Change of Law).

No Dedication.

No undertaking by Seller under this PPA is intended to constitute: (i) the dedication to the public of the Facility or any part of the Facility; or (ii) affect Seller’s status as an independent entity and not a public utility or public service company.

Compliance.

Throughout the Term, Seller must comply with all applicable laws, including (i) laws regarding the Site or the Facility, including the design, construction, ownership, operation, maintenance, and decommissioning (if applicable) of the Facility; (ii) required Consents, including requirements to seek, obtain, comply with, maintain compliance with, and, as necessary, renew or modify from time to time, all applicable certificates, licenses, permits, Governmental Authority approvals; (iii) Environmental Laws; and (iv) laws pertaining to environmental emissions. Seller is responsible for all costs, expenses, charges, and fees concerning all compliance required in this Section 17.3, subject to Seller’s rights under Section 17.1 (Change of Law), if applicable.

Environmental Compliance.

Throughout the Term, Seller must comply with (i) Required BMPs as set forth in Section 17.4.1 (Required BMPs), and (ii) Environmental Recommendations as set forth in Section 17.4.2 (Environmental Recommendations).

Required BMPs. Throughout the Term, Seller must comply with all Required BMPs regarding the Site or the Facility, including the design, construction, ownership, operation, maintenance, and decommissioning (if applicable) of the Facility. “Required BMPs” are those “Best Management Practices” required by a Governmental Authority as made available at https://gadnr.org/  or, for a facility outside Georgia, similar best management practices applicable in the state where the Facility is located, in each case whether in effect as of the Effective Date or implemented during the Term. Seller is responsible for all costs, expenses, charges, and fees concerning all compliance required in this Section 17.4.1 (Required BMPs), subject to Seller’s rights under Section 17.1 (Change of Law), if applicable.

Environmental Recommendations. Throughout the Term, to the extent commercially practicable, Seller must comply with all Environmental Recommendations applicable to the Site or the Facility, including the design, construction, ownership, operation, maintenance, and decommissioning (if applicable) of the Facility. “Environmental Recommendations” mean non-binding recommendations made pursuant to Environmental Law or by a Governmental Authority published before or during the Term, including those regarding: (i) studies or assessments of the actual or potential impacts of the Facility on the environment, wildlife, or cultural resources, (ii) the mitigation or avoidance of environmental impacts, including mitigation measures to reduce or avoid impacts to environmental, wildlife, or cultural resources, such as a species conservation strategy, conservation agreement, or cultural resources treatment plan; and (iii) for a Facility located in Georgia, recommended practices published by the Georgia DNR and made available at https://gadnr.org. Seller’s compliance with Environmental Recommendations includes, to the extent commercially practicable, adopting, maintaining, and updating policies and procedures in accordance with Environmental Recommendations. Accordingly, on a regular basis throughout the Term, Seller must review  Environmental Recommendations and take steps to comply with the same in accordance with this Section 17.4.2 (Environmental Recommendations). Seller is responsible for all costs, expenses, charges, and fees concerning all compliance required in this Section 17.4.2.

Wildlife.

If any species survey or study indicates that a direct or indirect taking of wildlife listed as threatened, endangered, or other special status under Environmental Laws, or any impacts to habitat of such wildlife, will occur as a result of development or construction activities (including due to grading, ground disturbance, tree clearing, or nest removal) or during operation of the Facility, Seller will consult with the relevant Governmental Authority to determine whether incidental take authorization or a species habitat conservation or management plan is required under Environmental Laws for the Facility or the Site. If required by any permit, Seller will develop and share with GPC a plan for addressing such impacts. During development and construction of the Facility, any wildlife protected by Environmental Laws discovered on the Site must be reported by Seller in accordance with any applicable conservation or management plans.

Notices of Violations and Potential Violations; NOV Remediation Plan.

Notices of Violations.

Within seven Days after receipt, Seller must provide GPC with copies of any written notification from any Governmental Authority alleging that Seller is in violation of any law, including any Environmental Law applicable to the Facility or the Site with respect to the design, construction, ownership, operation, maintenance, or decommissioning of the Facility (an “NOV”).

NOV Remedy Plan.

If (i) an NOV impacts, or is reasonably expected to impact, Seller’s performance of its PPA obligations; and (ii) GPC requests a remedy plan from Seller in writing, Seller must prepare and submit to GPC an “NOV Remedy Plan” setting forth Seller’s plan and schedule for mitigation and other remedial measures to cure such NOV as soon as reasonably practicable and in accordance with any requirements of any applicable Governmental Authority. Seller must diligently pursue the performance of the NOV Remedy Plan to completion.

Monthly Status Reports and Updates to NOV Remedy Plan.

While an NOV Remedy Plan is in effect, Seller must provide Monthly status reports to GPC, notifying GPC of the implementation of the NOV Remedy Plan, including the steps taken to remedy the NOV, any change to the NOV Remedy Plan, any impact on Seller’s performance of its obligations under this PPA, as well as any additional relevant information as may be reasonably requested by GPC. Seller must modify the NOV Remedy Plan if and as required to comply with any requirement of any applicable law or Governmental Authority.

Assignment, Transfers, and Changes of Control

Assignment, Transfers, and Changes of Control.

Assignment by Seller. Except as expressly provided in Section 18.2 (Financing Assignment; Estoppels), Seller must not assign this PPA in whole or in part to any Person without the prior written consent of GPC. Any proposed assignee of this PPA must: (i) agree to assume Seller’s obligations under this PPA and provide assurances of its ability to perform all PPA obligations; (ii) deliver, on GPC’s reasonable request, assurances of its Creditworthiness and, if applicable, Eligible Collateral; and (iii) cooperate with GPC to comply with any legal requirement that results from such assignment.

Release. Any assignment of this PPA made in compliance with Section 18.1.1 (Assignment by Seller) will constitute, as of the effective date of the assignment, an acceptance and assumption by assignee of all obligations under this PPA and a release and discharge by GPC of Seller from all obligations under this PPA arising after the effective date of the assignment.

Assignment by GPC. GPC may not assign this PPA or any portion of this PPA to any Person without the prior written consent of Seller. However, GPC may, without the consent of Seller and with the approval of the Commission, assign this PPA to a Creditworthy Affiliate subject to the jurisdiction of a state regulatory commission.

Transfer; Change of Control. Seller agrees that, without the prior written consent of GPC, there will be no: (i) Change of Control Transaction with respect to Seller; or (ii) delegation by Seller of operational responsibility for the Facility. For the avoidance of doubt, nothing in Section 18.1.4(ii) (Transfer; Change of Control) will be construed to prohibit Seller from engaging qualified contractors for discrete services related to day-to-day Facility operations without GPC’s prior written consent. Seller, without GPC’s consent, may enter into a Reorganization Transaction so long as: (a) Seller provides notice to GPC at least 30 Days before the anticipated effective date of the proposed transaction; and (b) the Reorganization Transaction does not: (1) limit GPC’s rights under this PPA; (2) expand the liability, risks, or obligations imposed on GPC under this PPA; (3) release or discharge Seller from any PPA obligation or liability; or (4) require substitution or amendment of (I) Eligible Collateral, (II) insurance, or (III) W-9. A Reorganization Transaction that requires or will result in substitution or amendment of (I) Eligible Collateral, (II) insurance, or (III) W-9 will be documented and treated as if it were an assignment of this PPA and Section 18.1.1 (Assignment by Seller) will apply.

Request for Consent. When GPC’s consent is required under Sections 18.1.1 (Assignment by Seller) or 18.1.4 (Transfer; Change of Control), Seller must: (i) request GPC’s consent to the transaction by providing notice at least 30 Days before the anticipated effective date of the proposed transaction; and (ii) receive GPC’s written consent. GPC and Seller will cooperate to finalize the form of written consent between the relevant parties. Subject to Seller’s satisfaction of all applicable provisions of Sections 18.1 through 18.4, inclusive, GPC will seek any required Consent from the Commission after GPC is satisfied that: (a) Seller’s transaction is final but for such Consent; (b) a plan for any replacement of Eligible Collateral is satisfactory and sufficient; and (c) any required accounting determination has been made by GPC and is acceptable.

Transferee Assurances. Before any transaction requiring GPC’s consent under Section 18.1.1 (Assignment by Seller) or Section 18.1.4 (Transfer; Change of Control), Seller must obtain for GPC written assurances from the transferee of the limitations of and protections against liability following the proposed transfer at least equivalent to those afforded GPC and its Affiliates under this PPA. Any transfer contrary to the provisions of this Section 18.1.6 (Transferee Assurances), will make Seller the indemnitor of GPC and its Affiliates against any liabilities incurred by GPC and its Affiliates in excess of those that would have been incurred had no such transfer taken place. If Seller is not the sole owner of the Facility, Seller represents and warrants that it has (and will maintain) written assurances from each other owner of the Facility limitations of and protections against liability of GPC and its Affiliates with respect to each such other owner at least equivalent to that afforded GPC and its Affiliates under this PPA. Any breach of this Section 18.1.6 by Seller will make Seller the indemnitor of GPC and its Affiliates against any liabilities incurred by any of them arising out of any such breach.

Financing Assignment; Estoppels.

Seller, without the consent of GPC, may make a Financing Assignment. GPC agrees to execute a reasonable written consent to the collateral assignment in a form acceptable to GPC if the financing party reasonably requests such consent. Upon reasonable request to GPC in connection with a Financing Assignment or any transaction for which GPC’s consent is required under Sections 18.1 (Assignment, Transfers, and Changes of Control) through 18.4 (General Requirements), inclusive, GPC will execute a written confirmation, if true, but without investigation, that to the best of GPC’s knowledge at the time of the request, Seller is not in default of this PPA.

Reimbursement of GPC’s Costs.

Seller agrees that Seller will pay to GPC a fee of $15,000 per occurrence for each proposed transaction for which Seller requests GPC’s consent under Section 18.1.1 (Assignment by Seller) or 18.1.4 (Transfer; Change of Control) and will pay to GPC a fee of $10,000 per occurrence for each request for an estoppel under Section 18.2 (Financing Assignment; Estoppels). For the avoidance of doubt, if Seller requests GPC’s consent under Sections 18.1.1 or 18.1.4 or an estoppel under Section 18.2, and GPC undertakes drafting of documents to provide such consent or estoppel, and Seller does not consummate the proposed transaction, GPC reserves the right, in its sole discretion, to require Seller to pay the applicable fee under this Section 18.3 (Reimbursement of GPC’s Costs).

General Requirements.

In connection with any transaction for which GPC’s consent is required under Section 18.1.1 (Assignment by Seller) or 18.1.4 (Transfer; Change of Control) or for which Seller’s consent is required under Section 18.1.3 (Assignment by GPC), it is a condition of the required consent that it will not place any limitation on either Party’s rights under this PPA or expand the PPA liability, risks, or obligations of the other Party (including changes in accounting treatment). It will be reasonable for either Party to condition its consent under Section 18.1 (Assignment, Transfers, and Change of Control) on the execution of amendments to this PPA that are reasonably determined by such Party to be necessary to preserve the value and protection afforded to such Party under this PPA. It will be a condition of GPC’s consent to any transaction under Sections 18.1.1 or 18.1.4 or other disposition with respect to this PPA or the Facility, including those contemplated in Section 2.1.10 (Sale, Lease, Transfer, or Other Disposal of Business or Assets Resulting in Material Adverse Effect), that all Performance Security required under Section 6.1 (Performance Security)  will remain in full force and effect unless and until GPC has received (i) Commission approval, if applicable, and (ii) replacement security in form, substance, and amount in full compliance with this PPA, if applicable.. Following GPC’s receipt of such applicable Commission approval and replacement security, GPC will return to Seller any unused portion of Seller’s Performance Security. Any purported assignment, transfer of interest in the Facility or this PPA, or Change of Control Transaction that is not in compliance with the applicable provisions of Sections 18.1 through 18.4, inclusive, will be void.

Dispute Resolution

Notice of Dispute; Dispute Resolution Process.

Either Party (“Disputing Party”) has the right to give notice to the other Party (“Responding Party”) that the Responding Party is not performing in accordance with the terms and conditions of this PPA. The notice (“Notice of Dispute”) must describe with specificity the basis for the Disputing Party’s belief and may propose a resolution of such dispute. Within 15 Business Days after receiving the Notice of Dispute, the Responding Party must provide the Disputing Party with a written response to the Notice of Dispute, which will describe with specificity the basis for the Responding Party’s position and which may include additional issues (if any) regarding the dispute raised by the Notice of Dispute and may propose a resolution of the dispute (“Dispute Response”). This Section 19.1 will not apply to a Billing Dispute until the completion of the dispute resolution process for Billing Disputes set forth in Section 5.2 (Billing Disputes and Financial Accounting). Within five Business Days after the submission of the Dispute Response, the dispute must be submitted to a Seller designated senior Representative and a GPC designated senior Representative for resolution. If the designated senior Representatives are unable to resolve the dispute to the mutual satisfaction of the Parties within 20 Business Days after the submission to the designated senior Representatives, or any other period as the Parties may agree upon, then: (i) in the case of disputes described in Section 19.2 (Expert Arbitration), either Party may provide notice to the other Party declaring an impasse (“Impasse Notice”) and, after notice is given, the Parties must arbitrate the disputes under Section 19.2; (ii) in the case of disputes described in Section 19.3 (JAMS Arbitration), either Party may provide an Impasse Notice and then the Parties must arbitrate the disputes under Section 19.3; or (iii) in the case of any dispute that is not described in Section 19.2 or Section 19.3, either Party may pursue rights and remedies as may be available under applicable law or in equity subject to the terms and conditions of this PPA.

Expert Arbitration.

Upon the submission of an Impasse Notice, a dispute regarding: (i) the results of a Performance Test (under any provision of this PPA); (ii) Seller Event of Default under Section 16.1.9 (Tested Storage Capacity Below 70% Contracted Capacity; Cure; Remedies); or (iii) the development of Maintenance Schedules under Section 10.2.1 (Maintenance Schedule Reporting and Approvals) will be resolved by arbitration as set forth in this Section 19.2.

Selection of Expert.

The Parties will attempt to agree upon the selection of an independent third-party expert to make a determination concerning any dispute described in this Section 19.2 (Expert Arbitration). If the Parties cannot mutually agree on the selection of an expert within 15 Days after the submission of the Impasse Notice, GPC will provide Seller with a list of three qualified experts, and Seller will select one expert from the list. As a condition to appointment as a qualified expert, the expert must: (i) be competent and experienced in matters involving the electric energy business in the United States, with at least 10 years of experience in the electric industry; (ii) have no interest, financial or otherwise, in either Party or this PPA beyond payment of the fees and expenses for serving as the expert under this Section 19.2; and (iii) have not performed, or been employed by a firm that has provided services for either Party, and otherwise have not been previously or currently employed or engaged in any capacity by, and not have a personal or professional relationship with, either Party other than as the expert under this Section 19.2, unless the employment, engagement, or relationship has been disclosed in writing to the Parties before the appointment as an expert under this Section 19.2 without objection by either Party. The expert must not advise or otherwise communicate ex parte in any way with either Party following their appointment as an expert under this Section 19.2. The expert must also treat all information relating to the PPA or the arbitration, including the dispute, as confidential and must not disclose any information (other than to the Parties jointly) without the prior written consent of both Parties.

Expert Decision.

No later than 15 Days after the selection of the expert, each Party must file with the expert written positions (with supporting documentation) concerning the dispute. The expert may request additional filings and will render a decision within 15 Days after receipt of all filings. In the case of any dispute resolved under this Section 19.2 (Expert Arbitration), the decision rendered by the independent expert will be final and binding upon Seller and GPC. Following the resolution of a dispute under this Section 19.2 regarding Performance Guarantees, Monthly Capacity Payment(s) will (if necessary and as soon as practicable) be adjusted retroactively (with interest at the Interest Rate) to reflect tested performance equal to the expert’s determination. For avoidance of doubt, this Section 19.2 does not apply to any dispute regarding GPC’s application of the Performance Metrics, which will be resolved under Section 19.3 (JAMS Arbitration).

Costs.

If the independent expert adopts the position of one of the Parties, then the other Party will pay the fees and expenses of the expert. Otherwise, the Parties will share equally the fees and expenses.

JAMS Arbitration.

Upon the submission of an Impasse Notice: (i) a dispute regarding the calculation of a Termination Payment in accordance with Section 16.3.3 (Determining Gains, Losses, and Costs); or (ii) a billing dispute under Section 5.2 (Billing Disputes and Final Accounting), including a dispute concerning GPC’s application of the Performance Metrics and resulting calculation of a Monthly Capacity Payment in accordance with Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements) (each a, “Billing Dispute”), will be resolved by arbitration as set forth in this Section 19.3.

JAMS.

The Billing Dispute will be resolved under the Federal Arbitration Act by binding arbitration following the JAMS Comprehensive Arbitration Rules and Procedures (“Rules”) of Judicial Arbitration and Mediation Services (“JAMS”) then in effect, including its evidentiary and procedural rules, except as modified in this PPA. It is the Parties’ intent that the arbitration, including the selection and qualification of arbitrators, will be conducted in accordance with the Rules, as amended and supplemented, except where specifically modified by this PPA, and not by the terms of any state arbitration act or other applicable law.

Initiation of Arbitration; Selection of Arbitrators.

      - Initiation of Arbitration; Selection of Party-Appointed Arbitrators. Within 10 Business Days after delivering an Impasse Notice, the delivering Party must contact JAMS to commence arbitration and must provide notice to the other Party. Arbitration will be deemed to be commenced when JAMS issues a Commencement Letter (as defined in the Rules) in accordance with the Rules. The Party initiating arbitration will nominate one arbitrator at the same time it initiates arbitration. The other Party will nominate one arbitrator within 10 Business Days after receiving the Commencement Letter. The two Party-nominated arbitrators will be deemed neutrals and not the representative of the appointing Party. The two arbitrators (“Party-Appointed Arbitrators”) will appoint a third arbitrator (“Third Arbitrator”). The “Arbitration Panel” will include the two Party-Appointed Arbitrators and the Third Arbitrator. All arbitrators must: (a) be competent and experienced in matters involving the electric energy business in the United States, with at least 10 years of legal, engineering, or business experience in the electric industry; (b) have no interest, financial or otherwise, in the Parties or this PPA beyond payment of their fees and expenses for serving on the Arbitration Panel; and (c) have not performed, or been employed by a firm that has provided, services for either Party, and otherwise have not been previously or currently employed or engaged in any capacity by, and not have a personal or professional relationship with, either Party other than as a member of the Arbitration Panel, unless the employment, engagement, or relationship has been disclosed in writing to all Parties prior to the selection of the Arbitration Panel without any unresolved objection by either Party. Arbitrators must not advise or otherwise communicate ex parte in any way with either Party following appointment to the Arbitration Panel and must treat the details of this PPA and all Arbitration Panel activity as private and confidential, and not publish or disclose any information related to the arbitration without the prior written consent of both Parties. Further, the Third Arbitrator will be independent of the Parties and the Party-Appointed Arbitrators. Each Party will pay the fees and expenses incurred by its Party-Appointed Arbitrator and the fees and expenses of the Third Arbitrator will be divided equally between the Parties.

      - Appointment of Third Arbitrator. If the Party-Appointed Arbitrators are unable to agree on the Third Arbitrator within 10 Business Days after the initiation of arbitration, then the Third Arbitrator will be selected by JAMS with due regard given to the selection criteria in Section 19.3.2(i) (Initiation of Arbitration; Selection of Party-Appointed Arbitrators) and input from the Parties and the Party-Appointed Arbitrators. Parties will undertake to request JAMS to complete selection of the Third Arbitrator no later than 60 Days after initiation of arbitration. Costs charged by JAMS for this service will be borne by the Parties equally. If JAMS should fail to select the Third Arbitrator within 60 Days after initiation of arbitration, then either Party may petition a court of competent jurisdiction in Atlanta, Fulton County, Georgia to select the Third Arbitrator. Due regard will be given to the selection criteria in Section 19.3.2(i) and input from the Parties and the Party-Appointed Arbitrators. If, before the conclusion of the arbitration, any member of the Arbitration Panel becomes incapacitated or otherwise unable to serve, then a replacement arbitrator will be appointed in the manner set forth in this Section 19.3.2 (Initiation of Arbitration; Selection of Arbitrators).

Discovery; Hearing.

Discovery and other pre-hearing procedures will be conducted as agreed by the Parties, including at least one corporate representative deposition, or if they cannot agree, as determined by a majority of the Arbitration Panel so long as all pre-hearing discovery is be completed within 90 Days after selection of the Third Arbitrator. Within 15 Business Days after completion of the pre-hearing discovery, each Party will submit, either individually or jointly, by overnight delivery to the other Party and the Arbitration Panel a separate, precise statement for each issue in dispute, that Party’s proposed means of resolving each issue, and the factual or legal support for such proposal (“Proposed Resolutions”). No later than 30 Business Days after all pre-hearing discovery has been completed, a hearing will be conducted at which Seller and GPC will each present evidence and witnesses as it may choose. Arbitration will be conducted in accordance with the Rules, as amended and supplemented, except where specifically modified by this PPA.

Confidential Proceeding.

Each Party must maintain the confidentiality of the arbitration proceedings, except as reasonably necessary to effectively represent itself in the proceeding to enforce the arbitration award or determination, or as otherwise required by law. All discovery materials will remain confidential in accordance with Section 20.16 (Confidentiality).

Arbitration Cost.

Each Party will be responsible for its own legal and arbitration expenses incurred in connection with the arbitration proceeding, including attorneys’ fees, investigation, or discovery (including e-discovery) costs, and expert, consultant or arbitrator fees and expenses.

Arbitrator Decisions.

          - Considerations. The Arbitration Panel will consider the terms and conditions of this PPA, including all relevant evidence and testimony, and will render its decision (by means of a written reasoned decision) within 30 Days after the conclusion of the hearing. However, the Arbitration Panel is expressly and specifically limited to selecting one of the Proposed Resolutions provided by either Seller or GPC for each issue in dispute. The Arbitration Panel will have no authority to award consequential, special, indirect, treble, exemplary, incidental, or punitive damages of any type under any circumstance, regardless of whether such damages may be available under applicable state law, federal law, the Federal Arbitration Act, or any other applicable law.

          - Decision of Arbitration Panel. The written decision rendered by a majority of the Arbitration Panel will be provided to the Parties. The decision may be filed in a court of competent jurisdiction and may be enforced by Seller or GPC as a final judgment in such court.

Location of Arbitration.

Any arbitration under Section 19.2 (Expert Arbitration) or Section 19.3 (JAMS Arbitration) will take place in Atlanta, Fulton County, Georgia.

Mandatory Arbitration.

Subject to Section 19.3.6 (Arbitrator Decisions), each Party understands and agrees that when arbitration is required under this Part 19, arbitration is mandatory and each Party waives any right to seek judicial relief or file court proceedings to determine the specified matters under Section 19.2 (Expert Arbitration) or Section 19.3 (JAMS Arbitration), other than the right to seek judicial relief to compel arbitration, to confirm an arbitration award, or to seek injunctive relief under Section 19.6 (Injunctive Relief) of this PPA.

Injunctive Relief.

Despite any other provision of this Part 19 (Dispute Resolution), the Parties acknowledge that an award of damages may not afford complete relief or furnish an adequate legal remedy as between them (such as when Seller’s Event of Default arises from Seller’s actions designed to achieve an economic gain by selling energy, capacity, or Ancillary Services to a third party in violation of this PPA). Accordingly, the Parties agree that a Party will be permitted to seek at any time, in accordance with applicable laws, procedures, and the terms of this PPA, injunctive relief relating to the performance of this PPA from an arbitrator, a Governmental Authority of appropriate jurisdiction, or a court of competent jurisdiction located in Atlanta, Fulton County, Georgia. The Parties expressly agree that this Section 19.6 does not present a question of substantive arbitrability and waive any right to have an arbitrator decide whether preliminary injunctive relief is available in court. In the event of entry of any interlocutory injunctive relief, the Party against whom such relief is entered waives the right to have a bond or security posted pending resolution of the dispute giving rise to the issuance of the injunction.

Continued Performance.

The Parties agree to continue performing their respective obligations under this PPA while the dispute is being resolved, unless and until such obligations are terminated or expire in accordance with this PPA.

Miscellaneous Provisions

Amendments.

This PPA may be amended only by a written document duly executed by authorized representatives of GPC and Seller, each of GPC and Seller having received all approvals of Governmental Authorities necessary for the effectiveness of the Amendment.

Binding Effect.

This PPA and any extension will inure to the benefit of and will be binding upon the Parties and their respective permitted successors and permitted assigns.

Counterparts.

This PPA may be executed in two or more counterparts and by electronic transmission of signatures in portable document format (PDF) or another electronic format, each of which will be deemed an original but all of which together will constitute one and the same agreement.

Notice.

Except as otherwise provided in this PPA, all notices, requests, consents, claims, demands, waivers, and other communications under this PPA must be in writing (email being sufficient if Exhibit P (Notices) includes an email address for the receiving Party), must include this PPA’s title and the Facility name, must be addressed to the receiving Party’s point-of-contact specified on Exhibit P, and will be deemed to have been delivered when sent by: (i) personal delivery (effective the date of delivery); (ii) if Exhibit M includes an email address for the receiving Party, email delivery (effective that date if sent by 5:00 p.m. (recipient’s time); otherwise, the next Business Day); (iii) prepaid nationally- or internationally- recognized commercial overnight courier (receipt requested; effective the next Business Day); or (iv) registered or certified U.S. mail, with proper postage (effective after the fourth Business Day).

Entire Agreement.

This PPA constitutes the entire understanding between the Parties and replaces any previous or contemporaneous oral or written discussion, representation, promise, arrangement, understanding, or agreement between the Parties related to the subject matter of this PPA. The Parties have entered this PPA in reliance upon the representations and mutual undertakings contained in this PPA and not in reliance upon any oral or written representations or information provided by one Party to the other Party not contained or incorporated in this PPA.

Governing Law.

The validity, interpretation, and performance of this PPA will be governed by the laws of the state of Georgia, without giving effect to any conflict of law principles that would require the application of the laws of another jurisdiction, except that the Federal Arbitration Act, 9 U.S.C. §§ 1 et seq. will govern the Parties’ agreement to arbitrate certain disputes as described in Part 19 (Dispute Resolution). Subject to Part 19 regarding arbitration, each Party agrees that the state and federal courts, as applicable, of the state of Georgia will have exclusive jurisdiction for resolution of disputes under this PPA and each Party irrevocably consents to the jurisdiction of and venue in those courts.

Liability.

Neither Party will be responsible for the other Party’s performance, non-performance, or delay in performance under this PPA.

GPC’s Agent.

Wherever this PPA requires Seller to provide information, schedules, notice or the like to, or to take direction from, GPC, Seller will provide information, schedules, notice, or the like to, or receive from, GPC or such agent of GPC as GPC may direct from time to time pursuant to a notice given to Seller.

No GPC Affiliate Liability.

Notwithstanding any other provision of this PPA, no Affiliate of GPC (including any Affiliate of GPC acting as GPC’s agent where GPC’s agent is given certain authorities) will have any liability whatsoever for any performance, nonperformance, or delay in performance under this PPA, except in the event of an assignment of this PPA to an Affiliate of GPC pursuant to Section 18.1.3 (Assignment by GPC), in which case, such assignee will be liable for GPCs obligations arising under this PPA from and after the date of assignment.

Time of Essence; No Waiver.

Time is of the essence with respect to performance under this PPA. A Party’s failure to enforce a PPA provision, or to require at any time performance by the other Party of any of the provisions under this PPA, does not constitute a waiver of that, or any other PPA provision or any right or remedy in the future. Acquiescence to or acceptance of late performance, with or without reservation does not waive a future right to require timely performance. No modification or waiver of all or any part of this PPA will be valid unless it is reduced to a writing, signed by both Parties, that expressly states that the Parties agree to a waiver or modification, as applicable.

Headings.

The headings contained in this PPA are used solely for convenience and do not constitute a part of this PPA between the Parties, nor should they be used to aid in any manner in the construction of this PPA.

Third Parties.

Except as provided in Section 14.3 (Scope of Indemnity), nothing in this PPA will be construed to create any duty, obligation or liability of GPC or Seller to any Person not a party to this PPA.

Agency.

This PPA will not be interpreted or construed to create an association, joint venture, or partnership between the Parties or to impose any partnership obligation or liability upon either Party. Neither Party will have any right, power, or authority to enter into any agreement or undertaking for, or act on behalf of, or to act as or be an agent or representative of, or to otherwise bind, the other Party.

Severability.

If any term or provision of this PPA or its application to any Person or circumstance is determined to any extent to be invalid or unenforceable, the remainder of this PPA, or the application of such term or provision to Persons or circumstances other than those as to which it is invalid or unenforceable, will not be affected by such determination, and each term and provision of this PPA will be valid and enforceable to the fullest extent permitted by law. The Parties agree to negotiate in good faith to modify this PPA to replace or modify such term or provision so as to effect the original intent of the parties as closely as possible.

Negotiated Agreement.

This PPA will be considered for all purposes as prepared through the joint efforts of the Parties and will not be construed against one Party or the other because of the preparation, substitution, or other event of negotiation, drafting or execution of this PPA.

Confidentiality.

Confidentiality Obligations.

Each Party acknowledges that portions of this PPA contain Confidential Information and may require the Parties to disclose additional Confidential Information to one another. Each Party agrees that it will not, without the written consent of the other Party or as otherwise provided in this PPA, disclose a disclosing Party’s Confidential Information to any third party, except that receiving Party may disclose Confidential Information: (i) to its Affiliates, consultants, agents, advisors, the Renewable Resource Seller, if applicable, or actual and potential funding sources who: (a) need to know or have a contractual right to the information concerning the receiving Party’s performance of its obligations under this PPA; and (b) are subject to an obligation in writing or pursuant to a legally recognized fiduciary or professional duty to maintain confidentiality of Confidential Information; (ii) to its contractors, vendors, and purchasers who require access to the Confidential Information and are subject to legally binding confidentiality obligations that are at least as protective of the Confidential Information as those set forth in this PPA; and (iii) to the extent required by applicable law. Seller acknowledges and agrees that all price and payment information provided by GPC to Seller is Confidential Information.

Disclosure of Confidential Information to a Governmental Authority.

Each Party agrees that if applicable law requires the disclosure of Confidential Information to a Governmental Authority, including the Commission or FERC, the disclosing Party will take reasonable efforts to obtain protection from disclosure of such Confidential Information under the trade secret rules or other rules concerning confidentiality of the applicable Governmental Authority; provided that nothing in this Section 20.16.2 (Disclosure of Confidential Information to a Governmental Authority) will require GPC to take any legal action against any Governmental Authority, including any requirement to appeal a determination concerning Confidential Information. Seller understands and acknowledges that certain terms, conditions, and provisions of this PPA must be disclosed in connection with GPC’s regulatory obligations before the Commission, including the application for the Commission Certificate. GPC makes no assurance or commitment regarding GPC’s ability to obtain requested confidential treatment from any Governmental Authority, including the Commission or FERC.

Public Statements.

Any public statement or other announcement by a Party concerning the transaction described in this PPA will be reviewed and agreed upon by the Parties before release, which agreement will not be unreasonably withheld, conditioned, or delayed. Seller and its Affiliates must not issue any public statement (including any news release, internet, website, social media posting, or other publication) concerning: (i) this PPA or the transactions described in this PPA; (ii) the Facility with respect to this PPA; or (iii) Seller’s relationship with GPC without the communication first being reviewed and agreed upon by the Parties before release to the public. In addition, Seller is responsible for ensuring that its contractors, Affiliates, and contractual counterparties, and each of their respective employees, contractors, and agents, fully comply with this Section 20.16.3 (Public Statements).

Designation of Confidential Information.

Confidential Information not designated by this PPA as Confidential Information must be designated in writing as confidential by the disclosing Party to the receiving Party contemporaneously with the supply of the information to the receiving Party. In addition to any information designated as Confidential Information in other sections of this PPA, the Parties designate the following information as Confidential Information: (i) PPA pricing and payment information; (ii) non-public Electric System information; and (iii) GPC technical requirements.

GPC use of Facility Operational Data.

Despite any other provision in this PPA, GPC may share Facility operational data (but not pricing information), including actual delivery data, PHL estimate data and data components, weather station data, and loss and efficiency data with third parties for the purpose of analysis, modeling, model development and validation, and forecasting.

Survival of Confidentiality Obligations.

Despite any other PPA provision, the terms of this Section 20.16 (Confidentiality) will survive for a period of three years after the termination or expiration of this PPA, except that, to the extent any Confidential Information constitutes a “trade secret” under any applicable law, the receiving Party’s obligations under Section 20.16 will apply for the life of such trade secret.

Contract Interpretation.

Each exhibit, attachment, appendix, schedule, regulatory requirement, policy, procedure, standard, or other document attached to or referenced in this PPA (expressly including the Schedule of Defined Terms) is incorporated into, and is integral to, this PPA as if included in the main body. In this PPA and in all attached or incorporated documents: (i) whenever the term “include,” “including,” or “e.g.” is used in connection with a listing of items included within or an example of the prior reference, the listing will be interpreted to be illustrative only, and will not be interpreted as a limitation on or exclusive listing of the items included in the prior reference; and (ii) “or” means either or all (i.e., “A or B” means “A or B or both A and B”).

Unless otherwise specified, a reference to a given agreement or document, and all the schedules, exhibits, appendices, and attachments to the agreement or document, will be a reference to that agreement or document as modified, amended, supplemented, or restated, and in effect from time to time. Whenever the term “consent” or “approval” is used, the consent or approval will not be unreasonably withheld, conditioned, or delayed by the consenting or approving Party, unless this PPA provides that the consent or approval is in the sole discretion of the consenting Party. If the Party has provided email contact information, “written” or “in writing” includes email communication, absent express statement otherwise.

Reference to: (i) a Party or Person includes any allowed successor or assign; (ii) a regulatory authority includes an authority succeeding to the same function; and (iii) an applicable law is to the law as modified or amended and then effective. Reference to a PPA part by caption (e.g., Facility Operations) or number (e.g., Part 6 (Performance Security)) includes all separate sections (e.g., Section 6.2 (Replacement Collateral; Substituted Collateral; Release of Collateral) and subsections (e.g., Section 6.2.1 (Replacement Collateral)) within that part and reference to a section by caption or number includes all separate clauses within that section. To the extent there is a conflict between CPT and ET, CPT will prevail.

A defined term may be singular or plural, as the context requires, and, absent an express statement otherwise, each defined term has the same meaning in all PPA documents. Captions are for convenience only and do not affect PPA interpretation.

Replacement Index.

Should any index or tariff referenced in this PPA be discontinued, no longer published, or deemed unrepresentative, the Parties will cooperate in establishing substitute benchmarks through reference to equivalent indices or tariffs.

Recording.

Each Party acknowledges and consents to the tape or electronic recording of all telephone conversations between the Parties, and that any recordings will be retained in confidence, secured from improper access, and may be submitted in evidence in any proceeding or action relating to this PPA. Each Party waives any further notice of such monitoring or recording and agrees to notify its officers and employees of any monitoring or recording and to obtain any necessary consent of such officers and employees.

Further Assurances.

Each Party agrees to provide reasonable cooperation to the other Party as necessary to give effect to the terms of this PPA.

Transfer of Information Acknowledgement.

Seller agrees to execute contemporaneous with the execution of this PPA, the Transfer of Information Acknowledgement attached as Exhibit N (Transfer of Information Acknowledgement), and GPC agrees to the limited use and confidential treatment of the information as set forth in Exhibit N.

Service Contract.

Each Party intends this PPA to be a “service contract” within the meaning of Section 7701(o) of the Internal Revenue Code of 1986.

Each Party agrees to all terms and conditions of this PPA as of the Effective Date (the date on which GPC signs, as shown below). The Parties may exchange counterparts of this PPA as a scanned image (e.g., .pdf or .tiff file extension) as an attachment to email. An electronic or scanned signature is an original signature for all purposes.

| Georgia Power Company |  |  | #SellerLegalName# |  |
| --- | --- | --- | --- | --- |
| By: |  |  | By: |  |
|  | #Name |  |  | #SellerSignatureName |
|  | #Title |  |  | #SellerSignatureTitle |
| Date: |  |  | Date: |  |

Exhibit A – Facility Description and Additional Details

| Table A-1 Facility and Site Information |  |
| --- | --- |
| Site | #Street Address# #City, #State, #ZipCode |
| GPS Coordinates | #Latitude, #Longitude |
| Seller Information | #SellerName, a #Seller Entity Type#, organized under the laws of the state of #State# |
| IC Number | IC-#InterconnectionID# |
| Facility Description | The #Number MW BESS at the #FacilityName, interconnected to the Southern Company Transmission System at the POI. |
| POI | #DescribeLocation (further described in the IA), which is the same for the Facility and Renewable Resource if the BESS is paired with a Renewable Resource |
| Renewable Resource Name (if Facility is Paired with Renewable Resource) | #RenewableResourceNameOR#N/A |
| Renewable Resource PPA (if Facility is Paired with Renewable Resource) | #NameAndDateofRenewableResourcePPA |

| Table A-2 Term, RCOD |  |
| --- | --- |
| Term | #NumberBetweenFiveAndThirty Annual Periods |
| RCOD: | #Month #Day, #Year |

[Note to Bidders: Term of 5, 10, 15, 20, 25, or 30 Annual Periods based on Delivery Commencement Date.]

| Table A-3 Additional Facility and Operating Information |  |
| --- | --- |
| A | #____# (%) Guaranteed Round-Trip Efficiency (RTE)* |
| B | #____# (Hours) Storage Device Discharge Duration (SDDD)* |
| C | #____# (MWh) Storage Device Operating Energy (SDOE) – per Cycle* |
| D | #____# (MW) Maximum Rate of Charge (ROC)* |
| ##### E | #____# (MW) Storage Device Design Capacity (SDDC) (continuous discharge)* |
| ##### F | #____# (MW) Contracted Capacity (Equal to (E) above & remains unchanged for the Term) |
| G | #____# (#) Daily Cycle Limits |
| H | #____# (#) Cycle Limit (per Annual Period – minimum 365/366) |
| I | #____# (MW) Interconnection Limit |

*NOTE: Starred items will be Seller Performance Guarantees used by GPC in evaluating BESS performance.

The Facility includes the following: [Description to be provided by Seller and conformed to the Bid]

(For example, storage facility technology type, number and arrangement of cells and inverters, round-trip efficiency, etc.)

| Table A-4 Renewable Resource and Site Information |  |
| --- | --- |
| Renewable Resource Seller Name | #SellerName#, a #SellerEntityType#, organized under the laws of the state of #State# |
| Renewable Resource Facility Name | #RenewableResourceName |
| Site | #Street Address# #City, #State, #ZipCode |
| GPS Coordinates | #Latitude, #Longitude |
| IC Number | IC-#InterconnectionID# |
| Facility Description | The #Number MW Renewable Resource at #FacilityName, interconnected to the Southern Company Transmission System at the POI. |
| POI | #DescribeLocation |

Exhibit A-1 – Key Milestones and Required Key Milestone Dates

[Note to Bidders: This Key Milestones and Required Key Milestone Dates Exhibit will be revised to reflect Key Milestones applicable to the Facility and project prior to PPA execution]

| Key Milestone | Key Milestone Date | Required Substantiation |
| --- | --- | --- |
| Interconnection IA execution |  | Copies of: Executed copy of IA reflecting a commercial operation date no later than the RCOD |
| EPC Contract execution |  | A copy of the executed EPC Contract reflecting a substantial completion date that supports the RCOD, with pricing and other commercially sensitive information redacted |
| Full execution of all major equipment procurement agreements, including those between Seller and applicable suppliers and vendors for GSU, Switchyard equipment, Generator, BESS components, Medium Voltage Transformer, and [Note to Bidders: Please list additional major equipment]: • #AddEquipment • #AddEquipment • #AddEquipment • #AddEquipment and issuance of any applicable full notice to proceed. |  | A copy of each executed major equipment procurement agreement, with pricing and other commercially sensitive information redacted, but including: (i) a description of the country of origin for all equipment and components to be supplied under the agreement; (ii) any applicable full notice to proceed; and (iii) schedules with required delivery dates consistent with the RCOD. |
| EPC Contract Schedule Complete |  | A copy of the EPC Contract schedule, which must be at least a level 3 critical path method schedule that supports the RCOD. |
| All permits required for Facility construction and Commercial Operation. • Applications submitted • All permits obtained |  | A matrix of required permits, copies of applications submitted, and a copy of permits obtained. |
| Financial Closing |  | A letter from an officer of Seller certifying that the following occurred: (i) Seller obtained and has closed on all financing arrangements necessary to obtain funds for the anticipated cost of completing construction of the Facility; (ii) all conditions precedent to the availability of funds pursuant to such financing arrangements have been satisfied or waived by the applicable parties (other than customary conditions to each drawdown of a construction loan), and such funds (subject to customary conditions to each drawdown of a construction loan) will be made available for disbursement to Seller; and (iii) an officer of Seller has provided GPC with an executed certification that the foregoing (i) and (ii) have occurred. |
| Interconnection Notice to Proceed | The date by which the IA notice to proceed must be issued for commercial operation (as defined in the IA) to be achieved in time to support RCOD. | An executed copy of the Interconnection Notice to Proceed |
| EPC Notice to Proceed |  | A copy of the EPC Notice to Proceed. |
| Delivery of all Major Equipment to the Facility site by date required to support Commercial Operation by the RCOD. |  |  |
| Achievement of EPC Contract key milestones: • Site mobilization • Mechanical Completion • Substantial Completion • Initial synchronization |  |  |
| RCOD |  |  |

Exhibit A-2 – Performance Security and Liquidated Damages

All amounts shown as $/kW will be calculated based on the Facility’s Contracted Capacity.

Part 1.  Performance Security

[Note to Bidders: A Performance Security table will be added to include the applicable Performance Security amounts in Attachment 1 (Performance Security and Termination Liquidated Damages Summary) of RFP Exhibit E (Summary of Fees, Costs, Security, and Deadlines).]

Part 2. Liquidated Damages

The following table represents delay liquidated damages amounts that will be owed if Seller does not timely achieve Commercial Operation by RCOD. The amounts shown in the table are daily amounts that will be owed for each Day of delay beyond the RCOD and in the applicable Month.

[Note to Bidders: A Liquidated Damages table will be added to include the applicable delay liquidated damages stated in Attachment 2 (Delay Liquidated Damages Summary) of RFP Exhibit E (Summary of Fees, Costs, Security, and Deadlines).]

Exhibit B – Capacity; Capacity Payments and Payment Reductions; Buydown

- Testing Requirements

  - Contracted Capacity Cap.

Throughout the Term, SDDC will be capped at the Contracted Capacity.

  - Tested Storage Capacity; Performance Testing.

    - Pre-COD Performance Testing.

Pre-COD Performance Testing will be conducted in accordance with Section 1.2.2 (Performance Testing) and Exhibit E (Performance Testing Procedures) to establish the tested performance of the BESS for the Performance Guarantees stated as A – E in Table A-3 (Additional Facility and Operating Information) of Exhibit A (Facility Description and Additional Details). For Commercial Operation to be accepted by GPC, the tested performance of the BESS must equal or exceed the corresponding Performance Guarantee, except to the extent of a buydown payment made by Seller in accordance with Section 1.3 (Tested Storage Capacity Below SDDC; SDDC Buydown) for SDDC. In addition to Performance Testing, Seller must successfully complete any testing required by the IA and any required BESS AGC dispatch testing.

A.  Except as described in Section 1.3 (Tested Storage Capacity Below SDDC; SDDC Buydown), no Performance Test result will change any Performance Guarantee. All Performance Metrics will compare actual performance to the Performance Guarantees. Seller will not receive any additional compensation for tested or actual BESS performance that exceeds any of the Performance Guarantees.

B. As stated in Section 1.2.1 (Pre-COD Performance Testing), GPC acceptance of Commercial Operation is contingent on Seller meeting or exceeding all Performance Guarantees. Subject to Seller’s one-time option to buydown SDDC under Section 1.3.4.A (Buydown Liquidated Damages), if Performance Testing demonstrates that Seller failed to meet or exceed any Performance Guarantee, Seller must cure the performance deficiency to meet or exceed the Performance Guarantee.

    - Performance Testing.

Seller must conduct Performance Testing in accordance with Exhibit E (Performance Testing Procedures) to demonstrate that SDDC and all other Performance Guarantees are met.  To demonstrate the BESS capability, Performance Tests will measure the maximum output of the BESS at the POI over the SDDD as well as the moment-to-moment variability of energy discharged from the BESS. The moment-to-moment variability of energy discharged from the BESS as determined in the Performance Test will determine if the tested performance of the BESS meets or exceeds the Performance Guarantees specified in Exhibit A (Facility Description and Additional Details). Performance Testing must demonstrate that the Facility can operate autonomously, without human intervention that would not be available and responsive during normal commercial operation, during the charging and discharging Cycles and that the thermal management system performs as required. Prior to COD, Seller must not begin Performance Testing until Seller confirms the Facility is ready for Performance Testing, including confirmation that all commissioning is complete, all equipment is operational, and all activities to confirm BESS health and balancing are complete. After the Delivery Commencement Date and no more than twice each Annual Period, if GPC requests that Seller conduct additional Performance Testing because of documented BESS performance deficiencies, Seller must conduct additional Performance Testing to confirm the BESS meets the Performance Guarantees. If Performance Testing shows performance deficiencies, no such limit applies to the frequency with which GPC may request retesting. No later than 10 Days after receipt of a GPC request for Performance Testing, Seller must notify GPC of when the Performance Test will be conducted. Seller must conduct Performance Testing no later than 30 Days after receipt of GPC’s request.

    - GPC Election; No Waiver.

GPC in its sole discretion may elect to waive any Performance Test requirement. Any GPC election to waive any Performance Testing requirement will not waive any Performance Testing requirement for future Performance Tests or otherwise relieve Seller from any Performance Guarantee obligation.

    - Test Charge/Discharge Energy Price Before Commercial Operation Date.

For all Charging Energy prior to COD, GPC will sell and Seller will receive and purchase Charging Energy at the Test Charge Energy Price. For all energy delivered to the POI from the BESS prior to COD, but not after the Delivery Commencement Date, GPC will receive and purchase such energy from Seller at the Test Discharge Energy Price. After the Delivery Commencement Date, GPC will not pay Seller for any test energy delivered to the POI.

  - Tested Storage Capacity Below SDDC; SDDC Buydown.

This Section 1.3 applies to Tested Storage Capacity only and not to any other Performance Guarantee. During the Performance Test, Tested Storage Capacity must prove continuous and steady output (within the permitted deviation limits outlined in Exhibit E) from the BESS at the SDDC over the entire SDDD. In the event the Performance Test fails to demonstrate the Tested Storage Capacity is equal to or greater than the SDDC over the entire SDDD, Seller must remedy the failure per the provisions in this Section 1.3.

    - Cure Plan and Cure Period.

In addition to and without limiting the remedies available to GPC under PPA Section 16.1.9 (Tested Storage Capacity Below 70% Contracted Capacity; Cure; Remedies), if a Performance Test indicates that the Tested Storage Capacity, including continuous output over the SDDD, is less than SDDC but greater than or equal to 70% of Contracted Capacity, Seller must, by no later than 10 Days after the Performance Test date, submit to GPC a written cure plan for increasing the Tested Storage Capacity to the Contracted Capacity. Seller’s cure plan must be acceptable to GPC and include a reasonable Cure Period during which Seller will conduct additional Performance Tests. Except as permitted under Section 1.3.1.A (Cure Period Extension), the Cure Period must not exceed 180 Days.

      - Cure Period Extension. If Seller establishes a cure plan under this Section 1.3.1 (Cure Plan and Cure Period) but requires a Cure Period of more than 180 Days to cure the inadequate Tested Storage Capacity from the most recent Performance Test, then GPC may agree to extend the Cure Period for a reasonable additional period of time, but the extension will not exceed 180 Days. The total duration of the Cure Period, as extended, must not exceed 360 Days. As a condition to GPC granting the Cure Period extension, by no later than 15 Days before the expiration of the initial Cure Period, Seller must provide to GPC:

(i). A revised cure plan, acceptable to GPC, setting forth a reasonable extension of the Cure Period, not to exceed 180 Days; and

(ii). A written certification, acceptable to GPC, confirming that for Seller to cure the inadequate Tested Storage Capacity Seller must be afforded the requested additional amount of time.

    - Cured Inadequate Tested Storage Capacity.

The inadequate Tested Storage Capacity will be deemed cured under this Section 1.3 (Tested Storage Capacity Below SDDC; SDDC Buydown) only if: (i) Seller provides GPC with a written certification, reasonably acceptable to GPC, confirming that the inadequate Tested Storage Capacity has been cured; and (ii) the Tested Storage Capacity, as demonstrated by the most recent Performance Test, is increased to a value equal to or greater than the Contracted Capacity.

    - SDDC during a Cure Period.

During any Cure Period or Cure Period extension, the SDDC will be deemed to be the Tested Storage Capacity determined in accordance with the most recent Performance Test, but the SDDD will not be reduced. The ROC and SDOE will adjust proportionately to the reduction of SDDC.

    - Failure to Cure Inadequate Tested Storage Capacity Above 70% Contracted Capacity; Buydown Liquidated Damages.

If Seller fails to: (i) establish the cure plan within the required 10-Day period set forth in Section 1.3.1 (Cure Plan and Cure Period) or, if applicable, establish the revised cure plan within the required 15-Day period set forth in Section 1.3.1.A (Cure Period Extension) for a Cure Period extension; or (ii) diligently implement the cure plan (including implementation of actions as GPC may reasonably request); or (iii) cure the inadequate Tested Storage Capacity within the applicable Cure Period, the SDDC will be deemed to be the Tested Storage Capacity demonstrated in the most recent Performance Test.

A.     Buydown Liquidated Damages.  Seller will have a one-time option to adjust SDDC by paying GPC, as liquidated damages, the buydown payment shown in Table B-1 (Buydown Payment for Capacity Reduction Below SDDC) corresponding to the Annual Period following the Annual Period in which the most recent Performance Test was conducted, based on the difference (in kW) between the Contracted Capacity and the Tested Storage Capacity from the most recent Performance Test. Upon Seller making the buydown payment required under this Section 1.3.4.A (Buydown Liquidated Damages), the SDDC will be deemed to be the Tested Storage Capacity demonstrated in the most recent Performance Test. However, any reduction of the SDDC will not limit or modify GPC’s rights and remedies under PPA Section 16.1.9 (Tested Storage Capacity Below 70% Contracted Capacity; Cure; Remedies). Subject to PPA Section 16.1.9 the payment of buydown liquidated damages under this Section 1.3.4.A will be GPC’s exclusive remedy for the reduction of the SDDC to the Tested Storage Capacity from the most recent Performance Test. Seller will only be allowed to reduce SDDC once during the Term. Seller’s buydown of SDDC will not lower Contracted Capacity.

[Note to Bidders: Table B-1 will be populated using the applicable amounts stated in Attachment 1 (Performance Security and Termination Liquidated Damages Summary) of RFP Exhibit E (Summary of Fees, Costs, Security, and Deadlines).

| Table B-1 |  |
| --- | --- |
| Buydown Payment for Capacity Reduction below Contracted Capacity |  |
| Annual Period | Buydown Payment ($/kW) |
| 1-5 | #Amount |
| #6-10 | #Amount |
| #11-15 | #Amount |
| #16-20 | #Amount |
| #21 – 25 | #Amount |

If SDDC is reduced as set forth in this Section 1.3 (Tested Storage Capacity Below SDDC; SDDC Buydown), and, after the SDDC reduction, Seller restores the BESS capacity to a value equal to or greater than the Contracted Capacity, then: (i) GPC will not be required to refund to Seller any buydown liquidated damages Seller paid under this Section 1.3.4.A; and (ii) Seller may offer the restored capacity, up to the Contacted Capacity, to GPC at the Annual Capacity Price and in accordance with the payment terms set forth in Exhibit C (Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance Metrics and Requirements). If GPC accepts Seller’s offer, the SDDC will be increased by an amount equal to the portion of the restored capacity accepted by GPC, not to exceed the Contracted Capacity. Any adjustment to SDDC will be documented in the Operating Procedures.

Exhibit C – Monthly Capacity Payments; Monthly Capacity Reductions; AGC Performance METRICS AND Requirements

- Pricing

  - Capacity Pricing.

Commencing on the Delivery Commencement Date, the “Annual Capacity Price” for the first Annual Period will be $#Price/kW-year and will increase per Table C-1 (Annual Capacity Price) below on December 1 of each Annual Period thereafter, as follows:

| Table C-1 Annual Capacity Price |  |
| --- | --- |
| Annual Period | ($/kW-year) |

The Annual Capacity Price will include all costs, including operation and maintenance charges for the Facility.

  - Monthly Capacity Payment.

    - Monthly Capacity Payment. For each Month of each Annual Period, GPC will pay to the Seller the “Monthly Capacity Payment (MCP)” calculated as follows:

MCP = MCF – MCR

Where:

MCF = Monthly Capacity Fee, determined as follows:

MCF = SDDC * (ACP * 1000) * MVF

Where:

SDDC = Storage Device Design Capacity, as may be adjusted pursuant to Exhibit B Section 1.3. (Tested Storage Capacity Below SDDC; SDDC Buydown).

ACP =The applicable Annual Capacity Price (in $/kW-year) set forth in Table C-1 (Annual Capacity Price).

MVF =The applicable Monthly Value Factor from Table C-2 (Monthly Value Factor (MVF)).

MCR = The Monthly Capacity Reduction for the Month determined in accordance with Section 2.1 (Monthly Capacity Reduction).

    - Pro Rata MCP Calculation. If the Delivery Commencement Date occurs on a Day other than the first Day of a Month, or if the last Day of the Term occurs on a Day other than the last Day of a Month, GPC will calculate the MCP on a pro rata basis.

    - MVF; GPC Right to Modify.

    - The Monthly Value Factor for each Month is stated in Table C-2 (Monthly Value Factor (MVF)). Despite the Monthly Value Factors in Table C-2(Monthly Value Factor (MVF)), GPC has the right, in GPC’s sole discretion, to modify  Table C-2, in whole or in part, once every three Annual Periods by providing notice to Seller, so long as: (i) GPC provides Seller the notice at least 180 Days before the start of the Annual Period; (ii) each Monthly Value Factor is at least equal to 0.05 and is not greater than 0.25; (iii) only a single month has a Monthly Value Factor of 0.25; (iv) the sum of MVFs for any two immediately adjacent calendar months is not greater than 0.40; and (v) the sum of all Monthly Value Factors for each Annual Period equals 1.0.

| Table C-2 Monthly Value Factor (MVF) |  |
| --- | --- |
| Month | MVF |
| December | 0.10 |
| January | 0.25 |
| February | 0.10 |
| March | 0.05 |
| April | 0.05 |
| May | 0.05 |
| June | 0.05 |
| July | 0.10 |
| August | 0.10 |
| September | 0.05 |
| October | 0.05 |
| November | 0.05 |

  - No GPC Payment Obligation Before the Delivery Commencement Date.

GPC will not owe Seller any payment or other compensation for the capacity of the Facility for any Month before the Delivery Commencement Date even if Seller achieves Commercial Operation of the Facility more than nine Months before the RCOD.

- monthly capacity reductions; PERFORMANCE METRICS.

  - Monthly Capacity Reduction.

At the end of each Month, GPC will determine the Monthly Capacity Reduction as follows:

MCR = the sum of: (i) SPR; and (ii) Monthly RTE True-Up

Where:

SPR = the Storage Performance Reduction for such Month as determined in Section 2.2 (Storage Performance Reduction); and

Monthly RTE  True-Up = RTE Performance Reduction for such Month as determined in Section 2.4.2 (Monthly RTE True-Up).

  - Storage Performance Reduction.

For purposes of this Section 2.2, GPC will determine the Storage Performance Reduction (“SPR”) for each Month in accordance with Table C-3 (Storage Performance Reduction) below, based on the Storage Performance Metric Achieved for such Month.

| Table C-3 Storage Performance Reduction |  |
| --- | --- |
| Storage Performance Metric Achieved | Storage Performance Reduction |
| Storage Performance Metric Achieved ≥ 0.96 | No reduction |
| 0.96 > Storage Performance Metric Achieved ≥ 0.6 | (0.96 - Storage Performance Metric Achieved) * 1.5 * MCF($) |
| 0.6 > Storage Performance Metric Achieved | 1.0 * MCF($) |

  - Storage Performance Metric Achieved.

For purposes of determining the Storage Performance Reduction in Table C-3 (Storage Performance Reduction) above, GPC will determine the “Storage Performance Metric Achieved” for the Month by calculating the average of two components: (i) Energy Storage Performance Metric; and (ii) Charge/Discharge Rate Performance Metric. The two components will be calculated as follows:

    - Energy Storage Performance Metric. The Energy Storage Performance Metric for each Month is the sum of the 5-Minute Average Storage Capability, in MWhs, divided by the sum of the Storage Device Operating Energy (SDOE) for each 5-minute period. This calculation will include all periods when the BESS is expected to be Available, but will exclude those periods stated in Section 2.3.3 (Exclusions from Storage Performance Metric Achieved). GPC will calculate the Energy Storage Performance Metric for each Month as follows:

Where:

n = total number of 5-minute periods in the Month, excluding any Scheduled Outage, Maintenance Outage, and FME;

i = each 5-minute period in the Month, excluding any Scheduled Outage, Maintenance Outage, and FME;

5-Minute Average Storage Capability (MWh) = The average BESS capability (which is capped at SDOE) Available during each 5-minute period and given any limitation conveyed by Seller or as determined by GPC from Seller’s non-compliance with GPC’s AGC Setpoint signals; and

SDOE = Storage Device Operating Energy, as defined in the Definitions.

The Energy Storage Performance Metric will not exceed 1.0. Seller must provide GPC real-time access to telemetry data, as described in Exhibit G (AGC and Facility Minimum Data Requirements), from Seller’s control system to facilitate GPC’s calculation of these metrics. The 5-Minute Average Storage Capability time tolerances will be detailed in the Operating Procedures. If applicable, the Operating Procedures will detail how the Energy Storage Performance Metric will be calculated for partial BESS Availability during Scheduled Outages, Maintenance Outages, and any FME.

    - Charge/Discharge Rate Performance Metric. The Charge/Discharge Rate Performance Metric will be calculated for each Month as follows: (Note: all negative values will be converted to absolute values for calculation of this metric):

Charge/Discharge Rate Performance Metric=

[i=1n5-Minute Average Charge/Discharge Rate Limiti i=1nMaximum Rate of Charge or Dischargei ]

Where:

n = total number of 5-minute periods in the Month, excluding those periods stated in Section 2.3.3 (Exclusions from Storage Performance Metric Achieved);

i = each 5-minute period in the Month, excluding those periods stated in Section 2.3.3 (Exclusions from Storage Performance Metric Achieved);

5-Minute Average Charge/Discharge Rate Limit (MW) = the lower of: (i) the average rate at which the BESS can be charged (MW) each 5-minute period (capped at the Maximum Rate of Charge); or (ii) the average rate at which the BESS can be discharged (MW) each 5-minute period (capped at the SDDC). In five minute periods in which the BESS is fully charged and therefore cannot be charged further, the charge capability will be excluded from the 5-minute Average Charge/Discharge Rate metric calculation. In five minute periods in which the BESS is fully discharged and therefore cannot be discharged further, discharge rate will be excluded from the 5-Minute Average Charge/Discharge Rate metric. For both numbers, any rate reduction or limit will either be reported by Seller or determined by GPC from Seller’s non-compliance with AGC Setpoint signal determination criteria (as detailed in the Operating Procedures).; and

Maximum Rate of Charge or Discharge (MW) = The guaranteed continuous rate at which the BESS can be charged or discharged, as specified in Table A-3 (Additional Facility and Operating Information) of Exhibit A (Facility Description and Additional Details). For this calculation, GPC will use either the Maximum Rate of Charge or the SDDC, whichever corresponds to the charge or discharge rate selected in the numerator above.

The Charge/Discharge Rate Performance Metric for a Month will not exceed 1.0. Seller must provide GPC real-time access to telemetry data, as described in Exhibit G (AGC and Facility Minimum Data Requirements), from Seller’s control system to facilitate GPC’s determination of these metrics. The Operating Procedures, as described in Section 10.1.2 (Written Operating Procedures) will include specific details for these calculations.

    - Exclusions from Storage Performance Metric Achieved Calculations. For purposes of calculating the Storage Performance Metric Achieved, GPC will exclude from its calculations any period: (i) the BESS is Unavailable to the extent due to a Scheduled Outage, Maintenance Outage, FME, or GPC’s material breach of this PPA; and (ii) during which (a) GPC did not issue a statistically significant number of AGC signals or dispatch instructions (i.e., sufficient AGC signals or dispatch instructions for GPC to fairly and reliably evaluate BESS performance), as determined in accordance with the Operating Procedures, but (b) only to the extent the lack of dispatch prevents GPC from performing a meaningful assessment of BESS performance, in each case as determined in GPC’s sole, but reasonable, discretion.

  - Annual RTE Test; Monthly RTE True-Up; RTE Calculation Guidance

    - Annual RTE Performance Test. After Commercial Operation and no more than once every Annual Period, Seller must conduct, in coordination with GPC, a Performance Test to demonstrate RTE of the BESS (“Annual RTE Test”). The Annual RTE Test must: (i) be conducted in accordance with BESS manufacturer specifications and Prudent Industry Practices; and (ii) accurately measure the actual RTE of the BESS from 0% State of Charge to SDOE and back to 0% State of Charge while operating at the guaranteed parameters stated as Performance Guarantees in Table A-3 (Additional Facility and Operating Information) of Exhibit A (Facility Description and Additional Details).

Where applicable, the Annual RTE Test may allow for adjustments due to ambient temperature in accordance with BESS manufacturer specifications. GPC will have final discretion over the timing of the test charge and discharge, testing procedures, execution of the Performance Test, and any adjustment applied to determine the final test result. Upon confirmation by GPC, the Annual RTE Test result will be deemed the “Annual RTE” for the subsequent Annual Period. For purposes of the first Annual Period, the Annual RTE will be the RTE established during pre-COD Performance Testing.

The Parties will coordinate Annual RTE Test timing to cause the least reasonable disruption to GPC’s operation of the BESS.

If the Annual RTE is less than the Guaranteed RTE – 0.01, Seller may choose to perform up to one additional supplemental Annual RTE Test per Month during the next 12-Month period to try to achieve a better test result. If a supplemental Annual RTE Test achieves a better result than the most recent Annual RTE Test, GPC will accept it and make the most-recent Annual RTE equal to the supplemental Annual RTE Test result, as prorated daily from the test completion date during a Month as applicable.

Further, GPC may also request a supplemental Annual RTE Test at any time during an Annual Period and Seller must conduct this test within 30 Days after GPC’s request. GPC will use this Annual RTE Test result to replace the then-effective Annual RTE and will only delay the next scheduled Annual RTE Test if this test falls within the 90-Day window as detailed in the following paragraph.

If Seller’s or GPC’s supplemental test is accepted by GPC, that test does not reset the 12-Month period for the required Annual RTE Test unless that supplemental test was completed within 90 Days after the original 12-Month period end from the prior approved Annual RTE Test completion date and GPC agrees to reset the date. In that case, the previously completed regular Annual RTE Test 12-Month deadline is reset to the end of the following original 12-Month period with the total period between Annual RTE Tests to never exceed 15 Months.

Any Unavailability due to supplemental or regular Annual RTE Testing that exceeds four Days in total in an Annual Period, may be, at GPC’s discretion, counted as a Forced Derate in the Storage Performance metrics. However, if GPC requests supplemental Annual RTE Testing, the four-Day threshold will be extended, and GPC will not consider the resulting Unavailability as a Forced Derate.

    - Monthly RTE True-Up.

GPC will determine the Monthly RTE True-Up for each Month in accordance with Table C-4 (Monthly RTE True-Up) below, based on the then-effective Annual RTE. Any Month with a Storage Performance Metric Achieved of less than 0.6 will be excluded from the Monthly RTE True-Up.

| Table C-4 Monthly RTE True-Up |  |
| --- | --- |
| Monthly RTE | Monthly RTE True-Up |
| Annual RTE ≥ (Guaranteed RTE – 0.01) | No true-up |
| (Guaranteed RTE – 0.01) > Annual RTE | Reduction per Monthly RTE True-Up formula below |

Monthly RTE True-Up=

(Guaranteed RTE – Annual RTE Test) * Monthly Charging Energy * Monthly Avg AIER

Where:

Monthly Charging Energy = the total amount of Charging Energy provided for the applicable Month as  measured at, or adjusted to, the POI;

Monthly Average AIER = AIER averaged over all Hours charging the BESS in the Month with a non-zero AIER, as defined in the Definitions.

Guaranteed RTE = as specified in Table A-3 (Additional Facility and Operating Information) of Exhibit A (Facility Description and Additional Details).

Seller must provide GPC real-time access to telemetry data, as described in Exhibit G (AGC and Facility Minimum Data Requirements), from Seller’s control system to facilitate GPC’s calculation of these metrics.

    - RTE Calculation Guidance. Any Annual RTE Test results, including supplemental Annual RTE Test results, must show the individual loss contributions for the components both into and out of the BESS, as requested by GPC. If Seller is unable to provide such individual loss contributions, GPC may direct the Operating Committee to develop and implement alternative adjustment measures for such components.

  - Monthly AGC Status and Setpoint Requirements.

Seller is responsible for achieving the AGC Status Performance Requirement and the AGC Setpoint Response Performance Requirement for each Month, except: (i) any Month during which (a) GPC did not issue a statistically significant number of AGC signals (i.e., sufficient AGC signals for GPC to fairly and reliably evaluate BESS performance), as determined in accordance with the Operating Procedures, but (b) only to the extent the lack of AGC signals prevents GPC from performing a meaningful assessment of BESS performance, as determined in GPC’s sole, but reasonable, discretion; and (ii) to the extent Seller’s failure to achieve the AGC Status Performance Requirement or AGC Setpoint Response Performance Requirement during the applicable Month is caused by defective or faulty equipment on GPC’s side of the RTU or telecommunications or telemetry failures caused by equipment not provided or controlled by Seller..

  - Calculating AGC Status and Setpoint Requirements.

At the end of each Month, GPC will determine: (i) the AGC Status Performance Requirement by calculating the AGC Status Performance Metric; and (ii) the AGC Setpoint Response Performance Requirement by calculating the AGC Setpoint Response Performance Metric.

    - AGC Status Performance Requirement. The “AGC Status Performance Requirement” for each Month is that the AGC Status Performance Metric for the Month must equal 0.90 or greater. GPC will calculate the AGC Status Performance Metric for each Month as follows:

AGC Status Performance Metric =

Where:

n = total 6-second AGC periods in the Month.

i = 6-second data point; and,

“AGC Status” = “1” if the BESS is in AGC mode and capable of responding to GPC’s AGC Setpoint signal, or “0” if the BESS is not in AGC mode and is not capable of responding to GPC’s AGC Setpoint signal.

    - AGC Setpoint Response Performance Requirement.

The “AGC Setpoint Response Performance Requirement” for each Month is that the “AGC Setpoint Response Performance Metric” (i.e., Root Mean Squared Error (“RMSE”)) for the Month must be less than or equal to 5. Upon request of either Party, the Operating Committee may relax the RMSE requirement of 5 based on performance factors that affect the RMSE. The Operating Committee must: (i) agree to any adjustment, which agreement must not be unreasonably withheld, conditioned, or delayed; and (ii) document any adjustment in the Operating Procedures.

The RMSE for each Month will be calculated as follows:

Where:

n = Total 6-second AGC periods in the Month for which there is a non-zero AGC Setpoint signal;

i = 6-second data point; and

AGC Setpoint = AGC Setpoint value (MW) for the 6-second AGC period;

BESS Input/Output = The energy (MW) either delivered from the BESS or to the BESS for the 6-second AGC period;

Any 6-second period during which the AGC Setpoint signal = 0 will be excluded from the calculation of RMSE.

Exhibit D – Reserved

Exhibit E – Performance Testing Procedures

- performance testing summary

  - Performance Testing Duration.

    - Performance Testing will consist of two full Cycles carried out within five Days after Performance Testing begins. Results of the test must be calculated for each Cycle and then averaged over the two Cycles.  Each parameter must meet or exceed the guarantee. The BESS must be able to maintain constant power at the POI for the duration of the charge and discharge. A charge Cycle starts when the output at the POI is equal to or greater than 98% of the ROC. The BESS must maintain constant power at the POI for the duration of the charge Cycle.

  - Charge/Discharge Cycles.

    - The output must not deviate more than 2% from ROC. The charge Cycle ends when the BESS reaches 100% of SDOE or output at the POI drops below 98% of ROC for two minutes. None of the energy below 98% of ROC will be included in the Performance Testing calculations. The BESS will rest for 30 minutes between the end of the charge Cycle and start of the discharge Cycle. The discharge Cycle will start when output at the POI is at least 98% of the SDDC. The output at the POI should not deviate more than 2% from the SDDC during the discharge cycle. The discharge Cycle ends when the BESS reaches zero % of SDOE or the output at the POI drops below 98% of SDDC for two minutes. None of the energy below 98% of the SDDC will be included in the Performance Testing calculations. The BESS may rest and then be charged to a suitable SOC to rest overnight for the next Cycle the following Day. All relevant data points must be recorded in one-minute increments and the raw data must be made available three Days after conclusion of Performance Testing. A report including all Performance Testing calculations and a summary of results must be submitted to GPC five Days after conclusion of Performance Testing.

# [Remainder of procedures to be agreed upon by the Parties]

Exhibit F – Facility Operating and Dispatching Requirements

- Seller Requirements:

Seller is responsible for:

Discharging and charging of the BESS in accordance with the real-time directions provided by GPC through AGC Setpoint signals;

All other aspects of operation and maintenance of the Facility in accordance with Prudent Industry Practices and applicable law;

Complying with requirements contained in the IA, including operation and performance validation requirements;

Adhering to all operational data, interconnection, and telemetry requirements applicable to the Facility; and

Promptly and accurately communicating to GPC any and all BESS outage, derate, or other operational limitation via GPC’s specified data systems including the REM application or other data systems as GPC chooses, and also via Gencomm messages, E-mails, and phone calls as requested and specified in the Operating Procedures.

Dispatch.

During the Term, the Parties agree to the following parameters for the dispatch of the BESS:

Seller must not charge or discharge the BESS except as specifically directed by GPC or with specific prior authorization by GPC.

GPC will control the disposition of all energy going into and out of the BESS using its 6-second AGC Setpoint signals.

GPC will be able to request that the BESS be dispatched up to the Cycle Limit. GPC will track Cycles and ensure it remains in compliance with these requirements.

The BESS must be capable of receiving and responding to AGC Setpoint signals from GPC and allow GPC to monitor, measure, and record the State of Charge, charge rate, and discharge rate at all times in accordance with the AGC requirements defined herein.

In the event of an AGC disruption, GPC will communicate desired BESS operations to Seller and Seller must comply with GPC’s requests manually to the best of Sellers ability.

In no event will energy delivered from the BESS exceed the lesser of the SDDC or the Interconnection Limit.

Seller must ensure that the BESS satisfies all operational and performance requirements under the IA, including when the BESS is discharging (during cycling or otherwise).

Charging of the BESS.

During the Term, the Parties agree to the following parameters for charging the BESS:

GPC will have full control of the disposition of all energy directed into the BESS at no additional cost and the right to charge the BESS that may result in Charging Energy.

GPC will request the BESS use Charging Energy at any time and in any amount that GPC specifies up to the Maximum Rate of Charge or until the State of Charge equals SDOE or the Maximum Operational State of Charge Limit.

Communications. Real time communications between Seller and GPC are required with respect to the BESS and, if applicable, the Renewable Resource. Seller must have the capability to and continuously communicate the status of the BESS and, if applicable, the Renewable Resource to GPC in real time.

Exhibit G – AGC and Facility Minimum Data Requirements

Seller must operate the BESS, including the charging or receiving and delivering energy, in compliance with GPC’s AGC Setpoint signals. Seller must telemeter at all times during the operation of the BESS, and GPC’s AGC Setpoint signal will include the maximum Rate of Change as a limiting factor for changes in energy output. For purposes of this Exhibit G, the “Rate of Change” is the real-time maximum ramp rate when increasing or decreasing output (accounting for any equipment or operational issues that may affect such ramp rate).

All data points listed in this Exhibit G represent minimum requirements for a BESS utilizing AGC. This Exhibit incorporates by reference, and will automatically be updated as necessary to incorporate, any additional data point introduced in future revisions of the document titled Southern Company Typical Data and Application Requirements for SOCO BA Generators Final MMYYYY.pdf, which is located in the “Interconnection Implementation (NTP to COD)” subsection of the Southern Company OASIS site at www.oasis.oati.com/soco/index.html. The Operating Committee may develop and implement reasonable accommodations for Seller with respect to additional data points that (i) are not readily available from Seller’s existing equipment and (ii) are not required by the Interconnection Provider. Such reasonable accommodations may include coordinating required upgrades to Seller’s data capabilities with Scheduled Outages.

The Facility’s AGC system must be configured to interface with GPC’s AGC RTU to send and receive the following data for AGC:

Data Points FOR STANDALONE BESS FACILITY

- Data Points FOR STANDALONE BESS FACILITY

- From EMS to Site

    - Storage Setpoint (MW)

- From Site to EMS

    - All High-Side (Transmission Level 46kV & above) device analog measurements (at POI)

    - Storage net output AC MW (positive for discharging, negative for charging)

    - Storage net output AC MVAR

    - Three-phase voltage (kV)

    - Three-phase current (A)

    - All High-Side (Transmission Level 46kV & above) device status (Breakers, Switches, disconnects states (OPEN/CLOSED)

    - All Low-Side (34.5 kV) collector system analog measurements

    - Individual Feeder Aggregated Storage output AC MW

    - Individual Feeder Aggregated Storage output AC MVAR

    - Three-phase voltage (kV)

    - Three-phase current (A)

    - Reactive device output MVAR (if applicable)

    - All Low-Side (34.5 kV) collector system device status (OPEN/CLOSED)

    - Individual BESS Feeder Breaker status

    - Reactive device breaker status (LTC, shunts, dynamic reactive devices, etc.)

    - Reactive device circuit switcher status (if applicable)

    - Gross Storage DC MW (positive for discharging, negative for charging)

    - Plant Voltage Regulation Mode Status (Auto/Manual)

    - Reactive Support (MVARs) at Zero power Status (ENABLED/DISABLED)

    - Storage on AGC Signal (ENABLED/DISABLED)

    - Present State of Charge (MWh)

    - Maximum Operational State of Charge limit (MWh)

    - Minimum Operational State of Charge limit (MWh)

    - Discharge Time (minutes) (estimated discharge time based on remaining energy and current discharge rate)

    - Charge Time (minutes) (estimated charge time based on remaining energy capacity and current charge rate)

    - Current Discharge Limit [Operating High Limit (MW)]

    - Maximum Discharge Limit [High Limit (MW)]

    - Current Charge Limit [Operating Low Limit (MW)]

    - Maximum Charge Limit [Low Limit (MW)]

    - Storage AGC Ramp Rate Increase (+MW/min)

    - Storage AGC Ramp Rate Decrease (-MW/min)

    - High Limit Status (Normal/Alarm)

    - Low Limit Status (Normal/Alarm)

    - Average Site Cell Temperature, if available (°F)

    - % of stack in service

    - Station Service/Aux Power (MW)

    - Storage Setpoint Feedback (MW)

    - Number of inverters available

    - Number of inverters producing power

    - Number of inverters tripped

    - Number of inverters not communicating

    - Number of inverters out of service

    - Equivalent BESS Cycles per day counter

    - Equivalent BESS Cycles per year counter

- General Flow of AGC

The resource will send every scan of all its points to GPC (via EMS) and likewise, EMS will update its points every scan. Seller must place the resource on AGC when available for remote control and will echo back to EMS what it has received for the AGC Setpoint.

The Renewable Resource will receive AGC Setpoints equivalent to the Operating High Limit or the Potential High Limit and operate at full generation until an AGC Setpoint below the Potential High Limit is received. Upon receiving this AGC Setpoint for Curtailment, the Facility will reduce output to meet the AGC Setpoint.

The BESS will receive AGC Setpoints equivalent to the Operating High Limit or the Potential High Limit and operate at full generation until an AGC Setpoint below the Potential High Limit is received. Upon receiving this AGC Setpoint for curtailment, the BESS must reduce output to meet the AGC Setpoint.

The BESS is to remain on AGC and available for dispatch when available for dispatch regardless of output. For the avoidance of doubt, AGC will send AGC Setpoints at 0 MW during periods where the desired output is 0 MW and the Facility online and available for dispatch. A 0 MW BESS AGC Setpoint will result in the BESS going to idle and controls should be implemented to ensure the BESS is not discharging when a 0 MW AGC setpoint is dispatched to offset any station service at the POI.

Explanation of Points

  - Renewable Resource Setpoint (MW)

    - This will be an integer value that will range from the Operating Low Limit to the Operating High Limit for the Renewable Resource. If not in curtailment, this value will echo either the Operating High Limit or the Potential High Limit (PHL), depending on system conditions. If the setpoint echos the Operating High Limit, the site will operate as-capable.  If curtailment is active, the site output will follow the AGC setpoint below the Potential High Limit.

  - BESS Setpoint (MW)

    - This will be a value up to the BESS Discharge Rate for the BESS device in a positive (discharge) direction or to the BESS Charge Rate in a negative (charge) direction. Site to regulate to meet this value at the POI.

  - Renewable Resource Ramp Rate (+/- MW/min)

    - This is a plant controller level ramp rate at which the Renewable Resource will ramp up or down, up to the maximum allowable ramp rate specified in the IA. This is not the actual real-time ramp rate, but the rate at which the plant will transition to the next setpoint. The Renewable Resource Ramp Rate will be indicative of the Renewable Resource and indicates the rate at which the Renewable Resource would increase generation after a curtailment is lifted. In all cases, the Renewable Resource Ramp Rate should not exceed the maximum allowable ramp rate in the IA.

  - Max Renewable Resource Ramp Rate (+/- MW/min)

    - This is the maximum allowable ramp rate per the IA. This is a fixed value and will be the rate at which the Renewable Resource Setpoint could be curtailed by AGC.

  - Facility Voltage Regulation Mode Status (Auto/Manual)

    - This provides status of the voltage control mode and if the Facility's controller is regulating the POI voltage. Its normal state will be in Auto.

  - Facility Reactive Support (MVAR) at Zero power status (ON/OFF)

    - This status indicates the Facility’s capability to produce reactive power (MVARs) when at zero active power. Its normal state will be at OFF.

  - Gross BESS DC MW

    - Aggregated Gross BESS DC MW at the BESS. This is the actual DC MW entering the BESS or being discharged from the BESS to the power conversion station. Positive to indicate discharging, Negative to indicate charging.

  - Renewable Resource AGC Status

    - This will be an integer value that will range from 0 to 1. A '0' value will indicate the Renewable Resource is on local control and a '1' will indicate the Renewable Resource is available for AGC remote control.

  - Renewable Resource Operating High Limit (MW)

    - The current maximum generating capacity of the Renewable Resource. This is the maximum possible generation of the Renewable Resource including any de-rates, independent of Renewable Resource irradiance. This limit is to be reduced if equipment issues reduce the total Renewable Resource Capacity. If there are no equipment issues or de-rates, this value will be the same as the Renewable Resource Capacity.

  - Renewable Resource Capacity (MW) [High Limit]

    - This is the max design capacity of the Renewable Resource up to the POI limit. This will be a fixed number and is independent of Renewable Resource irradiance or equipment de-rates.

  - Renewable Resource High Limit Status

    - This will be an integer value that will range from 0 to 1. Its normal state will be to a 0. A value of 1 will indicate generation is at the high limit.

  - Renewable Resource Potential High Limit (MW)

    - This is the potential real time actual limit of the Renewable Resource inclusive of Renewable Resource irradiance and any equipment issues. This real-time telemetry point will indicate what the Renewable Resource’s output would be if no curtailment is present.

  - Renewable Resource Operating Low Limit (MW)

    - The current minimum generating capacity of the Renewable Resource. During normal operation, the facility will provide a low limit for available curtailment. Expectation is this would be 0 MW under normal conditions unless an equipment issue exists that prevents the Renewable Resource from returning to full normal output following the full curtailment.

  - Renewable Resource Low Limit Status

    - This will be an integer value that will range from 0 to 1. Its normal state will be to a 0. A value of 1 will indicate generation is at the Operating Low Limit.

  - Renewable Resource Setpoint Feedback (MW)

    - This is an echo of the value received from EMS for the EMS setpoint.

  - BESS Setpoint Feedback (MW)

    - This is an echo of the value received from EMS for the EMS setpoint.

  - BESS AGC Status

    - This will be an integer value that will range from 0 to 1. A '0' value will indicate the BESS is on local control and a '1' will indicate the BESS is available for AGC remote control.

  - Present State of Charge (MWh)

    - This will be a value representing the actual State of Charge and range from 0 to the SDOE for the device.

  - BESS Maximum Operational State of Charge limit (MWh)

    - This will be a value indicating the maximum usable State of Charge capability for the BESS. This is a calculated value inclusive of any de-rates or equipment issues and not the nameplate to give the operating range of the system. This value should indicate the maximum usable energy and indicates the amount of AC MW that can be discharged to the POI. For clarity, this is not the amount of DC MW that is stored in the BESS. AGC should be able to dispatch the BESS from the Maximum Operational State of Charge to the Minimum Operational State of Charge. If there are no operational constraints, this value should be equal to the SDOE.

  - BESS Minimum Operational State of Charge limit (MWh)

    - This will be a value indicating the minimum usable State of Charge capability for the BESS. This is a calculated value inclusive of any limiting operational issues and not the nameplate to give the operating range of the system. A value of 0 MWh should indicate the bottom range of usable energy, not necessarily the absolute lowest energy level of the BESS device. AGC should be able to dispatch the BESS from the Minimum Operational State of Charge to the Maximum Operational State of Charge.

  - BESS Discharge Time (minutes)

    - Estimated time to discharge the BESS to the Minimum Operational State of Charge Limit based on the remaining energy and current discharge rate.

  - BESS Charge Time (minutes)

    - Estimated time to charge the BESS to the Maximum Operational State of Charge Limit based on the remaining energy and current charge rate.

  - BESS Discharge Rate [Operating High Limit (MW)]

    - This will be a value indicating the real-time maximum rate of power that the BESS device can discharge. Discharged power is provided as a positive (+) value. This value is dependent on the state of the system (inclusive of any derated equipment or abnormal conditions). If the BESS device is part of a co-located Facility, this value will need to take into consideration the Interconnection Limit and the Renewable Resource Potential High Limit.

  - BESS SDDC [High Limit (MW)]

    - The guaranteed amount of BESS storage capacity allocated to GPC under this PPA and that represents the guaranteed continuous discharge capability of the BESS for the Storage Device Discharge Duration. This will be a value indicating the maximum rate of power that the BESS device can discharge provided as a positive (+) value. This is independent of the state of the system or any de-rates.

  - BESS Charge Rate [Operating Low Limit (MW)]

    - This will be a value indicating the real-time minimum rate of power that the BESS device can achieve when charging. This will be provided as a negative (-) value. This value is dependent on the state of the system (inclusive of any derated equipment or abnormal conditions).

  - BESS Maximum Rate of Charge [Low Limit (MW)]

    - The Maximum Rate of Charge of the BESS. This will be a value indicating the maximum rate of power that the BESS device can be charged at, from zero MWh to the SDOE, provided as a negative (-) value. This is independent on the state of the system or any de-rates.

  - BESS Discharge AGC Ramp Increase (+MW/min)

    - This will be a value indicating the maximum ramp rate of power the BESS can achieve when increasing output or decreasing the charge setpoint. This will be provided as a positive (+) value. The value should reflect the real-time capability to prevent AGC setpoints from exceeding the tolerance and must not exceed the limits in the IA.

  - BESS Charge AGC Ramp Decrease (-MW/min)

    - This will be a value indicating the maximum ramp rate of power the BESS can be charged or when decreasing output. This will be provided as a negative (-) value. The value should reflect the real-time capability to prevent AGC setpoints from exceeding the tolerance and must not exceed the limits in the IA. Under normal conditions, this value should be the same as the BESS Discharge AGC Ramp Increase.

  - Average Site Cell Temperature, if available (°C)

    - This will be a value indicating average site cell temperature provided as degrees Celsius.

  - Station Service & Auxiliary Operational Load (MW)

    - These values will be as defined and described in the PPA.

  - % of stacks in service

    - This will be a value indicating the number of battery stacks/racks in service and expressed as a percentage.

  - Number/Percentage of inverters producing power

    - Total number of inverters producing (for BESS device) power (real or reactive power) to the grid under normal operation.

  - Number/Percentage of inverters available

    - Total number of inverters available on-line (electrically connected based on inverter’s AC breaker status).

  - Number/Percentage of inverters offline

    - The total number of inverters that have stopped injecting power (real or reactive) to the grid for several reasons including but not limited to protection trip, momentary cessation etc. This may be calculated as a difference between inverters available and inverters producing power.

  - Average Site Irradiance

    - Average irradiance for the solar site based on meteorological stations.

  - Cycles per Day Counter

    - This value will be an equivalent cycles per Day calculated based on: (i) the amount of energy discharged at the POI from the BESS divided by (ii) the max storage capacity of the BESS. This will be reset to 0 at midnight and will be passed to the EMS to ensure the desired number of equivalent cycles per Day is not exceeded.

  - Cycles per Year Counter

    - This value will be an equivalent cycles counter calculated based on 1. the amount of energy discharged at the POI from the BESS divided by 2.  the max storage capacity of the BESS. This will be cumulative for the current year and will be passed to the EMS to ensure the desired number of equivalent cycles per year is not exceeded.

Exhibit H – Facility One-Line Diagram

[Insert one-line diagram for Facility]

Exhibit I – Requirements for PPA Facility

This document describes GPC’s required characteristics for the Facility. This document does not include all the legal, regulatory, and technical requirements for the Facility but outlines certain minimum requirements. Seller is required to execute this document acknowledging the following:

- BESS

  - Battery Energy Storage System (BESS)

    - Units listed to ANSI/VAN/UL UL 9540 Standard for Safety for Energy Storage Systems and Equipment.

    - Battery and battery enclosures must be tested in accordance with ANSI/CAN/UL 9540A Standard for Safety for Test Method Evaluating Thermal Runaway Fire Propagation in Battery Energy Storage Systems. The test report shall be accompanied by a supplemental report prepared by a registered design professional with expertise in fire protection engineering that provides interpretation of the test data in relation to the installation requirements for the energy storage system. GPC must have been provided with the required UL 9540A reports before any BESS component is delivered to the Site.

    - The Facility complies with the version of NFPA 855 in effect at the time of Commercial Operation in addition to state and local fire codes.

    - A permanent source of water for fire protection must be provided.

    - Identify any redundancy, operational margins, and contingency modes within the ESS thermal management system (TMS). All operational constraints should be specified in the event of a partial or complete TMS outage. The TMS design should include redundancy and/or contingency plans for TMS component failures (e.g., HVAC systems, fans, or the ability to operate in a reduced capacity if a TMS component fails).

    - Provide all documentation and training materials required by the relevant standards. This includes, but is not limited to, the Hazard Mitigation Analysis (HMA), and Failure Mode and Effects Analysis (FMEA). The development of a site specific HMA shall require the participation of the Supplier, the Company, the OEM of the inverter, and the EPC contractor, if applicable.

    - Provide detailed augmentation plan for the Facility over the PPA Term.

    - ESS must be appropriately sized and configured to ensure that it consistently maintains its rated nameplate instantaneous energy output capacity at the designated POI, thereby guaranteeing that the system can reliably meet the specified energy demands and operational requirements without any degradation in performance or efficiency. ESS must be sized to maintain rated nameplate instantaneous Energy output capacity at the POI.

  - Inverter

    - BESS inverters must be specified to be grid forming capable. Seller must provide documentation demonstrating the inverter is specified with grid forming capability.

    - Unless the inverter is fully integrated as part of the battery supplier’s product offering, proven integration experience must be provided between the inverter OEM and the battery supplier.

    - Inverter grid forming control points must be integrated into the Facility site control scheme, such that only controls change and site tuning will be required when GPC decides to enable grid forming features.

    - Inverter must be capable of providing reactive power support at zero active power, without reducing the state of charge of the battery (additional auxiliary power consumption shall be from the grid).

  - Facility Design

    - Facility engineering and design must account for BESS augmentation plan, including but not limited to site layout, block design, collection system design, aux power design, and controls design.

    - Battery enclosures must be spaced per NFPA 855, UL9540A testing results, state and local code, and AHJ requirements.

    - Backup source must be provided for the BESS auxiliary power in case of extended grid outage to maintain power to the BESS BMS, EMS, fire protection system, and thermal management system (if required by BESS vendor).

  - Testing

    - Continuous power test, energy capacity test, and RTE test must be performed for the BESS.

    - Testing must be performed to demonstrate the combined output of BESS and the Renewable Resource are controlled to mitigate equipment overload.

    - Technology specific characterization testing must be performed. (e.g., ramp rate testing) as per interconnection testing requirements.

    - Additional testing must be performed as required by any applicable interconnection testing requirement and to demonstrate the Facility complies with the operational requirements set forth in the PPA (e.g., AGC testing).

  - End-of Life Disposal / Demolition

    - Description of the end-of-life disposal/recycling plan to be included in the bid form.

  - Sourcing Restrictions

    - Programmable electronic components of the (i) BMS, (ii) BESS Controller, and (iii) Site Controller (including controls, hardware, and software) must not be sourced from or manufactured by Foreign Entities of Concern or other restricted countries, as further described in PPA Section 10.13.1 (Sourcing Restrictions).

Acknowledgment:

Seller hereby confirms that it will meet these requirements and provide evidence of Seller’s compliance with all referenced information to GPC upon request.

| #SellerLegalName# |  |  |
| --- | --- | --- |
| By: |  |
| Name Printed: |  |
| Title: |  |
| Date: |  |

Exhibit J – Form of Commercial Operation Completion Certificate

Georgia Power Company

Resource Planning Director/Capacity Procurement Manager

Bin 10196

241 Ralph McGill Blvd.

Atlanta, Georgia 30308

Re: Commercial Operation Completion Certificate – Power Purchase Agreement for Firm Capacity, Energy Storage Services, and Ancillary Services from a Battery Energy Storage System [Paired with a Renewable Resource] for 2026 All-Source Capacity Request for Proposals for Need Years 2032-2033 at #FacilityName# dated as of ______ ___, 20__ between Georgia Power Company (“GPC”) and #SellerLegalName# (“Seller”) (“PPA”).

In accordance with PPA Section 7.1.5 (Commercial Operation), Seller certifies to GPC that Seller fully satisfied the criteria for Commercial Operation of the Facility, including the following:

Seller has demonstrated to GPC’s reasonable satisfaction that the Facility is capable of receiving and delivering energy obligated to be received or delivered pursuant to this PPA at or to the POI on a reliable basis in accordance with the Interconnection Agreement and Prudent Industry Practices;

The Facility’s AGC equipment and system control and communications systems, as approved by GPC under PPA Section 10.8 (AGC) are completely installed and fully operational, and Seller has demonstrated that the these systems are operational and capable of responding to GPC’s AGC Setpoint signals to effectively dispatch energy both into and out of the BESS and to the POI, in real-time. Further, Seller confirms that GPC has real-time electronic access to all Facility data GPC requests in order to manage and control these energy flows as well as to retain data and calculate all Performance Metrics;

GPC is able to receive or deliver such energy at the POI on a reliable basis in accordance with Prudent Industry Practices;

Seller has delivered to GPC a certificate from a responsible officer of Seller that is reasonably acceptable to GPC, stating that the Facility has been designed, engineered, constructed, and tested in accordance with Prudent Industry Practices and the terms of the PPA, including the Facility technical and design requirements;

Seller has delivered to GPC any as-built drawings with respect to the Facility, as may be requested by GPC; and

Seller has delivered to GPC a certificate from a responsible officer of Seller that is reasonably acceptable to GPC certifying that Seller is in compliance with the Interconnection Agreement and Seller has obtained all applicable Consents required under applicable law to be obtained by Seller at the time of Commercial Operation of the Facility for the construction, ownership, operation and maintenance of the Facility in accordance with this PPA.

Seller certifies that Commercial Operation of the Facility was achieved as of #CommercialOperationDate#. Seller agrees to provide photographs of the Facility and Site at GPC’s request. The electrical inspection documentation in support of Seller’s certification of Commercial Operation is attached. Seller grants to GPC and its agents, affiliates, successors, and assigns an irrevocable, worldwide, royalty-free, and unrestricted right and license to use, duplicate, modify, sublicense, distribute, display, and otherwise engage the photographs and related intellectual property, including the creation of derivative works. Seller represents and warrants that it has the exclusive right to grant the license to GPC for the purposes stated in the PPA.

| #SellerLegalName# |  |  |
| --- | --- | --- |
| By: |  |
| Name Printed: |  |
| Title: |  |
| Date: |  |

Exhibit K – Form of Standby Letter of Credit

[Bank Letterhead]

Date of issuance:	________, 20__

Irrevocable Standby Letter of Credit No:_____________________

“Issuer”:

Address:

“Beneficiary”:	Georgia Power Company

Address: 	c/o Southern Company Services, Inc.

Attn: Assistant Treasurer

BIN SC1407

30 Ivan Allen Jr. Blvd., NW

Atlanta, GA 30308

“Account Party”:

Address:

“Expiry Date”:	______________, 20__, and any automatically extended date, as herein provided [(but in no event later than _____________, 20__)]

“Total Amount”:			United States Dollars (U.S. $_____________)

We, the Issuer, hereby establish in your favor, for the account of the Account Party, our irrevocable standby letter of credit (“Standby Letter of Credit”), in the aggregate amount not exceeding the Total Amount.

Funds under this Standby Letter of Credit are available to you on or before the Expiry Date by presentation of your demand signed by one of your officers or authorized representatives, and delivered to us in substantially the form attached as Annex 1 (Form of Sight Draft) and referring thereon to the number and date of this Standby Letter of Credit, accompanied by a written and completed certificate signed by a person purporting to be one of your officers or authorized representatives, in the form attached as Annex 2 (Form of Certificate), with appropriate insertions.

This Standby Letter of Credit is effective immediately and expires at 5:00 p.m. (Eastern Time) on the Expiry Date. It is a condition of this Standby Letter of Credit that the Expiry Date will be deemed automatically extended without amendment for a period of one year from the present or any future Expiry Date, unless we notify you not less than ninety (90) days prior to any such date, in accordance with the notice provisions set forth herein, that we have elected not to extend the Expiry Date for such additional period.

Delivery of demands and certificates will be made on any day that is a business day for us at or prior to 5:00 p.m. (Eastern Time) at our office located at __________, or at any other office in the United States of America that is designated by us in a written notice delivered to you. If such demand and such certificate are received at any such office on or prior to the Expiry Date, we hereby agree with you that we will duly honor the same within three (3) business days of such presentation. Notwithstanding the foregoing, you may demand payment under this Standby Letter of Credit by facsimile or electronic transmission when promptly confirmed by written demand; however, actual disbursement of funds under a demand presented by facsimile or electronic transmission may not occur until we are presented with the original Standby Letter of Credit.

Partial drawings and multiple presentations may be made under this Standby Letter of Credit, provided, however, that each such demand that is paid by us will reduce the amount available under this Standby Letter of Credit.

Except as is expressly set forth herein, payment of demands made under this Standby Letter of Credit is not subject to any agreement, condition or qualification. The obligation of the Issuer under this Standby Letter of Credit is the individual obligation of the Issuer and is in no manner contingent upon reimbursement with respect thereto.

Funds available for drawing under this Standby Letter of Credit may not directly or indirectly constitute funds or collateral deposited with the Beneficiary, or for the Issuer’s account by the Account Party, or pledged with or for the Issuer’s account by the Account Party.

This Standby Letter of Credit is transferable and can be successively transferred to any transferee that Beneficiary states in writing to us has succeeded such Beneficiary under this Letter of Credit; provided that such transfer to such transferee is in compliance with applicable U.S. laws and regulations. Transfer of this Standby Letter of Credit to any transferee will be effected by the presentation to us of this Standby Letter of Credit accompanied by a certificate in the form attached as Annex 3 (Form of Instruction to Assign in Entirety), with appropriate insertions, signed by a person purporting to be an officer or authorized representative of the Beneficiary. Upon such presentation, we will forthwith issue an irrevocable letter of credit to such transferee with provisions therein consistent with this Standby Letter of Credit.

We will not modify, revoke or terminate this Standby Letter of Credit without your written consent. This Standby Letter of Credit sets forth in full the terms of our undertaking, and such undertaking may not be modified, annulled or amplified by reference to any other document, instrument or agreement referred to herein or in which the Standby Letter of Credit is referred or to which the Standby Letter of Credit relates, and any such reference may not be deemed to incorporate herein by reference any document, instrument or agreement.

To the extent not contrary to the express terms hereof, this Standby Letter of Credit will be governed by the International Standby Practices (“ISP98”). This Standby Letter of Credit will be deemed to be a contract made under the laws of the state of Georgia and will, as to matters not governed by the ISP98, be governed by and construed in accordance with the laws of the state of Georgia.

Notices concerning this Standby Letter of Credit may be sent to a party by courier, certified mail, registered mail, facsimile, electronic transmission or similar communications facility to its respective address set forth herein. Any notice, demand, request or other communication is deemed to have been received by the party to whom it is sent at the time of its delivery. Each party may notify the other of any change of address in the manner provided above.

[ISSUING BANK]

By:

Authorized Signature

#### Annex 1

Form of Sight Draft

[Insert Place], [Insert Date]

Amount:	[Insert Currency] [Insert Amount in Numbers]

[Insert Amount in Letters]

Drawn under Irrevocable Standby Letter of Credit No. ___________ of [Insert Name of Issuing Bank]

At Sight

Pay to the Order of [Name of Beneficiary]

In reference to:	Irrevocable Standby Letter of Credit No. ____________, dated ________.

To:	[Insert Name of Issuing Bank]

[Insert Address]

[BENEFICIARY]

By:

Title:

#### Annex 2

#### Form of Certificate

Re:	[Insert Name of Agreement] dated _________, 20__ (“Agreement”) between [Name of Account Party] (“[Account Party]”) and [Name of Beneficiary] (“[Beneficiary]”).

The undersigned, an officer or authorized representative of [Beneficiary], hereby certifies to [ISSUING BANK] (“Bank”) with reference to irrevocable standby letter of credit no. (“Standby Letter of Credit”), issued by the Bank for the account of [Account Party] in favor of [Beneficiary] that:

(1)	(Insert one of the following, as applicable)

Under the Agreement, Beneficiary is entitled to demand payment under the Standby Letter of Credit in the amount of the sight draft accompanying this certificate.

or

[Beneficiary] has received written notice from the Bank in accordance with the terms of the Standby Letter of Credit that the Bank has elected not to extend the Expiry Date of the Standby Letter of Credit for an additional period past its then Expiry Date and the Account Party has failed to deliver a substitute letter of credit in accordance with the terms of the Agreement.

(2)	The undersigned is an officer or authorized representative of [Beneficiary] and is authorized to execute and deliver this certificate and to draw upon the Standby Letter of Credit.

IN WITNESS WHEREOF, the undersigned has executed and delivered this Certificate as of this __ day of ________ , 20__.

[BENEFICIARY]

By:

Title:

#### Annex 3

#### Form of Instruction to Assign in Entirety

Re: Irrevocable Standby Letter of Credit No.

Ladies/Gentlemen:

For value received, the undersigned beneficiary hereby irrevocably assigns to:

[Name of Assignee]

[Address]

all rights of the undersigned beneficiary to demand payment under the above Standby Letter of Credit in its entirety.

By this assignment, all rights of the undersigned beneficiary in such Standby Letter of Credit are transferred to the assignee and the assignee will hereafter have the sole rights as beneficiary thereof. The Account Party will be responsible for all fees and expenses related to the assignment.

The Account Party will be responsible for all fees and expenses related to this assignment.

The Standby Letter of Credit is returned herewith and in accordance therewith we ask you to issue a new irrevocable Standby Letter of Credit in favor of the assignee with provisions consistent with the Standby Letter of Credit.

Sincerely,

[Beneficiary]

By:

Title:

Exhibit L – Form of Guaranty

This Guaranty Agreement (“Guaranty”), effective as of ___________, 20__ (“Effective Date”), is entered into by __________________ (“Guarantor”) in favor of Georgia Power Company (“Beneficiary”). Guarantor acknowledges:

- Beneficiary and ____________________ (“Company”), [an Affiliate of Guarantor], have entered into a Power Purchase Agreement for Firm Capacity, Energy Storage Services, and Ancillary Services from a Battery Energy Storage System [Paired with a Renewable Resource] for 2026 All-Source Capacity Request for Proposals for Need Years 2032 - 2033 at #FacilityName# dated as of ____________, 20__ (as amended, restated, supplemented or otherwise modified from time to time, “PPA”) regarding a battery energy storage system located in #FacilityCity, #FacilityState, as further described in Exhibit A (Facility Description and Additional Details);

- Beneficiary has required, as an inducement to its entry into the PPA, that Guarantor deliver to the Beneficiary this Guaranty or other Eligible Collateral as and when required under the PPA;

- Guarantor qualifies as a Seller Guarantor under the PPA, and this Guaranty qualifies as Eligible Collateral under the PPA; and

- Guarantor will derive substantial direct and indirect benefit from the transactions contemplated by the PPA.

To induce Beneficiary to enter into and perform its obligations under the PPA, and for and in consideration of the foregoing premises, the mutual agreements contained herein, and other good and valuable consideration, the receipt and sufficiency of which are acknowledged, Guarantor agrees as follows:

# PART 1 Definitions

- Definitions. Unless otherwise defined in this Guaranty, capitalized terms have the meanings specified or referred to in the PPA.

# PART 2 Guaranty

## 2.1  Guaranty. Guarantor unconditionally and irrevocably guarantees to Beneficiary and Beneficiary’s successors and assigns, that Guarantor will make prompt and full payment of any obligations of Company to Beneficiary when due, whether by acceleration or otherwise, with any interest as may accrue under the PPA or under any other documents or instruments now or in the future evidencing, securing, or otherwise relating to the PPA (“Guaranteed Obligations”), except that Guarantor’s liability under this Guaranty will in no event exceed the aggregate amount of Eligible Collateral that Company must provide in accordance with PPA Part 6 (Performance Security) (plus costs of enforcement of this Guaranty as provided in Section 4.4 (Expenses)). Guarantor must immediately pay for any obligation of Company upon demand by Beneficiary.

## 2.2	Guaranty Absolute.

## 2.2.1. Guarantor Guarantees. Guarantor absolutely guarantees that the Guaranteed Obligations will be paid strictly in accordance with the terms of the PPA, regardless of any law or regulation in effect now, or that may come into effect in the future, in any jurisdiction affecting any of the terms or the rights of Beneficiary regarding the PPA. This Guaranty constitutes a guarantee of payment and not of collection. The obligations of Guarantor under this Guaranty are primary obligations and are several from Company or any other Person, and Guarantor is the principal obligor under this Guaranty. Guarantor’s liability under this Guaranty will be direct and immediate and not conditional or contingent upon the pursuit of any remedies against Company or any other person, nor against securities or liens available to Beneficiary or Beneficiary’s successors or assigns. Guarantor’s liability under this Guaranty will be irrevocable, absolute, and unconditional irrespective of, and Guarantor unconditionally and irrevocably waives any defenses it may now have or later acquire in any way relating to:

            - any change in the time, manner, or place of payment of, or in any other term of, any of the Guaranteed Obligations, or any other amendment, modification, or waiver of, or any consent to departure from, the terms of any Guaranteed Obligations, or any compromise, settlement, release, or termination of any of the Guaranteed Obligations;

            - any change, restructuring, or termination of the corporate structure or existence of Company or any of its subsidiaries, including Guarantor’s disposal of any part of Guarantor’s interest in Company, or Guarantor’s alteration of Guarantor’s investment in Company in any manner;

            - any lack of validity or enforceability, in whole or in part, of the Guaranteed Obligations, the PPA, or any agreement or instrument relating the Guaranteed Obligations or the PPA;

            - any failure of Beneficiary to disclose to either Company or Guarantor any information relating to the business, condition (financial or otherwise), operations, performance, properties, or prospects of either Company or any of its subsidiaries now or in the future known to Beneficiary (Guarantor waiving any duty on the part of Beneficiary to disclose the information);

            - any failure, omission, delay, or lack on the part of Beneficiary to enforce, ascertain, or exercise any right, power, or remedy under or pursuant to the terms of the PPA, the Guaranteed Obligations, or this Guaranty;

            - any failure by Beneficiary to commence an action against Company, including as contemplated by the provisions of O.C.G.A. Section 10-7-24, as amended; any lack of due diligence by Beneficiary in the collection or protection of or realization upon any collateral securing the Guaranteed Obligations;

            - the bankruptcy, insolvency, winding up, dissolution, liquidation, administration, reorganization, or other similar or dissimilar failure or financial disability of Guarantor or Company, or any legal limitation, disability, incapacity, or other circumstance relating to Guarantor or Company;

            - the addition, substitution or partial or entire release of any guarantor, maker, or other Parson (including Company) primarily or secondarily liable or responsible for the payment and observance of the Guaranteed Obligations or by any extension, waiver, amendment, or other action or instrument that may release or discharge (in whole or in part) a guarantor, maker, or other Person (other than as a result of the indefeasible payment of the Guaranteed Obligations in full);

            - the taking, variation, renewal, addition, substitution, subordination, or partial or entire release of any security or other credit support for the Guaranteed Obligations, or the enforcement or neglect to perfect or enforce the security or support; or

            - any circumstance whatsoever (including any statute of limitations) or any act of Beneficiary or any existence of or reliance on any representation by Beneficiary that might otherwise constitute a legal or equitable defense available to, or a discharge of, Guarantor.

###### 2.2.2. Guarantee Effectiveness. This Guaranty will continue to be effective or must be reinstated by Guarantor, as applicable, if at any time any payment of the Guaranteed Obligations should for any reason subsequently be asserted or declared to be void or voidable, or is unwound in any way under any state or federal law, including any provision of the U.S. Bankruptcy Code related to fraudulent conveyance or preference (each, a “Voidable Transfer”). Beneficiary or any other person is not required to repay or restore, in whole or in part, any Voidable Transfer, and any attempt to repay or restore any Voidable Transfer will be construed as though the payment had not been made.

###### 2.2.3. No Release of Guaranty. No action that Beneficiary takes or fails to take in connection with the Guaranteed Obligations, or any security for the payment of any of the Guaranteed Obligations, nor any course of dealing with Company or any other person, will release Guarantor’s obligations under this Guaranty, affect this Guaranty in any way, or give Guarantor any recourse against Beneficiary.

###### 2.2.4. Enforcement following PPA Event of Default. In the case of an Event of Default under the PPA or regarding any of the Guaranteed Obligations, Guarantor agrees that Beneficiary will have the right to enforce its rights, powers, and remedies under the PPA and Guaranty or under any other instrument now or in the future evidencing, securing, or otherwise relating to the Guaranteed Obligations, and apply any payments or credits received by Company or Guarantor or realized from any security, in any manner and in any order as Beneficiary, in its sole discretion, sees fit, and all rights, powers, and remedies available to Beneficiary in that event will be nonexclusive and cumulative of all other rights, powers, and remedies provided under the PPA, this Guaranty, by law, or in equity. If the Guaranteed Obligations are partially paid at the election of Beneficiary or Beneficiary’s successors or assigns, to pursue any of the remedies available to Beneficiary, or if the indebtedness is otherwise partially paid, this Guaranty will nevertheless remain in full force and effect, and Guarantor will remain liable for the entire balance of the Guaranteed Obligations even though any rights that Guarantor may have against Company may be destroyed or diminished by the exercise of the remedy.

  - Waivers and Acknowledgments.

###### 2.3.1. Guarantor Notice Waiver. Guarantor unconditionally and irrevocably waives promptness, diligence, presentment, demand of payment, acceptance, notice of acceptance, protest, notice of dishonor, and any other notices regarding any of the Guaranteed Obligations and this Guaranty.

###### 2.3.2. Guarantor Waiver of Guaranty and Acknowledgement of Continuing Obligations. Guarantor unconditionally and irrevocably waives any right to revoke this Guaranty and acknowledges that this Guaranty is continuing in nature and applies to all Guaranteed Obligations, whether existing now or in the future. The provisions of this Guaranty will extend and be applicable to any modification of the PPA.

###### 2.3.3. Waiver of Rights and Remedies. Guarantor unconditionally and irrevocably waives all rights and remedies accorded by application of law to sureties or guarantors and Guarantor must not assert or take advantage of those rights or remedies, including:

            - any right to require Beneficiary to proceed against Company or any other person or to proceed against or exhaust any security held by Beneficiary at any time or to pursue any other remedy in Beneficiary’s power before proceeding against Guarantor;

            - any defense that may arise because of the incapacity, lack of authority, death, or disability of any other Person or the failure of Beneficiary to file or enforce a claim against the estate (in administration, bankruptcy, or any other proceeding) of any other Person; or

            - any defense arising because of the exercise of any right or remedy available to, or election made by, Beneficiary under the U.S. Bankruptcy Code, whether as an unsecured or under secured creditor, seeking adequate protection or otherwise.

###### 2.3.4. Guarantor’s Waiver of Defenses Based on Set-Off or Counterclaim. Guarantor unconditionally and irrevocably waives any defense based on any right of set-off or counterclaim against or concerning the obligations of Guarantor under this Guaranty.

###### 2.3.5. Guarantor Waiver of Defenses, Claims, and Discharges. Guarantor unconditionally and irrevocably waives all defenses, claims, and discharges of Company, or any other obligor regarding the Guaranteed Obligations. Without limiting the generality of the preceding sentence, Guarantor will not assert, plead, or enforce against Beneficiary or any other Person any defense of waiver, release, statute of limitations, res judicata, statute of frauds, fraud, incapacity, minority, usury, illegality, or unenforceability that may be available to Company or any other person liable concerning any indebtedness, or any setoff available against Beneficiary to Company or any other Person, whether or not on account of a related transaction. Guarantor expressly waives reliance on any anti-deficiency statute(s). If a foreclosure proceeding is commenced, Guarantor expressly agrees that Guarantor will be and remain unconditionally liable, to the fullest extent permitted by applicable law, for any deficiency remaining after foreclosure of any mortgage or security interest securing indebtedness, whether or not the liability of Company or any other person for the deficiency is discharged under statute or judicial decision.

## 2.4	Subrogation. Despite any payment or payments made by Guarantor under this Guaranty, Guarantor unconditionally and irrevocably waives any rights of subrogation to the rights of Beneficiary against Company and any rights of reimbursement, assignment, indemnification, or implied contract or any similar rights (including any statutory rights of subrogation under U.S. Bankruptcy Code Section 509 (11 U.S.C. § 509)) against Company or against any other guarantor of all or any part of the Guaranteed Obligations until when the Guaranteed Obligations have been indefeasibly performed in full. If, despite the preceding sentence, any amount will be paid to Guarantor on account of the subrogation or similar rights at any time when all of the Guaranteed Obligations will not have been indefeasibly paid in full, those amounts will be held by Guarantor in trust for Beneficiary and Guarantor must turn over to Beneficiary those amounts in the exact form received by Guarantor, to be applied against the Guaranteed Obligations in the order that Beneficiary may determine in Beneficiary’s sole discretion.

## 2.5	Contribution, Indemnification, Reimbursement. Guarantor unconditionally, irrevocably, and absolutely waives all right of contribution, indemnification, reimbursement, or similar rights against Company regarding the Guaranty, whether the rights arise under an express or implied contract or by operation of law, and it is the intention of Guarantor and Company that Guarantor will not be deemed to be a “creditor” (as defined in U.S. Bankruptcy Code Section 101 or any other applicable law) of Company because of the existence of this Guaranty if Company becomes a debtor in any proceeding under the U.S. Bankruptcy Code or any other applicable law.

## 2.6	Agreement regarding Bankruptcy of Company. So long as any Guaranteed Obligations are owed to Beneficiary, Guarantor must not, without the prior written consent of Beneficiary, commence, or join with any other person in commencing, any bankruptcy, reorganization or insolvency proceeding against Company.

# PART 3 Representations and Warranties

Guarantor hereby represents and warrants as follows:

## 3.1	Organization. Guarantor is #a OR #an #GuarantorEntityType# organized, validly existing, and in good standing under the laws of the state of #GuarantorEntityRegistrationState.

## 3.2	Authorization; No Conflict. The execution and delivery by Guarantor of this Guaranty, and the performance by Guarantor of its obligations under this Guaranty: (i) are within Guarantor’s #GuarantorEntityType# powers; (ii) have been duly authorized by all necessary #GuarantorEntityType# action; (iii) do not contravene its #bylaws OR #operating agreement OR #OtherOrganizationalDocument or any law or regulation applicable to or binding on Guarantor or any of its properties; and (iv) do not require the consent or approval of any Person that has not already been obtained or the satisfaction or waiver of any conditions precedent to the effectiveness of this Guaranty that have not been satisfied or waived.

## 3.3	Enforceability. This Guaranty constitutes the legal, valid, and binding obligation of Guarantor, enforceable against Guarantor in accordance with its terms, except to the extent that that enforceability may be limited by applicable bankruptcy, insolvency, dissolution, reorganization, moratorium, liquidation, or other similar laws affecting creditors’ rights generally and by general principles of equity (regardless of whether enforcement is sought in a proceeding in equity or at law).

## 3.4	No Bankruptcy Proceedings. There are no bankruptcy proceedings pending or being contemplated by Guarantor or, to Guarantor’s knowledge, threatened against it.

## 3.5	No Legal Proceedings. There are no legal proceedings that would be reasonably likely to materially adversely affect Guarantor’s ability to perform this Guaranty.

# PART 4 - Miscellaneous

## 4.1	Continuing Guaranty; Assignment. This Guaranty is a continuing guaranty and will: (i) remain in full force and effect until all of the Guaranty Obligations have been satisfied; (ii) consistent with the terms of this Guaranty, apply to all Guaranteed Obligations whenever arising; (iii) be binding upon Guarantor, its successors and assigns; and (iv) inure to the benefit of, and be enforceable by, Beneficiary and its permitted assignees under this Guaranty. Guarantor must not assign or delegate Guarantor’s rights or obligations under this Guaranty without: (i) the prior written consent of Beneficiary, which consent may be withheld in Beneficiary’s sole discretion; and (ii) a written assignment and assumption agreement in form and substance reasonably acceptable to Beneficiary. Without prejudice to the survival of any of the other agreements of Guarantor under this Guaranty, the agreements and obligations of Guarantor contained in Section 4.4 (Expenses) (regarding enforcement expenses) and the last sentence of Section 2.2.1 (Guarantor Guarantees) will survive the payment in full of the Guaranteed Obligations and all of the other amounts payable under this Guaranty.

4.2	Notices. All notices, requests, demands and other communications that are required or may be given under this Guaranty must be in writing and will be deemed to have been given when actually received if: (i) personally delivered; (ii) transmitted by facsimile, electronic, or digital transmission method; or (iii) if sent by certified or registered mail, return receipt requested. In each case, notice will be to the contacts identified in this Section 4.2 (Notices) or to the other place and with the other copies as Beneficiary or Guarantor may designate for itself by written notice to the other under this Section 4.2. Delivery by facsimile of an executed counterpart of a signature page to any amendment or waiver of any provision of this Guaranty will be effective as delivery of an original executed counterpart to the amendment or waiver.

| Notice to GPC: | With Copy to: |
| --- | --- |
| Georgia Power Company c/o Southern Company Services, Inc. Attn: Assistant Treasurer, BIN SC 1407 30 Ivan Allen Junior Boulevard, NW Atlanta, GA 30308 G2GPCERG@southernco.com | Georgia Power Company Legal Dept. Attn: Commercial & Transactions, Bin 10180 241 Ralph McGill Blvd., N.E. Atlanta, GA 30308 |
| Notice to Guarantor: |
| #CompanyName Attn: #IndividualName #Title #StreetAddress #City, #State #ZipCode #Email# |

4.3	Delay and Waiver. No failure on the part of Beneficiary to exercise, and no delay in exercising, any right under this Guaranty will operate as a waiver any right under this Guaranty; nor will any single or partial exercise of any right under this Guaranty preclude any other or further exercise of the right under this Guaranty or the exercise of any other right. The remedies provided in this Guaranty are cumulative and not exclusive of any remedies provided by law.

## 4.4	Expenses. Guarantor agrees to pay or reimburse Beneficiary and any permitted assignees of Beneficiary on demand for its reasonable costs, charges, and expenses (including reasonable fees and expenses of counsel) incurred in connection with the enforcement of this Guaranty or caused by any breach by Guarantor of any of its obligations under this Guaranty, including any actions taken in any bankruptcy or insolvency proceedings, if Guarantor is required to pay under this Guaranty.

## 4.5	Entire Agreement; Amendments; Other Guarantees. This Guaranty and any agreement, document, or instrument attached to this Guaranty or referred to in this Guaranty integrate all the terms and conditions mentioned in or incidental to this Guaranty and supersede all oral negotiations and prior writings in respect to the subject matter of this Guaranty. In the event of any conflict between the terms and conditions of this Guaranty and any related agreement, document, or instrument, the terms and conditions of this Guaranty will prevail. This Guaranty may only be amended or modified by an instrument in writing signed by each of Guarantor and Beneficiary and any permitted assignees of Beneficiary. Without limiting the preceding in this Section 4.5 (Entire Agreement; Amendments; Other Guarantees): (i) this Guaranty will not release, modify, revoke, or terminate any other guaranty existing previously, now, or in the future executed by Guarantor; nor will any other guaranty previously, now, or in the future executed by Guarantor release, modify, revoke, or terminate this Guaranty; and (ii) all of Guarantor’s liabilities and obligations and Beneficiary’s rights and remedies under this Guaranty are in addition to and cumulative with those under any other guaranty executed by Guarantor in favor of Beneficiary or any affiliate of Beneficiary on or about the Effective Date or at any other time.

## 4.6	Headings. The headings of the various Sections of this Guaranty are for convenience of reference only and will not modify, define, or limit any of the terms or provisions in this Guaranty.

## 4.7	Governing Law; Consent to Jurisdiction.

## 4.7.1. Governing Law. This Guaranty will be construed and interpreted, and the rights of the parties determined, in accordance with the laws of the state of Georgia, without giving effect to principles of conflicts of law that would require the application of the laws of another jurisdiction.

###### 4.7.2. Consent to Jurisdiction. Guarantor irrevocably and unconditionally: (i) agrees that any suit, action, or other legal proceeding arising out of this Guaranty must be brought in federal or state court located in the state of Georgia; (ii) submits to the exclusive jurisdiction of those courts for any such suit, action, or proceeding; and (iii) waives any objection to venue in those courts and any claim that the suit, action, or proceeding has been brought in an inconvenient forum. [Applicable Only to Foreign Guarantor: Guarantor and Beneficiary further agree that a final judgment in any action or proceeding arising out of or relating to this Guaranty will be conclusive and may be enforced in any other jurisdiction within or outside the Untied States by suit on the judgment, a certified or exemplified copy of which will be conclusive evidence of the fact and the amount of indebtedness or liability therein described, or in any other manner provided by applicable law.]

###### 4.7.3. [Applicable Only to Foreign Guarantor: Guarantor’s Process Agent. Guarantor irrevocably designates, appoints and empowers [_________________________________________ Georgia, ____ United States of America] as its authorized agent to receive on its behalf and on behalf of its property service of copies of the summons and complaint and any other process which may be served in any action or proceeding between Beneficiary and Guarantor arising out of or relating to this Guaranty. The service may be made by mailing or delivering a copy of the process in care of the process agent, and Guarantor irrevocably authorizes and directs its designated process agent to accept the service on its behalf. Guarantor further agrees that failure by a process agent appointed in accordance with this section to notify Guarantor of the process will not invalidate the process or service or the proceeding concerned. Despite the preceding sentences, nothing in this Guaranty will affect the rights of either party to serve process in any other manner permitted by applicable law. Guarantor will maintain the process agent, or any other Person located within the State of Georgia as may be acceptable to Beneficiary, as its agent for service of process in the State of Georgia during the duration of this Guaranty and twelve months after, at Guarantor’s sole cost and expense. If for any reason, the appointed process agent is no longer acting as process agent, Guarantor must promptly (and in any event within seven Days) appoint a replacement agent in the State of Georgia as its authorized agent to receive on its behalf and on behalf of its property, service of copies of the summons and complaint and any other process which may be served in any action or proceeding between Beneficiary and Guarantor arising out of or relating to this Guaranty. If Guarantor fails to appoint a replacement process agent as provided in this Section 4.7.3, Beneficiary may appoint the replacement process agent on behalf of Guarantor, at Guarantor’s sole cost and expense.]

###### 4.7.4 [Applicable Only to Foreign Guarantor: Payment in U.S. Dollars; Judgement Currency. This Guaranty is made by the Guarantor regarding a transaction in which the specification of payment in United States Dollars (“Dollars”) and payment at the designated place of payment is of the essence, and Dollars will be the currency of accounting in all events. The payment obligations of the Guarantor under this Guaranty will not be discharged by any amount paid in another currency or in another place, whether in accordance with a judgment or otherwise, to the extent that any amount paid on conversion to Dollars and transferred to the designated place of payment under normal banking procedures does not yield the amount of Dollars due under this Guaranty.]

###### 4.7.5 [Applicable Only to Foreign Guarantor: Withholding Taxes.

###### a. 	Each payment by Guarantor to Beneficiary in accordance with this Guaranty must be made free and clear of, and without deduction or withholding for or on Beneficiary of, any present or future taxes, duties, assessments, fees, deductions, withholding, levies, imposts, or charges of whatsoever nature (other than taxes imposed on income or gross revenue), together with any liabilities (including penalties, interest and expenses) in regarding the preceding imposed or levied by or on behalf of the government of any jurisdiction(s) in which the Guarantor is organized, headquartered, or conducting business, or any political subdivision of the government or any authority or agency of the government having the power to tax (“Withholding Taxes”), unless the deduction or withholding is required by the laws of any jurisdiction(s) in which the Guarantor is organized, headquartered, or conducting business, or any province or political subdivision of the jurisdiction(s) or by the administrative practice of any taxing authority. If any such deduction or withholding is required, or if no such deduction or withholding is required but Withholding Taxes are otherwise payable concerning the payment, Guarantor must:

###### i.  Pay any additional amount to Beneficiary as may be necessary to ensure that Beneficiary receives and retains a net sum after such deduction, withholding, or payment of Withholding Taxes (including any deduction, withholding, or payment of Withholding Taxes regarding the additional amount), free from any liability regrading the Withholding Taxes, equal to the sum that Beneficiary would have received and retained had no such deduction or withholding of Withholding Taxes been made or required to be made and had no such Withholding Taxes been payable;

###### ii.	Deduct the Withholding Taxes from the payment:

###### iii.	Pay the full amount deducted to the relevant authority on account of the Withholding Taxes within the time provided under, and otherwise in accordance with applicable law or any jurisdiction; and

###### iv.	Promptly after the date the Withholding Taxes are due under the applicable law of any jurisdiction, deliver to Beneficiary the forms prescribed by the relevant authority of the Withholding Taxes.

###### b.	Without duplication of Section 4.7.5.a above, Guarantor agrees to indemnify and hold harmless Beneficiary for any Withholding Taxes that may become payable by Beneficiary concerning any payment made by Guarantor under this Guaranty. Without limiting the generality of the preceding sentence, if:

###### i.	Guarantor or Beneficiary is assessed or reassessed by any applicable taxing authority for any Withholding Taxes regarding any payment made by the Guarantor under this Guaranty, Guarantor must pay the Withholding Taxes together with interest or penalties on the Withholding Taxes to the taxing authority on behalf of Beneficiary and without recourse against Beneficiary within 30 Days of demand by Beneficiary; or

###### ii.	Beneficiary pays any Withholding Taxes regarding any payment made by Guarantor under this Guaranty, Guarantor agrees to indemnify Beneficiary upon receipt of the notice called or in Section 4.7.5.d. below.

###### c.	Without duplication of Section 4.7.5.a. or b. above, Guarantor agrees to indemnify and hold harmless Beneficiary for any additional taxes on net income that Beneficiary may be obligated to pay because of the receipt by it or payment by Guarantor of any amount under this Section 4.7.5.

###### d.	Beneficiary will promptly notify Guarantor of any Withholding Taxes that Beneficiary has paid or received an assessment or reassessment from any applicable taxing authority and for which the Guarantor is required to indemnify it in accordance with this Section 4.7.5 and of the amount payable to it by Guarantor this Section 4.7.5, and Guarantor will indemnify Beneficiary within 60 Days of receipt of such notice. Beneficiary will reasonably determine the amount payable to it, will contest in good faith any taxes that Beneficiary believes in good faith are not assessable, and the determination will, absent manifest error, be final and binding on Guarantor.

###### e.	Guarantor’s obligations under this Section 4.7.5 will survive for one year following termination of this Guaranty and the payment of all amounts payable under other provisions of this Guaranty.

###### 4.7.6. [Applicable Only to Foreign Guarantor: Waiver of Objection to Venue. GUARANTOR HEREBY IRREVOCABLY WAIVES, TO THE FULLEST EXTENT PERMITTED BY APPLICABLE LAW, ANY OBJECTION WHICH IT MAY NOW OR HEREAFTER HAVE TO THE LAYING OF VENUE OF ANY SUIT, ACTION OR PROCEEDING BETWEEN THEM ARISING OUT OF OR RELATING TO THIS GUARANTY BROUGHT IN ANY COURT IN OR OF THE STATE OF GEORGIA, AND HEREBY FURTHER IRREVOCABLY WAIVES ANY CLAIM THAT ANY SUCH SUIT, ACTION OR PROCEEDING BROUGHT IN ANY COURT IN OR OF THE STATE OF GEORGIA HAS BEEN BROUGHT IN AN INCONVENIENT FORUM.]

###### 4.7.7. [Applicable Only to Foreign Guarantor: Waiver of Immunity. TO THE EXTENT THAT THE GUARANTOR HAS OR HEREAFTER MAY ACQUIRE ANY IMMUNITY FROM JURISDICTION OF ANY COURT IN THE STATE OF GEORGIA OR FROM ANY LEGAL PROCESS THEREIN, GUARANTOR HEREBY WAIVES, TO THE FULLEST EXTENT PERMITTED BY LAW, SUCH IMMUNITY, AND AGREES NOT TO ASSERT, BY WAY OF MOTION, AS A DEFENSE, OR OTHERWISE, IN ANY SUCH SUIT, ACTION OR PROCEEDING, THE DEFENSE OF SOVEREIGN IMMUNITY, OR ANY CLAIM: (1) THAT IS NOT PERSONALLY SUBJECT TO THE JURISDICTION OF THE COURTS IN THE STATE OF GEORGIA BY REASON OF SOVEREIGN IMMUNITY OR OTHERWISE; (2) THAT IT IS IMMUNE FROM ANY LEGAL PROCESS (WHETHER THROUGH SERVICE OR NOTICE, ATTACHMENT PRIOR TO THE JUDGMENT, ATTACHMENTS IN AID OF EXECUTION, EXECUTION OR OTHERWISE) REGARDING ITSELF OR ITS PROPERTY, BY REASON OF SOVEREIGN IMMUNITY; (3) THAT ANY ACTION IS BROUGHT IN AN INCONVENIENT FORUM; (4) THAT THE VENUE OF ANY ACTION IS IMPROPER; OR (5) THAT THIS GUARANTY MAY NOT BE ENFORCED IN OR BY A FEDERAL COURT IN THE STATE OF GEORGIA. THE GUARANTOR EXPRESSLY ACKNOWLEDGES THAT THE FOREGOING WAIVERS AND SUBMISSIONS TO JURISDICTION ARE INTENDED TO BE IRREVOCABLE UNDER THE LAWS OF THE STATE OF GEORGIA AND OF THE UNITED STATES OF AMERICA AND OF THE LAWS APPLICABLE TO THE GUARANTOR, INCLUDING THE LAWS OF THE JURISDICTION IN WHICH THE GUARANTOR IS ORGANIZED.]

###### 4.7.8. Waiver of Right to Jury Trial. GUARANTOR UNCONDITIONALLY AND IRREVOCABLY WAIVES ALL RIGHT TO TRIAL BY JURY IN ANY ACTION, PROCEEDING, OR COUNTERCLAIM (WHETHER BASED ON CONTRACT, TORT, OR OTHERWISE) ARISING OUT OF OR RELATING TO, THIS GUARANTY, OR THE ACTIONS OF BENEFICIARY IN THE NEGOTIATION, ADMINISTRATION, PERFORMANCE OR ENFORCEMENT OF THIS GUARANTY.

## 4.8	Severability. Any provision of this Guaranty that is prohibited or unenforceable will be ineffective to the extent of the prohibition or unenforceability without invalidating the remaining provisions of this Guaranty.

## 4.9	Execution and Attestation.

## 4.9.1. Electronic Signature. This Guaranty may be executed by handwritten signature or Electronic Signature. An “Electronic Signature” means any electronic sound, symbol, or process attached to or logically associated with a record and executed and adopted by a Person with the intent to sign the record, including facsimile or e-mail electronic signatures. Guarantor acknowledges that electronic records and Electronic Signatures may be used in connection with the execution of this Guaranty and Electronic Signatures transmitted by electronic mail in so-called “.pdf” format will be legal and binding and will have the same full force and effect as if a paper original of this Guaranty had been delivered and signed using a handwritten signature. Guarantor: (i) agrees that an Electronic Signature, whether digital or encrypted, is intended to authenticate this Guaranty and to have the same effect as a handwritten signature; (ii) intends to be bound by the signature (whether original, faxed, or electronic) on any document sent or delivered by facsimile, electronic mail, or other electronic means; (iii) is aware that Beneficiary will rely on the signatures; and (iv) waives any defenses to the enforcement of the terms of this Guaranty based on the forms of signature described in this Section 4.9 (Execution and Attestation). If Guarantor executes this Guaranty by Electronic Signature, Guarantor expressly consents under the Electronic Signatures in Global and National Commerce Act (“E-SIGN”), and Uniform Electronic Transactions Act as enacted in the State of Georgia (“UETA”), that a signature by fax, email, or other electronic means will constitute an Electronic Signature to an Electronic Record under both E-SIGN and UETA regarding this transaction.

## 4.9.2. Digital or Electronic Signature. In addition to his Guaranty, any other documents to be delivered in connection with this Guaranty may be executed by handwritten signature or Electronic Signature. Guarantor acknowledges that any digital or Electronic Signature (including pdf, facsimile, or electronically imaged signatures provided by DocuSign or any other digital signature provider) appearing on this Guaranty or other documents to be delivered in connection with this Guaranty are the same as handwritten signatures for the purposes of validity, enforceability, or admissibility, and that delivery to Beneficiary of an Electronic Signature, or a signed copy of, this Guaranty and related documents may be made by facsimile, email, or other electronic transmission.

Guarantor has caused this Guaranty to be executed and delivered under seal by its authorized representative as of Effective Date.

| #GuarantorLegalName# |  |
| --- | --- |
| By: |  |
| Name Printed: |  |
| Title: |  |
| Date: |  |

Exhibit M – VIE Certification

AGREEMENT – Power Purchase Agreement for Firm Capacity, Energy Storage Services, and Ancillary Services from a Battery Energy Storage System [Paired with a Renewable Resource] for 2026 All-Source Capacity Request for Proposals for Need Years 2032-2033 at #Facility Name# dated #Month #Day, #Year between Georgia Power Company (“GPC”), and #SellerLegalName# (“Seller”) (“PPA”).  Capitalized terms used herein will have the meaning assigned in the PPA.

The undersigned individual, being the Chief Financial Officer of Seller and having responsibilities for financial accounting matters associated with this PPA, certifies that this PPA WILL (_____)/WILL NOT (_____) require Seller, over the Term and based on U.S. Generally Accepting Accounting Principles in effect as of the date of this certificate, to deconsolidate on its books and records any assets, liabilities, cash flow, profits, or losses of Seller as a result of GPC being determined to be the Primary Beneficiary. My determination of the most likely accounting treatment of this transaction results from my personal consideration after necessary discussions with relevant officers of Accounting Standards Codification (“ASC”) Topic 810, Consolidation, and the following factual matters:

- Seller’s accounting policies, procedures, and internal controls are sufficient to provide GPC with an appropriate basis for confirming the information contained herein.

________Yes

________No (please explain)

Explain:_______________________________________________________________________

- Seller qualifies for one of the scope exceptions listed in paragraphs 810-10-15-12 and 810-10-15-17 of ASC Topic 810.

________Yes

________No (please explain)

Explain:_______________________________________________________________________

- Seller is financed with equity equal to or greater than 10% of Seller’s total assets per paragraphs 810-10-25-45 to 47 of ASC Topic 810.

________Yes

________No (please explain)

Explain:_______________________________________________________________________

- The PPA revenues correlate with fluctuations in Seller’s operating cash flows (operating expenses).

________Yes

________No (please explain)

Explain:_______________________________________________________________________

- The PPA reduces variability in the fair value of Seller’s assets, for example by absorbing fuel or electricity price risk.

_______Yes

_______No (please explain)

Explain:_______________________________________________________________________

- The PPA Term is for greater than 50% of the remaining economic life of the unit.

________Yes

________No

- The PPA is for substantially all of the proposed Facility’s productive output.

________Yes

________No

- GPC and its affiliates participated significantly in the design or redesign of the Facility.

________Yes

________No

- The percentage that the Facility’s fair value represents, of the fair value of the proposed Seller’s total assets, is approximately;

_______%

- The Facility is essentially the only source of payment for specified liabilities or specified other interest (there is specific debt associated with the Facility).

________Yes

________No

[CERTIFICATION ON NEXT PAGE]

Certification

The above information (and any attachments) has been completed in full and agrees with our records as of the date of this Certification.

| #SellerLegalName# |  |  |
| --- | --- | --- |
| By: |  |
| Name Printed: |  |
| Title: |  |
| Date: |  |

Exhibit N – RESERVED

Exhibit N – Transfer of Information Acknowledgement

TRANSFER OF INFORMATION ACKNOWLEDGEMENT

#SellerLegalName# (“Seller”) and Georgia Power Company (“GPC”) have entered into the Power Purchase Agreement for Firm Capacity, Energy Storage Services, and Ancillary Services from a Battery Energy Storage System [Paired with a Renewable Resource] for 2026 All-Source Capacity Request for Proposals for Need Years 2032-2033 at (#FacilityName#) (“PPA”) dated as of _____________________, 202__. The PPA contemplates that Seller will provide to GPC or GPC’s affiliate Southern Company Services, Inc. (“SCS”) as agent for the transmission-owning subsidiaries of Southern Company (GPC, Alabama Power Company, and Mississippi Power Company) certain information that could be considered non-public information that potentially has implications under the Federal Energy Regulatory Commission (“FERC”) Standards of Conduct. Seller acknowledges that the information is being provided for the purposes of operational implementation and administration of the PPA (which includes conducting GPC’s system operations and dispatch functions) and will be used by GPC or SCS individuals in both Transmission/Distribution and energy affiliate/wholesale marketing unit functions under the FERC Standards of Conduct.

The individuals within the Southern Company organizations indicated above may use the information only for purposes of implementing and administering the PPA (including conducting GPC’s system operations and dispatch functions). Seller understands that the information will not be used or disseminated in any manner contrary to the confidentiality provisions in the PPA or in violation of the FERC Standards of Conduct.

Seller’s provision of this information has not been and is not being provided in exchange for any preferential treatment, either operational or rate-related, by SCS or by any of the transmission-owning subsidiaries of Southern Company. Seller also acknowledges that Seller is not providing the information under duress or coercion. In accordance with FERC requirements, SCS may post on Southern Company’s Open Access Same-time Information System (OASIS) the fact of Seller’s consent to the provision of the information specified above to certain employees that may be employed within organizational units deemed to be energy affiliates/wholesale marketing units under the Standards of Conduct.

Acknowledged on behalf of Seller by Seller’s authorized representative signing below:

| #SellerLegalName# |  |
| --- | --- |
| By: |  |
| Name Printed: |  |
| Title: |  |
| Date: |  |

Exhibit O – Environmental Compliance Certification

CERTIFICATION OF ENVIRONMENTAL COMPLIANCE

AGREEMENT – Power Purchase Agreement for Firm Capacity, Energy Storage Services, and Ancillary Services from a Battery Energy Storage System [Paired with a Renewable Resource] for 2026 All-Source Capacity Request for Proposals for Need Years 2032-2033 at #FacilityName# dated as of ______ ___, 20__ between Georgia Power Company (“GPC”), and #SellerLegalName# (“Seller”) (“PPA”). Capitalized terms used herein will have the meaning assigned in the PPA.

The undersigned individual, being the [●] of Seller and having responsibilities for [environmental compliance and reporting] matters associated with this PPA, certifies to the following:

- Since the date of Seller’s prior Certification of Environmental Compliance delivered in accordance with the PPA, there have been no changes in the design or construction of the Facility that resulted in or, to the best of the knowledge of the undersigned after reasonable inquiry, are expected to result in, additional impacts to the environment that have not been previously disclosed in writing to GPC.

________Yes

________No (please explain)

Explain:_______________________________________________________________________

(a)	If “no,” a figure set or plan sheets that highlights such changes is attached.

(b)	If “no,” copies of all documentation that all necessary Permits have been obtained and/or that the appropriate Governmental Authority coordination has occurred to legally allow for such impacts is attached.

- A list of Permits for the Facility that were obtained (opened) or Governmental Authority prescriptions that were issued since the previous Certification is attached.

- A list of Permits for the Facility that were applied for but have not yet been obtained (opened) since the previous Certification is attached.

- A list of any notices of violation (NOV) since the previous certification that were issued with respect to Seller [or in connection with the Facility], including: (i) the Governmental Authority that issued the NOV, (ii) the status of remediation of the violation; and (iii) if remediation has not been completed, the duration anticipated for resolution is attached. Copies of any NOVs are also attached.

- Attached is a list identifying (by name and address) any adjacent landowner, lessee or neighbor complaints against Seller or the Facility since the previous certification, as well as: (i) a general description of the complaint; and (ii) plans that Seller took to resolve the complaint or, if not yet resolved, what actions Seller has taken to date, or intends to take, to resolve the complaint, along with a timeline for completing such actions.

- A list of any Permits and/or other Governmental Authority prescribed actions that have been fulfilled and/or closed since the previous Certification is attached.

- Except as already referenced or included in an attachment to this Certification, there are no other documents, notices or correspondence from any Governmental Authority indicating that the Facility and the Site is not in compliance with or is not in good standing under, and Environmental Laws, Permit or other Governmental Authority prescribed actions.

Confirmation

The above information (and any attachments) has been completed in full and agrees with our records as of the date of this Certification.

| #SellerLegalName# |  |  |
| --- | --- | --- |
| By: |  |  |
| Name Printed: |  |  |
| Title: |  |  |
| Date: |  |  |

Exhibit P – Notices

Address for delivery of Eligible Collateral for Performance Security in accordance with PPA Section 6.6 (Delivery of Eligible Collateral for Performance Security):

For any Eligible Collateral in the form of a Letter of Credit or Seller Guaranty, the following address:

Georgia Power Company

c/o Southern Company Services Inc.

Attn: Assistant Treasurer, BIN SC1407

30 Ivan Allen Jr. Blvd.

Atlanta, Georgia 30308

For any Eligible Collateral in the form of cash, GPC will provide the GPC Security Account information, including wiring instructions, within a reasonable time after receipt of Seller’s written request.

Addresses for delivery of notices to the Parties in accordance with PPA Section 20.4 (Notice):

In accordance with PPA Section 20.4, all notices must include the PPA’s title and the Facility name.

| Notice to GPC: Georgia Power Company Attention: #GPCContact Name 241 Ralph McGill Boulevard N.E. BIN #BinNumber# Atlanta, Georgia 30308 Email: #GPCNoticeEmail | With Copy To: Georgia Power Company Legal Dept. Attn: Commercial & Transactional Counsel Bin 10180 241 Ralph McGill Blvd., N.E. Atlanta, GA 30308 |
| --- | --- |

| Notice to Seller: #SellerLegalName# Attention: #SellerContactIndividualName# #Title #SellerAddress #City, #State #Zip Email: #SellerContactEmail# |  |
| --- | --- |

Note to Bidders: Surplus Interconnection issues to be addressed, if applicable.

[Note to Bidders: Table A-3 may include any applicable average annual state of charge limitation , so long as supporting OEM documentation that substantiates the proposed limitation is provided as part of the Bid.]

Without limiting any other PPA requirement, as a condition to achieving each Key Milestone on or before the Key Milestone Date, Seller must provide evidence satisfactory to GPC demonstrating that each Key Milestone was achieved by the Key Milestone Date, including the items described in this table.

If Seller’s business structure does not designate an officer with this or a similar title, Seller must provide written documentation affirming the authority of the individual who attests to this certification.